MUNGAWALI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701003/IF/22012034586528 — निजी खेत में फलोद्यान श्री वासुदेव पिता बाबूलाल | Completed | 296503 | 126388.2 | 2020-08-29 | 2023-11-09
MUNGAWALI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Boundary Line Plantation of Horticulture Trees for Individuals | Plantation | 1701003/IF/22012034586537 — निजी खेत में फलोद्यान श्री दिनेश सिंह पिता श्री बाबू लाल | Ongoing | 141869 | 37556.96 | 2020-09-17
SIRMITI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701003/IF/22012034586570 — निजी खेत में फलोद्यान श्रीमती सगुना बाई पति रतन सिंह | Completed | 453954 | 187502 | 2020-08-29 | 2023-11-09
JINGNI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701003/IF/22012034586925 — निजी खेत में फलोद्यान श्री मेहरवान सिंह पिता श्री रामनाथ सिंह | Completed | 147369 | 116334 | 2020-08-29 | 2023-11-09
SIRMITI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701003/IF/22012034586942 — निजी खेत में फलोद्यान श्री राजकुमार पिता श्री रूप सिंह | Completed | 141869 | 69406 | 2020-08-29 | 2023-11-09
JARAH | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701003/IF/22012034586951 — निजी खेत में फलोद्यान श्री नेकराम कुशवाह पिता श्री द्वारिका | Completed | 141869 | 72760.5 | 2020-09-29 | 2023-11-09
JARAH | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1701003/IF/22012034586962 — निजी खेत में फलोद्यान श्री केशव सिंह पुत्र श्री प्रीतम सिंह | Ongoing | 163440 | 68086.5 | 2020-09-26
MEHTOLI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Line Plntation(Coast) - horti-trees (Individuals) / Along the coast Line Plantation of Horticulture Trees for Individuals | Plantation | 1701003/IF/22012034587056 — निजी खेत में फलोद्यान श्री कमल सिंह पिता प्रताप सिंह | Completed | 141869 | 102240.8 | 2020-09-24 | 2023-11-09
KARUA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1701003/IF/22012034587065 — निजी खेत में फलोद्यान श्री निहाल सिंह पिता छविराम | Ongoing | 141869 | 97129 | 2020-09-02
KARUA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701003/IF/22012034590497 — निजी खेत में फलोद्यान श्री अशोक सिंह गुर्जर पिता श्री जंगजीत सिंह गुर्जर | Completed | 141869 | 115486 | 2020-09-02 | 2023-11-09
MUNGAWALI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701003/IF/22012034603322 — निजी खेत में फलोद्यान श्री रामभरोसी पिता श्री राम सिंह | Completed | 147369 | 108798.5 | 2020-09-02 | 2023-11-09
RITHORA KHURD | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701003/IF/22012034617097 — निजी खेत में फलोद्यान श्री राजेन्‍द्र सिंह परमार पिता श्री गरसिंह परमार | Completed | 296738 | 199740.99 | 2020-09-29 | 2023-11-09
RITHORA KHURD | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701003/IF/22012034617121 — निजी खेत में फलोद्यान श्री जयसिंह परमार पिता गरसिंंहपरमार | Completed | 185979 | 138235 | 2020-09-29 | 2023-11-09
KHIRAWALI | 2011-2012 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1701003/IF/353 — मेढवंधान कार्य | Deleted | 0 | 0 | 2011-04-14
DHANELA | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701003/LD/1092 — मेड वन्‍धान कार्य धनेला भाग 2 | Completed | 0 | 15834 | 2009-05-08 | 2017-01-10
DHANELA | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701003/LD/1093 — मेड वन्‍धान कार्य धनेला भाग 1 | Completed | 0 | 2184 | 2009-04-01 | 2017-01-10
BARENDA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701003/LD/22 — मेडबंधान कार्य बरैन्‍डा | Completed | 0 | 526596 | 2009-02-13 | 2011-09-30
JARERUA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701003/LD/23 — मैढ बंधान कार्य जरेरूआ | Completed | 0 | 848836 | 2009-03-01 | 2011-01-31
NURABAD | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701003/LD/24 — मेड. बंधान कार्य | Completed | 0 | 538956 | 2009-03-01 | 2011-04-01
NURABAD | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701003/LD/25 — मेड बन्‍धान ग्राम पंचायत नूराबाद | Completed | 0 | 343878 | 2009-03-01 | 2011-09-18
DHANELA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701003/LD/26 — मेड वन्‍धान कार्य धनेला भागा 3 | Completed | 0 | 923350 | 2009-03-01 | 2011-04-01
BICHOLA | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701003/LD/30 — मेउ बन्‍धान | Completed | 0 | 302720 | 2009-06-15 | 2017-04-20
JAKHODA | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701003/LD/31 — मेड वन्‍धान कार्य | Completed | 0 | 621672 | 2009-08-28 | 2011-03-04
JAINAGAR | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701003/LD/32 — मेड वन्‍धान कार्य | Completed | 0 | 401504 | 2009-08-16 | 2011-01-11
JAKHODA | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701003/LD/33 — मेड वन्‍धान कार्य | Completed | 0 | 228636 | 2009-07-13 | 2011-09-04
JAKHODA | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701003/LD/34 — मेड वन्‍धान कार्य | Completed | 0 | 199836 | 2009-06-29 | 2011-03-04
JAKHODA | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701003/LD/35 — मेड वन्‍धान कार्य | Completed | 0 | 598920 | 2009-09-25 | 2011-03-18
CHURHELA | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701003/LD/36 — मेड वन्‍धान कार्य | Completed | 0 | 398416 | 2009-07-31 | 2011-04-01
NAUGAON | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701003/LD/37 — मेड वन्‍धान कार्य | Completed | 0 | 403468 | 2009-09-25 | 2011-03-04
RITHAURAKALAN | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003/RC/276 — सी सी खरंजा निमार्ण कार्य टॉवर से डॉ गोतम की दुकान एवं यूनियन बैंक से स्‍कूल के पीछे रिठोराकला | Completed | 0 | 227923 | 2008-09-19 | 2010-12-10
RITHAURAKALAN | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003/RC/277 — सी सी खरंजा निमार्ण कार्य हीरालाल बोहरे के मकान से राम सेवक के मकम की ओर रिठोराकला | Completed | 0 | 209036 | 2008-09-23 | 2010-12-10
RITHAURAKALAN | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003/RC/445 — सी सी खरजा निर्माण कार्य हाकिम सिह के मकान से मदिर वाली रोड तक | Completed | 0 | 340190 | 2008-06-20 | 2010-12-10
HETAMPUR | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701003/RC/551 — बारह मासी सडक निर्माण् कार्य ए वी रोड से होला का पुरा | Completed | 0 | 204480.9 | 2010-07-21 | 2011-10-10
GOSPUR | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701003/RC/552 — बारह मासी सडक निर्माण् कार्य ए वी रोड से होला का पुरा | Completed | 0 | 888680.3 | 2010-06-02 | 2012-03-30
AITi | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1701003/WH/157 — ऐती न-2 तालाब का सुदिकरण ग्राम पंचायत ऐती | Completed | 1937000 | 196882 | 2008-12-30 | 2013-08-12
BADWARI | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Excavation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1701003/WH/160 — तालाब जीर्णोधर कार्य कारर्य जल संसाधन वभिाग | Completed | 272000 | 265113 | 2009-01-11 | 2017-01-10
URHANA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Excavation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1701003/WH/168 — उरेहना तालाव का रखरखा कार्य | Deleted | 0 | 24835 | 2009-01-01
AITi | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Excavation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1701003/WH/169 — एती 01 उरेहना तालाव का रखरखा कार्य | Deleted | 0 | 12604 | 2009-01-08
AITi | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Excavation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1701003/WH/170 — एती तालाव का रखरखा कार्य | Deleted | 0 | 0 | 2008-09-07
PACHOKHARA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Excavation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1701003/WH/171 — एती तालाव का रखरखा कार्य | Deleted | 0 | 0 | 2008-09-10
GADAJAR | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Excavation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1701003/WH/172 — एती तालाव का रखरखा कार्य | Deleted | 0 | 0 | 2008-04-15
GADAJAR | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Excavation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1701003/WH/173 — एती तालाव का रखरखा कार्य | Deleted | 0 | 0 | 2008-04-15
RITHAURAKALAN | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Excavation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1701003/WH/174 — एती तालाव का रखरखा कार्य | Deleted | 0 | 0 | 2008-04-15
ARDAUNI | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Excavation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1701003/WH/175 — एती तालाव का रखरखा कार्य | Completed | 0 | 1190 | 2008-10-03 | 2015-09-17
PIPARSEVA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Excavation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1701003/WH/176 — एती तालाव का रखरखा कार्य | Deleted | 0 | 0 | 2008-08-22
PAHADI | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Excavation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1701003/WH/177 — तालाव का रखरखा कार्य | Deleted | 0 | 0 | 2008-04-15
SILGILA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Excavation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1701003/WH/178 — तालाव का रखरखा कार्य | Completed | 0 | 169009 | 2008-09-12 | 2017-04-21
RITHAURAKALAN | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Excavation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1701003/WH/179 — तालाव का रखरखा कार्य | Completed | 0 | 153835 | 2009-04-15 | 2017-01-10
DEWARI | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Nursery Raising / Raising of Nursery for Community | Nursery Development | 1701/DP/22012034235309 — फलपौध उत्पादन शासकीय रोपणी देवरी | Deleted | 1196257 | 0 | 2016-02-17
DEWARI | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701/DP/22012034235570 — MOTHER PLANT PLANTESTION | Deleted | 0 | 0 | 2016-02-17
DEWARI | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Nursery Raising / Raising of Nursery for Community | Nursery Development | 1701/DP/22012034235784 — MOTHER PLANTESTION 2 | Deleted | 667613 | 0 | 2016-02-17
JINGNI | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1701/DP/22012034237529 — कब्रिस्तान निर्माण कार्य - मस्जिद के सामने, अम्बाह रोड़ जींगनी | Completed | 1000000 | 1010605.37 | 2017-02-20 | 2019-05-28
DEWARI | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701/DP/99091 — plant prepation | Deleted | 0 | 0 | 2010-04-01
DEWARI | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701/DP/99094 — Plant prepration | Deleted | 1995000 | 0 | 2010-04-01
DEWARI | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701/DP/9926690475 — बास पौधा | Completed | 428000 | 138070 | 2011-03-18 | 2017-04-20
NAUPURA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701/DP/9926693490 — सामुदायिक वृक्षारोपण बनी, नाउपुरा | Completed | 1113200 | 405807.8 | 2012-06-12 | 2014-08-30
DEWARI | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701/DP/9926693706 — फल पौधा उत्‍पादन | Completed | 700000 | 379539.4 | 2012-05-31 | 2016-05-16
JAKHODA | 2012-2013 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Strengthening of Embankment / Construction of Embankment for community | Strengthening of Embankment | 1701/FP/9977521196 — मेशनरी नाला बंधान जखोदा | Completed | 450000 | 455505.5 | 2012-09-04 | 2012-12-26
DHANELA | 2012-2013 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Drainage in Water Logged Areas / Drainage of Community Waterlogged Land | Works for Flood Control and Protection | 1701/FP/9977521203 — नाला बंधान धनेला | Completed | 450000 | 480012.88 | 2012-10-11 | 2013-03-20
KHEDAMEWDA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Micro Irrigation Works | Lining of Canals / Lining of distributary Canal for Community | Lining of Canal | 1701/IC/60099 — नहर मरम्‍मत | Completed | 0 | 299946 | 2010-11-12 | 2011-01-20
KAITHODA | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Horticulture / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701/IF/1000001426 — नन्‍दन फलोउघान कार्य कमल सिह पुञ चरन सिह | Completed | 156000 | 36997.44 | 2012-06-06 | 2015-10-03
KAITHODA | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Horticulture / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701/IF/1000001427 — नन्‍दन फलो उधान सरमन पुञ मुरली | Completed | 156000 | 24813.4 | 2012-07-27 | 2015-07-27
KAITHODA | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Horticulture / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701/IF/1000001428 — नन्‍दन फलोउधान कार्य प्रकाश पुञ जीवन लाल | Completed | 156000 | 26481.4 | 2012-07-27 | 2015-07-27
MIRGHAN | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Horticulture / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701/IF/1000001429 — नन्‍दन फलो उधान कार्य रामजीनान पुञ रामजीलाल | Completed | 153000 | 15141.4 | 2012-08-01 | 2015-08-01
SURJANPUR | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Horticulture / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701/IF/1000001432 — नन्‍दन फलो उधान कार्य शिवराम पुञ सोवरन | Completed | 153000 | 19156.2 | 2012-07-27 | 2015-07-27
SURJANPUR | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Horticulture / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701/IF/1000001433 — नन्‍दन फलो उधान कार्य हरी सिह पुञ राम सिह | Completed | 156000 | 26089.8 | 2012-07-27 | 2015-07-27
SURJANPUR | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Horticulture / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701/IF/1000001434 — नन्‍दन फलो उधान कार्य रामपदन पूञ सोवरन | Completed | 153000 | 24107.93 | 2012-07-27 | 2015-07-27
SURJANPUR | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Horticulture / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701/IF/1000001435 — नन्‍दन फलो उधान कार्य केदार पुञ अजव सिह | Completed | 156000 | 22834.13 | 2012-07-27 | 2015-07-27
KAITHODA | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Horticulture / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701/IF/1000001436 — नन्‍दन फलो उधान कार्य रामरतना पुञ हरिविलाश | Completed | 156000 | 22172.4 | 2012-07-27 | 2015-07-27
GANJRAMPUR | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Horticulture / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701/IF/1000001437 — नन्‍दन फलो उधान कार्य राजेश पुञ विृधाराम | Completed | 153000 | 10618.2 | 2012-07-28 | 2015-07-28
HINGONAKALAN | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Horticulture / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701/IF/1000001438 — नन्‍दन फलो उधान कार्य जगमन पुञ चन्‍नीराम | Completed | 156000 | 30370.8 | 2012-07-27 | 2015-07-27
KAITHODA | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Horticulture / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701/IF/1000001439 — नन्‍दन फलो उधान कार्य मथिलेश पुञ दिनेश | Completed | 153000 | 9088.4 | 2012-08-01 | 2015-08-03
GANJRAMPUR | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Horticulture / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701/IF/1000001564 — वक्षारोपड कार्य रामस्‍वरूप पुञ सामलिया | Completed | 153000 | 13533.4 | 2012-07-28 | 2015-07-28
DONGARPURLODHA | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Horticulture / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701/IF/1000001565 — वक्षारोपड कार्य हरी सिह पुञ गिरवर | Completed | 153000 | 9095.8 | 2012-08-15 | 2015-08-16
KAITHODA | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Horticulture / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701/IF/1000001566 — वक्षारोपड कार्य पंचम सिह पुञ इदेवीराम | Completed | 153000 | 12597.4 | 2012-08-15 | 2015-08-24
HINGONAKALAN | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Horticulture / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701/IF/1000001568 — वक्षारोपड कार्य शोभाराम पुञ चुन्‍नी | Completed | 153000 | 26799.4 | 2012-08-15 | 2015-08-16
DONGARPURLODHA | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Horticulture / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701/IF/1000001569 — वक्षारोपड कार्य महेन्‍द्रसिह पुञ सरमन | Completed | 153000 | 21787.8 | 2012-08-01 | 2015-08-24
KHEDAMEWDA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701/LD/3799381592 — गली प्‍तग खेरा | Completed | 200000 | 28548 | 2012-01-20 | 2013-03-20
KHEDAMEWDA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701/LD/3799381593 — मैढ बंधान कार्य खेरा | Completed | 100000 | 37332 | 2012-01-13 | 2013-03-20
DHANELA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701/LD/3799381594 — मैढ बंधान | Completed | 100000 | 99384 | 2012-01-27 | 2013-02-15
BICHOLA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701/LD/3799381642 — मैढ बंधान लोलक पुर | Completed | 200000 | 65472 | 2012-02-08 | 2013-03-20
DHANELA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701/LD/3799381643 — मैढ बंधान धनेला | Completed | 200000 | 187392 | 2012-02-09 | 2013-02-15
JAKHODA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701/LD/3799381665 — गली प्‍लग जखोदा | Completed | 70000 | 38064 | 2012-02-17 | 2013-03-20
NAUPURA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701/LD/3799381666 — गली प्‍लग नाउपुरा | Completed | 60000 | 29280 | 2012-02-26 | 2013-03-20
NAUPURA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701/LD/3799381667 — मैढबंधान बनी | Completed | 60000 | 180312 | 2012-02-22 | 2013-03-20
NURABAD | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701/LD/3799381744 — गलीप्‍लग व मैढ बंधान नूराबाद | Completed | 150000 | 106140 | 2012-03-10 | 2012-10-17
JAINAGAR | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701/LD/3799381745 — मैढ बंधान जयनगर | Completed | 250000 | 261168 | 2012-03-10 | 2013-03-25
JAKHODA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701/LD/3799381746 — मैढ बंधान कार्य जखोदा | Completed | 240000 | 75104 | 2012-03-10 | 2013-03-20
NAUPURA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701/LD/3799381778 — गलीप्‍लग बनी | Completed | 150000 | 23424 | 2012-02-28 | 2013-03-20
NURABAD | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701/LD/3799381779 — गलीप्‍लग नूराबाद | Deleted | 250000 | 0 | 2011-12-01
NURABAD | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701/LD/3799381780 — गली प्‍लग नूराबाद | Completed | 150000 | 87840 | 2012-03-15 | 2012-12-12
NAUPURA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701/LD/3799381788 — गलीप्‍लग नरसिंहपुर | Completed | 120000 | 32208 | 2012-02-01 | 2012-02-16
BICHOLA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701/LD/3799381866 — गली प्‍लग लोलक पुर | Completed | 200000 | 47520 | 2012-04-01 | 2013-03-20
BICHOLA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701/LD/3799381889 — गली प्‍लग लोलकपुर | Completed | 28000 | 25344 | 2012-04-01 | 2013-03-20
PILUA | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701/RC/22 — रिठौरा मालनपुर रोड से नरसिंगपुर | Completed | 0 | 876359.5 | 2010-10-18 | 2011-10-26
SEWA | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701/RC/22012034151581 — mitti grawal road A.B. road se subekapura morena | Deleted | 0 | 0 | 2010-05-01
SEWA | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701/RC/22012034151583 — mitti grawal road A.B. road se subekapura morena | Deleted | 0 | 0 | 2010-05-01
SEWA | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701/RC/22012034151584 — mitti grawal road A.B. road se subekapura morena | Deleted | 0 | 0 | 2010-05-01
SEWA | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701/RC/22012034151585 — mitti grawal road A.B. road se subekapura morena | Deleted | 0 | 0 | 2010-05-01
SEWA | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701/RC/22012034151589 — mitti grawal road A.B. road se subekapura morena | Deleted | 0 | 0 | 2010-05-01
SEWA | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701/RC/22012034151600 — mitti grawal road A.B. road se subekapura morena | Deleted | 0 | 0 | 2010-05-01
HETAMPUR | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701/RC/22012034151727 — mitti grawal road A.B. road se Hola ka pura morena | Completed | 0 | 297400.6 | 2012-04-01 | 2012-07-12
SANGOLI | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701/RC/22012034151728 — mitti grawal road Bhattpura se sangoli morena | Completed | 1402000 | 1355779.6 | 2011-02-22 | 2012-03-19
JEWRAKHERA | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701/RC/22012034151729 — mitti grawal road Dongarpurkirar road se panchi ka pura morena | Deleted | 879000 | 0 | 2010-05-01
NAGRA | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701/RC/22012034151732 — mitti grawal road Nagra se Zinawali morena | Completed | 1512000 | 632553.1 | 2011-05-12 | 2012-02-16
NAUPURA | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701/RC/22012034151734 — mitti grawal road Bani road se patukhue ka pura morena | Completed | 1374000 | 775199.95 | 2011-01-28 | 2012-03-09
KARARI | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701/RC/22012034151735 — mitti grawal road sidhari ka pura se tutt ka pura morena | Completed | 758000 | 387748.02 | 2011-01-12 | 2013-03-31
SEWA | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701/RC/22012034151736 — mitti grawal road A.B.road se suve ka pura vaya seva morena | Completed | 468000 | 198814.81 | 2011-02-22 | 2012-02-29
KHARAGPUR | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Bitumen Top / Construction of Bitumen Top Roads for Community | Construction of Road and Culvert | 1701/RC/22012034151737 — mitti grawal road Noorabad padawali road se Rampal ka pura morena | Deleted | 1684000 | 0 | 2010-05-01
KHIRAWALI | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701/RC/22012034151738 — mitti grawal road khirawali se maharaj singh ka pura morena | Completed | 1967000 | 918464.8 | 2011-02-15 | 2012-02-29
DONGARPURKIRAR | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701/RC/22012034153022 — डोगरपुर किरार से पधीपुरा | Completed | 1662000 | 625735.24 | 2011-06-08 | 2012-03-30
DEWARI | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701/RC/22012034154984 — C.C.Road and Nali Nirman nivi Road se Buddhi pura | Completed | 547000 | 162380 | 2012-12-19 | 2013-03-20
MIRPUR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701/RC/22012034188546 — मिटटी बजरी रोड आंगनवाडी भवन से रघुवर के पुरा तक | Completed | 1764005 | 886146.4 | 2013-10-05 | 2016-09-19
RAMPURGUNJ | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701/RC/22012034188556 — मिटटी बजरी सड्क डब्‍लू बीएम रोड से लाखन का पुरा एवं तिगरा का पुरा | Deleted | 1731997 | 0 | 2013-10-05
JINGNI | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Bitumen Top / Construction of Bitumen Top Roads for Community | Construction of Road and Culvert | 1701/RC/22012034188563 — मिटटी मुरम रोड बसैया रोड से जलालपुर स्‍कूल तक | Deleted | 1491000 | 0 | 2013-10-05
PILUA | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701/RC/31 — मिट्रटी ग्रेवल रोड रिठौरा मालनपुर से खेरा का पुरा | Completed | 0 | 825398.3 | 2010-11-16 | 2012-06-19
HANSAIMEWADA | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701/RC/35 — मिटटी ग्रेवल रोड निवी रोड से गादीपाल का पुरा | Completed | 0 | 239097.8 | 2010-12-27 | 2012-03-30
GOSPUR | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701/RC/36 — मिटटी ग्रेवल रोड गोसपुर से धान्‍धू का पुरा | Completed | 0 | 279899 | 2010-12-14 | 2011-08-05
DAURAWALI | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701/WC/22012035048496 — अमृत सरोवर तालाब निर्माण कार्य करौली माता मंदिर के पास ग्राम दौरावली | Closed | 5570000 | 0 | 2022-10-02
PIPARSEVA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701/WC/22012035048803 — अमृत सरोवर तालाब निर्माण कार्य झार की नरिया ग्राम पिपरसेवा | Ongoing | 5103000 | 2598667.98 | 2023-05-04
AITi | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701/WC/22012035048891 — अमृत सरोवर तालाब निर्माण कार्य हनुमान मंदिर के पीछे ऐंती | Ongoing | 4892000 | 2656405.16 | 2023-05-15
AITi | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701/WC/22012035048913 — अमुत सरोवर तालाब निर्माण कार्य शनि मंदिर के पीछे ग्राम ऐंती | Ongoing | 5159000 | 2809840.05 | 2023-05-20
DHANELA | 2011-2012 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1701/WC/9993624129 — तलैया (फर्म पाण्‍ड) | Completed | 100000 | 86376 | 2012-01-24 | 2013-02-15
JAKHODA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Gully Plug / Construction of Earthen Gully Plugs for Community | Boulder Check/Gully Plug | 1701/WC/9993624173 — गली प्‍लग जखोदा | Completed | 200000 | 20130 | 2012-01-24 | 2013-03-20
JAKHODA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Gully Plug / Construction of Earthen Gully Plugs for Community | Boulder Check/Gully Plug | 1701/WC/9993624174 — गली प्‍लग जखोदा | Completed | 200000 | 48312 | 2012-01-11 | 2013-03-20
JAKHODA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Gully Plug / Construction of Earthen Gully Plugs for Community | Boulder Check/Gully Plug | 1701/WC/9993624175 — गली प्‍लग जखोदा | Completed | 200000 | 32940 | 2012-01-11 | 2013-03-20
NAUPURA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Sunken Pond / Construction of Community Water Harvesting Ponds | Farm Pond | 1701/WC/9993624176 — तलैया निर्माण बनी | Deleted | 200000 | 0 | 2011-12-11
JAKHODA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1701/WC/9993624182 — तालाब निर्माण जखोदा | Completed | 200000 | 130906 | 2011-12-10 | 2013-03-20
BICHOLA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1701/WC/9993624194 — तलैया निर्माण लोलकपुर | Completed | 200000 | 46848 | 2012-01-16 | 2013-03-20
SANGOLI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1701/WC/9993624195 — तालाब निर्माण सांगोली | Completed | 300000 | 58560 | 2011-08-20 | 2012-10-04
NAUPURA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1701/WC/9993624196 — तलैया निर्माण | Completed | 200000 | 40992 | 2012-01-16 | 2013-03-20
DHANELA | 2011-2012 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1701/WC/9993624302 — फार्म पोण्‍ड तलैया धनेला | Completed | 200000 | 76128 | 2012-01-26 | 2013-02-15
BARENDA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1701/WC/9993624303 — तालाब बर्रेण्‍डा | Completed | 190000 | 189903 | 2012-01-27 | 2017-10-22
CHURHELA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1701/WC/9993624391 — सोख्‍ता गढढा चुरहेला 9 | Completed | 50000 | 105783.22 | 2012-02-01 | 2012-10-17
JAKHODA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1701/WC/9993624393 — सोख्‍ता गढढा जखोदा | Completed | 50000 | 21101.68 | 2012-02-17 | 2013-03-30
JAINAGAR | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Loose Boulder Structure / Construction of Stone boulder Gully Plugs for Community | Boulder Check/Gully Plug | 1701/WC/9993625002 — तालाब निर्माण कार्य जयनगर | Completed | 420000 | 352932.62 | 2012-04-01 | 2013-04-25
JARERUA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1701/WC/9993625306 — गली बंधान जरेरूआ | Completed | 25000 | 22176 | 2012-04-17 | 2013-03-25
JARERUA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1701/WC/9993625307 — गलीबंधान जरेरूआ | Completed | 26000 | 22176 | 2012-04-17 | 2013-03-25
JARERUA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1701/WC/9993625308 — मैढ बंधान कार्य जरेरूआ | Completed | 90000 | 59400 | 2012-04-17 | 2013-03-25
JAKHODA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1701/WC/9993625309 — मैढ बंधान सपचोली | Completed | 176000 | 81576 | 2012-04-01 | 2013-03-20
DHANELA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1701/WC/9993625310 — मैढ बंधान धनेला | Completed | 176000 | 106128 | 2012-04-30 | 2013-03-28
SANGOLI | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Mini Percolation tank / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1701/WC/9993625372 — तालाब निर्माण सांगोली | Completed | 2752000 | 907070.68 | 2012-05-13 | 2014-05-05
CHURHELA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Sunken Pond / Construction of Community Water Harvesting Ponds | Farm Pond | 1701/WC/9993625496 — तलैया निर्माण चुरहेला | Completed | 38000 | 34056 | 2012-06-22 | 2012-10-17
JARERUA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Gully Plug / Construction of Earthen Gully Plugs for Community | Boulder Check/Gully Plug | 1701/WC/9993625499 — गली प्‍लग जरेरूआ | Completed | 50000 | 19008 | 2012-07-11 | 2012-07-19
JAKHODA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1701/WC/9993625500 — नाला बंधान सपचोली | Completed | 460000 | 451688.48 | 2012-06-06 | 2013-02-16
CHURHELA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Gully Plug / Construction of Earthen Gully Plugs for Community | Boulder Check/Gully Plug | 1701/WC/9993625502 — गली प्‍लग चुरहेला | Completed | 20000 | 16632 | 2012-06-28 | 2012-10-17
CHURHELA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Gully Plug / Construction of Earthen Gully Plugs for Community | Boulder Check/Gully Plug | 1701/WC/9993625505 — गली प्‍लग चुरहेला 1 | Completed | 20000 | 17424 | 2012-06-28 | 2012-07-03
BICHOLA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1701/WC/9993625507 — मैढ बंधान लोलक पुर | Completed | 30000 | 19008 | 2012-07-11 | 2012-07-18
JAKHODA | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1701/WC/9993625509 — फार्म पौण्‍ड | Completed | 30000 | 22176 | 2012-06-12 | 2013-03-20
CHURHELA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Gully Plug / Construction of Earthen Gully Plugs for Community | Boulder Check/Gully Plug | 1701/WC/9993625537 — गली प्‍लग चुरहेला | Completed | 30000 | 28512 | 2012-06-25 | 2012-10-17
BICHOLA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1701/WC/9993625548 — चैकडेम (मेशनरी टाइप) लोलकपुर | Completed | 190000 | 105300.82 | 2012-07-01 | 2012-08-21
JARERUA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1701/WC/9993625549 — मेशनरी जरेरूआ | Completed | 145000 | 101598 | 2012-07-04 | 2012-07-29
JAKHODA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Continuous Contour Trench / Construction of Continuous Contour Trench for Community | Construction of Trench | 1701/WC/9993625780 — ट्न्‍च जखोदा | Completed | 150000 | 33264 | 2012-09-08 | 2013-03-20
NAUPURA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Continuous Contour Trench / Construction of Continuous Contour Trench for Community | Construction of Trench | 1701/WC/9993625782 — टृन्‍च निर्माण बनी, नाउपुरा | Completed | 150000 | 69696 | 2012-08-14 | 2013-03-20
DHANELA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Continuous Contour Trench / Construction of Continuous Contour Trench for Community | Construction of Trench | 1701/WC/9993625783 — टृन्‍च निर्माण धनेला | Completed | 250000 | 151272 | 2012-08-19 | 2013-02-15
BARENDA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Continuous Contour Trench / Construction of Continuous Contour Trench for Community | Construction of Trench | 1701/WC/9993625784 — टृन्‍च निर्माण बर्रेण्‍डा | Completed | 75000 | 8712 | 2012-09-02 | 2013-03-30
DHANELA | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1701/WC/9993625785 — फार्म पोण्‍ड निर्माण धनेला | Completed | 120000 | 95040 | 2012-08-26 | 2013-02-15
CHURHELA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Gully Plug / Construction of Earthen Gully Plugs for Community | Boulder Check/Gully Plug | 1701/WC/9993625887 — गली प्‍लग चुरहेला | Completed | 70000 | 12672 | 2012-10-04 | 2012-10-16
CHURHELA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Gully Plug / Construction of Earthen Gully Plugs for Community | Boulder Check/Gully Plug | 1701/WC/9993625888 — गल्‍ली प्‍लग चुरहेला | Completed | 70000 | 21384 | 2012-09-28 | 2012-10-18
DHANELA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Gully Plug / Construction of Earthen Gully Plugs for Community | Boulder Check/Gully Plug | 1701/WC/9993625889 — गली प्‍लग धनेला | Completed | 100000 | 38016 | 2012-10-06 | 2013-03-20
BARENDA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Gully Plug / Construction of Earthen Gully Plugs for Community | Boulder Check/Gully Plug | 1701/WC/9993625890 — गली प्‍लग बर्रेण्‍डा | Completed | 80000 | 20592 | 2012-10-10 | 2013-03-30
BARENDA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Gully Plug / Construction of Earthen Gully Plugs for Community | Boulder Check/Gully Plug | 1701/WC/9993625891 — गली प्‍लग बर्रेण्‍डा | Completed | 100000 | 34056 | 2012-09-26 | 2013-03-30
NURABAD | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Gully Plug / Construction of Earthen Gully Plugs for Community | Boulder Check/Gully Plug | 1701/WC/9993625955 — गली प्‍लग तिघरा नूराबाद | Completed | 400000 | 251064 | 2012-10-30 | 2012-12-23
JAKHODA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Gully Plug / Construction of Earthen Gully Plugs for Community | Boulder Check/Gully Plug | 1701/WC/9993625956 — गलीप्‍लग सपचोली | Completed | 36000 | 19008 | 2012-10-17 | 2013-03-20
DHANELA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Gully Plug / Construction of Earthen Gully Plugs for Community | Boulder Check/Gully Plug | 1701/WC/9993627548 — गली प्‍लग धनेला | Completed | 75000 | 31680 | 2012-11-24 | 2013-02-15
BICHOLA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1701/WC/9993627553 — तलैया निर्माण शमशान के पास लोलक पुर विचोला | Completed | 125000 | 121968 | 2013-01-18 | 2013-03-20
DHANELA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Loose Boulder Structure / Construction of Stone boulder Gully Plugs for Community | Boulder Check/Gully Plug | 1701/WC/9993627658 — लूज बोल्‍डर नाला बंधान धनेला | Completed | 200000 | 152247.2 | 2012-12-19 | 2013-03-20
DHANELA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1701/WC/9993627659 — नाला बंधान शोभाराम का पुरा धनेला | Completed | 450000 | 396437.5 | 2013-01-03 | 2013-03-15
JARERUA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Gully Plug / Construction of Earthen Gully Plugs for Community | Boulder Check/Gully Plug | 1701/WC/9993627660 — गली प्‍लग जरेरूआ | Completed | 50000 | 42768 | 2012-10-24 | 2013-03-25
BICHOLA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Artificial Recharge of Well Through Sand Filter / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1701/WC/9993627661 — सोख्‍ता गढढे हैण्‍ड पम्‍प पर लोलकपुर | Completed | 85000 | 42580.8 | 2013-02-01 | 2013-08-03
PILUA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Gully Plug / Construction of Earthen Gully Plugs for Community | Boulder Check/Gully Plug | 1701/WC/9993630092 — गली प्‍लग खेरा पिलुआ | Completed | 177000 | 138600 | 2013-02-11 | 2013-03-20
JARERUA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Sunken Pond / Construction of Community Water Harvesting Ponds | Farm Pond | 1701/WC/9993630093 — तलेया निर्माण जरेरूआ | Completed | 90000 | 74448 | 2013-02-26 | 2013-03-25
PILUA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1701/WC/9993630094 — मैढ बंधान नरसिंह पुर पिलुआ | Completed | 104000 | 97416 | 2013-02-20 | 2013-03-30
JARERUA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1701/WC/9993630098 — मैढ बंधान जरेरूआ | Completed | 200000 | 95040 | 2013-02-26 | 2013-03-25
BARENDA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1701/WC/9993630419 — मैढ बंधान बर्रेण्‍डा | Completed | 99000 | 95040 | 2013-02-21 | 2013-03-30
BARENDA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Sunken Pond / Construction of Community Water Harvesting Ponds | Farm Pond | 1701/WC/9993630657 — सोखता गड्डा बरेंडा | Completed | 130000 | 105544.38 | 2013-02-01 | 2013-10-10
NAUPURA | 2012-2013 | D--RURAL INFRASTUCTURE / Renovation of traditional water bodies | Strengthening of Embankment / Construction of Embankment for community | Renovation of traditional water bodies | 1701/WH/19952211 — रिंग बेन्‍ड बनी | Completed | 430000 | 55644.5 | 2012-11-06 | 2017-11-13
BADWARI | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Bharat Nirman Seva Kendra / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | /AV/22012034373130 — आंगनबाडी भवन एवं बाण्ड्रीवाल निर्माण कार्य बडवारी | Deleted | 256000 | 0 | 2018-07-20