## Work List
Exported on: 2026-09-01 00:53:01
Filters applied:
Data source: MGNREGA
District: GWALIOR
Block: GHATIGAON
Panchayat: BHAYPURA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
| 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Bharat Nirman Seva Kendra / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1703001061/AV/22012034640991 — पंचायत भवन निर्माण कार्य ग्राम भयपुरा | Ongoing | 1484000 | 1461219.98 | 2023-09-14
| 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1703001061/DP/22012034576866 — वृक्षमाला योजना के तहत छबच्चा नाले पर वृक्षारोपण कार्य ग्राम पंचायत भयपुरा | Ongoing | 230752.72 | 92611.04 | 2023-07-20
| 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Farm Forestry-Community / Boundary Line Plantation of Farm Forestry Trees for Community | Plantation | 1703001061/DP/22012034581321 — ब्रक्षरोपण कार्य नवीन काली माता मन्दिर रोड के किनारे से पुरानी कालीमाता मंदिर रोड के किनारे तक | Ongoing | 427106.07 | 147482 | 2023-08-17
| 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Horticulture -Community / Boundary Line Plantation of Horticulture Trees for Community | Plantation | 1703001061/DP/22012034582904 — ब्रक्षरोपण कार्य भाग-2 काली माता मन्दिर रोड के किनारे से पुरानी कालीमाता मंदिर रोड के किनारे तक | Ongoing | 427106.07 | 171674.42 | 2023-08-31
| 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1703001061/DP/22012034589056 — अमृत वाटिका चेक डेम छलबचा नाले पर ग्राम पंचायत भयपुरा | Closed | 55847.4 | 0 | 2023-04-15
| 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation of Forestry-Community / Boundary Line Plantation of Forestry Trees for Community | Plantation | 1703001061/DP/22012034609445 — CNG NIRMAN KARYA CHAMAR KHO GP BHAYPURA | Closed | 0 | 0 | 2023-08-16
| 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1703001061/DP/22012034620370 — ब्रक्षरोपण कार्य स्वच्छता परिसर ग्राम भयपुरा | Approved | 453563.17 | 0 | 2024-04-14
| 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Coast Line plntation of Forestry Trees-Individuals / Along the coast Line Plantation of Forestry Trees for Individuals | Plantation | 1703001061/IF/22012035125884 — ब्रक्षरोपण कार्य खेत की मेड पर नारायण / श्यामलाल ग्राम भयपुरा | Ongoing | 163586.73 | 16006 | 2023-08-11
| 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Coast Line plntation of Forestry Trees-Individuals / Along the coast Line Plantation of Forestry Trees for Individuals | Plantation | 1703001061/IF/22012035125885 — ब्रक्षरोपण कार्य खेत की मेड पर मानसिंह/ श्यामलाल ग्राम भयपुरा | Closed | 163586.73 | 0 | 2023-04-14
| 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Coast Line plntation of Forestry Trees-Individuals / Along the coast Line Plantation of Forestry Trees for Individuals | Plantation | 1703001061/IF/22012035125889 — ब्रक्षरोपण कार्य खेत की मेड पर जयश्रीराम/ धनीराम ग्राम भयपुरा | Ongoing | 163586.73 | 16589 | 2023-08-03
| 2023-2024 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1703001061/IF/22012035176221 — nadep nirman gurmel ke gar pr | Closed | 16247.79 | 0 | 2023-10-03
| 2023-2024 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1703001061/IF/22012035176238 — nadep nirman adiram ke gar pr bhaypura | Closed | 16247.79 | 0 | 2023-10-03
| 2023-2024 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1703001061/IF/22012035176254 — Nadep Nirman deewan kushwah ke gar pr Bhaypura | Closed | 16247.79 | 0 | 2023-10-03
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1703001061/IF/22012035342671 — Khet talab nirman satyaveer kushwah baypura | Approved | 0 | 0 | 2025-04-14
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1703001061/IF/22012035342770 — Khet talap nirmad Gurunath Singh bhaypura | Approved | 0 | 0 | 2025-04-14
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1703001061/IF/22012035347736 — JGS 2025 KHET TALAB NIRMAD GORU NATH SINGH bhaypura | New | 0 | 0 | 2025-04-14
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1703001061/IF/22012035370036 — Khet Talab nirman Guru nath JGS ABHIYAN 20250BHAYPURA | New | 0 | 0 | 2025-04-14
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1703001061/IF/22012035370893 — Khek Talab nirman Guru nath JGS ABHIYAN 2025 | Physically Completed | 147621.16 | 89256.98 | 2025-04-20 | 2026-04-11
| 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1703001061/IF/22012035371400 — DUG WELL Recharch structure Ragunath kushwah JGS 2025 | Completed | 25899.46 | 20339.07 | 2025-04-24 | 2026-01-23
| 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1703001061/IF/22012035371731 — DUG WELL RECHARGE STRUCTURE MUNNA/SIYAM LAL JGS A 2025 | Completed | 25899.46 | 19295.07 | 2025-04-24 | 2026-02-26
| 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1703001061/IF/22012035372395 — DUG WEEL RECHARGE STRUCTURE INDER SINGH JGS A 2025 bhaypura | Completed | 25899.46 | 22688.07 | 2025-05-01 | 2026-03-09
| 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1703001061/IF/22012035372500 — DUG WELL RECHARCH STRUCTURE DEVIRAM/RAM SINGH JGS A 2025 BHAYPURA | New | 0 | 0 | 2025-04-14
| 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1703001061/IF/22012035372550 — DUG WELL RECHARCH STRUCTURE DEVIRAM JGS A 2025 BHAYPURA | New | 0 | 0 | 2025-04-14
| 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1703001061/IF/22012035372776 — DUG WRLL RECHARGE STRUCTURE Gajraj Singh JGS A2025 | New | 0 | 0 | 2025-04-14
| 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1703001061/IF/22012035372782 — DUG WRLL RECHARGE STRUCTURE Gajraj Singh JGS A2025 | Completed | 25899.46 | 22277.67 | 2025-04-24 | 2026-03-10
| 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1703001061/IF/22012035372850 — DUG WEEL RECHARGE STRUCTURE DEVI SINGH JGS A 2025 bhaypura | Completed | 25899.46 | 11987.07 | 2025-04-20 | 2026-02-20
| 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1703001061/IF/22012035439552 — Dugwell recharge well motiram ke koop per baypura | Approved | 0 | 0 | 2025-04-14
| 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1703001061/IF/22012035449965 — DUG WEEL RECHARGE STRUCTURE murari JGS A 2025 bhaypura | Completed | 25899.46 | 21122.07 | 2025-05-10 | 2026-03-09
| 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-borewellrecharge for Indiv / Construction of Sand filter for Borewell recharge for Individual | Well Recharge | 1703001061/IF/22012035450074 — GUG WEEL RECHARGE STRUCTURE Hari Singh JGS A2025 BHAYPURA | Approved | 0 | 0 | 2025-04-14
| 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1703001061/IF/22012035472668 — Dugwell RECHARGE harisingh ke koop per JGSA 2025 | New | 0 | 0 | 2025-04-14
| 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1703001061/IF/22012035473303 — DUG WEEL RECHARGE STRUCTURE HARI SINGH JGS A 2025 BHAYPURA | Approved | 0 | 0 | 2025-04-14
| 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1703001061/IF/22012035475360 — DUG WEEL RECHARGE STRUCTURE HARI SINGH JGS A 20250bhaypura | Completed | 25899.46 | 21122.07 | 2025-05-10 | 2026-03-09
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1703001061/IF/22012035624651 — EK BAGIYA MAA KE NAAM PHOOLKALI KE KHET PAR 135C GP BHAYPURA | New | 0 | 0 | 2025-08-16
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1703001061/IF/22012035624657 — EK BAGIYA MAA KE NAAM PHOOLKALI KE KHET PAR 135C GP BHAYPURA | New | 0 | 0 | 2025-08-16
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1703001061/IF/22012035624663 — EK BAGIYA MAA KE NAAM PHOOLKALI KE KHET PAR 135C GP BHAYPURA | New | 0 | 0 | 2025-08-16
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1703001061/IF/22012035624674 — EK BAGIYA MAA KE NAAM PHOOLKALI KE KHET PAR 135C GP BHAYPURA | New | 0 | 0 | 2025-08-16
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1703001061/IF/22012035624679 — EK BAGIYA MAA KE NAAM BRAJESH KE KHET PAR 137C GP BHAYPURA | Ongoing | 260769.1 | 79631 | 2025-10-24
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1703001061/IF/22012035624697 — EK BAGIYA MAA KE NAAM PHOOLKALI KE KHET PAR 135C GP BHAYPURA | New | 0 | 0 | 2025-08-16
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1703001061/IF/22012035624702 — EK BAGIYA MAA KE NAAM PHOOLKALI KE KHET PAR 135C GP BHAYPURA | Ongoing | 260769.1 | 35235 | 2026-01-01
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703001061/IF/IAY/4759301 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118359812 | Ongoing | 23490 | 18684 | 2025-02-20
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703001061/IF/IAY/4762612 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121012275 | Ongoing | 23490 | 20790 | 2025-02-13
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703001061/IF/IAY/4765290 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115395567 | Completed | 23490 | 21492 | 2025-02-13 | 2026-02-16
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703001061/IF/IAY/4802266 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150940576 | Completed | 23490 | 21249 | 2025-02-13 | 2026-04-02
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703001061/IF/IAY/4802267 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150940927 | Completed | 23490 | 23274 | 2025-02-13 | 2026-02-14
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703001061/IF/IAY/4802269 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150941406 | Completed | 23490 | 21231 | 2025-02-13 | 2026-04-22
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703001061/IF/IAY/4802276 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150949265 | Ongoing | 23490 | 9396 | 2025-06-26
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703001061/IF/IAY/4802277 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150950109 | Ongoing | 23490 | 21060 | 2025-02-13
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703001061/IF/IAY/4884547 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118359668 | Physically Completed | 23490 | 17856 | 2025-02-13 | 2026-01-17
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703001061/IF/IAY/4886680 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150946310 | Physically Completed | 23490 | 19881 | 2025-03-06 | 2026-04-05
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703001061/IF/IAY/5825400 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106843739 | Physically Completed | 23490 | 4437 | 2025-10-31 | 2026-04-05
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703001061/IF/IAY/5826062 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106502122 | Completed | 23490 | 21924 | 2025-11-27 | 2026-04-02
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703001061/IF/IAY/5828492 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118359972 | Ongoing | 23490 | 13833 | 2025-10-31
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703001061/IF/IAY/5828493 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118360164 | Ongoing | 23490 | 18270 | 2025-11-06
| 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Development of chaur Land for Community | Land Development | 1703001061/LD/22012034940426 — cpw nirman samudhayik swachhtha parisar gram panchayat bhaypura | Approved | 999828.17 | 0 | 2024-04-14
| 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1703001061/LD/22012034951624 — Khel Medan Kali mata Mandir ke pas Bhaypura | Approved | 0 | 0 | 2025-03-08
| 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Fallow Land for Community / Development of Fallow Land for Community | Land Development | 1703001061/LD/22012034951657 — khel medan nirmad kali mata mandir ke pas bhaypura | Approved | 0 | 0 | 2025-03-08
| 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Repair & maint of Cement Concrete Roads for Comm / Repair and maintenance of Cement Concrete Roads for Community | Repair & maint of Road | 1703001061/RC/22012034658626 — cc road seh nali nirman main road se durg singh ke gar ki or bhaypura | Completed | 41137 | 38670 | 2023-10-02 | 2026-02-28
| 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Repair & maint of Cement Concrete Roads for Comm / Repair and maintenance of Cement Concrete Roads for Community | Repair & maint of Road | 1703001061/RC/22012034658651 — cc road seh nali nirman mahendra ke gar se mandir ki or gp bhaypura | Completed | 28796 | 16569 | 2023-10-02 | 2025-07-14
| 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Repair & maint of Cement Concrete Roads for Comm / Repair and maintenance of Cement Concrete Roads for Community | Repair & maint of Road | 1703001061/RC/22012034658654 — cc road seh nali nirman main road se alkesh ke gar ki or bhaypura | Completed | 37023 | 32033 | 2023-10-02 | 2025-07-14
| 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1703001061/RC/22012034683902 — cc road seh nali nirman balkishan ke gar se gopal ke gar ki or gram bhaypura | Closed | 28796 | 0 | 2023-08-16
| 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Vermi Compost structure for Community / Construction of Vermi Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1703001061/RS/22012034692881 — Gram Bhaypura Me Naveen Samudhayik Swachtha Parisar Nirman Kali Mata Mandir Parisar | Completed | 44000 | 39110 | 2023-08-24 | 2025-07-26
| 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1703001061/RS/22012034705355 — Nala Nirman Omprakash ke Gar se Narkhora Puliya Ki or GP Bhaypura | Ongoing | 1036415.54 | 69394 | 2023-10-02
| 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1703001061/RS/22012034705357 — Nala Nirman Loten Ke Gar se Suresh ke Gar Ki Or Tori Ka Pura GP Bhaypura | Completed | 516216.52 | 457553 | 2023-10-02 | 2025-07-08
| 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1703001061/RS/22012034705358 — Nala Nirman Loten Ke Gar se Suresh ke Gar Ki Or Tori Ka Pura GP Bhaypura | Deleted | 0 | 0 | 2023-08-16
| 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Repair & maint of Open/Covered Grey_Water for Comm / Repair and maintenance of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1703001061/RS/22012035113572 — nali nirman uttam singh kushwah ke gar se gajraj member ke gar ki or gp bhaypura | Ongoing | 112168 | 104081.28 | 2023-10-02
| 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1703001061/RS/22012035114538 — Nala Nirman Motiram Ke Gar se Narkhora Puliya Ki Or GP Bhaypura | Closed | 0 | 0 | 2023-08-16
| 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Repair & maint of Open/Covered Grey_Water for Comm / Repair and maintenance of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1703001061/RS/22012035123624 — nala nirman murari ke ghar se satyaveer ke khet ki or gram bhaypura | Completed | 1090880.99 | 1069779 | 2024-03-09 | 2025-06-12
| 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1703001061/RS/22012035123625 — nala nirman chandan ke ghr se vijay singh ke ghar ki or gram bhaypura | Closed | 440609.75 | 0 | 2024-01-25
| 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & maint of Community Ponds for Comm / Repair and maintenance of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1703001061/WC/22012035043920 — Nala Nirman Mahendra Gurjar ke Gar se Primary School Chak Bhaypura Ki Or GP Bhaypura | Completed | 1090875.35 | 1050648.5 | 2023-04-13 | 2025-07-08
| 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1703001061/WC/22012035045014 — Nala nirman satyaveer ki gali se dilip dairy wale ki Boundary ki or | Deleted | 0 | 0 | 2023-01-24
| 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1703001061/WC/22012035045015 — Nala nirman satyaveer ki gali se dilip dairy wale ki Boundary ki or | Completed | 656525.21 | 627786.5 | 2023-04-13 | 2025-07-26
| 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1703001061/WC/22012035052842 — Chek Dam Nirman chalbacha Nale Per Gram Bhaypura | Completed | 537000 | 535370 | 2023-04-13 | 2025-08-10
| 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Level Bench Terrace Terrace for Comm / Construction of Level Bench Terrace for Community | Terracing | 1703001061/WC/22012035094732 — Contootrench Nirman Marghat Wali Pahadi pr GP Bhaypura | Closed | 0 | 0 | 2023-04-15
| 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1703001061/WC/22012035169874 — Perculation tank nirman karya pappu sardar ke khet ke pass bhaypura | Physically Completed | 866407.87 | 603564.96 | 2024-03-09 | 2026-04-10
| 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1703001061/WC/22012035169875 — Perculation tank nirman karya pappu sardar ke khet ke pass bhaypura | Deleted | 0 | 0 | 2024-01-25
| 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1703001061/WC/22012035169878 — Perculation tank nirman karya malkeet sardar ke khet ke pass bhaypura | Closed | 489864.85 | 663 | 2024-03-09
| 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1703001061/WC/22012035169882 — Perculation tank nirman karya gurunath sardar ke khet ke pass bhaypura | Physically Completed | 489864.85 | 238835.46 | 2024-03-09 | 2026-04-15
| 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1703001061/WC/22012035205249 — contotrench nirman karya bhaypura pahadi pr gram bhaypura | Ongoing | 399691.42 | 146422.56 | 2026-03-19
| 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1703001061/WC/22012035205256 — loose boulder nirman karya narkora nale pr gram bhaypura | Completed | 119869.86 | 114544.68 | 2025-01-30 | 2026-02-22
| 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1703001061/WC/22012035205267 — loose boulder nirman karya shantidam nale pr gram bhaypura | Physically Completed | 119449.63 | 112428.78 | 2026-03-12 | 2026-06-24
| 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1703001061/WC/22012035205277 — loose boulder nirman karya peepri kho nale pr gram bhaypura | Approved | 0 | 0 | 2024-04-14
| 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1703001061/WC/22012035205284 — loose boulder nirman karya chak bhaypura jharna nale pr gram bhaypura | Approved | 0 | 0 | 2024-04-14
| 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1703001061/WC/22012035246566 — Loose Boulder Nirman Shyar Wale Nale Per Bhaypura | Physically Completed | 199794.72 | 187978.03 | 2025-03-06 | 2026-04-13
| 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1703001061/WC/22012035246690 — Loose Boulder karya shayar wale nale pr Bhaypura | Approved | 0 | 0 | 2025-01-26
| 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1703001061/WC/22012035247596 — Loose Boulder karya Moraiya Kho wale nale pr Bhaypura | Physically Completed | 199794.72 | 174985.93 | 2025-02-27 | 2026-04-13
| 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1703001061/WC/22012035247597 — Loose Boulder karya Jirna wale Kho nale pr Bhaypura | Physically Completed | 199794.72 | 184721.53 | 2025-03-13 | 2026-04-13
| 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1703001061/WC/22012035247598 — Loose Boulder karya Mata wale Pahadi kho nale pr Bhaypura | Physically Completed | 199794.72 | 184795.63 | 2025-03-13 | 2026-04-13
| 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1703001061/WC/22012035247599 — Loose Boulder karya Harmohan ke Khet wale nale pr Bhaypura | Completed | 199794.72 | 188842.03 | 2025-03-13 | 2026-03-02
| 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1703001061/WC/22012035255594 — CHECK DAM NIRMAN KARYA NARKHORA NALE PAR GRAM BHAYPURA | Physically Completed | 711000 | 581768.43 | 2025-09-25 | 2026-06-06
| 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1703001061/WC/22012035260958 — Loose boulder jalaiwali kho nale per baypura | Physically Completed | 199655.95 | 183199.63 | 2025-09-25 | 2026-04-09
| 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1703001061/WC/22012035260973 — Loose boulder structure Rudra bali kho nale per bhaypura kho | New | 0 | 0 | 2025-04-07
| 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1703001061/WC/22012035260989 — LBS rudrawali kho nale per bhaypura | Physically Completed | 199655.95 | 173584.5 | 2025-09-25 | 2026-04-09
| 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1703001061/WC/22012035261004 — Loose boulder Jageswar kho nale per bhaypura | Physically Completed | 199655.95 | 175832.49 | 2025-09-25 | 2026-04-09
| 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1703001061/WC/22012035261016 — Loose boulder Odi kho nale per bhaypura | Physically Completed | 199655.95 | 174156.95 | 2025-09-25 | 2026-04-09
| 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1703001061/WC/22012035261021 — Loose boulder Chamar kho ke uper bale nale per bhaypura | Physically Completed | 199655.95 | 180258.27 | 2025-09-25 | 2026-04-09
| 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1703001061/WC/22012035327616 — lbs | New | 0 | 0 | 2025-10-02
| 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1703001061/WC/22012035328098 — loose boulder nirman siddh baba ke nale par | Approved | 0 | 0 | 2025-10-02
| 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1703001061/WC/22012035328100 — loose boulder nirman sardar ke nale par | New | 0 | 0 | 2025-10-02
| 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1703001061/WC/22012035328101 — loose boulder nirman sardar ke nale par | Approved | 0 | 0 | 2025-10-02
| 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1703001061/WC/22012035328407 — loose boulder nirman bhadkho nale par | Approved | 0 | 0 | 2025-10-02
| 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1703001061/WC/22012035328408 — loose boulder nirman sankhora ke nale par | Approved | 0 | 0 | 2025-10-02