## Work List
Exported on: 2026-08-31 08:13:29
Filters applied:
Data source: MGNREGA
District: GWALIOR
Block: MORAR
Panchayat: KASHIPUR
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
| 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Sericulture- in Fields-Community / Block Plantation of Sericulture Trees in Fields for Community | Plantation | 1703002083/DP/22012034576599 — वृक्षारोपण कार्य झिर वाले हनुमान जी मंदिर पर गुहिसर का पुरा | Ongoing | 238574.63 | 12557 | 2023-07-24
| 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Sericulture- in Fields-Community / Block Plantation of Sericulture Trees in Fields for Community | Plantation | 1703002083/DP/22012034576600 — वृक्षारोपण कार्य बाबा के डांडे पर काशीपुर | Ongoing | 232374.3 | 8358 | 2023-07-24
| 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Farm Forestry-Community / Boundary Line Plantation of Farm Forestry Trees for Community | Plantation | 1703002083/DP/22012034586630 — अमृत वाटिका वृक्षारोपण कार्य प्रा.शा.वि. आदिवासी का पुरा ग्रा.प.काशीपुर | Ongoing | 55847.4 | 1989 | 2023-08-08
| 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation - Shelter Belt for Individuals / Block Plantation of Shelter Belt Trees for Individuals | Plantation | 1703002083/IF/22012035088508 — हितग्राही मूलक वृक्षारोपण कार्य गोपीराम / चुरामन | Deleted | 0 | 0 | 2023-05-04
| 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation of Forstry Trees for Individual / Boundary Line Plantation of Forestry Trees for Individuals | Plantation | 1703002083/IF/22012035088663 — हितग्राही मूलक वृक्षारोपण कार्य गोपीराम / चूरामन काशीपुर | Deleted | 0 | 0 | 2023-05-04
| 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation of Forstry Trees for Individual / Boundary Line Plantation of Forestry Trees for Individuals | Plantation | 1703002083/IF/22012035088667 — हितग्राही मूलक वृक्षारोपण कार्य गोपीराम / चुरामन काशीपुर | Deleted | 0 | 0 | 2023-05-04
| 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Sericulture in fields-Individuals / Block Plantation of Sericulture Trees in fields for Individuals | Plantation | 1703002083/IF/22012035089094 — वृक्षारोपण कार्य गोपीराम / चुरामन के खेत पर काशीपुर | Deleted | 0 | 0 | 2023-05-04
| 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Sericulture in fields-Individuals / Block Plantation of Sericulture Trees in fields for Individuals | Plantation | 1703002083/IF/22012035089098 — वृक्षारोपण कार्य गोपीराम / चुरामन के खेत पर काशीपुर | Deleted | 0 | 0 | 2023-05-04
| 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Sericulture in fields-Individuals / Block Plantation of Sericulture Trees in fields for Individuals | Plantation | 1703002083/IF/22012035089307 — वृक्षरोपण कार्य गोपीराम /चुरामन के खेत पर काशीपुर | Ongoing | 133391.6 | 35516 | 2023-07-24
| 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Block Plantation of Farm Forestry Trees in Fields for Individuals | Plantation | 1703002083/IF/22012035106206 — वृक्षारोपण कार्य कोमल सिंह गुर्जर / छोटे सिंह के खेत पर काशीपुर | Deleted | 0 | 0 | 2023-05-03
| 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Sericulture in fields-Individuals / Block Plantation of Sericulture Trees in fields for Individuals | Plantation | 1703002083/IF/22012035106209 — वृक्षारोपण कार्य कोमल सिंह गुर्जर / छोटे सिंह के खेत पर काशीपुर | Ongoing | 133391.6 | 14546 | 2023-07-24
| 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Sericulture in fields-Individuals / Block Plantation of Sericulture Trees in fields for Individuals | Plantation | 1703002083/IF/22012035106213 — वृक्षारोपण कार्य/ छोटे सिंह / अर्जुन सिंह के खेत पर काशीपुर | Ongoing | 133391.6 | 4159 | 2023-07-24
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1703002083/IF/22012035239169 — VRAKCHAROPAN RAGHUVEER SINGH / PRABHU DAYAL KASHIPUR | Deleted | 0 | 0 | 2024-06-12
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1703002083/IF/22012035239178 — VRAKCHAROPAN RAGHUVEER SINGH / PRABHU DAYAL KASHIPUR | Closed | 145230.58 | 0 | 2024-07-24
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1703002083/IF/22012035300500 — PMAY NIRMAN RAMVEER / RAJARAM GUHISAR KA PURA | Deleted | 21870 | 0 | 2025-01-26
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1703002083/IF/22012035300568 — PMAY NIRMAN RAMVEER / RAJARAM GUHISAR KA PURA | Deleted | 0 | 0 | 2025-01-26
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1703002083/IF/22012035300572 — PMAY NIRMAN RAMVEER / RAJARAM GUHISAR KA PURA | Completed | 21870 | 20097 | 2025-04-18 | 2026-04-16
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1703002083/IF/22012035300582 — PMAY NIRMAN MUKESH UTTAM GUHISAR KA PURA KASHIPUR | Completed | 21870 | 21402 | 2025-04-18 | 2026-04-16
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1703002083/IF/22012035300594 — PMAY NIRMAN KUNDAN SINGH / PREM SINGH GOSPURA KASHIPUR | Completed | 21870 | 21402 | 2025-05-02 | 2026-04-16
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1703002083/IF/22012035300599 — PMAY NIRMAN INDAL SINGH / GANGARAM GOSPURA KASHIPUR | Completed | 21870 | 21663 | 2025-04-18 | 2026-04-16
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1703002083/IF/22012035300605 — PMAY MAHESH / DALIP GOSPURA KASHIPUR | Completed | 21870 | 20358 | 2025-04-18 | 2026-04-16
| 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1703002083/IF/22012035370544 — JGSA 2025 DUGWELL RICHARJ STRUCTURE SANTOSH BAGHEL KE KUA PAR KASHIPUR | Completed | 25899.46 | 24175 | 2025-04-22 | 2026-03-29
| 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1703002083/IF/22012035370668 — JGSA 2025 DUGWELL RICHARJ STRUCTURE SUNEEL BAGHEL KE KUA PAR KASHIPUR | Completed | 25899.46 | 25480 | 2025-04-22 | 2026-03-29
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1703002083/IF/22012035376594 — JGSA 2025 KHET TALAB NIRMAN PARMANAND / CHURAMAN KASHIPUR | Completed | 147621.16 | 111969 | 2025-04-22 | 2026-04-20
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1703002083/IF/22012035376634 — JGSA 2025 KHET TALAB NIRMAN BHAN SINGH / SUMER SINGH KASHIPUR | Physically Completed | 147621.16 | 137399.62 | 2025-04-22 | 2026-04-16
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1703002083/IF/22012035469862 — JGSA 2025 KHET TALAB NIRMAN DAYANAND SINGH / BABU LAL KE KHET PAR KASHIPUR | Approved | 0 | 0 | 2025-04-14
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1703002083/IF/22012035469896 — JGSA 2025 KHET TALAB NIRMAN ANAND SINGH / BABU LAL KE KHET PAR KASHIPUR | Physically Completed | 147621.16 | 101960 | 2025-05-07 | 2026-05-07
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1703002083/IF/22012035469943 — JGSA 2025 KHET TALAB NIRMAN RAGHUVEER SINGH / PRABHU DAYAL KE KHET PAR KASHIPUR | Completed | 147621.16 | 35496 | 2025-05-07 | 2026-05-05
| 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1703002083/IF/22012035472242 — JGSA 2025 DUGWELL RICHARJ STRUCTURE SEEMA BAGHEL KE KUA PAR KASHIPUR | Completed | 25899.46 | 25480 | 2025-05-08 | 2026-03-29
| 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1703002083/IF/22012035472291 — JGSA 2025 DUGWELL RICHARJ STRUCTURE SEVARAM / BATURI KASHIPUR | Completed | 25899.46 | 25480 | 2025-05-08 | 2026-03-29
| 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Construction of Stone graded Bund for Community / Construction of Stone graded Bund for Community | Construction of Bund | 1703002083/LD/22012034602654 — SHNTI DHAM NIRMAN KASHIPUR | Closed | 314999.58 | 0 | 2024-01-24
| 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Construction of Pebble graded Bund for Community / Construction of Pebble graded Bund for Community | Construction of Bund | 1703002083/LD/22012034602655 — SHANTI DHAM NIRMAN PATEL KA PURA KASHIPUR | Closed | 314999.58 | 0 | 2024-01-25
| 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Construction of Pebble graded Bund for Community / Construction of Pebble graded Bund for Community | Construction of Bund | 1703002083/LD/22012034602656 — SHANTI DHAM NIRMAN GOSPURA KASHIPUR | Closed | 314999.58 | 0 | 2024-01-27
| 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Construction of Pebble graded Bund for Community / Construction of Pebble graded Bund for Community | Construction of Bund | 1703002083/LD/22012034602657 — SHANTI DHAM NIRMAN ADIWASI PURA KASHIPUR | Closed | 314999.58 | 0 | 2024-01-28
| 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Construction of Pebble graded Bund for Community / Construction of Pebble graded Bund for Community | Construction of Bund | 1703002083/LD/22012034602658 — SHANTI DHAM NIRMAN GUHISAR KA PURA KASHIPUR | Closed | 314999.58 | 0 | 2024-01-29
| 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1703002083/RC/22012034628142 — C-C ROAD MAIN ROAD BANJARON KE PURA SE JHIR KE HANUMN MANDIR KI OR GUHISAR KA PURA | Completed | 30600 | 29682 | 2023-06-02 | 2024-11-19
| 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1703002083/RC/22012034659480 — C-C ROAD NIRMAN GANGA RAM KE GHAR SE GOVIND KE GHAR TAK GOSPURA KASHIPUR | Ongoing | 55800 | 1105 | 2023-10-06
| 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1703002083/RS/22012034684836 — NALI NIRMAN ADIWASI PURA PAR GRAM PANCHAYAT KASHIPUR | Closed | 0 | 0 | 2022-10-02
| 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1703002083/RS/22012035114210 — NALI NIRMAN KARY ADIWASI PURA SE NADI KI OR GRAM ADIWASI KA PURA KASHIPUR | Ongoing | 1253941.3 | 0 | 2023-08-19
| 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1703002083/WC/22012035034645 — LBS - NO 01 (LOOSE BOLDER STRUCTURE ) NIRMAN BHADAWNA SE ADIVASIPURA NAALE PAR | Completed | 233180.58 | 157332.2 | 2023-05-03 | 2024-06-28
| 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1703002083/WC/22012035034648 — LBS - NO 02 (LOOSE BOLDER STRUCTURE ) NIRMAN BHADAWNA SE ADIVASIPURA NAALE PAR | Completed | 233360.58 | 152502.2 | 2023-05-03 | 2024-06-28
| 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1703002083/WC/22012035034650 — LBS - NO 03 (LOOSE BOLDER STRUCTURE ) NIRMAN BHADAWNA SE ADIVASIPURA NAALE PAR | Completed | 233180.58 | 148809.6 | 2023-07-07 | 2024-06-28
| 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1703002083/WC/22012035034651 — LBS - NO 04 (LOOSE BOLDER STRUCTURE ) NIRMAN BHADAWNA SE ADIVASIPURA NAALE PAR | Completed | 233180.58 | 144831.6 | 2023-09-22 | 2024-06-28
| 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1703002083/WC/22012035034652 — LBS - NO 05 (LOOSE BOLDER STRUCTURE ) NIRMAN BHADAWNA SE ADIVASIPURA NAALE PAR | Completed | 309860.1 | 151019.6 | 2023-09-22 | 2024-06-28
| 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1703002083/WC/22012035034854 — CANTU TRANCH NIRMAN MEHTAR WALI PHADI PAR KASHIPUR | Completed | 493367.58 | 423589 | 2023-05-18 | 2024-01-28
| 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1703002083/WC/22012035034856 — TALAB NIRMAN KOTA WALI PHADIYA KE PASS KASHIPUR | Closed | 0 | 0 | 2022-10-02
| 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1703002083/WC/22012035034858 — TALAB NIRMAN DANT KHO KE NICHE KASHIPUR | Closed | 0 | 0 | 2022-10-02
| 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1703002083/WC/22012035036000 — CONTU TRANCH NIRMAN MAHTAR WALI PHADI PAR PART 02 KASHIPUR | Completed | 493367.58 | 416816 | 2023-05-03 | 2025-04-16
| 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1703002083/WC/22012035036915 — PARCOLATION TANK NIRMAN DANT KHO KE NICHE KASHIPUR | Closed | 0 | 0 | 2022-10-02
| 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1703002083/WC/22012035051212 — QGIS LBS - 06 (LOOSE BOLDER STRUCTURE ) BHADAWANA SE ADIWASI PURA NALE PAR NIRMAN | Deleted | 0 | 0 | 2023-03-11
| 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1703002083/WC/22012035051213 — QGIS LBS - 07 (LOOSE BOLDER STRUCTURE ) BHADAWANA SE ADIWASI PURA NALE PAR NIRMAN | Deleted | 0 | 0 | 2023-03-11
| 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1703002083/WC/22012035051216 — QGIS LBS - 06 (LOOSE BOLDER STRUCTURE ) BHADAWANA SE ADIWASI PURA NALE PAR NIRMAN | Closed | 0 | 0 | 2023-03-11
| 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1703002083/WC/22012035051217 — QGIS LBS - 07 (LOOSE BOLDER STRUCTURE ) BHADAWANA SE ADIWASI PURA NALE PAR NIRMAN | Closed | 0 | 0 | 2023-03-11
| 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1703002083/WC/22012035051219 — QGIS LBS - 08 (LOOSE BOLDER STRUCTURE ) BHADAWANA SE ADIWASI PURA NALE PAR NIRMAN | Closed | 0 | 0 | 2023-03-11
| 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1703002083/WC/22012035065285 — QGIS TALAB NIRMAN KALIJRA KHO BHADAWNA DHAM KASHIPIU | Closed | 0 | 0 | 2023-04-15
| 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1703002083/WC/22012035065397 — QGIS TALAB NIRMA KOTA WALI PAHADIYA KE PAAS KASHIPUR | Physically Completed | 1180900.71 | 452530 | 2023-10-04 | 2026-04-26
| 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1703002083/WC/22012035065399 — QGIS TALAB NIRMA DANT KHO KE NICHE KASHIPUR | Physically Completed | 1412988.76 | 1036150.93 | 2023-10-04 | 2026-04-09
| 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1703002083/WC/22012035207525 — JAL GANGA SAMBARDHAN CONTUTRANCH NIRMAN KOTA WALI PHADIYA PAR PART 01 KASHIPUR | Approved | 308019.69 | 0 | 2024-06-12
| 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1703002083/WC/22012035207531 — JAL GANGA SAMBARDHAN CONTUTRANCH NIRMAN KOTA WALI PHADIYA PAR PART 02 KASHIPUR | Approved | 318689.23 | 0 | 2024-06-12
| 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Underground Dykes for Community / Construction of Underground Dykes for Community | Underground Dyke for Ground Water Recharge | 1703002083/WC/22012035209418 — JAL GANGA SAMBARDHAN LBS NO 06 NIRMAN BHADAWNA NALE PAR KASHIPUR | Approved | 203098.41 | 0 | 2024-06-12
| 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Underground Dykes for Community / Construction of Underground Dykes for Community | Underground Dyke for Ground Water Recharge | 1703002083/WC/22012035209423 — JAL GANGA SAMBARDHAN LBS NO 07 NIRMAN BHADAWNA NALE PAR KASHIPUR | Approved | 200857.27 | 0 | 2024-06-12
| 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Underground Dykes for Community / Construction of Underground Dykes for Community | Underground Dyke for Ground Water Recharge | 1703002083/WC/22012035209428 — JAL GANGA SAMBARDHAN LBS NO 08 NIRMAN BHADAWNA NALE PAR KASHIPUR | Approved | 200857.27 | 0 | 2024-06-12
| 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1703002083/WC/22012035226318 — CONTU TRANCH NIRMAN ADIWASI PAHADIYA PAR GRAM ADIWASI KA PURA KASHIPUR | Approved | 0 | 0 | 2024-10-05
| 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1703002083/WC/22012035226326 — CONTU TRANCH NIRMAN MEHTAR WALI PHADI PAR PART 03 KASHIPUR | Approved | 0 | 0 | 2024-10-02
| 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1703002083/WC/22012035274570 — JGSA 2025 KHET TALAB NIRMAN BHAN SINGH / SUMER SINGH KASHIPUR | Deleted | 0 | 0 | 2025-04-14