## Work List
Exported on: 2026-08-24 13:10:23
Filters applied:
Data source: MGNREGA
District: GWALIOR
Block: BHITARWAR
Panchayat: SIRSULA(P)
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
| 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1703004079/AV/22012034581812 — DINING ROOM SHA.PRA.VI.NONEVAR | Closed | 0 | 0 | 2021-04-20
| 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1703004079/AV/22012034621047 — CPW NIrman Anganwadi Bhavan Bhadeshwar | Completed | 860000 | 803198.71 | 2022-09-27 | 2023-10-06
| 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Forest Protection / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1703004079/DP/22012034237681 — CPW NIRMAN | Deleted | 0 | 0 | 2017-01-26
| 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1703004079/DP/22012034239127 — SATIDHAM BHADESWAR | Completed | 180000 | 170915.21 | 2017-05-09 | 2017-11-22
| 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Grass Land Development and Silvi-pasture / Development of Silvipasture Grassslands for Community | Grass Land Development | 1703004079/DP/22012034328873 — CPW g ps sirsula | Deleted | 0 | 0 | 2017-10-02
| 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Land development / Levelling/shaping of Wasteland Land for Community | Land Development | 1703004079/DP/22012034328880 — CPW NIRMAN G P S NONEVAR | Deleted | 0 | 0 | 2017-10-02
| 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1703004079/DP/22012034432494 — CPW nirman shaskiy prathamik school nonewar | Physically Completed | 368000 | 343577.85 | 2018-10-02 | 2026-04-10
| 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1703004079/DP/22012034432755 — C P W NIRMAN MADMIK VIDYALAYA OR PRATHAMIK VIDYALYA SIRSULA | Completed | 912000 | 664916.93 | 2018-10-02 | 2024-06-21
| 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1703004079/DP/22012034587732 — Amrit watika virchharopan gram bhadeshwar | Closed | 55847.4 | 1989 | 2023-08-22
| 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation of Forestry-Community / Boundary Line Plantation of Forestry Trees for Community | Plantation | 1703004079/DP/22012034610191 — Baundary wall nirman shanti dham bhadeshwar | Closed | 523485.96 | 442 | 2023-10-06
| 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Land development / Levelling/shaping of Wasteland Land for Community | Land Development | 1703004079/DP/9993630637 — BOUNDARY WALL GOVT.PRIMARY SCHOOL BHDESHWAR | Completed | 377996 | 396838.4 | 2015-11-03 | 2018-03-27
| 2020-2021 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1703004079/FP/22012034366317 — Flood control baal nirman non nadi ke pas bhadeshwar | Deleted | 0 | 0 | 2020-06-08
| 2020-2021 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Renovation of Flood/ Diversion Channel for Comm / Renovation of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1703004079/FP/22012034366318 — Flood control baal nirman non nadi ke pas bhadeshwar | Deleted | 0 | 0 | 2020-06-07
| 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Renovation of Flood/ Diversion Channel for Comm / Renovation of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1703004079/FP/22012034366321 — Flood control ball nirman non nadi ke pas bhadeshwar | Physically Completed | 1314800 | 813602 | 2021-08-17 | 2026-05-21
| 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of drain for coastal protection for Comm. / Construction of Storm Water drain for coastal protection for Community | Works for Flood Control and Protection | 1703004079/FP/22012034629558 — Flood Control Wall Nirman Anganwadi Ke pas Gram Bhadeshwar | Completed | 877000 | 871534.49 | 2022-09-13 | 2023-10-06
| 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of drain for coastal protection for Comm. / Construction of Storm Water drain for coastal protection for Community | Works for Flood Control and Protection | 1703004079/FP/22012034630516 — Flood Cantrol wall Nirman men Road se Aganwadi ke pichhe non nadi Bhdeshwar | Physically Completed | 855000 | 849570.32 | 2022-11-08 | 2026-05-23
| 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of drain for coastal protection for Comm. / Construction of Storm Water drain for coastal protection for Community | Works for Flood Control and Protection | 1703004079/FP/22012034632368 — Flood Cantrol wall Nirman Poorvav Flood kantrol wal se shanti dham ki or bhadeshwar | Closed | 1310000 | 0 | 2023-02-01
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1703004079/IC/22012034891217 — JGSA 2025 Loose boldar nirman Talwindar singh ke khet ke paad | New | 0 | 0 | 2025-04-14
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1703004079/IC/22012034891221 — JGSA 2025 Loose boldar nirman sowran singh ke khet ke paas | New | 0 | 0 | 2025-04-14
| 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1703004079/IF/1000040753 — pashoo shed darshan singh/asha singh | Completed | 34337.2 | 33879.81 | 2013-10-01 | 2014-10-13
| 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1703004079/IF/1000041652 — CATTLE SHED-GURUDEEP KAUR/JARNEL SINGH BHADESWAR | Completed | 34334 | 33879.81 | 2013-10-01 | 2014-10-13
| 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1703004079/IF/1000041662 — CATTLE SHED MALVINDAR SINGH / TARSEM SINGH | Completed | 34334 | 31210.81 | 2013-10-01 | 2016-08-06
| 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1703004079/IF/1000041667 — CATTLE SHED GURUDEV SINGH/DHEER SINGH | Completed | 34334 | 33722.81 | 2013-10-01 | 2014-10-13
| 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1703004079/IF/1000041679 — CATTLE SHED AJEET SINGH/MEGH SINGH | Completed | 34334 | 33722.81 | 2013-10-01 | 2014-10-13
| 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1703004079/IF/22012034315458 — NADEP PIT 2 | Deleted | 0 | 0 | 2017-01-26
| 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1703004079/IF/22012034315459 — NADEP PIT 3 | Deleted | 0 | 0 | 2017-01-26
| 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1703004079/IF/22012034315460 — NADEP PIT 4 | Deleted | 0 | 0 | 2017-01-26
| 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1703004079/IF/22012034315461 — NADEP PIT 5 | Deleted | 0 | 0 | 2017-01-26
| 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Bondry Block - Coastal Shelter Belt-Individuals / Boundary Block Plantation of Coastal Shelter Belt Trees for Individuals | Other Works | 1703004079/IF/22012034346012 — BRACHHA ROPAN KARYA BHADESHVAR GANI SALAMPUR ROAD SCHOOL BHADESHVAR | Ongoing | 335000 | 13255 | 2018-09-25
| 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Biodrainage in Fields-Individuals / Block Plantation of Biodrainage Trees in Fields for Individuals | Plantation | 1703004079/IF/22012034346016 — BRACHHA ROPAN KARYA SHANTI DHAM PRATHAMIK VIDHYALAY | Ongoing | 335000 | 7710 | 2017-07-11
| 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1703004079/IF/22012034424870 — NADEP LAKHVINDAR SINGH /JASPAAL SINGH | Completed | 17000 | 16776.99 | 2018-08-21 | 2019-09-17
| 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1703004079/IF/22012034424997 — NADEP NIRMAN JAGTAR SINGH /BAKSHI SINGH | Completed | 17000 | 16776.99 | 2018-08-21 | 2019-09-17
| 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1703004079/IF/22012034425314 — NADEP NIRMAN BALDEV SINGH /BAKSHI SINGH | Completed | 17000 | 16776.99 | 2018-08-21 | 2019-09-17
| 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1703004079/IF/22012034425321 — NADEP NIRMAN HARPINDAR SINGH /BAKSHI SINGH | Completed | 17000 | 16776.99 | 2018-08-28 | 2019-09-17
| 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1703004079/IF/22012034425328 — NADEP NIRMAN JAGEER SINGH /SOHAN SINGH | Completed | 17000 | 17069.85 | 2018-10-02 | 2020-06-08
| 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1703004079/IF/22012034425802 — NADEP NIRMAN HUKAM SINGH/HAREERAM | Completed | 17000 | 16627 | 2018-08-28 | 2020-06-08
| 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1703004079/IF/22012034427242 — NADEP NIRMAN SANKAR SINGH /SUGHAR SINGH | Completed | 17000 | 16776.99 | 2018-08-21 | 2019-09-17
| 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1703004079/IF/22012034427245 — NADEP NIRMAN NARAYAN SINGH /SUGHAR SINGH | Completed | 17000 | 16776.99 | 2018-08-21 | 2019-09-17
| 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1703004079/IF/22012034429615 — NADEP NIRMAN SUVINDAR SINGH /SADHU SINGH | Ongoing | 17000 | 174 | 2018-10-02
| 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1703004079/IF/22012034429618 — NADEP NIRMAN BHEEM SINGH /PHATE SINGH | Ongoing | 17000 | 174 | 2018-10-02
| 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1703004079/IF/22012034429620 — NADEP NIRMAN BANTI /SOBHA SINGH | Completed | 17000 | 16776.99 | 2018-08-21 | 2019-09-17
| 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1703004079/IF/22012034429622 — NADEP NIRMAN KAIIU /JANVED | Completed | 17000 | 16975 | 2018-09-25 | 2020-06-08
| 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1703004079/IF/22012034429711 — NADEP NIRMAN KABUL SINGH/GURDYAL SINGH | Completed | 17000 | 16776.99 | 2018-08-21 | 2019-09-17
| 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1703004079/IF/22012034430239 — NADEP NIRMAN UTTAM SINGH /BALKISAN | Ongoing | 17000 | 174 | 2018-10-02
| 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1703004079/IF/22012034430240 — NADEP NIRMAN KESAV /BADAM SINGH | Ongoing | 17000 | 174 | 2018-10-02
| 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1703004079/IF/22012034430241 — NADEP NIRMAN JAGANNATH/HALKE | Ongoing | 17000 | 174 | 2018-10-03
| 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1703004079/IF/22012034430242 — NADEP NIRMAN RAGHUVEER SINGH/CHIMAN SINGH | Ongoing | 17000 | 174 | 2018-10-02
| 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1703004079/IF/22012034430287 — NADEP NIRMAN HARDEV SINGH/JARNEL SINGH | Completed | 17000 | 17069.85 | 2018-10-02 | 2020-06-08
| 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1703004079/IF/22012034430288 — NADEP NIRMAN KULDEEP SINGH/CHARAN SINGH | Completed | 17000 | 17069.85 | 2018-10-02 | 2020-06-08
| 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1703004079/IF/22012034430289 — NADEP NIRMAN HARDEEP SINGH/ CHANDAN SINGH | Completed | 17000 | 16541.85 | 2018-10-02 | 2020-06-08
| 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1703004079/IF/22012034430290 — NADEP NIRMAN KASHAMEER SINGH/ CHANDAN SINGH | Completed | 17000 | 16541.85 | 2018-10-02 | 2020-06-08
| 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1703004079/IF/22012034430299 — NADEP NIRMAN SARMAN SINGH/MANGAL SINGH | Completed | 17000 | 17064.85 | 2018-10-02 | 2020-06-08
| 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1703004079/IF/22012034430301 — NADEP NIRMAN AJEETSINGH/MEHGA SINGH | Completed | 17000 | 17064.85 | 2018-10-02 | 2020-06-08
| 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Boundary Line Plantation of Horticulture Trees for Individuals | Plantation | 1703004079/IF/22012034577516 — KHET KI MED PAR BRACHHAROPAN KARYA HAKIM SINGH S/O NINUARAM | Closed | 199622.55 | 20557 | 2020-09-29
| 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Boundary Line Plantation of Horticulture Trees for Individuals | Plantation | 1703004079/IF/22012034577840 — KHET KI MED PAR VIRCHHA ROPAN GIRRAJ S/0 NINUARAM | Closed | 199622.55 | 20557 | 2020-09-29
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1703004079/IF/22012035377545 — Jgsa 2025 opan weell Rechage Hanumaan mandir ke pass bhadeswar | Closed | 25899.46 | 261 | 2025-04-28
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1703004079/IF/22012035377655 — JGSA 2025 Khet talab nirman Harjeet kaur ke khet par | Physically Completed | 147621.16 | 135326.94 | 2025-04-28 | 2026-04-09
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1703004079/IF/22012035465814 — JGSA 2025 Khet talab nirman Jitendra kaur ke khet par | Physically Completed | 147621.16 | 107230.98 | 2025-05-07 | 2026-05-15
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1703004079/IF/22012035466062 — Jgsa 2025 Dug weell Rechage Tarsem singh ke ghar ke pass kuye par bhadeswar | Physically Completed | 25899.46 | 25502 | 2025-05-07 | 2026-05-06
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1703004079/IF/22012035467939 — JGSA 2025 Dug well nirman jageer singh ke ghar ke pass kuye par | Completed | 25899.46 | 25486.16 | 2025-05-07 | 2026-04-09
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1703004079/IF/22012035468072 — JGSA 2025 khet talab nirman Anokh singh ke khet par sirsula | Closed | 147621.16 | 6525 | 2025-05-07
| 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004079/IF/9993670930 — IAY House Dharmu / Jagnu Bhdeshwar | Completed | 14310 | 10431 | 2015-08-11 | 2017-09-28
| 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1703004079/IF/9993676896 — IAY House Atar Singh / Jagram Sirsula | Deleted | 14310 | 0 | 2015-09-22
| 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1703004079/IF/9993696685 — PASU FHRSH HUKAM SINGH/HAREERAM | Deleted | 61236 | 0 | 2015-10-02
| 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1703004079/IF/9993696699 — PASU FHARSH BALVINDAR SINGH/MOHAN SINGH | Deleted | 61100 | 0 | 2015-12-25
| 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1703004079/IF/9993696710 — PASU FHRSH MAHESH /MAJBOOT SINGH | Deleted | 61100 | 0 | 2015-12-26
| 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1703004079/IF/9993696713 — PASU FHRSH UTTAM/ BALKISAN | Deleted | 61250 | 0 | 2015-10-02
| 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1703004079/IF/9993696715 — PASU FHRSH DHRMENDAR /BABU SINGH | Deleted | 61100 | 0 | 2015-10-02
| 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1703004079/IF/9993696717 — PASU FHRSH JUJHAR SINGH/VEER SINGH | Deleted | 61100 | 0 | 2015-12-27
| 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1703004079/IF/9993696718 — PASU FHRSH SATENDAR SINGH/ | Deleted | 61100 | 0 | 2015-12-27
| 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1703004079/IF/9993696719 — PASU FHRSH RAVIDAR SINGH /SOVRAN SINGH | Deleted | 61100 | 0 | 2015-10-02
| 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1703004079/IF/9993696721 — PASU FHRSH RISPAL SINGH/SOVRAN SINGH | Deleted | 61236 | 0 | 2015-10-02
| 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1703004079/IF/9993696722 — PASU FHRSH GURDYAL SINGH/BALVANT SINGH | Deleted | 61236 | 0 | 2015-10-02
| 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1703004079/IF/9993696724 — MU. AAVAS PARMAL/KISHORI | Completed | 14300 | 12024 | 2016-12-20 | 2017-09-28
| 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Horticulture / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1703004079/IF/9993697636 — MED BANDHAN SATENDAR SINGH/CHANDAN SINGH | Deleted | 91000 | 0 | 2016-04-10
| 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Horticulture / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1703004079/IF/9993697639 — MED BANDHAN BALVINDAR SINGH /MOHAN SINGH | Deleted | 91000 | 0 | 2015-10-02
| 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Horticulture / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1703004079/IF/9993697642 — MED BANDHAN GURDYAL SINGH /BALVNT SINGH | Deleted | 91800 | 0 | 2015-10-02
| 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Horticulture / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1703004079/IF/9993697647 — MED BANDHAN MAHESH/MAJBOOT SINGH | Deleted | 91000 | 0 | 2016-04-10
| 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Horticulture / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1703004079/IF/9993697648 — MED BANDHAN RISPAL SINGH /SOVRAN SINGH | Deleted | 91800 | 0 | 2015-10-02
| 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1703004079/IF/9993701134 — PASU SED ASOK/ HARIVILAS | Deleted | 61100000 | 0 | 2015-12-27
| 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1703004079/IF/9993701145 — PASU SED RAMLAL CHIMA RAM | Deleted | 61236 | 0 | 2015-12-26
| 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1703004079/IF/9993701149 — IAY RAM SINGH /UMRAV SINGH | Deleted | 14310 | 0 | 2015-04-14
| 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1703004079/IF/9993701156 — IAY JUGENDAR KAUR /BAKSHI SINGH | Deleted | 14310 | 0 | 2015-04-14
| 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004079/IF/9993701158 — IAY JUGENDAR KAUR /BAKSHI SINGH | Completed | 14310 | 14028 | 2016-11-15 | 2017-09-27
| 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1703004079/IF/9993701168 — IAY SHANKAR /SUGHAR SINGH | Deleted | 14310 | 0 | 2015-04-14
| 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1703004079/IF/9993701172 — IAY RAMPRASAD BHAJANLAL | Completed | 14310 | 11022 | 2016-11-15 | 2018-04-12
| 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004079/IF/IAY/245895 — Construction of IAY House -IAY REG. NO. MP1720359 | Completed | 15030 | 15111 | 2017-01-31 | 2018-01-19
| 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004079/IF/IAY/255077 — Construction of IAY House -IAY REG. NO. MP2112672 | Completed | 15030 | 12703 | 2017-01-31 | 2018-03-28
| 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004079/IF/IAY/276114 — Construction of IAY House -IAY REG. NO. MP3420993 | Completed | 15030 | 14762 | 2017-01-31 | 2018-01-19
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004079/IF/IAY/3695875 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106669899 | Completed | 18360 | 17136 | 2022-06-14 | 2023-02-01
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004079/IF/IAY/4327516 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114740624 | Completed | 18360 | 17136 | 2022-08-30 | 2023-07-15
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004079/IF/IAY/4365684 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116582923 | Completed | 18360 | 18156 | 2022-10-04 | 2023-07-15
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004079/IF/IAY/4375722 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114952145 | Completed | 18360 | 18156 | 2022-11-01 | 2023-07-15
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004079/IF/IAY/4385002 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP107068741 | Completed | 18360 | 17952 | 2022-11-29 | 2024-03-04
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004079/IF/IAY/4737915 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106243190 | Completed | 23490 | 21627 | 2025-01-28 | 2026-05-28
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004079/IF/IAY/4738427 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105270747 | Completed | 23490 | 21627 | 2024-11-26 | 2026-05-28
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004079/IF/IAY/4743962 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114855847 | Completed | 23490 | 21735 | 2024-11-07 | 2026-05-28
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004079/IF/IAY/4745155 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113586069 | Completed | 23490 | 20493 | 2025-01-07 | 2026-05-28
| 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004079/IF/IAY/54512 — Construction of IAY House -IAY REG. NO. MP-03-004-079-002/34 | Approved | 23490 | 0 | 2015-06-23
| 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004079/IF/IAY/71988 — Construction of IAY House -IAY REG. NO. MP-03-004-076-001/58 | Approved | 23490 | 0 | 2015-06-23
| 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004079/IF/IAY/71998 — Construction of IAY House -IAY REG. NO. MP-03-004-079-001/3 | Approved | 23490 | 0 | 2015-06-01
| 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004079/IF/IAY/71999 — Construction of IAY House -IAY REG. NO. MP-03-004-079-002/13 | Approved | 23490 | 0 | 2015-06-01
| 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004079/IF/IAY/72000 — Construction of IAY House -IAY REG. NO. MP-03-004-079-002/13p | Approved | 23490 | 0 | 2015-06-01
| 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004079/IF/IAY/952995 — Construction of IAY House -IAY REG. NO. MP3121746 | Completed | 15480 | 14792 | 2017-06-27 | 2018-03-23
| 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004079/IF/IAY/954016 — Construction of IAY House -IAY REG. NO. MP3147501 | Completed | 15480 | 15308 | 2017-06-27 | 2018-04-08
| 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004079/IF/IAY/954883 — Construction of IAY House -IAY REG. NO. MP3169862 | Completed | 15480 | 15308 | 2017-06-27 | 2018-03-23
| 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004079/IF/IAY/956381 — Construction of IAY House -IAY REG. NO. MP3205117 | Completed | 15480 | 15480 | 2017-06-27 | 2018-03-11
| 2017-2018 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1703004079/PG/22012034312521 — KHEL MEDAN SIRSULA | Closed | 186000 | 0 | 2017-04-20
| 2017-2018 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1703004079/PG/22012034312524 — KHEL MEDAN BHDESHVAR | Closed | 186000 | 0 | 2017-04-20
| 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1703004079/RC/1206 — KHARANJA NIRMAD CHAK SUKHDEV PURA -SIRSULA | Completed | 359743 | 285408 | 2011-05-20 | 2014-06-18
| 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1703004079/RC/1249 — BARHMASI PAHUCCH MARG SIRSULA SE NONEVAR KI OR (SI | Completed | 2235000 | 722400 | 2010-06-16 | 2014-06-19
| 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1703004079/RC/1295 — C C NIRMAN PNCHPARMESWAR YOJANA BHDESWAR | Completed | 74239 | 85800 | 2012-04-22 | 2015-03-03
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1703004079/RC/22012034185579 — खरंजा निर्माण भीकम सिंह के मकान से नहर तक | Completed | 261850 | 876 | 2013-09-24 | 2016-08-06
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1703004079/RC/22012034185581 — खरंजा निर्माण गुरदेव सिंह के मकान से स्‍वर्ण सिंह | Completed | 491084 | 377009.85 | 2013-09-24 | 2015-09-28
| 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1703004079/RC/22012034283990 — CC ROAD KARAHIYA ROAD SE SUCCHA SINGH DOLATPUR ROAD SE ANGANWADI, SALAMPUR SE KAMMO KI OR | Completed | 225267 | 219146.41 | 2015-09-08 | 2017-09-26
| 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1703004079/RC/22012034293447 — KHRANJA NIRMAD KARHIYA ROD SEMALKEET SINGH KE DERA KEE OR | Completed | 329000 | 259628.1 | 2016-01-05 | 2018-07-31
| 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1703004079/RC/22012034293448 — KHARNJA NIRMAD DOLTPUR ROD SE HARPAL SINGH DERA KEE OR | Completed | 329000 | 120212.7 | 2016-01-05 | 2018-07-31
| 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1703004079/RC/22012034317233 — CC ROAD NIRMAN SUHAN SINGH KE MAKAN SE MANDIR KI OR & JAGDISH SE RASAL SINGH KI OR | Completed | 189708 | 115122 | 2016-12-20 | 2018-03-27
| 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1703004079/RC/22012034322543 — CC ROAD NIRMAN | Deleted | 0 | 0 | 2017-01-26
| 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1703004079/RC/22012034360638 — cc nirman karya jatav basti se nahar ki puliyan ki or sirsula | Completed | 78300 | 73616 | 2017-09-19 | 2018-03-13
| 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1703004079/RC/22012034364073 — C C NIRMAN KARY PURANI CC SE AGAN VADI KI OR SIRSULA | Completed | 28800 | 28552 | 2017-10-17 | 2018-02-13
| 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1703004079/RC/22012034386334 — cc sadak nirman main road se harjindar ke makan and baldev ke makan ki or | Completed | 39510 | 40144 | 2018-03-13 | 2019-03-31
| 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1703004079/RC/22012034386335 — cc sadak nirman main road se kallu baghel ki or bhadeswar | Completed | 10575 | 9046 | 2018-03-13 | 2019-12-15
| 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1703004079/RC/22012034386353 — cc sadak dolatpur marg se hanuman mandir ki or | Completed | 13950 | 12700 | 2018-03-20 | 2019-12-10
| 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1703004079/RC/22012034386370 — cc sadak dolatpur marg se santidham bhadeswar | Completed | 65100 | 51852 | 2018-08-07 | 2020-05-20
| 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1703004079/RC/22012034386373 — cc sadak doiatpur marg se raghuveer ke ghar ki or | Completed | 11610 | 9396 | 2018-09-04 | 2019-12-20
| 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Repair & maint of Mitti Murram Roads for Comm / Repair and maintenance of Mitti Murram Roads for Community | Repair & maint of Road | 1703004079/RC/22012034442087 — GREVAL ROD MENROD SE BALVEER SINGH KE GHAR TAK | Closed | 0 | 0 | 2018-12-21
| 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1703004079/RC/22012034442102 — cc road sahba singh se pratipal ki or sirsula | Closed | 0 | 0 | 2018-12-21
| 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1703004079/RC/22012034442108 — CCROAD MAAN SINGH KE GHAR SE BHEEKAM OR GIRRAJ KE GHAR TAK | Closed | 0 | 0 | 2018-12-21
| 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1703004079/RC/22012034442121 — CC ROAD MEN ROAD SE MAHESHA PAWAIYA KE OR | Closed | 0 | 0 | 2018-12-21
| 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1703004079/RC/22012034517305 — CC ROAD PRADEEP SINGH KE GHAR SE HARPAL SINGH KE GHAR KI OR | Completed | 75000 | 73956 | 2020-02-11 | 2021-09-23
| 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1703004079/RC/22012034517306 — CC ROAD DOLATPUR MARG SE RAJ SINGH KE MAKAN TAK | Completed | 37200 | 36452 | 2020-02-11 | 2021-09-23
| 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1703004079/RC/22012034523438 — CC Road Dolatpur marg se Shantidham marg shesh bhag and shantidham chabutara ke charo taraf | Completed | 65336 | 44982 | 2020-06-02 | 2022-04-15
| 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1703004079/RC/22012034523439 — CC Road ANganwadi ke samne prangad | Completed | 4693 | 4560 | 2020-06-02 | 2021-11-01
| 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1703004079/RC/226 — मि.मु. मुख्‍य मार्ग बुडडा सरदार के मकान तक | Deleted | 28300 | 7200 | 2009-06-20
| 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1703004079/RC/227 — खरंजा निर्माण कार्य भदेश्‍वर मैन रोड से सरदार राजिन्‍द्र तक | Deleted | 92400 | 24230 | 2009-08-16
| 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1703004079/RC/28 — मि.मु. कार्य सिरसुला से चक सुखदेव पुरा तक | Completed | 493000 | 73509 | 2008-05-05 | 2014-06-18
| 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1703004079/RC/388 — C.C.NIMAD BHADESUAR- SIRSULA | Completed | 80000 | 26880 | 2010-11-04 | 2011-02-03
| 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1703004079/RC/389 — KHARENJA NIRMAD JATAV MUHOOLA - SIRSULA | Completed | 132000 | 131960 | 2010-12-10 | 2014-06-18
| 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1703004079/RC/393 — सी.सी. निर्माण भदेश्‍वर 12वां वित्‍त प्रथम | Completed | 27000 | 30420 | 2009-12-15 | 2010-12-09
| 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1703004079/RC/394 — सी.सी. निर्माण भदेश्‍वर 12वां वित्‍त द्वितीय | Completed | 27000 | 32820 | 2009-12-15 | 2010-09-12
| 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1703004079/RC/92 — सी.सी. निर्माण कार्य कन्‍वर्जन ग्राम सिरसुला | Completed | 78450 | 44576.79 | 2008-12-24 | 2017-01-16
| 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1703004079/RS/22012034241703 — NBA TOILET/Herdevsing/dheersingh | Completed | 4400 | 4399 | 2014-08-26 | 2015-03-27
| 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1703004079/RS/22012034241822 — NBA JAGEER SINGH/SOBARAN SINGH | Completed | 5400 | 3021 | 2015-08-11 | 2016-10-21
| 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1703004079/RS/22012034241825 — NBA TOILET RISHPAL SINGH/SOBRAN SINGH | Completed | 5400 | 3021 | 2015-07-28 | 2016-10-21
| 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1703004079/RS/22012034241829 — NBA TOILET HARJINDAR/HARVANT SINGH | Completed | 5400 | 3021 | 2015-07-28 | 2016-10-21
| 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1703004079/RS/22012034241831 — NBA TOILET MALVINDAR SINGH/TARSEM SINGH | Completed | 4400 | 4399 | 2014-07-22 | 2015-03-27
| 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Compost Pit / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1703004079/RS/22012034241836 — NBA TOILET DASHAN SINGH/ASA SINGH | Completed | 4400 | 4399 | 2014-08-19 | 2015-03-27
| 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1703004079/RS/22012034241837 — NBA TOILET DHARM SINGH/SADHU SINGH | Completed | 5400 | 3021 | 2015-07-29 | 2016-10-21
| 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1703004079/RS/22012034241839 — NBA TOILET SUWINDAR SINGH /SADHU SINGH | Completed | 5400 | 3021 | 2015-08-11 | 2016-11-03
| 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1703004079/RS/22012034241841 — NBATOILET KULDEEP SINGH/MOHAN SINGH | Completed | 4400 | 4399 | 2014-07-22 | 2015-03-27
| 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1703004079/RS/22012034241843 — NBATOILET/RANJEET SINGH/MOHANSINGH | Completed | 4400 | 4399 | 2014-07-22 | 2015-03-27
| 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1703004079/RS/22012034241845 — NBATOILET EKBAL SINGH/JUGENDER SINGH | Completed | 5400 | 2862 | 2015-08-25 | 2016-10-26
| 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1703004079/RS/22012034241849 — NBATOILET AJEET SINGH/MEGHHASINGH | Completed | 4400 | 4399 | 2014-07-22 | 2015-03-27
| 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1703004079/RS/22012034241853 — NBATOILET DELBAGSINGH/MEGHHASINGH | Completed | 4400 | 4399 | 2014-08-19 | 2015-03-27
| 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1703004079/RS/22012034241855 — NBATOILET ARCHNA/NARESH | Completed | 5400 | 1113 | 2015-08-25 | 2016-11-03
| 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1703004079/RS/22012034241860 — NBATOILET RAJVEERSINGH /CHIMANSINGH | Completed | 5400 | 4399 | 2014-08-26 | 2015-03-27
| 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1703004079/RS/22012034241863 — NBATOILET CHANDANSINGH/BALVINDERSINGH | Completed | 5400 | 3021 | 2015-08-11 | 2016-11-03
| 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1703004079/RS/22012034241870 — NBATOILET MALKEETSINGH/BALKARSINGH | Deleted | 5400 | 0 | 2016-10-22
| 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1703004079/RS/22012034241872 — NBATOILET GURDEEPSINGH/BALKARSINGH | Deleted | 5400 | 0 | 2016-10-22
| 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1703004079/RS/22012034241876 — NBATOILET JITENDERSINGH/SUKHVINDERSINH | Completed | 5400 | 3021 | 2015-08-11 | 2015-09-28
| 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1703004079/RS/22012034241879 — NBATOILET /PALVINDERSINGH/HERVANTSINGGH | Completed | 0 | 3021 | 2015-08-11 | 2015-09-28
| 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1703004079/RS/22012034242411 — NBA TOILET HERDEP SINGH/CHNDANSINGH | Completed | 5400 | 3021 | 2015-08-25 | 2016-11-03
| 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1703004079/RS/22012034242415 — NBA TOILET MALVINDER SINGH/KASMEERSINGH | Completed | 5400 | 2544 | 2015-08-14 | 2016-10-26
| 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1703004079/RS/22012034242423 — NBATOILET BALVINDERSINGH/MANGALSINGH | Deleted | 5400 | 0 | 2016-10-22
| 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1703004079/RS/22012034242429 — NBA TOILET GURMEETSINGH/MEGHHASINGH | Deleted | 5400 | 0 | 2016-10-22
| 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1703004079/RS/22012034242450 — NBATOILET DALBEERSINGH/SUGHRSIINGH | Deleted | 5400 | 0 | 2016-10-22
| 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1703004079/RS/22012034242453 — NBATOILET NARAYAN/SUGHARSINGH | Deleted | 5400 | 0 | 2016-10-23
| 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1703004079/RS/22012034242454 — NBA TOILET HAREE SINGH/PHERANSINGH | Completed | 5400 | 2544 | 2015-08-14 | 2016-10-26
| 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1703004079/RS/22012034242455 — NBA TOILET KULDEEP SINGH / BOOTASINGH | Completed | 5400 | 3021 | 2015-07-29 | 2016-11-03
| 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1703004079/RS/22012034242457 — NBATOILET MANGALSINGH/HANSASINGH | Deleted | 5400 | 0 | 2016-10-22
| 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1703004079/RS/22012034242458 — NBATOILET MEHBOTKHAN/RASULKHAN | Deleted | 0 | 0 | 2015-09-28
| 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1703004079/RS/22012034242471 — NBA TOILET GURMEETKOUR/SURENDERSINGH | Completed | 5400 | 3021 | 2015-07-28 | 2016-11-03
| 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1703004079/RS/22012034242473 — NBA TOILET HEERASINGH/KASMEERSINGH | Completed | 5400 | 3021 | 2015-07-28 | 2016-11-03
| 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1703004079/RS/22012034242474 — NBATOILET PAVNDEEPSINGH/HERPALSINGH | Completed | 5400 | 3021 | 2015-08-25 | 2015-09-28
| 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1703004079/RS/22012034242476 — NBATOILET BARATSINGH/SOHANSINGH | Completed | 5400 | 3021 | 2015-08-25 | 2016-11-03
| 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1703004079/RS/22012034242479 — NBATOILAT BRAJMOHN/JAGRAM | Completed | 5400 | 2862 | 2015-08-25 | 2016-11-03
| 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1703004079/RS/22012034242481 — NBATOILET PRABODYAL/SAMLIYA | Deleted | 5400 | 0 | 2016-10-22
| 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1703004079/RS/22012034242484 — NBA TOILET HUKAMSINGH/SAMLIYA | Deleted | 5400 | 0 | 2016-10-23
| 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1703004079/RS/22012034242487 — NBA TOILET KESAV/BADAM SINGH | Deleted | 5400 | 0 | 2014-07-01
| 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1703004079/RS/22012034242489 — NBA TOILET LAKHAN /BADAMSINGH | Deleted | 5400 | 0 | 2016-10-22
| 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1703004079/RS/22012034242491 — NBATOILET BHRAT/BADAMSINGH | Deleted | 5400 | 0 | 2016-10-23
| 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1703004079/RS/22012034242493 — NBA TOILET JAGANNATH/RAMDHAN | Deleted | 5400 | 0 | 2014-07-01
| 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1703004079/RS/22012034242499 — NBA TOILET UTTAMSINGH/BALKISAN | Deleted | 5400 | 0 | 2016-10-23
| 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1703004079/RS/22012034242501 — NBA TOILET ASOK /HARVILAS | Completed | 5400 | 3021 | 2015-08-25 | 2016-11-03
| 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1703004079/RS/22012034242503 — NBA TOILET NARAYAN/GYASEERAM | Deleted | 5400 | 0 | 2016-10-23
| 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1703004079/RS/22012034242752 — NBATOILET OMPRKAS/GYASHERAM | Deleted | 5400 | 0 | 2016-10-24
| 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1703004079/RS/22012034242753 — NBA TOILET RVINDERSINGH/SOVRANSINGH | Completed | 5400 | 159 | 2015-08-25 | 2015-09-28
| 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Compost Pit / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1703004079/RS/22012034242755 — NBA TOILET NIRMALSINGH/GURDEVSINGH | Completed | 4400 | 4399 | 2014-08-26 | 2015-03-27
| 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1703004079/RS/22012034242757 — NBATOILAT KULDEEPSINGH/HERWANSHSINGH | Completed | 4400 | 4399 | 2014-08-12 | 2015-03-27
| 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1703004079/RS/22012034242759 — NBA TOILET SARVJEETSINGH/RAJSINGH | Completed | 4400 | 4399 | 2014-07-22 | 2015-03-27
| 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1703004079/RS/22012034242761 — NBA TOILET PARMAL SINGH/PHATESINGH | Completed | 5400 | 3021 | 2015-07-28 | 2016-11-03
| 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1703004079/RS/22012034242763 — NBATOILET HERPAL SINGH/JUGENDAR SINGH | Completed | 4400 | 4399 | 2014-08-26 | 2015-03-27
| 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1703004079/RS/22012034242941 — NBATOILET RISPALSINGH/SADHUSINGH | Completed | 4400 | 4399 | 2014-08-12 | 2015-03-27
| 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1703004079/RS/22012034242942 — NBATOILET SARJEETSINGH/AMARSINGH | Deleted | 5400 | 0 | 2016-10-24
| 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1703004079/RS/22012034242945 — NBATOILET KULDEEPSINGH/GURBAKSHSINGH | Completed | 4400 | 4399 | 2014-08-26 | 2015-03-27
| 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1703004079/RS/22012034242947 — NBATOILET RAMESVARSINGH/JAGDEESHSINGH | Completed | 5400 | 3021 | 2015-08-25 | 2016-11-03
| 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1703004079/RS/22012034242950 — NBATOILET GOPALSINGH/VIJAYSINGH | Completed | 4400 | 4399 | 2014-08-19 | 2015-03-27
| 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1703004079/RS/22012034246679 — NBATOILET RAMESH/TIRLOK | Completed | 4400 | 4399 | 2014-08-19 | 2015-03-27
| 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1703004079/RS/22012034247009 — NBATOILET JAGANNATH/HALKE | Deleted | 5400 | 0 | 2016-10-24
| 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1703004079/RS/22012034247057 — NBATOILET RANJEET SINGH /SADHU SINGH | Completed | 5400 | 159 | 2015-08-25 | 2016-10-25
| 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1703004079/RS/22012034247058 — NBATOILET HAKIMSINGH/NINUAARAM | Deleted | 5400 | 0 | 2016-10-24
| 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1703004079/RS/22012034247060 — NBATOILET MUKESH/PREETAM | Deleted | 5400 | 0 | 2016-10-25
| 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1703004079/RS/22012034247061 — NBATOILET RAMSRUP/JAGRAM | Deleted | 5400 | 0 | 2016-10-25
| 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1703004079/RS/22012034247068 — NBATOILET MHESH/MAJBOTSINGH | Completed | 4400 | 4399 | 2014-08-12 | 2015-03-27
| 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1703004079/RS/22012034247070 — NBA TOILET RANVEERSINGH/UMRAVSINGH | Deleted | 5400 | 0 | 2016-10-25
| 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1703004079/RS/22012034247072 — NBATOILET MAANSINGH/TEJSINGH | Completed | 4400 | 4399 | 2014-08-19 | 2015-03-27
| 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1703004079/RS/22012034247078 — NBATOILETSUGHRSINGH//KESRIYA | Completed | 5400 | 2544 | 2015-08-14 | 2016-11-02
| 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1703004079/RS/22012034263380 — NBA TOILET GURDEEPKAUR/JARNELSINGH | Completed | 4400 | 4399 | 2014-08-26 | 2015-03-27
| 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1703004079/RS/22012034287639 — ODF TOILET SURES SINGH/DASRATH SINGH | Deleted | 12000 | 0 | 2015-10-02
| 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Drainage Channel / Construction of Flood/ Diversion Channel for Community | Solid and Liquid Waste Management | 1703004079/RS/22012034289564 — U-SHAPE NALA NIRMAN BALDEV SINGH KE MAKAN SE NON NADI KI OR | Completed | 344550 | 340323.68 | 2015-11-10 | 2017-09-26
| 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Drainage Channel / Construction of Flood/ Diversion Channel for Community | Solid and Liquid Waste Management | 1703004079/RS/22012034289565 — U SHAPE NALA GURUBEL KE MAKAN SE NON NADI & GPS SE ATINDAR | Completed | 524825 | 479698.89 | 2016-11-29 | 2018-03-27
| 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Drainage Channel / Construction of Flood/ Diversion Channel for Community | Solid and Liquid Waste Management | 1703004079/RS/22012034321453 — NALA NIRMAN SIRSULA NATHU SINGH KE MAKAN SE G.P.S KI OR | Deleted | 0 | 0 | 2017-01-26
| 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Drainage Channel / Construction of Flood/ Diversion Channel for Community | Solid and Liquid Waste Management | 1703004079/RS/22012034326292 — U SHAPE NALA NIRMAN AJIT KE MAKAN SE NON NADI KI OR | Completed | 850000 | 557460.07 | 2017-02-21 | 2020-06-08
| 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Drainage Channel / Construction of Flood/ Diversion Channel for Community | Solid and Liquid Waste Management | 1703004079/RS/22012034353854 — NALA NIRMAN SIRSULA NATHU SINGH KE MAKAN SE G.P.S KI OR | Deleted | 0 | 0 | 2017-04-20
| 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Drainage Channel / Construction of Flood/ Diversion Channel for Community | Solid and Liquid Waste Management | 1703004079/RS/22012034353866 — USEP NALA NIRMAN NATHU KE MAKAN SE GPS KI OR | Completed | 525000 | 507903.02 | 2017-06-20 | 2019-09-20
| 2018-2019 | D--RURAL INFRASTUCTURE / Rural Sanitation | Repair & maint of Open/Covered Grey_Water for Comm / Repair and maintenance of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1703004079/RS/22012034428501 — U SEP nala nirman Gurpej Singh ke makan se puliya ki or bhadeswar | Completed | 309000 | 303339.49 | 2018-09-25 | 2020-06-08
| 2018-2019 | D--RURAL INFRASTUCTURE / Rural Sanitation | Repair & maint of Open/Covered Grey_Water for Comm / Repair and maintenance of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1703004079/RS/22012034428847 — U SEP NALA NIRMAN KUMER KE MADAYA SE HADPAMP KI OR | Ongoing | 214000 | 1044 | 2018-10-02
| 2018-2019 | D--RURAL INFRASTUCTURE / Rural Sanitation | Repair & maint of Open/Covered Grey_Water for Comm / Repair and maintenance of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1703004079/RS/22012034429735 — U SEP NALA NIRMAN GADDI SALAMPUR ROD SE NON NADI KI OR BHADRSWAR | Completed | 256000 | 220668.93 | 2018-10-02 | 2020-06-07
| 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1703004079/RS/22012034660471 — RCC Nali Nirman Veer Singh ke Makan se Nale ki or Avam Dharamveer ke makan se nale ki or | Physically Completed | 128000 | 115056 | 2022-08-30 | 2026-06-14
| 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1703004079/RS/22012034660473 — Samudayik Nadep Nirman Bhadeshwar | Completed | 42000 | 41820 | 2022-08-09 | 2022-10-28
| 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1703004079/RS/22012034660475 — Samudayik nadep Nirman kraman 1 sirsula | Completed | 42000 | 41616 | 2022-08-16 | 2022-11-03
| 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1703004079/RS/22012034660477 — Samudayik Nadep Nirman Kramak 2 sirsula | Completed | 42000 | 39168 | 2022-08-16 | 2022-11-03
| 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1703004079/RS/22012034660479 — Samudayik Nadep Nirman Nonewar | Completed | 42000 | 41616 | 2022-11-08 | 2023-04-27
| 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1703004079/RS/22012034663035 — Samudayik Nadep Nirman Sirsula Kramank 3 | Closed | 84000 | 0 | 2022-04-14
| 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1703004079/RS/22012034663036 — Samudayik Nadep Nirman Bhadeshwar Kramank 2 | Completed | 42000 | 41616 | 2022-08-30 | 2023-04-27
| 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1703004079/RS/22012034697387 — Simenet kankrit nali nirman kallu bhagel ke ghar se nadi ki or bhadeshwar | Physically Completed | 49000 | 40737 | 2023-06-20 | 2026-06-14
| 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1703004079/RS/22012034697391 — Simenet kankrit nali nirman hardev singh ke ghar se nale ki or bhadeshwar | Physically Completed | 27000 | 24315 | 2023-06-20 | 2026-06-14
| 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1703004079/RS/22012034697393 — Under ground Nali nirman Tarsem singh ke ghar se dolatpur road ki puliya tak bhadeshwar | Ongoing | 24000 | 1326 | 2023-06-20
| 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1703004079/RS/22012034697395 — Simenet kankrit nani nirman sahab singh ke ghar se nale ki or bhadeshwar | Physically Completed | 51000 | 40476 | 2023-06-20 | 2026-06-14
| 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1703004079/RS/22012034697401 — USEP NALA NIRMAN NIRMAL SINGH KE GHAR SE PURANE NALE TAK BHADESHWAR KI OR BHADESHWAR | Physically Completed | 531647.09 | 432768 | 2023-06-20 | 2026-06-14
| 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1703004079/RS/22012034697404 — USEP NALA NIRMAN DOLATPUR ROAD KI PULIYA SE NONNADI TAK BHADESHWAR KI OR BHADESHWAR | Physically Completed | 582349.55 | 515554 | 2023-06-20 | 2026-06-14
| 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Repair & maint of Open/Covered Grey_Water for Comm / Repair and maintenance of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1703004079/RS/22012034702502 — NALA NIRMAN ANOKH SINGH KE MKAN SE CHATUR SINGH KE MKAN TAK | Closed | 390272.1 | 0 | 2023-08-15
| 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1703004079/RS/22012034702506 — NALA NIRMAN CHATUR SINGH KE MAKAN SE NINDAR SINGH KE MAKAN TAK | Closed | 0 | 0 | 2023-08-15
| 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1703004079/RS/22012034702508 — NALA NIRMAN NINDAR SINGH KE MAKAN SE NISHAN SINGH KE MAKAN TAK | Closed | 0 | 0 | 2023-08-15
| 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Repair & maint of Open/Covered Grey_Water for Comm / Repair and maintenance of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1703004079/RS/22012034702509 — NALA NIRMAN AMAR SINGH KE MAKAN SE PURANE NALE KI OR | Physically Completed | 279278.98 | 245552 | 2024-06-12 | 2026-06-14
| 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1703004079/RS/22012034702517 — Nala nirman Hardeep singh ke makan se non nadi ki or bhadeshwar | Physically Completed | 800369.51 | 713927 | 2023-09-26 | 2026-06-14
| 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1703004079/RS/22012034702864 — WATER CHANNEL NIRMAN CHATUR SINGH KE GHAR SE NINDAR SINGH KE GHAR KI OR SIRSULA | Ongoing | 871083.68 | 442 | 2023-09-26
| 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1703004079/RS/22012034702965 — NALA NIRMAN HARJINDER SINGH KE GHAR SE NADI KI OR BHADESHWAR | Physically Completed | 819715.92 | 742578.26 | 2023-09-26 | 2026-06-14
| 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Multi Unit Toilets for School / Construction of Multi Unit Toilets for School | Construction of Toilets | 1703004079/RS/22012034703062 — Samudayik swachhta parisar nirman karya shasakiyprathmik vidyalay Bhadeshwar panchayat bhavan | Physically Completed | 45000 | 42653 | 2023-09-19 | 2026-06-14
| 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1703004079/RS/22012035113631 — WATER CHANNEL NIRMAN PRABUDYAL KUSHWAH KE MAKAN SE BALKISHAN KE KUAA WALE NALE KI OR | Closed | 736880.07 | 0 | 2023-08-16
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1703004079/RS/69962 — NBA SAUCHALAY RAJVINDR/BUDDA | Completed | 4400 | 4399 | 2013-11-12 | 2015-03-27
| 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1703004079/RS/69974 — NBA SAUCHALYA ANIL/MUST KHAN | Completed | 4400 | 4399 | 2014-07-15 | 2015-03-27
| 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1703004079/RS/71192 — NBA TOILET JUJHAR SINGH/VEER SINGH | Completed | 4400 | 4399 | 2014-07-15 | 2015-03-27
| 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1703004079/RS/71200 — NBA TOILET GURUMEET KAUR /MANGAL SINGH | Deleted | 4400 | 0 | 2016-10-25
| 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1703004079/RS/71216 — NBA TOILET GURMEJKAUR/HANSAASINGH | Deleted | 4400 | 0 | 2016-10-25
| 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1703004079/RS/71220 — NBA TOILET HARBILAS/CHIMARAM | Completed | 4400 | 2544 | 2015-08-14 | 2016-11-02
| 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1703004079/RS/71224 — NBA TOILET PARMAL SINGH/PREETAM SINGH | Completed | 0 | 2544 | 2015-08-14 | 2015-09-28
| 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1703004079/RS/71236 — NBA TOILET BABU SINGH/FHATE/SINGH | Completed | 4400 | 2544 | 2015-08-14 | 2016-11-02
| 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1703004079/RS/71243 — NBA TOILET VIRENDAR SINGH/ARJUN SINGH | Completed | 4400 | 2544 | 2015-08-14 | 2016-11-02
| 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1703004079/RS/71248 — NBA TOILETJUGENDAR KAUR/BAKSHEE SINGH | Deleted | 4400 | 0 | 2016-10-23
| 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1703004079/RS/71253 — NBA TOILET SHANKAR SINGH/SUGHARSINGH | Deleted | 4400 | 0 | 2016-10-25
| 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Compost Pit / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1703004079/RS/71256 — NBA TOILET JASVEER SINGH/JUGENDAR SINGH | Completed | 4400 | 5966 | 2014-07-22 | 2015-03-27
| 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1703004079/RS/71261 — NBA TOILET MAAN SINGH /PHATESINGH | Completed | 4400 | 4399 | 2014-07-15 | 2015-03-27
| 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1703004079/RS/71342 — N BA TOYLET VIJENDAR SINGH/LAXMAN SINGH | Completed | 4400 | 3021 | 2015-07-28 | 2016-11-02
| 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1703004079/RS/71346 — NBA TOILET sanju/bhrat | Completed | 4400 | 4399 | 2014-07-15 | 2015-03-27
| 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1703004079/RS/71348 — NBA TOILET/ LACHHMEE/ATAR SINGH | Deleted | 4400 | 0 | 2016-10-25
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1703004079/RS/71352 — NBA TOILET / BHEEM SINGH/JAGRAM | Completed | 4400 | 3021 | 2013-11-12 | 2016-11-02
| 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1703004079/RS/71355 — NBA TOILET HANUMANT SINGH/PHATE SINGH | Deleted | 4400 | 0 | 2016-10-25
| 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1703004079/RS/71358 — NBA TOILET NATHU SINGH /HANUMANT SINGH | Completed | 4400 | 4399 | 2014-07-15 | 2015-03-27
| 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1703004079/RS/71361 — NBA TOILET LEELA BAEE/PRAN SINGH | Completed | 4400 | 4399 | 2014-07-15 | 2015-03-27
| 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1703004079/RS/71366 — NBA TOILET VASUDEV /HAREERAM | Completed | 4400 | 4399 | 2014-07-15 | 2015-03-27
| 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1703004079/RS/71367 — NBA TOILET HUKAMSINGH/HAREERAM | Completed | 4400 | 4399 | 2014-07-15 | 2015-03-27
| 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1703004079/RS/71369 — NBA TOILET/JITENDAR SINGH/PANCHAM | Completed | 4400 | 2862 | 2015-08-25 | 2016-11-02
| 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1703004079/RS/71371 — NBA TOILET RAMBHADUR RASHAL SINGH | Completed | 4400 | 2544 | 2015-08-14 | 2016-10-26
| 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1703004079/RS/71374 — NBA TOILET DHARA SINGH/CHEEMARAM | Deleted | 4400 | 0 | 2016-10-26
| 2013-2014 | D--RURAL INFRASTUCTURE / Bharat Nirman Sewa Kendra | New Construction / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1703004079/SK/881 — Bharat Nirman Rajeev Gandhi Sewa Kendra,SIRSULA(P) | Completed | 1285000 | 1752 | 2013-09-24 | 2017-01-09
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1703004079/WC/22012034684278 — CTR WATER HARVESITING NIRMAN G P S SIRSULA | Completed | 23300 | 22233 | 2021-05-25 | 2023-10-09
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1703004079/WC/22012034684380 — CTR WATER HARVESTING NIRMAN SHASKIY MADHMIK VIDHYALY SIRSULA | Completed | 23300 | 22233 | 2021-05-25 | 2023-10-09
| 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1703004079/WC/22012034684392 — CTR WATER HARVESITING NIRMAN G P S NONEVAR | Completed | 23300 | 22482 | 2023-08-15 | 2023-10-09
| 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1703004079/WC/22012035209794 — Bhadeshwar puliyapar Ring Bund nirman kramank 1 | Approved | 0 | 0 | 2024-06-09
| 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1703004079/WC/22012035209864 — Bhadeshwar puliya par Ring Bund nirman kramank 2 | Approved | 0 | 0 | 2024-06-09
| 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1703004079/WC/22012035209877 — Bhadeshwar puliya par Ring Bund nirman kramank 3 | Approved | 0 | 0 | 2024-06-09
| 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1703004079/WC/22012035209887 — Bhadeshwar puliya par Ring Bund nirman kramank 4 | Approved | 0 | 0 | 2024-06-09
| 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1703004079/WC/22012035209895 — Bhadeshwar puliya par Ring Bund nirman kramank 5 | Approved | 0 | 0 | 2024-06-09
| 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1703004079/WC/22012035209903 — Bhadeshwar puliya par Ring Bund nirman kramank 6 | Approved | 0 | 0 | 2024-06-09
| 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1703004079/WC/22012035209907 — Bhadeshwar puliya par Ring Bund nirman kramank 7 | Approved | 0 | 0 | 2024-06-09
| 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1703004079/WC/22012035212445 — Loose bodar nirman harjeet kaur ke khet ke pass | Approved | 338141.21 | 0 | 2024-06-09
| 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1703004079/WC/22012035212446 — Loose boldar nirman Gagandeep ke khet ke pass | Approved | 338141.21 | 0 | 2024-06-09
| 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1703004079/WC/89 — Nirmal Neer Jatav Mohlla | Completed | 8300 | 8502 | 2009-03-04 | 2015-03-02
| 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1703004079/WC/90 — निर्मल नीर बस स्‍टेण्‍ड के पास भदेश्‍वर | Completed | 8400 | 8502 | 2009-03-18 | 2015-04-09
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1703004080/RC/22012034188057 — खरंजा निर्माण मैन रोड से गांव की ओर | Deleted | 450000 | 0 | 2013-04-15
| 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Repair & maint of Gravel Road Roads for Comm / Repair and maintenance of Gravel Road Roads for Community | Repair & maint of Road | 1703/RC/22012034610990 — CMGSY Road Periodical Regravelling | Completed | 224000 | 217225.26 | 2023-07-18 | 2026-05-26