HIRDEPUR | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1711005/RC/2 — सी सी रोड हिरदेपुर | Completed | 1800000 | 209616 | 2009-12-10 | 2010-05-16
ABHANA | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1711005/RC/22012034152249 — Abhana main road to Lakahanpur | Completed | 1211000 | 999943.8 | 2010-12-31 | 2014-05-15
JHAPAN | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1711005/RC/22012034153503 — mitti murum road Jhapan to Van avrodh Naka | Deleted | 431000 | 0 | 2008-04-01
JHAPAN | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1711005/RC/22012034153506 — Road from van avrodh naka to Jhapan | Deleted | 431000 | 0 | 2008-04-01
MUHLI | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1711005/RC/22012034624183 — Conts of Gravel Road Mudiya Khurd Road to Amrit Sarovar | Completed | 4512000 | 4488086 | 2022-12-26 | 2024-04-24
RIYANA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1711005/RC/22012034624186 — Conts of Gravel Road Riyana Tigadda to Amrit Sarovar ki Aur | Completed | 4512000 | 4465120.37 | 2023-06-18 | 2024-12-04
PIPARIYA SAHNI | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1711005/RC/22012034625236 — Const of Sudoor Sadak Work Sidhdh Baba to Amrit Sarovar Ki Aur, Pipariya Sahni | Ongoing | 2961000 | 2923002.68 | 2023-04-22
ARTHKHEDA | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1711005/RC/22012034625495 — Const of Sudoor Sadak Bhagwan Das ke khet se Amrit Sarovar ki aur Arthkheda | Ongoing | 3842000 | 3749739.45 | 2023-01-13
MUHLI | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1711005/RC/22012034627055 — Renovation of Gravel road T02 km 105 to Muhli | Completed | 528000 | 522398 | 2024-01-09 | 2024-05-21
MUHLI | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1711005/RC/22012034627059 — Renovation of Gravel road T02 to Panda | Completed | 402000 | 379006 | 2024-01-10 | 2024-05-29
SEMRA MADIYA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1711005/RC/22012034637842 — Const. of Sudoor Sadak Patna Khurd School to Amrit Sarovar Pahuch Marg Cheel Pahadi Tak Semra Madiya | Ongoing | 4986000 | 4544483.7 | 2023-10-06
DHANGOUR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1711005/RC/22012034641145 — Const. of Sudoor Sadak main Road Puliya To Hallu Badda Ke Khet Tak Dhangour Gunji | Ongoing | 2927000 | 2607864.52 | 2023-06-11
PARSORIYA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1711005/RC/22012034641444 — Const. of Sudoor Sadak Railway Fatak To Parsoriya Ki Aur Parsoriya | Ongoing | 3328000 | 2263674.66 | 2023-06-16
SALAIYA HATRI | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1711005/RC/22012034642752 — Const of Khet Sadak/ Sudur Sadak Imaliya Ghat Manka Road to Amrit Sarovar tak Saliya Hatri | Ongoing | 4019000 | 3083852.87 | 2023-10-09
GUWARI | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1711005/RC/22012034643306 — Const. of Khet Sadak/Sudour Sadak Jamuniya Nala to Main Road | Ongoing | 3573000 | 3441179.14 | 2023-10-07
BHURI | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1711005/RC/22012034643360 — Const of Khet Sadak/ Sudur Sadak Vivke Thakur ke khet se Phadi Thakur ke khet tad Bhuri | Closed | 3530000 | 0 | 2023-04-15
CHOUPRA KHURD | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1711005/RC/22012034643973 — JABALPUR NAKA VAN VIBHAG DIPO SE KISAN TALIYA SHRI PANCHMUKHI HANUMAAN MANDIR TAK GRAVAL SADAKNIRMAN | Completed | 1957000 | 1767299.53 | 2024-02-27 | 2025-04-18
DEORIJAMADAR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1711005/RC/22012034669564 — Renovation of Deori jamadar to Mohra | Closed | 438000 | 0 | 2023-04-04
DEORIJAMADAR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1711005/RC/22012034669580 — Renovation of GSB Road Sagoriya To Mahuyakheda SalaiyaHatri Kalapani | Closed | 2526000 | 0 | 2023-04-04
SALAIYA HATRI | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1711005/RC/22012034669589 — Renovation of GSB Road Khamkheda to Mahuakheda | Closed | 500000 | 0 | 2023-04-04
DEORIJAMADAR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1711005/RC/22012034669592 — Renovation of GSB Deori jamdar To Mahuakheda | Closed | 352000 | 0 | 2023-04-04
ABHANA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1711005/RC/22012034669680 — Renovation of GSB Abhana Main Road to Sheeshpur Pati Khadantola | Ongoing | 4116000 | 150573 | 2024-03-13
SALAIYA HATRI | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Repair & maint of Cement Concrete Roads for Comm / Repair and maintenance of Cement Concrete Roads for Community | Repair & maint of Road | 1711005/RC/22012034680288 — Renovation Road Khamkheda to Mahuakheda | Ongoing | 500000 | 341957.25 | 2024-03-07
DEORIJAMADAR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Repair & maint of Gravel Road Roads for Comm / Repair and maintenance of Gravel Road Roads for Community | Repair & maint of Road | 1711005/RC/22012034680316 — Renovation Road Deori Jamadar to Mohra | Ongoing | 438000 | 323099.04 | 2024-03-08
DEORIJAMADAR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Repair & maint of Gravel Road Roads for Comm / Repair and maintenance of Gravel Road Roads for Community | Repair & maint of Road | 1711005/RC/22012034680320 — Renovation Road Deori Jamadar To Mahuakheda | Ongoing | 352000 | 311962.38 | 2024-03-08
DEORIJAMADAR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Repair & maint of Gravel Road Roads for Comm / Repair and maintenance of Gravel Road Roads for Community | Repair & maint of Road | 1711005/RC/22012034680380 — Renovation of Sagoria Via Mahugkheda Salaiya Hatri Kalapani | Ongoing | 2526000 | 1532100.26 | 2024-03-08
HARDUA MUDAR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Repair & maint of Gravel Road Roads for Comm / Repair and maintenance of Gravel Road Roads for Community | Repair & maint of Road | 1711005/RC/22012034680404 — Renovation Road Abhana Main Road to Shishpur Pati Khadantola | Deleted | 1711000 | 0 | 2023-12-21
SIHORAPADARIYA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1711005/WC/01 — मिली वाटरसेड सिहोरा पडरिया | Deleted | 160000 | 209476 | 2009-03-05
HIRDEPUR | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1711005/WC/03 — स्‍टाप डेम निर्माण कार्य ऐजेन्‍सी संसाधन विभाग हिरदेपुर | Completed | 1464000 | 665924.96 | 2010-06-01 | 2013-02-28
HATHNA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1711005/WC/06 — हथना पडरिया स्‍टापडेम सह रपटा हथना | Completed | 2335000 | 2184941 | 2011-04-25 | 2016-04-21
HATHNA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1711005/WC/07 — हथना स्‍टाप डेम सह रिपटा हथना | Completed | 2300000 | 2152167 | 2011-03-10 | 2016-04-21
MANKA | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1711005/WC/11 — मनका नाला स्‍टाप डेम जल संसाधन संभाग दमोह | Completed | 2529000 | 2027412.22 | 2009-09-17 | 2011-10-06
HINOTIRAMGARH | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1711005/WC/15 — हिनौतीरामगढ जलाशय निर्माण कार्य जल संसाधन संभाग दमोह | Completed | 3562000 | 1407422 | 2010-12-25 | 2014-10-10
KUWAKHEDANAYAK | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Stop Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1711005/WC/22012034317232 — Slab Culvert Cum Stop Dam Semarpati G.P.-Kuakhedha Nayak | Completed | 821000 | 398696 | 2017-04-11 | 2018-05-17
BALAKOT | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1711005/WC/22012034614076 — Talab Nirman Simarbahadur | Physically Completed | 942000 | 801327.49 | 2021-12-21 | 2026-06-06
HARDUA MUDAR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1711005/WC/22012034614552 — Talab Nirman Lakhanpur Raiyatwari | Ongoing | 1135000 | 300088 | 2022-06-08
MARUTAL | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1711005/WC/22012034614557 — Talab Nirman Sidhbaba Bhadawari | Physically Completed | 1115000 | 753436 | 2022-01-24 | 2026-05-16
ADHROTA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1711005/WC/22012034614562 — Talab Nirman Badyau | Closed | 719000 | 0 | 2020-12-28
ADHROTA | 2020-2021 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Construction of Embankment for community / Construction of Embankment for community | Construction of Embankment | 1711005/WC/22012034618184 — Stopdam Nirman Adhrota | Closed | 810000 | 0 | 2020-12-28
SALAIYA HATRI | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Trench for Community | Construction of Trench | 1711005/WC/22012034875227 — Contur trench Kalapani | Closed | 0 | 0 | 2021-11-01
SALAIYA HATRI | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Trench for Community | Construction of Trench | 1711005/WC/22012034875230 — Contur trench Kalapani | Deleted | 0 | 0 | 2021-11-01
PATOUHA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1711005/WC/22012034965007 — Const. of Amrit Sarovar Patouha | Deleted | 4017000 | 0 | 2022-04-04
CHANDORA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1711005/WC/22012034965905 — Const. of Amrit Sarovar Chandora | Closed | 4006000 | 0 | 2022-04-14
BALAKOT | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1711005/WC/22012034965935 — Const. of Amrit Sarovar Joshi Wale Balakot | Ongoing | 3921000 | 3719601.88 | 2022-05-16
BALAKOT | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1711005/WC/22012034965979 — Const. of Amrit Sarovar Datera Bahar Balakot | Deleted | 0 | 0 | 2022-04-01
BALAKOT | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1711005/WC/22012034968476 — Const. of Amrit Sarovar Datere Bahar Balakot | Ongoing | 4386000 | 4182954.8 | 2022-05-14
SINGHPUR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1711005/WC/22012034976138 — REnovation Tank Pushkar Yojna Singpur JP Damoh | Deleted | 0 | 0 | 2022-04-14
SINGHPUR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1711005/WC/22012034976139 — REnovation Tank Pushkar Yojna Singpur JP Damoh | Completed | 4643000 | 4468143.25 | 2022-05-22 | 2024-10-29
KHAMKHEDA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1711005/WC/22012034976201 — Renovation of Tank Pushkar Yojna Khamkheda | Ongoing | 2099000 | 1263649.51 | 2022-05-21
ARTHKHEDA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1711005/WC/22012034987036 — Const of Amrit Sarovar Arthkheda | Completed | 3029000 | 3023482.36 | 2022-06-23 | 2024-12-04
PARSORIYA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1711005/WC/22012034987040 — Const of Amrit Sarovar Parsoriya | Completed | 1811000 | 1764536.43 | 2023-05-13 | 2024-12-24
MUHLI | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1711005/WC/22012035028299 — Const of Amrit Sarovar Madhiya Khurd Muhli | Physically Completed | 4500000 | 4183527.53 | 2022-12-26 | 2026-04-30
RIYANA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1711005/WC/22012035028306 — Const of Amrit Sarovar Teda Pahad Khuchhiya Maidan Riyana | Ongoing | 4499000 | 4254993.75 | 2023-01-12
ABHANA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1711005/WC/22012035029004 — Const of Amrit Sarovar Siddho K Pas Khora Me | Ongoing | 4480000 | 3632346.8 | 2023-05-18
ABHANA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1711005/WC/22012035029009 — Const of Amrit Sarovar Kachhware Ke Pass Abhana | Deleted | 0 | 0 | 2022-08-16
ABHANA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1711005/WC/22012035029011 — Const of Amrit Sarovar Kachhware Ke Pass Abhana | Ongoing | 4470000 | 4450525.32 | 2023-04-12
DHIGSAR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1711005/WC/22012035032490 — Const. of Stopdam Puroshattam Patel Ke Khet Ke Pass Dhigsar | Ongoing | 2985000 | 2964864.31 | 2023-01-18
SEMRA MADIYA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1711005/WC/22012035033364 — Const of Amrit Sarovar Goan Ke Pass Patnakhurd | Completed | 4839000 | 4693613.67 | 2023-04-29 | 2024-10-23
DATLA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1711005/WC/22012035033388 — Const of Amrit Sarovar Lal Singh ke khet ke pass Datla | Ongoing | 4916000 | 4753368.27 | 2023-03-23
PIPARIYA SAHNI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1711005/WC/22012035033400 — Const of Amrit Sarovar Basankhora Pipariya Sahni | Ongoing | 3447000 | 3429295.55 | 2023-03-21
MARAHAR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1711005/WC/22012035042595 — Amrit Sarover Talab Marha | Ongoing | 1901000 | 1852438.99 | 2023-04-21
SEMRA MADIYA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1711005/WC/22012035043282 — Const. of Amrit Sarovar Siddho Ki Pahadi ke pass Semra Madiya | Ongoing | 4921000 | 3989643.48 | 2023-03-05
HALGAJ | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1711005/WC/22012035043364 — Const. of Amrit Sarovar Hanuman mandir Ke Pass Halgaj | Ongoing | 3700000 | 45305 | 2023-04-24
TEJGARH KHURD | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1711005/WC/22012035043405 — Const. of Amrit Sarovar Behra | Ongoing | 3700000 | 3614071.03 | 2023-04-21
BANSA TARKHEDA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1711005/WC/22012035068648 — Const. of Stopdam Basni Road per Bansa Tarkheda | Ongoing | 3469000 | 2587337.46 | 2023-05-22
KHERUWA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1711005/WC/22012035068651 — Const. of Stopdam Gram Madla ke Nala Per Kherua | Ongoing | 3445000 | 2032010.75 | 2023-05-24
JAMUNIYA HAZARI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1711005/WC/22012035070762 — NAVIN TALAB NIRMAN JAMUNIYA HAZARI | Ongoing | 2478000 | 2238466.07 | 2023-06-03
ADHROTA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1711005/WC/22012035071435 — Const. of Navin Talab Badyau | Ongoing | 3193000 | 2070231.36 | 2023-06-10
HINOTIRAMGARH | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1711005/WC/22012035072244 — Const. of Stopdam Hinoti Ramgarh | Ongoing | 3448000 | 2738051.4 | 2023-06-06
KANIYAGHATPATI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1711005/WC/22012035077708 — Const. of Stopdam deepchand Ahirwar ke khet ke pass Kaniya Ghatpati | Ongoing | 3445000 | 2380242.3 | 2023-10-02
KANIYAGHATPATI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1711005/WC/22012035077742 — Const. of Stopdam Kaniyaghat Pati | Ongoing | 3169000 | 2528715.62 | 2023-10-02
GUNJI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1711005/WC/22012035080704 — Const. of Stopdam Karondi nala per Gunji | Ongoing | 3524000 | 2441018.67 | 2023-12-04
TIKRI BUZURG | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1711005/WC/22012035082026 — Const of Stopdam Panghata Tikari Buzurg | Ongoing | 3254000 | 2759525.15 | 2024-01-25
ADHROTA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1711005/WC/22012035083802 — Const. of Navin Talab Adhrota | Ongoing | 3843000 | 3815719.56 | 2023-06-18
IMALIYALANJJI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1711005/WC/22012035083979 — Const of Stopdam bagai Nala pa maiya Dham ke pass Imaliya Lanji | Physically Completed | 3220000 | 3172221.16 | 2023-10-06 | 2026-04-29
PAYRA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1711005/WC/22012035085701 — Const. of Stopdam Ramesh Ahirwar ke Khet ke Pass Payra | Ongoing | 3671000 | 2789610.04 | 2023-10-07
SALAIYA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1711005/WC/22012035085937 — Const. of Naven Talab Gram Panchayt Salaiya | Ongoing | 4451000 | 3767036.83 | 2023-10-06
BIJORI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1711005/WC/22012035086338 — Const of Stopdam Bijori | Ongoing | 2595000 | 2040387.47 | 2024-05-06
IMALIYALANJJI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1711005/WC/22012035086990 — Const. of Navin Talab Asharam Rajak ke Ghar ke Pass Imaliya Lanji | Ongoing | 1890000 | 1639031.56 | 2023-10-06
MANKA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1711005/WC/22012035087128 — Const. of Stopdam of Virendra Lodhi ke khet ke Pass Manka | Ongoing | 3314000 | 34992 | 2024-06-11
IMALIYALANJJI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1711005/WC/22012035091566 — Const. of Stopdam Bagai Nala per maiya Dham ke Pass Imaliya Lanji | Deleted | 3220000 | 0 | 2023-04-02
JAMUNIYA HAZARI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1711005/WC/22012035116771 — CPW work khamkheda jamuniyahazari | Completed | 797000 | 716502.34 | 2023-10-05 | 2024-11-21
NONPANI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1711005/WC/22012035136139 — NAVEEN TALAB NIRMAN GP NONPANI | Physically Completed | 1162000 | 999972.76 | 2023-10-11 | 2026-04-30
GUNJI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1711005/WC/22012035142273 — NAVEEN TALAB NIRMA 1 GUNJI | Ongoing | 1876000 | 1126669.24 | 2024-03-02
GUNJI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1711005/WC/22012035142449 — NAVEEN TALAB NIRMA 2 GUNJI | Physically Completed | 1444000 | 1190765.85 | 2023-11-01 | 2026-05-20
IMALIYAGHAT | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1711005/WC/22012035172683 — Construction of Navin Talab Jamuniya Paran Talaiya ki Talaiya Par Imaliya Ghat | Completed | 3209000 | 3202890.27 | 2024-02-23 | 2025-12-30
MUHLI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1711005/WC/22012035207062 — Construction of Navin Talab Madiya Khurd Muhli | Deleted | 3609000 | 0 | 2024-04-02
MARAHAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1711005/WC/22012035313109 — Construction of Amrit Sarovar Marahar Halke Khora ke Pass | Approved | 3649000 | 0 | 2025-04-14
BHILAMPURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1711005/WC/22012035315510 — Amrit Sarovar Nirman Karya Kurmiyau Ki Pulliya Ke Pass Gram Chourai | Closed | 3630000 | 0 | 2025-06-30
CHHAPRITHAKUR | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1711005/WC/3 — स्‍टाप डेम निर्माण कार्य छापरी ठाकुर | Completed | 2579000 | 393560 | 2010-06-02 | 2015-08-25
MANKA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1711005/WC/9993622973 — chirai manka stop dem manka | Deleted | 3774000 | 0 | 2010-08-10
BALAKOT | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1711005/WH/22012034445995 — Talab Nirman Khajora | Deleted | 942000 | 0 | 2020-12-28
CHOUPRA KHURD | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1711005/WH/22012034939085 — TALAB GHARIKARAN NIRMAN WORK KISHAN KI TALIYA GRAM MARHA GP CHOUPRAKKHURAD | Closed | 497000 | 0 | 2023-04-04
DATLA | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1711/RC/22012034151211 — bm l075 अमखेडा से अमखिरिया | Completed | 2215000 | 3474302 | 2010-11-08 | 2014-10-15
ADHROTA | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Bitumen Top / Construction of Bitumen Top Roads for Community | Construction of Road and Culvert | 1711/RC/22012034151213 — बढयाउ से नयागाव टोला | Completed | 958000 | 495245.06 | 2010-09-07 | 2013-01-13
SEMRA MADIYA | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Bitumen Top / Construction of Bitumen Top Roads for Community | Construction of Road and Culvert | 1711/RC/22012034151644 — L 078 Jhinna To Gopalpura | Completed | 1611000 | 1219056.3 | 2010-11-15 | 2013-07-22
KANIYAGHATPATI | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Bitumen Top / Construction of Bitumen Top Roads for Community | Construction of Road and Culvert | 1711/RC/22012034151954 — L082 Abhana To Kaniyaghatpati khurd | Completed | 3029000 | 2203075.2 | 2010-11-08 | 2015-01-26
ATHAI | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Bitumen Top / Construction of Bitumen Top Roads for Community | Construction of Road and Culvert | 1711/RC/22012034152186 — L 090 Athai To Patharia Khurd | Completed | 776000 | 917459.1 | 2010-10-27 | 2013-01-23
DATLA | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Bitumen Top / Construction of Bitumen Top Roads for Community | Construction of Road and Culvert | 1711/RC/22012034154696 — bm l075 अमखेडा से अमखिरिया | Completed | 2215000 | 1475426.5 | 2011-04-29 | 2013-03-26
HARDUA MUDAR | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Bitumen Top / Construction of Bitumen Top Roads for Community | Construction of Road and Culvert | 1711/RC/22012034154808 — l 072 abhana to khadan tola road | Completed | 6227000 | 5260547.92 | 2012-08-27 | 2015-07-20
CHOUPRA KHURD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Bitumen Top / Construction of Bitumen Top Roads for Community | Construction of Road and Culvert | 1711/RC/22012034185613 — cement road main road to bhairo behar gram panchay | Completed | 497000 | 399263.81 | 2013-10-03 | 2015-01-26
SAMANNA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Bitumen Top / Construction of Bitumen Top Roads for Community | Construction of Road and Culvert | 1711/RC/22012034312403 — gramin khel maidan ke samne pauchmarg | Completed | 3834000 | 3040782.32 | 2016-05-25 | 2020-05-30
BANDAKPUR | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1711/RC/22012034313156 — Gaushala Approach Marg Nirman Bandakpur | Deleted | 0 | 0 | 2016-01-26
MARUTAL | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen Gully Plugs for Community / Construction of Earthen Gully Plugs for Community | Boulder Check/Gully Plug | 1711/WC/22012034326443 — Bhadawari marg par slab culvert nirman marutal | Completed | 446000 | 445584 | 2017-05-22 | 2020-07-07
PATOUHA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1711/WC/22012034965001 — Const. of Amrit Sarovar Patouha | Deleted | 4017000 | 0 | 2022-04-01
DHIGSAR | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1711/WC/9993625704 — stopdam nirman dihgsar khajri nala | Completed | 232000 | 186200.4 | 2012-04-16 | 2015-04-01
PAYRA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1711/WC/9993625707 — Stop dam payra | Completed | 341000 | 313965.2 | 2011-12-05 | 2013-02-28
MAHANDPUR | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Mini Percolation tank / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1711/WC/9993640970 — talab renovation work gp mahandpur | Completed | 632000 | 419689.4 | 2013-12-27 | 2015-04-01