## Work List
Exported on: 2026-08-27 23:23:57
Filters applied:
Data source: MGNREGA
District: REWA
Block: MAUGANJ
Panchayat: JAMURAHA NO.1
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
| 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1713006035/AV/22012034368366 — SHANTI DHAM JOGIYA TALAB PAR | Completed | 800000 | 52674 | 2017-09-22 | 2020-06-23
| 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of SHG/Fed building for Groups / Construction of SHG/Federation Building for Groups | Construction of building/workshed for SHG | 1713006035/AV/22012034536323 — swachhata parishar nirman jamuhara no 1 harijan basti me | Physically Completed | 53000 | 64980 | 2020-09-21 | 2026-05-17
| 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1713006035/AV/22012034589849 — Shantidham Mati talab me | Closed | 0 | 0 | 2021-08-15
| 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Repair & Maint of Crematorium for Community / Repair and Maintenance of Crematorium | Repair & Maint of Community infrastructure | 1713006035/AV/22012034589853 — Shantidham Tendua talab me | Closed | 0 | 0 | 2021-08-15
| 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1713006035/AV/22012034624398 — सार्व. चबूतरा निर्माण बनिया पोखरी हनुमान मंदिर के पास | Closed | 0 | 0 | 2022-08-15
| 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1713006035/AV/22012034624399 — सार्व. चबूतरा निर्माण बनिया पोखरी हनुमान मंदिर के पास | Completed | 36000 | 8772 | 2022-12-04 | 2024-06-05
| 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1713006035/AV/22012034631584 — bondari wal nirman prathmik pathshala nirman jamuhara tiw | Ongoing | 220000 | 174757 | 2023-09-07
| 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert / cross drainage structues for Community | Culvert | 1713006035/AV/22012034662363 — PAKKI NALI NIRMAN KARYA HANUMAN MANDIR SE MRIGENDRA SINGH KE GHAR KI OR | New | 0 | 0 | 2024-04-01
| 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert / cross drainage structues for Community | Culvert | 1713006035/AV/22012034662365 — PAKKI NALI NIRMAN KARYA HANUMAN MANDIR SE MRIGENDRA SINGH KE GHAR KI OR | Approved | 122000 | 0 | 2024-04-01
| 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1713006035/DP/10/जमुर01 — निर्मल वाटिका A.P.L 30 हितग्राही के यहा | Deleted | 150000 | 11937 | 2011-02-16
| 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1713006035/DP/1/जमुर01न1 — पथ व्रक्षारोपण रोपण पन्‍नी सीतापुर रोड के किनारे | Completed | 452000 | 404159 | 2008-09-11 | 2015-02-09
| 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1713006035/DP/22012034423808 — Mati talab me paudha ropan | Closed | 0 | 0 | 2018-07-17
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1713006035/DP/22012034538711 — briksharopan karya mati talab me | Ongoing | 900000 | 43540 | 2021-11-22
| 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Land Development / Levelling/shaping of Wasteland Land for Community | Land Development | 1713006035/DP/2/जमुर01न1 — नंन्‍दन फलोद्वान लालमण‍ि सिंह के भूमि मे | Completed | 144000 | 18930 | 2008-08-29 | 2015-02-09
| 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Land Development / Levelling/shaping of Wasteland Land for Community | Land Development | 1713006035/DP/3/जमुर01न1 — नंन्‍दन फलोद्वान बुद्वसेन पटेल के भूमि मे | Completed | 144000 | 5810 | 2008-08-29 | 2015-02-09
| 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1713006035/DP/4/जमुर01न1 — नंन्‍दन फलोद्वान बिहारी के भूमि मे | Completed | 144000 | 2895 | 2008-08-29 | 2014-04-12
| 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1713006035/IF/22012034315875 — kapildhara koop sah khet talab nirman | Closed | 0 | 0 | 2016-10-02
| 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1713006035/IF/22012034355053 — बृक्षारोपण कार्य जोगिया तालाब में | Closed | 4800 | 0 | 2017-06-26
| 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1713006035/IF/22012034355067 — banaiya talab ke med me plantetion | Closed | 6400 | 0 | 2017-04-14
| 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1713006035/IF/22012034363829 — बृक्षारोपण कार्य जोगिया तालाब में | Deleted | 23400000000 | 0 | 2017-04-24
| 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Boulder Check Dam for Individuals / Construction of Boulder Check Dam for Individuals | Construction of Check Dam/Stop Dam | 1713006035/IF/22012034469908 — praveen singh ke bhumi me khet talab | Completed | 288000 | 186350 | 2019-03-08 | 2021-12-29
| 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1713006035/IF/22012034585411 — gaya prasad kushwaha ke yha pashused nirman | Closed | 0 | 0 | 2020-07-06
| 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1713006035/IF/22012034585412 — mohanlal kushwaha ke yha pashu sed nirman | Closed | 0 | 0 | 2020-07-06
| 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1713006035/IF/22012034585413 — rambahor kushwaha ke yha pashu sed nirman | Closed | 0 | 0 | 2020-07-06
| 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1713006035/IF/22012034587422 — SHG PASHU PALAN NIRMAN BRIJWASI KUSHWAHA KE BHUMI ME GRAM PANCHAYAT JAMUHARA NO 1 | Closed | 0 | 0 | 2020-04-14
| 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1713006035/IF/22012034587425 — SHG PASHU PALAN NIRMAN TEJ PRATAP KUSHWAHA KE BHUMI ME GRAM PANCHAYAT JAMUHARA NO. 1 | Closed | 0 | 0 | 2020-04-14
| 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1713006035/IF/22012034587433 — SHG PASHU SHED NIRMAN VIMLESH PRASAD PATEL KE BHUMI ME GRAM PANCHAYAT JAMUHARA NO 1 | Closed | 0 | 0 | 2020-04-14
| 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1713006035/IF/22012034587447 — SHG PASHU SHED NIRMAN PREMLAL KUSHWAHA KE BHUMI ME GRAM PANCHAYAT JAMUHARA NO 1 | Closed | 0 | 0 | 2020-04-14
| 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1713006035/IF/22012034902313 — SHG Radha SW SAhayat SAmooh Davendra kumar singh ki bhumi par | Closed | 0 | 0 | 2021-08-16
| 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1713006035/IF/22012034902320 — SHG Durga Sw sahayata samoh Pashu Shed Nirman Ramsiya ki Bhumi me | Closed | 0 | 0 | 2021-08-16
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1713006035/IF/22012034980163 — SHG Sw radha sw Sahayata Samooh Pashu sed Nirman Kary Devendra Kumar Singh | Completed | 103482.45 | 82474.35 | 2022-08-27 | 2024-05-13
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1713006035/IF/22012034980170 — SHG Sw Durga Samooh Pashu sed Nirman Kary Ramsiya ki bhumi par | Completed | 103482.45 | 61291.94 | 2022-09-09 | 2024-05-13
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1713006035/IF/22012035005880 — pashu shed nirman ambuj singh ki bhoomi par | Closed | 0 | 0 | 2022-04-14
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1713006035/IF/22012035030298 — SHG KE TAHAT AMBUJ SINGH KE YHA PASHUSED NIRMAN | Physically Completed | 105982.64 | 93447.6 | 2022-11-27 | 2026-04-29
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1713006035/IF/22012035030302 — SHG KE TAHAT PASHUSED NIRMAN GAYA PRASAD KE YHA | Physically Completed | 106029.65 | 95019.39 | 2022-11-27 | 2026-04-29
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1713006035/IF/22012035030304 — SHG KE TAHAT PASHUSED NIRMAN DILRAJ KE YHA | Completed | 105982.64 | 63035.13 | 2023-03-23 | 2024-05-13
| 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1713006035/IF/22012035076725 — khet talab nirman | Closed | 0 | 0 | 2023-04-04
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1713006035/IF/22012035334011 — pmay MP127484446 awas nirman satyabhan yadav ke yha | Approved | 23500 | 0 | 2025-04-02
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1713006035/IF/22012035556906 — nammai gange ke tahat brihbhan kushwaha ke yha khet talab nirman | Ongoing | 147621.16 | 54410.75 | 2025-06-05
| 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1713006035/IF/9993694205 — CATTAL SHED | Closed | 0 | 0 | 2015-11-30
| 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1713006035/IF/9993694209 — PASHU SHED LAXAMAN KUSHWAHA | Closed | 0 | 0 | 2015-11-30
| 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1713006035/IF/9993694405 — पशु शेड निर्माण कार्य लालमणि कुशवाहा के भूमि पर | Completed | 56000 | 55542 | 2015-12-11 | 2017-04-24
| 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1713006035/IF/9993694446 — पशु शेड रामयश कुशवाहा के भूमि पर | Completed | 56000 | 56822 | 2015-12-11 | 2017-04-24
| 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1713006035/IF/9993694594 — PASHU SHAD RAMYASH | Closed | 0 | 0 | 2015-11-28
| 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006035/IF/IAY/1008008 — Construction of IAY House -IAY REG. NO. MP1469124 | Completed | 15480 | 15360 | 2017-05-10 | 2019-03-10
| 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006035/IF/IAY/195336 — Construction of IAY House -IAY REG. NO. MP-13-006-035-001/4 | Approved | 23490 | 0 | 2015-10-15
| 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006035/IF/IAY/195337 — Construction of IAY House -IAY REG. NO. MP-13-006-035-001/14 | Approved | 23490 | 0 | 2015-10-15
| 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006035/IF/IAY/195338 — Construction of IAY House -IAY REG. NO. MP-13-006-035-003/02 | Approved | 23490 | 0 | 2015-10-15
| 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006035/IF/IAY/2487695 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4180470 | Completed | 17100 | 13680 | 2020-09-05 | 2022-04-25
| 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006035/IF/IAY/2510285 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4480816 | Completed | 17100 | 14610 | 2021-10-29 | 2024-05-13
| 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006035/IF/IAY/2529980 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4798631 | Completed | 17100 | 14572 | 2020-07-21 | 2022-04-20
| 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006035/IF/IAY/2545977 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5216961 | Completed | 17100 | 15996 | 2020-09-09 | 2021-12-27
| 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006035/IF/IAY/3102019 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4192589 | Physically Completed | 17370 | 10266 | 2022-03-15 | 2024-11-21
| 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006035/IF/IAY/3102020 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4192549 | Closed | 17370 | 0 | 2021-05-04
| 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006035/IF/IAY/3102028 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4836692 | Closed | 17370 | 0 | 2021-05-04
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006035/IF/IAY/3102101 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5555760 | Completed | 17370 | 11950 | 2022-04-01 | 2024-05-13
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006035/IF/IAY/3102125 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4390725 | Completed | 17370 | 17628 | 2022-05-16 | 2023-07-07
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006035/IF/IAY/3102196 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4153342 | Physically Completed | 17370 | 12240 | 2022-11-07 | 2024-11-21
| 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006035/IF/IAY/3102197 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4154222 | Closed | 17370 | 0 | 2021-05-04
| 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006035/IF/IAY/3102331 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5526554 | Completed | 17370 | 13063 | 2021-07-08 | 2024-05-13
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006035/IF/IAY/3102348 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4175221 | Completed | 17370 | 1330 | 2022-07-01 | 2024-05-17
| 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006035/IF/IAY/3102507 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4786440 | Completed | 17370 | 16235 | 2021-10-01 | 2024-03-28
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006035/IF/IAY/3102509 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4848614 | Completed | 17370 | 10640 | 2022-04-01 | 2024-05-17
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006035/IF/IAY/3149000 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4451327 | Completed | 17370 | 7600 | 2022-04-01 | 2024-05-17
| 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006035/IF/IAY/3150775 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4436124 | Completed | 17370 | 14040 | 2021-07-10 | 2024-05-13
| 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006035/IF/IAY/3168257 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4468757 | Completed | 17370 | 12960 | 2021-09-04 | 2024-05-13
| 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006035/IF/IAY/3168880 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5567817 | Physically Completed | 17370 | 9282 | 2023-12-10 | 2024-11-21
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006035/IF/IAY/3169412 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5538821 | Completed | 17370 | 4645 | 2022-07-01 | 2024-06-13
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006035/IF/IAY/3324994 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP1715853 | Physically Completed | 17370 | 11400 | 2022-04-12 | 2024-11-21
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006035/IF/IAY/3369380 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP1693304 | Completed | 17370 | 8170 | 2022-04-12 | 2024-05-17
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006035/IF/IAY/3369384 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP1699112 | Completed | 17370 | 17588 | 2022-05-05 | 2024-05-13
| 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006035/IF/IAY/3370999 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3235887 | Closed | 17370 | 0 | 2021-11-24
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006035/IF/IAY/3371355 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3529325 | Physically Completed | 17370 | 7600 | 2022-05-05 | 2024-11-21
| 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006035/IF/IAY/3372297 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4087403 | Completed | 17370 | 5746 | 2024-03-04 | 2024-06-13
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006035/IF/IAY/3372730 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4153286 | Completed | 17370 | 1930 | 2022-04-14 | 2024-06-13
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006035/IF/IAY/3372851 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4176947 | Physically Completed | 17370 | 9554 | 2022-04-07 | 2024-11-26
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006035/IF/IAY/3373066 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4210632 | Physically Completed | 17370 | 18420 | 2022-04-14 | 2024-11-26
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006035/IF/IAY/3376634 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4752339 | Physically Completed | 17370 | 11440 | 2022-07-23 | 2024-11-27
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006035/IF/IAY/3376802 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4773551 | Completed | 17370 | 11834 | 2022-04-07 | 2024-05-13
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006035/IF/IAY/3376921 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4787898 | Completed | 17370 | 17356 | 2022-07-30 | 2022-12-15
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006035/IF/IAY/3377189 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4818775 | Completed | 17370 | 17176 | 2022-05-17 | 2023-05-06
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006035/IF/IAY/3379626 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5145612 | Physically Completed | 17370 | 5840 | 2022-04-12 | 2024-11-27
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006035/IF/IAY/3383343 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5574741 | Physically Completed | 17370 | 8414 | 2022-04-06 | 2024-11-27
| 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006035/IF/IAY/3383416 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5585300 | Closed | 17370 | 0 | 2021-11-24
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006035/IF/IAY/3383467 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5588338 | Physically Completed | 17370 | 8794 | 2022-04-12 | 2024-11-27
| 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006035/IF/IAY/3383651 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5599062 | Approved | 23490 | 0 | 2021-11-18
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006035/IF/IAY/3454760 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4810733 | Completed | 17370 | 5700 | 2022-04-21 | 2024-06-13
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006035/IF/IAY/3454761 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4810799 | Completed | 17370 | 8170 | 2022-04-21 | 2024-06-13
| 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006035/IF/IAY/3457331 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5584357 | Closed | 17370 | 0 | 2021-12-07
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006035/IF/IAY/3523161 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4181200 | Completed | 17370 | 7084 | 2022-04-07 | 2024-06-13
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006035/IF/IAY/3525972 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4153256 | Completed | 17370 | 3990 | 2022-04-07 | 2024-06-13
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006035/IF/IAY/3548558 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4773267 | Completed | 17370 | 5700 | 2022-05-05 | 2024-05-17
| 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006035/IF/IAY/3548583 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4773745 | Closed | 17370 | 0 | 2022-01-09
| 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006035/IF/IAY/3568903 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5166041 | Approved | 23490 | 0 | 2022-01-05
| 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006035/IF/IAY/3570405 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5216430 | Completed | 17370 | 15030 | 2022-03-16 | 2024-05-13
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006035/IF/IAY/3575517 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5223549 | Completed | 17370 | 16682 | 2022-04-12 | 2024-03-28
| 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006035/IF/IAY/3600690 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5579760 | Approved | 23490 | 0 | 2022-01-05
| 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006035/IF/IAY/3611426 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5584782 | Closed | 17370 | 0 | 2022-01-12
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006035/IF/IAY/3615588 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5622297 | Completed | 17370 | 10640 | 2022-08-22 | 2024-05-17
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006035/IF/IAY/3634781 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3654444 | Completed | 17370 | 5320 | 2022-08-10 | 2024-05-17
| 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006035/IF/IAY/3636390 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4812452 | Approved | 23490 | 0 | 2022-01-20
| 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006035/IF/IAY/3636392 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4812813 | Approved | 23490 | 0 | 2022-01-20
| 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006035/IF/IAY/3641929 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4814761 | Completed | 17370 | 16354 | 2023-12-13 | 2024-05-13
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006035/IF/IAY/3846833 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128099291 | Closed | 18360 | 0 | 2022-05-06
| 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006035/IF/IAY/459027 — Construction of IAY House -IAY REG. NO. MP1676035 | Completed | 15030 | 15480 | 2017-02-06 | 2018-09-07
| 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006035/IF/IAY/5437187 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128098203 | Ongoing | 23490 | 7308 | 2026-05-05
| 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006035/IF/IAY/554283 — Construction of IAY House -IAY REG. NO. MP3486070 | Completed | 15030 | 15330 | 2017-02-06 | 2019-03-10
| 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006035/IF/IAY/559585 — Construction of IAY House -IAY REG. NO. MP3643103 | Completed | 15030 | 15188 | 2017-02-06 | 2019-03-10
| 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006035/IF/IAY/646499 — Construction of IAY House -IAY REG. NO. MP1676386 | Completed | 15030 | 16446 | 2017-05-24 | 2018-12-15
| 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006035/IF/IAY/669558 — Construction of IAY House -IAY REG. NO. MP2283402 | Completed | 15030 | 15188 | 2017-06-12 | 2019-03-10
| 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006035/IF/IAY/733944 — Construction of IAY House -IAY REG. NO. MP2076285 | Completed | 15030 | 14828 | 2018-07-16 | 2019-09-13
| 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006035/IF/IAY/863305 — Construction of IAY House -IAY REG. NO. MP1651803 | Completed | 15480 | 15480 | 2018-07-09 | 2018-12-15
| 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006035/IF/IAY/866920 — Construction of IAY House -IAY REG. NO. MP1692956 | Completed | 15480 | 15552 | 2018-06-30 | 2018-12-15
| 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006035/IF/IAY/956315 — Construction of IAY House -IAY REG. NO. MP3203756 | Completed | 15480 | 15896 | 2018-06-25 | 2018-09-03
| 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1713006035/LD/1/जमुर01न1 — निर्मल वाटिका BPL 50 हितग्राही जनुहरा नं01मे | Completed | 250000 | 171100 | 2010-05-22 | 2014-05-12
| 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1713006035/LD/22012034256624 — भूमि शिल्प निर्माण कार्य | Closed | 0 | 0 | 2016-04-14
| 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1713006035/LD/22012034294705 — Shantidham Nirman Kary Jmuhra No. 1 | Ongoing | 205000 | 18931 | 2017-02-17
| 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Land Leveling / Levelling/shaping of Wasteland Land for Community | Land Development | 1713006035/LD/22012034302219 — SHANTI DHAM NIRMAN JAMUHARA ME | Closed | 205000 | 0 | 2016-10-02
| 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1713006035/LD/22012034476962 — मेड़ बंधान कार्य सावित्री मिश्रा के भूमि पर | Closed | 0 | 0 | 2020-01-26
| 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1713006035/LD/22012034476963 — मेड़ बंधान कार्य अरविन्द्र कुमार के भूमि पर | Closed | 0 | 0 | 2020-01-26
| 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1713006035/LD/22012034476964 — मेड़ बंधान कार्य बृजभान कुशवाहा के भूमि पर | Closed | 22187.55 | 0 | 2020-01-26
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1713006035/LD/22012034476965 — मेड़ बंधान कार्य देवेंद्र कुमार सिंह के भूमि पर | Completed | 19017.9 | 18384 | 2021-06-16 | 2023-03-22
| 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1713006035/LD/22012034517363 — Med badhan kary Manvati ke khet me | Closed | 0 | 0 | 2020-01-26
| 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1713006035/LD/22012034517365 — med Badhan kary narvada ke khet me | Closed | 0 | 0 | 2020-01-26
| 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1713006035/LD/22012034517366 — med Badhan kary Anil ke khet me | Closed | 0 | 0 | 2020-01-26
| 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1713006035/LD/22012034517597 — med bandhan karya narvada kushwaha ke bhumi per | Closed | 22492.82 | 0 | 2020-04-14
| 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1713006035/LD/22012034517598 — med bandhan karya anil kumar kushwaha ke bhumi per | Completed | 21592.82 | 19940 | 2020-07-18 | 2023-03-22
| 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1713006035/LD/22012034517599 — med bandhan karya weba manwati kol ke bhumi per | Closed | 0 | 0 | 2020-04-14
| 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Level Bench Terrace Terrace for Comm / Construction of Level Bench Terrace for Community | Terracing | 1713006035/LD/22012034518348 — vijay krishn patel ke ghar se jamuhara panni sitapur pahuch marg ki aur | Closed | 0 | 0 | 2020-04-27
| 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1713006035/LD/22012034594908 — samatalikaran kary primary school jamuhara no1 | Ongoing | 362754.8 | 160723.3 | 2024-09-20
| 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1713006035/LD/22012034599280 — prathmik pathshala jamuhara tiwariya me samtalikaran kary | Closed | 0 | 0 | 2023-10-02
| 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1713006035/LD/2/जमुर01न1 — निर्मल वाटिका APL 30 हितग्राही जनुहरा नं01मे | Completed | 150000 | 118031 | 2010-06-17 | 2014-04-15
| 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1713006035/LD/3/जमुर01न1 — निर्मल वाटिका APL 21 हितग्राही जनुहरा नं01मे | Completed | 150000 | 31125 | 2010-07-10 | 2014-04-15
| 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1713006035/LD/4/जमुर01न1 — निर्मल वाटिका APL 25 हितग्राही जनुहरा नं01मे | Completed | 85000 | 94350 | 2010-05-05 | 2011-10-20
| 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1713006035/LD/8/ज0 नं01 — शांती धाम निर्माण कार्य ग्राम बेलहाई मे | Completed | 166000 | 47092 | 2012-02-13 | 2015-02-09
| 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play field for Community | Construction of Play field | 1713006035/PG/9425891202 — khel maidan Govt. Prathmik pathshala Jamuhra Tiwariyan | Completed | 244000 | 248575.09 | 2016-12-08 | 2019-10-02
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1713006035/RC/22012034205771 — खेत सडक देव शरण कुशवाहा खेत से विश्राम गया के खेत | Completed | 784318 | 52656 | 2014-02-20 | 2016-09-05
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713006035/RC/22012034209446 — पी सी सी सडक निर्माण र्इ. जी. एस. शाला से लक्ष्‍मण | Deleted | 135000 | 0 | 2014-01-26
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713006035/RC/22012034209459 — पीसीसी सह नाली ईजीएस शाला से लछिमन कुशवाहा के घर त | Completed | 135000 | 82722 | 2014-03-02 | 2017-03-30
| 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713006035/RC/22012034263923 — PCC Road Niman 150 Mtr | Deleted | 0 | 0 | 2015-01-26
| 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713006035/RC/22012034293223 — PCC Aur Nali Nirman Rajnish Saket ke Ghar se Bhaiyalal saket ke ghar tak | Completed | 142000 | 90453 | 2015-12-17 | 2019-03-03
| 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713006035/RC/22012034296034 — PCC & Nali Nirman Ambika Kushwaha ke Ghar se Kachiyan tola | Completed | 142000 | 63918 | 2016-01-11 | 2018-03-10
| 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1713006035/RC/22012034326518 — RCC NALI NIRMAN SHASHKIYA DUKAN SE SHYAMKALI KE GHAR KI OR | Completed | 609000 | 154976 | 2017-02-12 | 2018-03-10
| 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1713006035/RC/22012034334412 — PCC SAH NALI NIRMAN KARYA SATISH SINGH KE GHAR SE DHIRENDRA SINGH KE GHAR TAK | Completed | 66300 | 63738 | 2017-05-16 | 2019-06-10
| 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713006035/RC/22012034344774 — PCC SADAK RAMBAHADUR KOL KE GHAR SE HARIJAN BASTI MUNSI LAL SAKET KE GHAR TAK | Completed | 66300 | 65862 | 2017-10-06 | 2019-10-10
| 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713006035/RC/22012034373737 — Pcc road nirman nali sahit 200 Mtr | Closed | 0 | 0 | 2017-10-02
| 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713006035/RC/22012034433518 — pcc rode nirman Durghar kushwaha ke ghar se laxman kushwaha ke ghar tak | Completed | 38300 | 38628 | 2019-01-01 | 2019-10-10
| 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713006035/RC/22012034437820 — अनुरुद्ध पटेल के घर से फूलमती मंदिर की ओर | Completed | 114000 | 107396 | 2019-01-25 | 2020-07-07
| 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713006035/RC/22012034437939 — देवानमा तालाब से हरिशंरण सिंह के घर की ओर | Completed | 76000 | 73488 | 2019-01-25 | 2020-07-07
| 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713006035/RC/22012034440332 — PCC SADAK NIRMAN KARYA BAIRA KE GHAR SE FUGGU KE GHAR TAK | Closed | 0 | 0 | 2019-04-14
| 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713006035/RC/22012034448810 — रामकृष्ण कुशवाहा के घर से रामसिया कुशवाह के घर की ओर | Closed | 75000 | 0 | 2019-01-26
| 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1713006035/RC/22012034517766 — sudur sadak raghunath patel ke ghar se shanti dhaam prathmik school harijan basti ki or | Completed | 1452262.81 | 1413977.41 | 2020-02-18 | 2022-04-15
| 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1713006035/RC/22012034517916 — sudur samak sadak jamuhara no 1 me | Closed | 0 | 0 | 2019-10-02
| 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Mitti Murram Roads for Community / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1713006035/RC/22012034526289 — sudur gram sampark sadak nirman vijay krishn patel ke ghar se jamuhara panni sitapur pahuch marg ki | Completed | 1449220.15 | 1390648.21 | 2020-08-20 | 2024-03-28
| 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713006035/RC/22012034571963 — pakki nali nirman raghunath ke ghr se kushwaha basti ki aur | Closed | 0 | 0 | 2021-05-06
| 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713006035/RC/22012034571964 — pakki nali nirman sahdev kol ke ghr se ramvishal saket ke ghr aur | Closed | 0 | 0 | 2021-05-06
| 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Interlocking block/tiles Roads for Comm / Construction of Inter-locking cement block/tiles Roads for Community | Constr of Cement Concrete Roads | 1713006035/RC/22012034636496 — pakki nali nirman mrijendra singh ke ghr se kd singh ke ghr ki aur 400mtr | Closed | 0 | 0 | 2023-04-14
| 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1713006035/RC/33 — ग्रेवलरोड निर्माण मती तालाब से रघुनाथ कुशवाहा के | Completed | 497000 | 357534 | 2012-05-07 | 2015-12-30
| 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713006035/RC/9/जमुहरा 1 — पी.सी.सी. एवं नाली निर्माण हनुमान मंदिर से ब्रजभान | Completed | 142000 | 133796 | 2012-01-30 | 2013-12-22
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713006035/RS/16432 — निर्मल भारत अभियान अन्‍तर्गत शौलायल निर्माण कार्य | Completed | 4400 | 4370 | 2013-05-02 | 2014-08-22
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713006035/RS/16437 — निर्मल भारत अभियान अन्‍तरगत शौचालय निर्माण वीरहादु | Completed | 4400 | 4370 | 2013-05-02 | 2014-08-22
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713006035/RS/16446 — निर्मल भारत अभियान अन्‍तर्गत बुधिमान शौलायल निर्मा | Completed | 4400 | 4370 | 2013-05-02 | 2014-08-22
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713006035/RS/16450 — निर्मल भारत अभियान अन्‍तर्गत शौलायल निर्माण कार्य | Completed | 4400 | 4370 | 2013-05-02 | 2014-08-22
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713006035/RS/22012034188240 — निर्मल भारत शौचालय निर्माण रामप्रताप/बैशाखू के घर | Completed | 4400 | 3282 | 2014-01-01 | 2014-04-04
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713006035/RS/22012034190209 — निर्मल भारत शौचालय निर्माण रघुपति के घर मे जमुहरा | Completed | 4400 | 3282 | 2014-01-01 | 2014-04-04
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713006035/RS/22012034193848 — निर्मल भारत शौचालय रामक्रष्‍ण के घर मे जमुहरा न0 1 | Completed | 4400 | 3840 | 2014-01-13 | 2014-04-04
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713006035/RS/22012034193851 — निर्मल भारत शौचालय धुजा/ठाकुरदीन के घर मे जमुहरा न0 1 | Completed | 4400 | 3840 | 2014-01-13 | 2014-04-04
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713006035/RS/22012034201448 — निर्मल भारत शौचालय श्‍यामलाल के घर मे जमुहरा न0 1 | Completed | 4400 | 3548 | 2014-02-03 | 2014-04-04
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713006035/RS/22012034205398 — निर्मल भारत शौचालय रामसिया/ठाकुरदीन के घर मे जमुहरा ना0 1 | Completed | 4400 | 2628 | 2014-02-15 | 2014-04-04
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713006035/RS/22012034205406 — निर्मल शौचालय श्‍यामलाल /जमुना के घर पर जमुहरा न01 | Completed | 4400 | 2628 | 2014-02-15 | 2014-04-04
| 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713006035/RS/22012034243427 — निर्मल भारत शौचालय श्‍यामवती/श्‍यामडी तिवारी के घर | Deleted | 0 | 0 | 2012-08-10
| 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713006035/RS/22012034256416 — निर्मल भारत शौचालय श्‍यामवती/श्‍यामडी तिवारी के घर | Completed | 5400 | 2826 | 2014-08-04 | 2016-10-19
| 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713006035/RS/22012034256420 — निर्मल भारत शौचालय रमेश/ उग्रभान के घर पर | Deleted | 5400 | 0 | 2014-08-04
| 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713006035/RS/22012034256423 — निर्मल भारत शौचालय शेलेन्द्र तिबरी के घर में | Deleted | 5400 | 0 | 2014-08-04
| 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713006035/RS/22012034333219 — sauchalay ka nirman vrndra prasad ke ghar me | Completed | 12000 | 860 | 2017-04-13 | 2024-06-05
| 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713006035/RS/22012034333222 — SAUCHALAY KA NIRMAN BRIJBHAN PRASAD KE GHAR ME | Completed | 12000 | 11204 | 2017-03-25 | 2018-08-14
| 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713006035/RS/22012034333226 — SAUCHALAY KA NIRMAN RAMAYAN PRASAD KE GHAR ME | Completed | 12000 | 11204 | 2017-03-25 | 2018-08-14
| 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713006035/RS/22012034333231 — SAUCHALAY KA NIRMAN TULSIDAS KE GHAR ME | Completed | 12000 | 2004 | 2017-03-25 | 2024-06-05
| 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713006035/RS/22012034333235 — SAUCHALAY KA NIRMAN RAMKAILASH KE GHAR ME | Completed | 12000 | 2004 | 2017-03-25 | 2017-05-15
| 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713006035/RS/22012034333237 — SAUCHALAY KA NIRMAN VASANT PRASAD KE GHAR ME | Completed | 12000 | 11204 | 2017-03-25 | 2018-08-14
| 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713006035/RS/22012034333240 — SAUCHALAY KA NIRMAN VISHRAM SAKET KE GHAR ME | Completed | 12000 | 11204 | 2017-03-25 | 2018-08-14
| 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713006035/RS/22012034333245 — SAUCHALAY KA NIRMAN BUDDHASEN PATEL KE GHAR ME | Completed | 12000 | 11204 | 2017-03-25 | 2018-08-14
| 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713006035/RS/22012034333250 — SAUCHALAY KA NIRMAN SHIVPRASAD KE GHAR ME | Completed | 12000 | 11204 | 2017-03-25 | 2018-08-14
| 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713006035/RS/22012034333293 — SAUCHALAY KA NIRMAN SUBHADRA SINGH KE GHAR ME | Completed | 12000 | 11204 | 2017-03-25 | 2018-08-14
| 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713006035/RS/22012034333297 — SAUCHALAY KA NIRMAN JAGANNATH KUSHWAHA KE GHAR ME | Completed | 12000 | 11204 | 2017-03-25 | 2018-07-25
| 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713006035/RS/22012034333300 — SAUCHALAY KA NIRMAN INDRALAL KUSHWAHA KE GHAR ME | Completed | 12000 | 10202 | 2017-04-14 | 2024-06-05
| 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713006035/RS/22012034338379 — SAUCHALAY KA NIRMAN RAMESH SAKET KE GHAR ME | Completed | 12000 | 1002 | 2017-04-14 | 2024-06-05
| 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713006035/RS/22012034338397 — SAUCHALAY KA NIRMAN GULABWATI KE GHAR ME | Completed | 12000 | 10202 | 2017-04-14 | 2018-08-14
| 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713006035/RS/22012034338400 — SAUCHALAY KA NIRMAN MANWATI KE GHAR ME | Completed | 12000 | 10202 | 2017-04-14 | 2018-08-14
| 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713006035/RS/22012034338402 — SAUCHALAY KA NIRMAN RAMKHELAWAN SINGH KE GHAR ME | Completed | 12000 | 1002 | 2017-04-14 | 2024-06-05
| 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713006035/RS/22012034338404 — SAUCHALAY KA NIRMAN PRAVEEN SINGH KE GHAR ME | Completed | 12000 | 1002 | 2017-04-14 | 2024-06-05
| 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713006035/RS/22012034338406 — SAUCHALAY KA NIRMAN JITLAL KE GHAR ME | Closed | 12000 | 0 | 2017-03-15
| 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713006035/RS/22012034338509 — sauchalay nirman kary laxminidhi mishra ke ghar me | Completed | 12000 | 10868 | 2017-04-07 | 2018-08-10
| 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713006035/RS/22012034339169 — SAUCHALAY KA NIRMAN DAYASHANKAR KE GHAR ME | Completed | 12000 | 10202 | 2017-04-14 | 2018-08-14
| 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713006035/RS/22012034347694 — sauchalay nirman kary kusum bati sen ke ghar me | Completed | 12000 | 3006 | 2017-05-21 | 2017-08-15
| 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713006035/RS/22012034361675 — sauchalay nirmaan karya shashi singh ke ghar men | Completed | 12000 | 11997 | 2017-08-01 | 2018-07-20
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713006035/RS/52144 — निर्मल भारत शौचालय ब्रहस्‍पति सिंह के घर पर जमुहरा | Completed | 4400 | 3880 | 2013-08-01 | 2014-08-22
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713006035/RS/52146 — निर्मल भारत शौचालय निर्माण अनिल सिंह के घर मे जमुह | Completed | 4400 | 3880 | 2013-08-01 | 2014-08-22
| 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Stone Bund / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1713006035/WC/005/जनुहरा नं 1 — सार्वजनिक कूप निमार्ण हरिजन वस्‍ती बेलहई शामूमि में ज नं 1 | Completed | 228701 | 281162 | 2008-03-28 | 2010-08-19
| 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1713006035/WC/22012034324511 — DEVNAMA talab ka jal shamata ka vistarikaran | Completed | 316000 | 86172 | 2017-05-15 | 2018-03-10
| 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1713006035/WC/22012034324526 — JOGIYA talab ka jal shamata ka vistarikaran | Completed | 37400 | 94188 | 2017-05-15 | 2018-03-20
| 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1713006035/WC/22012034324528 — JOGIYA talab ka jal shamata ka vistarikaran | Closed | 37400 | 0 | 2017-04-14
| 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1713006035/WC/22012034524783 — मती तालाब का बन्द बिस्तार | Closed | 0 | 0 | 2020-01-26
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1713006035/WC/22012034729102 — nala safayi karan jamuhara me | Closed | 0 | 0 | 2021-05-06
| 2021-2022 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1713006035/WC/22012034810016 — CTR Nali nirman Sahdev kol ke ghar se Ramvishal ke ghar ki oor | Closed | 0 | 0 | 2021-08-15
| 2021-2022 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Repair & Maint of Flood/Diversion Channel for Comm / Repair and Maintenance of Flood/ Diversion Channel for Community | Repair & maint of Water Harvesting Structures | 1713006035/WC/22012034810028 — CTR Nali nirman Mrigendra singh ke ghar se Kapidhwaj Singh ke ghar ki oor | Closed | 0 | 0 | 2021-08-15
| 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1713006035/WC/22012034896657 — CTR Med bandhan | Closed | 0 | 0 | 2022-04-14
| 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1713006035/WC/22012034936055 — Ctr soak pit recharge pit nirman kary | Closed | 2500 | 0 | 2022-04-01
| 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1713006035/WC/22012034936097 — Ctr soak pit recharge pit nirman kary | Closed | 2500 | 0 | 2022-04-01
| 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & maint of Community Ponds for Comm / Repair and maintenance of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1713006035/WC/22012034972276 — जीर्णोद्धार संधारण कार्य देमनवा तालाब | Closed | 0 | 0 | 2022-04-04
| 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & maint of Community Ponds for Comm / Repair and maintenance of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1713006035/WC/22012034972287 — जीर्णोद्धार संधारण कार्य देमनवा तालाब | Closed | 396000 | 0 | 2022-04-04
| 2022-2023 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Wire crate (gabion) Spur for Comm / Construction of Wire crate (gabion) Spur for Community | Constr of Gabion | 1713006035/WC/22012034996923 — gabian nirman karay jamuhara | Closed | 0 | 0 | 2022-07-16
| 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Underground Dykes for Community / Construction of Underground Dykes for Community | Underground Dyke for Ground Water Recharge | 1713006035/WC/22012034998011 — Percolation Tank | Closed | 0 | 0 | 2022-08-16
| 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1713006035/WC/22012035170181 — Contraction of recharge pits for community | New | 0 | 0 | 2024-04-14
| 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1713006035/WC/22012035212957 — namami gange ke tahat devgamna talab sudhar kary | Approved | 0 | 0 | 2024-06-08
| 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Desilting / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1713006035/WH/005/जमुहरा नं0 1 — 1713006035/WH/005/जमुहरा नं0 1 | Completed | 0 | 3576 | 2008-03-28 | 2013-03-28
| 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Excavation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1713006035/WH/6/जमुर01न1 — बनिया पोखरी तालाब का वण्‍ड बिस्‍तार कार्य | Completed | 395000 | 304753 | 2009-02-28 | 2011-05-30
| 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Excavation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1713006035/WH/7/जमुर01न1 — शा0 मती तालाव का वण्‍ड विस्‍तार | Completed | 448000 | 179282 | 2011-04-23 | 2014-07-03
| 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713006045/RS/267 — निर्मल भारत अभियान अन्‍तर्गत शौलायल निर्माण कार्य | Completed | 4400 | 4090 | 2013-03-14 | 2014-04-04