LAPTA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713008 /IF/IAY/423243 — Construction of IAY House -IAY REG. NO. MP1348819 | Completed | 17100 | 13560 | 2017-10-30 | 2020-12-23
LAPTA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713008 /IF/IAY/424560 — Construction of IAY House -IAY REG. NO. MP1357236 | Completed | 17100 | 13560 | 2017-10-30 | 2021-12-23
ATARIYA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713008 /IF/IAY/426064 — Construction of IAY House -IAY REG. NO. MP1367735 | Closed | 17100 | 0 | 2017-01-25
JOKIHA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713008 /IF/IAY/427836 — Construction of IAY House -IAY REG. NO. MP1380056 | Completed | 15030 | 15480 | 2017-04-03 | 2018-03-13
ATARIYA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713008 /IF/IAY/431348 — Construction of IAY House -IAY REG. NO. MP1404126 | Completed | 15030 | 14640 | 2018-04-19 | 2019-07-15
DIHIYA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713008 /IF/IAY/434876 — Construction of IAY House -IAY REG. NO. MP1429483 | Closed | 17100 | 0 | 2017-01-25
SEMARIYA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713008 /IF/IAY/435073 — Construction of IAY House -IAY REG. NO. MP1430565 | Closed | 17100 | 0 | 2017-01-25
BAMHAURI | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713008 /IF/IAY/436246 — Construction of IAY House -IAY REG. NO. MP1439021 | Completed | 15030 | 14616 | 2018-07-17 | 2019-02-25
BAMHAURI | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713008 /IF/IAY/438274 — Construction of IAY House -IAY REG. NO. MP1454124 | Completed | 15030 | 14616 | 2018-07-17 | 2019-02-25
DEORA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713008 /IF/IAY/442225 — Construction of IAY House -IAY REG. NO. MP1483998 | Completed | 17100 | 6264 | 2018-01-25 | 2020-11-05
SHIWAPURWA 601 | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713008 /IF/IAY/442351 — Construction of IAY House -IAY REG. NO. MP1484889 | Completed | 15030 | 15702 | 2017-10-28 | 2018-06-22
DEORA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713008 /IF/IAY/443809 — Construction of IAY House -IAY REG. NO. MP1496323 | Completed | 17100 | 8352 | 2018-07-30 | 2020-11-05
ATARIYA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713008 /IF/IAY/444894 — Construction of IAY House -IAY REG. NO. MP1504791 | Completed | 15030 | 15660 | 2018-04-19 | 2018-11-14
SHIWAPURWA 601 | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713008 /IF/IAY/445474 — Construction of IAY House -IAY REG. NO. MP1509537 | Completed | 15030 | 15504 | 2017-10-28 | 2018-06-05
ATARIYA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713008 /IF/IAY/445529 — Construction of IAY House -IAY REG. NO. MP1509983 | Closed | 17100 | 0 | 2017-01-25
SHIWAPURWA 601 | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713008 /IF/IAY/445612 — Construction of IAY House -IAY REG. NO. MP1511318 | Completed | 15030 | 15492 | 2017-10-28 | 2018-06-05
JORI | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713008 /IF/IAY/449970 — Construction of IAY House -IAY REG. NO. MP1562670 | Closed | 17100 | 0 | 2017-01-25
SANW | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713008 /IF/IAY/464865 — Construction of IAY House -IAY REG. NO. MP1758582 | Closed | 17100 | 0 | 2017-01-25
JERUKA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713008 /IF/IAY/467112 — Construction of IAY House -IAY REG. NO. MP1785083 | Completed | 15030 | 15552 | 2017-10-30 | 2018-06-03
BAHURI BANDH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713008 /IF/IAY/469456 — Construction of IAY House -IAY REG. NO. MP1819652 | Completed | 15030 | 15504 | 2018-12-01 | 2019-11-11
BAHURI BANDH | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713008 /IF/IAY/469460 — Construction of IAY House -IAY REG. NO. MP1819683 | Completed | 17100 | 18250 | 2022-03-22 | 2022-09-01
KANAUJA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713008 /IF/IAY/474577 — Construction of IAY House -IAY REG. NO. MP1893607 | Completed | 15030 | 15492 | 2017-10-30 | 2018-05-20
KANAUJA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713008 /IF/IAY/477177 — Construction of IAY House -IAY REG. NO. MP1933835 | Completed | 15030 | 15552 | 2017-10-31 | 2018-05-20
BAMHAURI | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713008 /IF/IAY/510381 — Construction of IAY House -IAY REG. NO. MP2384116 | Completed | 15030 | 15660 | 2018-07-17 | 2018-10-31
ATARIYA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713008 /IF/IAY/513837 — Construction of IAY House -IAY REG. NO. MP2427292 | Completed | 15030 | 15660 | 2018-04-19 | 2018-12-07
BAMHAURI | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713008 /IF/IAY/517475 — Construction of IAY House -IAY REG. NO. MP2496678 | Completed | 15030 | 15660 | 2018-07-17 | 2018-10-31
BAMHAURI | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713008 /IF/IAY/519694 — Construction of IAY House -IAY REG. NO. MP2546818 | Completed | 15030 | 15660 | 2018-07-17 | 2019-02-11
GAHIRA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713008 /IF/IAY/526202 — Construction of IAY House -IAY REG. NO. MP2703465 | Completed | 15030 | 15516 | 2018-02-11 | 2019-01-02
DHAUCHAT | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713008 /IF/IAY/526874 — Construction of IAY House -IAY REG. NO. MP2721932 | Completed | 15030 | 12970 | 2017-10-30 | 2018-10-12
ATARIYA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713008 /IF/IAY/528716 — Construction of IAY House -IAY REG. NO. MP2767436 | Completed | 15030 | 16704 | 2018-04-19 | 2018-11-23
SHIWAPURWA 601 | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713008 /IF/IAY/528856 — Construction of IAY House -IAY REG. NO. MP2771057 | Completed | 15030 | 15528 | 2017-10-28 | 2018-06-05
SHIWAPURWA 601 | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713008 /IF/IAY/530146 — Construction of IAY House -IAY REG. NO. MP2800530 | Completed | 15030 | 15576 | 2017-10-28 | 2018-07-07
SHIWAPURWA 601 | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713008 /IF/IAY/532736 — Construction of IAY House -IAY REG. NO. MP2869062 | Completed | 15030 | 15504 | 2017-10-28 | 2018-06-05
JERUKA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713008 /IF/IAY/538391 — Construction of IAY House -IAY REG. NO. MP3026747 | Completed | 15030 | 15600 | 2017-10-30 | 2018-08-14
BAHURI BANDH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713008 /IF/IAY/541991 — Construction of IAY House -IAY REG. NO. MP3123107 | Completed | 15030 | 14442 | 2018-04-28 | 2019-03-22
BAHURI BANDH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713008 /IF/IAY/542074 — Construction of IAY House -IAY REG. NO. MP3125447 | Completed | 15030 | 14819 | 2018-12-01 | 2019-09-09
MAGURAHAI | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713008 /IF/IAY/545421 — Construction of IAY House -IAY REG. NO. MP3224383 | Closed | 17100 | 0 | 2017-01-25
BAMHAURI | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713008 /IF/IAY/553513 — Construction of IAY House -IAY REG. NO. MP3462895 | Completed | 15030 | 14964 | 2018-07-17 | 2019-03-31
BAMHAURI | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713008 /IF/IAY/554465 — Construction of IAY House -IAY REG. NO. MP3490979 | Closed | 17100 | 0 | 2017-01-25
JERUKA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713008 /IF/IAY/561410 — Construction of IAY House -IAY REG. NO. MP3711238 | Completed | 15030 | 15552 | 2017-10-30 | 2018-06-03
JERUKA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713008 /IF/IAY/561554 — Construction of IAY House -IAY REG. NO. MP3716383 | Completed | 15030 | 15564 | 2017-10-30 | 2018-08-30
JERUKA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713008 /IF/IAY/563159 — Construction of IAY House -IAY REG. NO. MP3779880 | Completed | 15030 | 15380 | 2017-10-30 | 2018-05-02
JERUKA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713008 /IF/IAY/563606 — Construction of IAY House -IAY REG. NO. MP3792814 | Completed | 15030 | 15552 | 2017-10-30 | 2018-06-03
JERUKA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713008 /IF/IAY/569342 — Construction of IAY House -IAY REG. NO. MP4095192 | Completed | 17100 | 17100 | 2022-01-22 | 2022-09-30
JERUKA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713008 /IF/IAY/570777 — Construction of IAY House -IAY REG. NO. MP5022952 | Completed | 17100 | 17100 | 2022-01-22 | 2022-09-15
TEEKAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713008 /IF/IAY/591667 — Construction of IAY House -IAY REG. NO. MP1082282 | Completed | 15030 | 13352 | 2018-02-13 | 2019-08-25
TEEKAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713008 /IF/IAY/591721 — Construction of IAY House -IAY REG. NO. MP1092057 | Completed | 15030 | 13524 | 2018-02-10 | 2019-08-25
TEEKAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713008 /IF/IAY/592733 — Construction of IAY House -IAY REG. NO. MP1257473 | Completed | 17100 | 15349 | 2024-07-05 | 2025-02-17
BAMHAURI | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713008 /IF/IAY/592759 — Construction of IAY House -IAY REG. NO. MP1263471 | Completed | 15030 | 14616 | 2018-07-17 | 2019-02-25
JOKIHA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713008 /IF/IAY/593111 — Construction of IAY House -IAY REG. NO. MP1383057 | Completed | 15030 | 14812 | 2017-04-03 | 2019-03-22
BAJARANGPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713008 /IF/IAY/593395 — Construction of IAY House -IAY REG. NO. MP1497317 | Completed | 15030 | 14616 | 2018-10-25 | 2019-04-01
DUARI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713008 /IF/IAY/594104 — Construction of IAY House -IAY REG. NO. MP1962807 | Completed | 15030 | 15504 | 2017-10-30 | 2018-05-02
TEEKAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713008 /IF/IAY/76505 — Construction of IAY House -IAY REG. NO. MP-13-008-061-002/124 | Completed | 14310 | 14081 | 2024-06-23 | 2024-10-08
TEEKAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713008 /IF/IAY/87344 — Construction of IAY House -IAY REG. NO. MP-13-008-061-002/170 | Completed | 14310 | 14283 | 2024-06-14 | 2024-10-08
TEEKAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713008 /IF/IAY/87347 — Construction of IAY House -IAY REG. NO. MP-13-008-061-002/201 | Completed | 23490 | 10246 | 2024-06-14 | 2026-02-07
TEEKAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713008 /IF/IAY/87348 — Construction of IAY House -IAY REG. NO. MP-13-008-061-002/251 | Completed | 14310 | 14310 | 2024-06-14 | 2024-10-05
TEEKAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713008 /IF/IAY/87349 — Construction of IAY House -IAY REG. NO. MP-13-008-061-002/397 | Completed | 14310 | 14074 | 2024-06-23 | 2024-10-05
TEEKAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713008 /IF/IAY/87350 — Construction of IAY House -IAY REG. NO. MP-13-008-061-002/660 | Completed | 23490 | 13878 | 2024-06-24 | 2025-05-08
TEEKAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713008 /IF/IAY/87354 — Construction of IAY House -IAY REG. NO. MP-13-008-061-002/796 | Completed | 23490 | 14306 | 2024-06-23 | 2025-05-08
GAHIRA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713008 /IF/IAY/87355 — Construction of IAY House -IAY REG. NO. MP-13-008-062-001/47 | Completed | 23490 | 18837 | 2025-03-03 | 2025-06-14
KANAUJA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713008 /IF/IAY/87361 — Construction of IAY House -IAY REG. NO. MP-13-008-067-003/15 | Approved | 27000 | 0 | 2015-10-05
KANAUJA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713008 /IF/IAY/87362 — Construction of IAY House -IAY REG. NO. MP-13-008-067-003/158 | Approved | 27000 | 0 | 2015-10-05
KANAUJA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713008 /IF/IAY/87363 — Construction of IAY House -IAY REG. NO. MP-13-008-067-003/96 | Approved | 27000 | 0 | 2015-10-05
LAPTA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713008 /IF/IAY/87392 — Construction of IAY House -IAY REG. NO. MP-13-008-013-001/4823 | Ongoing | 27000 | 4472 | 2025-02-15
SANW | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713008 /IF/IAY/87399 — Construction of IAY House -IAY REG. NO. MP-13-008-016-001/131 | Approved | 27000 | 0 | 2015-10-05
ATARIYA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713008 /IF/IAY/87421 — Construction of IAY House -IAY REG. NO. MP-13-008-021-001/48 | Completed | 14310 | 13703 | 2023-11-29 | 2024-05-05
ATARIYA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713008 /IF/IAY/87422 — Construction of IAY House -IAY REG. NO. MP-13-008-021-001/51 | Completed | 14310 | 14157 | 2023-11-29 | 2024-05-05
ATARIYA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713008 /IF/IAY/87423 — Construction of IAY House -IAY REG. NO. MP-13-008-021-003/2420 | Completed | 14310 | 14144 | 2023-11-29 | 2024-05-05
ATARIYA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713008 /IF/IAY/87424 — Construction of IAY House -IAY REG. NO. MP-13-008-021-003/32 | Completed | 14310 | 14144 | 2023-11-29 | 2024-05-05
JERUKA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713008 /IF/IAY/87436 — Construction of IAY House -IAY REG. NO. MP-13-008-026-002/3 | Completed | 14310 | 14496 | 2017-10-30 | 2018-06-03
JERUKA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713008 /IF/IAY/87437 — Construction of IAY House -IAY REG. NO. MP-13-008-026-002/30 | Approved | 27000 | 0 | 2015-10-05
JERUKA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713008 /IF/IAY/87438 — Construction of IAY House -IAY REG. NO. MP-13-008-026-002/42 | Completed | 14310 | 14524 | 2017-10-30 | 2019-04-12
DHAUCHAT | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713008 /IF/IAY/87440 — Construction of IAY House -IAY REG. NO. MP-13-008-027-001/41 | Approved | 27000 | 0 | 2015-10-05
KHAIRA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713008 /IF/IAY/87461 — Construction of IAY House -IAY REG. NO. MP-13-008-043-001/120 | Approved | 27000 | 0 | 2015-10-05
SHIWAPURWA 601 | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713008 /IF/IAY/87473 — Construction of IAY House -IAY REG. NO. MP-13-008-072-001/33 | Approved | 27000 | 0 | 2015-10-05
SHIWAPURWA 601 | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713008 /IF/IAY/87474 — Construction of IAY House -IAY REG. NO. MP-13-008-072-001/359 | Approved | 27000 | 0 | 2015-10-05
BAMHAURI | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713008 /IF/IAY/88382 — Construction of IAY House -IAY REG. NO. MP-13-008-014-003/110 | Approved | 27000 | 0 | 2015-10-16
BAMHAURI | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713008 /IF/IAY/88383 — Construction of IAY House -IAY REG. NO. MP-13-008-014-003/68 | Approved | 27000 | 0 | 2015-10-16
BAMHAURI | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713008 /IF/IAY/88384 — Construction of IAY House -IAY REG. NO. MP-13-008-014-003/70 | Approved | 27000 | 0 | 2015-10-16
SEMARIYA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713008 /IF/IAY/88416 — Construction of IAY House -IAY REG. NO. MP-13-008-058-002/39 | Approved | 27000 | 0 | 2015-10-16
SEMARIYA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713008 /IF/IAY/88417 — Construction of IAY House -IAY REG. NO. MP-13-008-058-002/52 | Approved | 27000 | 0 | 2015-10-16
JORI | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713008 /IF/IAY/88437 — Construction of IAY House -IAY REG. NO. MP-13-008-083-003/112 | Approved | 27000 | 0 | 2015-10-16
JORI | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713008 /IF/IAY/88438 — Construction of IAY House -IAY REG. NO. MP-13-008-083-003/127 | Approved | 27000 | 0 | 2015-10-16
JORI | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713008 /IF/IAY/88439 — Construction of IAY House -IAY REG. NO. MP-13-008-083-003/28 | Approved | 27000 | 0 | 2015-10-16
SHIWAPURWA 601 | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713008 /IF/IAY/88442 — Construction of IAY House -IAY REG. NO. MP-13-008-072-001/183 | Approved | 27000 | 0 | 2015-10-16
SHIWAPURWA 601 | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713008 /IF/IAY/88443 — Construction of IAY House -IAY REG. NO. MP-13-008-072-001/184 | Approved | 27000 | 0 | 2015-10-16
LOHI | 2007-2008 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1713008/RC/01 — तालाब निर्माण | Completed | 0 | 0 | 2007-07-05 | 2011-11-11
BHITWA | 2007-2008 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1713008/RC/2007 — भिटवा तालाब से जेरूका नाला मार्ग का उन्नयन कार्य लम्बाई 700 मीटर | Completed | 592000 | 31946 | 2007-12-17 | 2011-08-13
BAHURI BANDH | 2007-2008 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1713008/RC/2008 — करहिया-अमवा-बहुरीबांध मार्ग का उन्‍नयन 11.20 किमी. | Completed | 6303000 | 32066 | 2008-03-10 | 2013-08-12
BAMHANGAWAN | 2007-2008 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1713008/RC/2010 — बम्हनगवां-डिहिया-ओडकी-पोडोखर-बांसी-बेल्हा-खैरा मार्ग का उन्नयन कार्य | Completed | 5970000 | 3228166 | 2008-03-04 | 2014-04-09
JIULA | 2007-2008 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1713008/RC/2016 — जिवला खाम्‍हा मार्ग के 1.30 किमी. लम्‍बाई में ग्रेवल निर्माण का कार्य विकासखंड-रीवा | Completed | 1225000 | 849922 | 2008-01-15 | 2014-04-22
HARADEE | 2007-2008 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1713008/RC/2017 — सावहर्दी रहट दादर मार्ग का उन्‍नयन कार्य लंम्‍बाई 12.02 किलोमीटर पहुच मार्ग विकाशखण्‍ड रीवा | Completed | 5754000 | 2083724 | 2008-02-04 | 2014-09-22
HARDISANKAR | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1713008/RC/2020 — गोविन्‍द्रगढ तालाव के हर्दी माइनर नहर के किनारे सडक निर्माण कार्य चैन क्र 0से 80 तक विकास खं0 रीवा | Completed | 455200 | 1134932.56 | 2008-05-03 | 2011-06-30
BANSA | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1713008/RC/2021 — गोविन्‍दगढ तालाब मुख्‍य नहर के किनारे सर्विस रोड निर्माण चेन क्रमांक 0 से 72 त‍क | Completed | 454400 | 945306 | 2008-06-05 | 2011-07-02
UMARI | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1713008/RC/2023 — रीठी से नौढिया मार्ग उन्‍नयन कार्य लम्‍बाई 2 कि0मी0 ग्राम पंचायत उमरी विकासखण्‍ड रीवा | Completed | 988000 | 550310 | 2009-08-24 | 2014-09-22
RITHI | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1713008/RC/2028 — ग्रेवल सडक निर्माण कार्य रीठी से सिरखिनी ग्राम पंचायत रीठी विकासखण्‍ड रीवा | Completed | 3191000 | 1665733 | 2010-02-01 | 2014-09-22
MADAWA | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1713008/RC/2030 — गो0 तालाबके हर्दीमा0मे नहर के किनारे मिटटी मु0 मुख्‍यरोड निर्माण चैन 61 से 110 तक जलउप0 संस्‍था गो0 | Completed | 1316000 | 1170752 | 2010-04-01 | 2011-06-22
MADAWA | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1713008/RC/2035 — गो0 मुख्‍यनहर के किनारे मिटटीमुरमीकरण रोडनिर्माण्‍ाकार्य चैन 81से153जलउपभोक्‍ता संस्‍था गोविन्‍दगढ | Completed | 1704000 | 1632370 | 2010-03-01 | 2011-05-19
HARDISANKAR | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1713008/RC/2037 — गो0 तालाब के हर्दी माइनर नहर के किनारे मिटटी मु0 मुख्‍य रोड निर्माणकार्य चैनक्र. 0 से50 तक जलउप0 गो0 | Completed | 1316000 | 859341 | 2010-03-01 | 2011-06-29
SILPARA | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1713008/RC/2050 — पी सी सी मार्ग निर्माण आंगनवाडी भवन से हीरासिंह के घर तक ल0 270 मी0 ग्राम पं0 सिलपरा वि0ख0 रीवा | Completed | 507000 | 120866 | 2008-08-25 | 2013-03-27
MAHASANW | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1713008/RC/2052 — ग्रेवल मार्ग निर्माण कार्य सगरवाहन टोला महसांव से बाबा तालाब त‍कग्राम पंचायत महसांव वि0ख0 रीवा | Completed | 360000 | 137727 | 2009-06-25 | 2014-04-21
AJGARAHA | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1713008/RC/2053 — जी एस बी मार्ग अजगरहा से वडहा बगीचा रोड से यादव वस्‍ती ग्रा0पं0 हरिहरपुर वि0ख0 रीवा | Completed | 1253000 | 565384 | 2009-05-15 | 2012-08-16
MAIDANI | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713008/RC/22012034625057 — pcc road nirmaan godhar railway stastion se duari road | Ongoing | 12766000 | 12715081.5 | 2023-02-03
MAIDANI | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713008/RC/22012034625168 — pcc road nirmaan maidani shivaji nagar marg se duari road | Ongoing | 13486000 | 13463093.5 | 2023-02-03
MAIDANI | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713008/RC/22012034627541 — PCC Road from Rani bhuniya Devi Mandir Ke Pass Sen Basti Me Shivji nagar Mukh Marg me | Ongoing | 648000 | 545403 | 2023-02-01
MAIDANI | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713008/RC/22012034627543 — PCC Road from Gas Godown Ke Samne Se Ghirma Nala ki Aur | Ongoing | 955000 | 877235 | 2023-03-12
SILPARA | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Repair & maint of Cement Concrete Roads for Comm / Repair and maintenance of Cement Concrete Roads for Community | Repair & maint of Road | 1713008/RC/22012034627667 — PCC Road from Ramratan Patwari ke GHar ke Pas se Yadav Basti Pahunch Marg | Ongoing | 360000 | 296808 | 2023-03-02
SILPARA | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Repair & maint of Cement Concrete Roads for Comm / Repair and maintenance of Cement Concrete Roads for Community | Repair & maint of Road | 1713008/RC/22012034627668 — PCC Road from chaubeyan tola pahunch marg | Closed | 401000 | 0 | 2022-04-24
KHAUR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713008/RC/22012034630081 — pcc sadak gaddi main road se jagannath ke ghar ke pas | Ongoing | 3658000 | 3585654 | 2023-05-05
KHAUR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713008/RC/22012034630120 — PCC SADAK NIRMAAN LAXMANPUR NAHAR KE SEEMA SE MAINAR NAHAR KE BAGAL SE DAGAR ROAD TAK | Ongoing | 3278000 | 2253416 | 2023-05-05
JORI | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713008/RC/22012034630123 — PCC SADAK NIRMAN OR RCC NALI NIRMAN LOHI JORI SEEMA SE KHAUR BHARARI TALAB SE BAGAL | Ongoing | 7384000 | 7350028.65 | 2023-06-09
LAXAMANPUR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713008/RC/22012034630135 — PCC SADAK LAXMAN NIRMAN NIRMANADHEEN PULIYA SE JOKIHA DURG MANDIR KI OR | Ongoing | 6313000 | 5424833.52 | 2023-06-20
MAIDANI | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713008/RC/22012034630147 — PCC SADAK OR NALI NIRMAA TURKAHA BANSAL ME 600 METER | Ongoing | 5359000 | 4871723.3 | 2023-06-16
KARAHIYA NO.1 | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713008/RC/22012034630151 — PCC SADAK NIRMAN NAHAR KE SAMNE SE SACHHA NAGAR KI OR HOUSING BOARD COLONY KE PAS 400 METER | Ongoing | 2176000 | 2166852.28 | 2023-06-05
JOKIHA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713008/RC/22012034641725 — pcc sadak laxman pur nirmandheen puliya se jokiha mandir ki or | Closed | 6313000 | 0 | 2023-04-14
MAIDANI | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713008/RC/22012034667104 — Gram Maidanime indian gas godown ke samne pcc sadak nirmaan | Ongoing | 188000 | 160085 | 2023-10-07
AMAWA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1713008/RC/22012034832903 — Cons of Gravel road Amawa Nahar to shashikaladhar Agnihotri ke khet ki taraf jp Rewa | Approved | 391000 | 0 | 2024-09-01
AMAWA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1713008/RC/22012034833505 — Cons of Gravel road Amawa Nahar to shashi kaladhar Agnihotri ke khet ki taraf jp Rewa | Ongoing | 391000 | 86467.03 | 2025-02-28
BIHRA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1713008/RC/22012034833705 — Cons of Gravel road Rewa main road kullu to bihra aproch road GP Bihra jp Rewa | Ongoing | 470000 | 0 | 2025-05-27
KULLU | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1713008/RC/22012034833711 — Cons of Gravel road main road to Indrabhan Shukla ke Ghar tak gp kullu jp rewa | Approved | 462000 | 0 | 2024-09-01
BAHURI BANDH | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1713008/RC/22012034834133 — Cons Sudor Sadak Semeriya main road to jagrati international school approach road tak | Ongoing | 525000 | 3888 | 2025-03-07
MAIDANI | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1713008/RC/22012034835147 — GP bidawa JP rewa me semariya antargat gravel sadak nirmaan kary bidawa kemar judmaniya tak | Ongoing | 800000 | 1215 | 2025-03-09
PAIPAKHARA-385 | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1713008/RC/22012034835149 — GP Paipakahara JP rewa me gravel sadak nirmaan bankuniya main road paipakhara se chipta ki or | Ongoing | 962000 | 202025.36 | 2025-02-27
KARAHIYA NO.1 | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713008/RC/22012034835150 — GP Karahiya JP rewa me PCC road gas godoam ke samne se ghirma nala ki choor tak | Ongoing | 785000 | 674767.52 | 2025-02-11
SAHIJANAHA N.1 | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1713008/RC/22012034841082 — Cons of Gravel road gram pateri Manmashi Hanumaan temple ke aage se nahar ke gate tak | Ongoing | 661000 | 296791.48 | 2025-04-26
SAHIJANAHA N.1 | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1713008/RC/22012034841087 — Cons of Gravel road gram pateri Manmashi Hanumaan temple se Teekar ki or | Ongoing | 661000 | 29253.6 | 2025-05-21
SAHIJANAHA N.1 | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1713008/RC/22012034841088 — Cons of Gravel road gram pateri Nahar road to Harijan Basti tak | Approved | 399000 | 0 | 2024-11-15
BAHURI BANDH | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1713008/RC/22012034843793 — Gravel sadak nirmaan khadda mod se dhari tak nahar me | Approved | 1295000 | 0 | 2025-04-02
SANW | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1713008/RC/22012034843862 — Gravel sadak nirmaan khadda mod se dhani ki or nahar ke uppar se | New | 0 | 0 | 2025-04-02
LOHI | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1713008/RC/78 — जीएसबी मार्ग निर्माण एनएच 75 आटा चक्‍की से दुर्गा प्रसाद दुबे के घर तक TS 78 | Completed | 628000 | 517146 | 2011-10-31 | 2016-09-07
SUMEDA | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1713008/WC/01 — रपटा निर्माण सुमेदा | Completed | 530000 | 421610 | 2009-12-14 | 2011-06-29
BARA | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1713008/WC/02 — रपटा निर्माण बरा बनकुइया टि एस1054 | Completed | 793000 | 491123 | 2009-12-24 | 2009-02-26
HARDISANKAR | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1713008/WC/03 — स्‍टाप डैम निर्माण भमरा नाला | Completed | 1965000 | 1883706 | 2009-06-18 | 2010-09-10
MAGURAHAI | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1713008/WC/04 — स्‍टाप डैम निर्माण डोभा मगुरिहाई | Completed | 1943000 | 1771505 | 2009-06-14 | 2010-09-10
CHHIJABAR | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1713008/WC/05 — रप्‍टा कम स्‍टाप डैम छिजवार | Completed | 611000 | 611991 | 2009-11-08 | 2012-04-02
HARDISANKAR | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Stone Bund / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1713008/WC/123 — स्टाप डैम निर्माण हर्दी ग्राम पंचायत हर्दीशंकर वि.खं. रीवा | Deleted | 400000 | 454432 | 2008-01-16
AMAWA | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1713008/WC/124 — स्टाप डैम निर्माण जयंती कुंज वन नर्सरी रीवा | Completed | 303000 | 350853 | 2008-02-02 | 2011-08-15
BANSI | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1713008/WC/128 — रिमारी स्‍टाप डैम विकासखंड रीवा | Completed | 1842000 | 1771537 | 2008-01-12 | 2008-01-12
DUARI | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1713008/WC/179 — दुआरी स्‍टापडैम निर्माण कार्य ग्राम पंचायत दुआरी विकासखण्‍ड रीवा | Completed | 1784000 | 1729537 | 2009-05-28 | 2008-08-15
TIGHARA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Stop Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1713008/WC/225 — घाट निर्माण धिरमा नाला ग्राम पंचायत तिघरा रीवा | Completed | 1991000 | 357798 | 2010-04-09 | 2019-04-01
TIGHARA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Stop Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1713008/WC/226 — रपटा कम सटाप डैम निर्माण कार्य धिरमानाला ग्रा0पं0 | Completed | 1923000 | 1582338.5 | 2010-04-09 | 2019-06-28
TIGHARA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Stop Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1713008/WC/227 — घाट निर्माण धिरमा नाला ग्राम पंचायत तिघरा वि0ख0 रीवा (sub. divi.semariya) | Completed | 1991000 | 354092 | 2010-04-09 | 2013-11-08
SANW | 2007-2008 | D--RURAL INFRASTUCTURE / Renovation of traditional water bodies | Strengthening of Embankment / Construction of Embankment for community | Renovation of traditional water bodies | 1713008/WH/188 — तालाब उन्‍नयन एवं विस्‍तरीकरण कार्य महाकाल ग्राम विकास समहित समूह सांव जनपद पंचायत रीवा | Deleted | 294000 | 0 | 2007-05-01
BANSI | 2007-2008 | D--RURAL INFRASTUCTURE / Renovation of traditional water bodies | Strengthening of Embankment / Construction of Embankment for community | Renovation of traditional water bodies | 1713008/WH/189 — कैमरी तालब गहरीकरण कार्य जलसम्‍बर्धन समहित समूह ग्राम पंचायत बांसी जन0पंचायत रीवा | Deleted | 185000 | 0 | 2007-05-01
RAUSAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Raising of Nursery for Community / Raising of Nursery for Community | Nursery Development | 1713/DP/22012034520644 — Nursery at Rausarbaag | Ongoing | 5222000 | 796900.34 | 2021-12-30
RAUSAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Raising of Nursery for Community / Raising of Nursery for Community | Nursery Development | 1713/DP/22012034539085 — Construction of Nursery at Rausar baag | Closed | 5222000 | 0 | 2021-08-15
SILPARA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713 /IF/IAY/67475 — Construction of IAY House -IAY REG. NO. MP-13-008-050-002/15 | Approved | 27000 | 0 | 2015-12-03
JOKIHA | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Bitumen Top / Construction of Bitumen Top Roads for Community | Construction of Road and Culvert | 1713/RC/2069 — जी0एस0बी0 रोड निर्माण कार्य गुढ रोड से जोकिहा जनपद पंचायत रीवा | Completed | 1747000 | 2008791 | 2010-12-23 | 2016-09-07
JOKIHA | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Bitumen Top / Construction of Bitumen Top Roads for Community | Construction of Road and Culvert | 1713/RC/2070 — जी0एस0बी0 रोड निर्माण कार्य गड्रडी रोड से भुसुडी जनपद पंचायत रीवा | Completed | 1574000 | 2180848 | 2010-12-20 | 2013-03-31
DUBI | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Bitumen Top / Construction of Bitumen Top Roads for Community | Construction of Road and Culvert | 1713/RC/2074 — G.S.B. रोड निर्माण कार्य दुबी से गढवा 149 जनपद पंचायत रीवा | Completed | 2256000 | 2726566 | 2010-10-27 | 2013-03-31
SAHIJANA N.2 | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Bitumen Top / Construction of Bitumen Top Roads for Community | Construction of Road and Culvert | 1713/RC/2084 — G.S.B. रोड निर्माण कार्य टी 04 से सटिहा पहुच मार्ग ग्राम पंचा0 सहिजना 02 वि0 ख0 रीवा | Completed | 2506000 | 1625157 | 2010-10-27 | 2014-05-18
AMIRATI | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Bitumen Top / Construction of Bitumen Top Roads for Community | Construction of Road and Culvert | 1713/RC/2085 — G.S.B. रोड निर्माण कार्य पाती रोड से धाधी तक पहुच मार्ग ग्राम पंचा0 अमिरिती वि0 ख0 रीवा | Completed | 3166000 | 2895482 | 2011-01-23 | 2014-05-18
DUBI | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Bitumen Top / Construction of Bitumen Top Roads for Community | Construction of Road and Culvert | 1713/RC/2086 — G.S.B. रोड निर्माण कार्य दूबी से महिया पहुच मार्ग ग्राम पंचा0 दूबी वि0 ख0 रीवा | Completed | 2694000 | 1260215 | 2011-01-11 | 2016-09-07
KOSTA | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Bitumen Top / Construction of Bitumen Top Roads for Community | Construction of Road and Culvert | 1713/RC/2087 — G.S.B. रोड निर्माण कार्य N.H .7 से विल्‍हा 451 तक पहुच मार्ग ग्राम पंचा कोष्‍ठा वि0 ख0 रीवा | Completed | 7436000 | 2777641 | 2010-11-22 | 2016-09-07
DIHIYA | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Bitumen Top / Construction of Bitumen Top Roads for Community | Construction of Road and Culvert | 1713/RC/2115 — जी एस बी रोड निमार्ण कार्य डिहिया रोड से खिरामा वि खं रीवा | Completed | 1439000 | 840867 | 2011-03-08 | 2013-07-12
TIGHARA | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Bitumen Top / Construction of Bitumen Top Roads for Community | Construction of Road and Culvert | 1713/RC/2122 — ग्रेवल रोड निर्माण कार्य मार्ग जोन्‍ही से भोलगढ लं0 3 कि0 मी0 ग्राम पंचा0 तिघरा वि खं0 रीवा | Completed | 3167000 | 1956374 | 2011-05-30 | 2014-09-22
MAGURAHAI | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Bitumen Top / Construction of Bitumen Top Roads for Community | Construction of Road and Culvert | 1713/RC/2123 — ग्रेवल रोड निर्माण कार्य मिगुरहाई से देवरा लं0 3 कि0 मी0 ग्राम पंचा0 मगुरहाई वि0 खं0 रीवा | Completed | 3167000 | 1014015 | 2011-05-30 | 2014-09-22
GAHIRA | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Bitumen Top / Construction of Bitumen Top Roads for Community | Construction of Road and Culvert | 1713/RC/2125 — ग्रेवल रोड निर्माण कार्य पहाड से गहिरा मार्ग का निर्माण वि0 खं0 रीवा | Completed | 2790000 | 2466049 | 2011-07-18 | 2013-05-13
TEEKAR | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1713/RC/2130 — प्रथम स्‍तरीय ग्रेवल सडक निर्माण टीकर मुख्‍य मार्ग | Completed | 1014000 | 1213606 | 2011-07-01 | 2014-05-18
SAHIJANAHA N.1 | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713/RC/22012034551570 — Construction of sudoor gram sampark sadak gaddi kerha koniya marg | Closed | 0 | 0 | 2020-04-20
LAPTA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713/RC/22012034552041 — Sudoor gram sampark sadak LAPTA PULIYA KE AGE SE NAGESH KE GHAR SE MOHNI PMGAY ROAD TAK | Ongoing | 3882000 | 3554025.41 | 2021-06-04
BAMHAURI | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713/RC/22012034552538 — shudoor sadak nirmaan mohni band sagar se chipta dhabiya baya barah gau tak | Completed | 3270000 | 2805096 | 2021-05-20 | 2024-01-09
RAHAT | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1713/RC/22012034552556 — shidoor sadak nirmaan rahat pamgsay se bara mukhay marge | Deleted | 4490000 | 0 | 2020-11-02
SHIWAPURWA 601 | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1713/RC/22012034552705 — Sudoor Gram sampark sadak Shivpurwa Chauki se Teekar Bia Kalara | Completed | 5982000 | 5176107.38 | 2021-05-07 | 2026-05-22
UMARI | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1713/RC/22012034552714 — Sudoor gram sampark sadak rithi bus stand se sigti tak | Completed | 3014000 | 2920419.45 | 2021-02-08 | 2023-11-29
KHAMHA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1713/RC/22012034552844 — Sdoor gram sampark sadak nh 75 se pandey tola | Completed | 1635000 | 1440239.68 | 2021-04-15 | 2026-02-11
SAHIJANAHA N.1 | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1713/RC/22012034552856 — Sudoor gram sampark sadak gaddi kerha koniya marge | Closed | 9340000 | 0 | 2020-10-02
BAHURI BANDH | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713/RC/22012034552866 — Sudoor gram sampark sadak nirmaan bahuribandh pmgsy sadak se madaha badariya road | Ongoing | 3501000 | 3020627 | 2021-06-13
PAIPAKHARA-385 | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1713/RC/22012034553008 — Sudoor gram sampark sadak BANKUIYA MUKHAY MARGE SE MANTOLWA386 TAK | Ongoing | 4745000 | 4399891.4 | 2022-05-13
KULLU | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1713/RC/22012034553536 — sudoor sadak nirmaan bankuiya mukhay marge kuiya gaow tak | Completed | 4279000 | 2786981 | 2022-02-17 | 2026-05-29
DADAR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1713/RC/22012034553542 — sudoor sadak pathargadhi devi mandir se bajraha barwah tak | Ongoing | 6501000 | 4099017.89 | 2021-05-07
SAKARWAT | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1713/RC/22012034553547 — sudoor sadak nirman dadar bankuiya marge se sakrwat tak | Ongoing | 5660000 | 4235500 | 2022-10-21
SAHIJANA N.2 | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713/RC/22012034557307 — sudoor gram sampark sadak gaddi keraha koniya marg | Ongoing | 9340000 | 8532553.75 | 2021-01-21
KANAUJA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Repair & maint of Gravel Road Roads for Comm / Repair and maintenance of Gravel Road Roads for Community | Repair & maint of Road | 1713/RC/22012034609248 — Periodical maintenance of cmgsy road kanauja to thaukar | Completed | 264000 | 198260.68 | 2022-03-19 | 2026-05-29
SAHIJANAHA N.1 | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Repair & maint of Gravel Road Roads for Comm / Repair and maintenance of Gravel Road Roads for Community | Repair & maint of Road | 1713/RC/22012034609346 — Periodic maintenance of cmgsy road shaijjana no1 to pateri 344 | Closed | 317000 | 0 | 2021-10-15
PANTI | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Repair & maint of Gravel Road Roads for Comm / Repair and maintenance of Gravel Road Roads for Community | Repair & maint of Road | 1713/RC/22012034609356 — Periodic maintainance for CMGSY Road panti to Dhadhi | Completed | 950000 | 708908 | 2022-03-19 | 2026-05-28
DUBI | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713/RC/22012034609795 — Periodic maintenance of CMGSY Road Dubi to Gadhwa | Deleted | 871000 | 0 | 2021-09-15
DUBI | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Repair & maint of Gravel Road Roads for Comm / Repair and maintenance of Gravel Road Roads for Community | Repair & maint of Road | 1713/RC/22012034609796 — Periodic maintenance of CMGSY Road Dubi to Gadhwa | Closed | 871000 | 0 | 2022-04-07
RAHAT | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713/RC/22012034615536 — Sudur sadak nirmaan rahat PMGSY SE Bara mukh marg tak | Closed | 4490000 | 0 | 2022-04-01
KHAUR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713/RC/22012034626771 — pcc bhardi talab se basti ki or 300 meter sodhiya | Completed | 755000 | 701120 | 2023-05-05 | 2026-05-26
KHAUR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713/RC/22012034626772 — pcc bhardi talab se se sodhiya basti me 300 m se 600 m | Completed | 755000 | 698574 | 2023-05-05 | 2026-05-26
KHAUR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713/RC/22012034626773 — pcc bhardi talab se basti ki or sankar shodhiya ke ghar ki or | Completed | 755000 | 675590 | 2023-05-05 | 2026-05-26
RAUSAR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713/RC/22012034626774 — pcc mukhay marge se gulabi basti ki or | Physically Completed | 998000 | 984095 | 2023-06-17 | 2026-06-29
RAUSAR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713/RC/22012034626775 — pcc gulabi basti me | Physically Completed | 998000 | 991744 | 2023-10-09 | 2026-06-29
MADAWA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713/RC/22012034641488 — PCC Sadak nirmaanmadwa mukhnahar se ward no 1 chaubey basti ki aur | Completed | 1054000 | 1049236 | 2023-09-12 | 2024-06-12
RAHAT | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1713/RC/22012034646011 — sudoor Sadak nirmaan rahat PMGSY sadak se bara mukh marg tak | Closed | 0 | 0 | 2023-04-15
CHHIREHATA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713/RC/22012034653990 — Gravek sadak Chhirehheta bichiya nala Pcc road se khushwaha basti tak 1.5 KM | Ongoing | 720000 | 719620 | 2023-09-21
GAHIRA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1713/RC/22012034660385 — Gravel Sadak nirmaan tikar mukh marg se gahira mukh marg tak bakshi tola | Completed | 390000 | 362183 | 2023-10-05 | 2026-05-26
SILPARA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713/RC/22012034673145 — PCC Sadak moliya harijan adiwashi basti | Completed | 370000 | 344393 | 2024-02-13 | 2024-07-24
SILPARA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713/RC/22012034673263 — PCC Choubey Tola Pahunch Marg | Closed | 0 | 0 | 2023-04-20
SILPARA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Repair & maint of Cement Concrete Roads for Comm / Repair and maintenance of Cement Concrete Roads for Community | Repair & maint of Road | 1713/RC/22012034673264 — PCC Choubey Tola Pahunch Marg | Completed | 401000 | 390675 | 2024-02-13 | 2024-07-24
SILPARA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Repair & maint of Cement Concrete Roads for Comm / Repair and maintenance of Cement Concrete Roads for Community | Repair & maint of Road | 1713/RC/22012034673265 — PCC Kamta Khushwaha ke ghar ke pass | Completed | 227000 | 213189 | 2024-02-13 | 2024-07-24
KARAHIYA NO.1 | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713/RC/22012034831870 — PCC Road Nirman Gas godam ke samne wale road se Dhirma Nala ke Chhore tak Karahiya 1 Rewa | Ongoing | 785000 | 0 | 2025-01-11
BAHURI BANDH | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1713/RC/22012034832706 — Cons Sudor Sadak Semeriya main road to jagrati international school approach road tak | Approved | 525000 | 0 | 2024-05-01
MAIDANI | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1713/RC/22012034833305 — Gravel road nirmaan bidawa kemar judmaniya tak Rewa | Approved | 814000 | 0 | 2024-08-16
PAIPAKHARA-385 | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1713/RC/22012034833307 — Gravel road nirmaan bankuia main road paipakhra to chipta tak Rewa | Approved | 962000 | 0 | 2024-08-16
SANW | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1713/RC/22012034833312 — Gravel road nirmaan khadda mode to dhari tak in nahar | Approved | 1295000 | 0 | 2024-08-16
SANW | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1713/RC/22012034833380 — Gravel road nirmaan khadda mode to dhari tak nahar me | Approved | 1295000 | 0 | 2024-08-16
JERUKA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713/RC/22012034837716 — PCC sadak nirman kary bankuiya main road se harijan basti tak GP Jeruka JP Rewa | Approved | 220000 | 0 | 2024-10-07
KULLU | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1713/RC/22012034837725 — Gravel road nirman karya Kachoor Road se kullu sachiddanand dwivedi ke ghar tak GP kullu | Approved | 462000 | 0 | 2024-10-07
JERUKA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713/RC/22012034837799 — const of pcc road bankuiya main road se harijan basti gp jeruka | Approved | 123000 | 0 | 2024-05-01
SILPARA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1713/RC/22012034837859 — Cons of Gravel road Rajmani patel ke ghar se mandir tak Patelan chaube basti gp silpara jp Rewa | Approved | 200000 | 0 | 2024-09-15
SAHIJANA N.2 | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1713/WC/22012035311056 — JGSA अमृत सरोवर निर्माण कार्य फूलमती मंदिर के पास गड्डी | Closed | 3799000 | 235.5 | 2025-05-28
SAHIJANA N.2 | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1713/WC/228 — स्‍टाप डैम निर्माण कार्य सहिजना खसरा नं 624 ग्राम पचा0 सहिजना न 2 जनपद पंचा0 रीवा | Completed | 445000 | 444966 | 2011-11-07 | 2014-05-18
SHIWAPURWA 603 | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1713/WC/229 — स्‍टाप डैम निर्माण कार्य शिवपूर्वा 603 खसरा नं 1091 ग्राम पंचा शिवपूर्वा जनपद पंचा0 रीवा | Completed | 445000 | 340765 | 2011-12-13 | 2014-06-25
SAHIJANA N.2 | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1713/WC/230 — स्‍टाप डैम निर्माण कार्य गडडी खसरा नं 626 -366 ग्राम पंचा0 सहिजना नं 2 जनपद पंचा0 रीवा | Completed | 226000 | 224969 | 2011-12-15 | 2014-05-18
SAHIJANA N.2 | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1713/WC/231 — स्‍टाप डैम निर्माण कार्य गडडी खसरा नं 640 ग्राम पंचा0 सहिजना नं 2 जनपद पंचा0 रीवा | Completed | 231000 | 230650 | 2011-11-17 | 2014-05-18
SAHIJANA N.2 | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Stone Bund / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1713/WC/232 — बोल्‍डर बन्‍धान कार्य सहिजना खसरा नं 624 ग्राम पंचा सहिजना वि खं रीवा | Completed | 9000 | 4728 | 2011-11-28 | 2014-05-18
TEEKAR | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Stone Bund / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1713/WC/233 — बोल्‍डर बन्‍धान कार्य टीकर खसरा नं 3758 ग्राम पंचा टीकर वि खं रीवा | Completed | 71000 | 70920 | 2011-11-24 | 2014-05-18
TEEKAR | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Stone Bund / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1713/WC/234 — बोल्‍डर बन्‍धान कार्य टीकर खसरा नं 2230 ग्राम पंचा टीकर वि खं रीवा | Completed | 48000 | 49980 | 2011-11-10 | 2014-05-18
TEEKAR | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Stone Bund / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1713/WC/235 — बोल्‍डर बन्‍धान कार्य टीकर खसरा नं 2229 ग्राम पंचा टीकर वि खं रीवा | Completed | 21000 | 20910 | 2011-11-10 | 2014-05-18
TEEKAR | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Stone Bund / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1713/WC/236 — बोल्‍डर बन्‍धान कार्य टीकर खसरा नं 1778 ग्राम पंचा टीकर वि खं रीवा | Completed | 36000 | 35734 | 2011-11-10 | 2014-05-18
TEEKAR | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Stone Bund / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1713/WC/237 — बोल्‍डर बन्‍धान कार्य टीकर खसरा नं 1813 ग्राम पंचा टीकर वि खं रीवा | Completed | 36000 | 35849 | 2011-11-10 | 2014-05-18
SHIWAPURWA 601 | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Loose Boulder Structure / Construction of Stone boulder Gully Plugs for Community | Boulder Check/Gully Plug | 1713/WC/238 — परकुलेशन पिट निर्माण कार्य शिवपूर्वा 601 खसरा नं 516 ग्राम पंचायत शिवपूर्वा वि खं रीवा | Completed | 123000 | 68250 | 2011-11-11 | 2014-05-18
SHIWAPURWA 601 | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Loose Boulder Structure / Construction of Stone boulder Gully Plugs for Community | Boulder Check/Gully Plug | 1713/WC/239 — परकुलेशन पिट निर्माण कार्य शिवपूर्वा 601 खसरा नं 479 प्रथम ग्राम पंचायत शिवपूर्वा वि खं रीवा | Completed | 132000 | 76088 | 2011-11-11 | 2014-05-18
SHIWAPURWA 601 | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Loose Boulder Structure / Construction of Stone boulder Gully Plugs for Community | Boulder Check/Gully Plug | 1713/WC/240 — परकुलेशन पिट निर्माण कार्य शिवपूर्वा 601 खसरा नं 479 द्वितीय ग्राम पंचायत शिवपूर्वा वि खं रीवा | Completed | 144000 | 123675 | 2011-12-06 | 2014-05-18
SHIWAPURWA 601 | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Stone Bund / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1713/WC/241 — बोल्‍डर बन्‍धान कार्य शिवपूर्वा 601 खसरा नं 436 ग्राम पंचा शिवपूर्वा वि खं रीवा | Completed | 12000 | 11004 | 2011-11-11 | 2014-05-18
SHIWAPURWA 601 | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Stone Bund / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1713/WC/242 — बोल्‍डर बन्‍धान कार्य शिवपूर्वा 601 खसरा नं 444 ग्राम पंचा शिवपूर्वा वि खं रीवा | Completed | 9000 | 9090 | 2011-11-11 | 2014-05-18
SHIWAPURWA 601 | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1713/WC/248 — स्‍टाप डैम निर्माण कार्य शिवपुर्वा 601 खसरा नं 1180 विकाश खंण्‍ड रीवा | Completed | 445000 | 409947 | 2012-02-17 | 2014-05-18
SHIWAPURWA 603 | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1713/WC/249 — स्‍टाप डैम निर्माण कार्य शिवपुर्वा 602 खसरा नं 37 विकाश खंण्‍ड रीवा | Completed | 345000 | 344910 | 2012-06-14 | 2014-06-25
TEEKAR | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1713/WC/250 — कंटूर बंडिग टीकर खसरा नं 3730 जनपद पंचा0 रीवा | Deleted | 54000 | 0 | 2012-02-20
LAPTA | 2013-2014 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | AWC / Construction of Anganwadi Building for Community | Constr of Aganwadi | /AV/1948 — Anganwadi Sewa Kendra,REWA | Deleted | 780000 | 0 | 2013-04-14