AMAHARA | 2006-2007 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1715008/WC/6 — तालाब निर्माण बुचवाटोला अमहरा | Completed | 0 | 0 | 2006-05-16 | 2008-08-08
JAMGADI | 2006-2007 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1715008/WC/60 — C.P.T. Niman Kary Piparadol Jamgadi | Completed | 0 | 0 | 2006-09-13 | 2009-04-11
SIGAHI | 2006-2007 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Mini Percolation tank / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1715008/WC/61 — Talab Nerman Padkude Sengahe | Completed | 0 | 9600 | 2006-05-29 | 2007-06-01
MAJHAULI | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1715008/WC/62 — Talab Nirman Bhasmadaad Maghauli | Completed | 0 | 13600 | 2008-04-01 | 2016-08-08
DHARI | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1715008/WC/63 — Talab Nirman Viyraan Tola Mithool | Completed | 0 | 675117.56 | 2009-03-02 | 2012-06-04
LANGHADOL | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1715008/WC/65 — तालाब निर्माण जालपानी | Completed | 0 | 153402 | 2009-09-20 | 2009-07-06
SAKHOHA | 2006-2007 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1715008/WC/7 — तालाब निर्माण सखौहां | Completed | 0 | 25000 | 2006-05-28 | 2008-02-02
SIGAHI | 2006-2007 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Mini Percolation tank / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1715008/WC/70 — Talab Nerman Padkude Sengahe | Deleted | 0 | 0 | 2006-04-18
HARRAHAWA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Stop Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1715008/WC/75 — RuptaStop Daim Nirman Thadghatta Nala Per Harrhaw | Completed | 2405000 | 744595.91 | 2009-01-30 | 2016-09-07
TIYARA | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Mini Percolation tank / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1715008/WC/8 — तालाब निर्माण कार्य तियरा | Completed | 0 | 22817.89 | 2008-01-15 | 2016-08-08
BHAOOKHAND | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Stop Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1715008/WC/80 — स्‍टापडैम निर्माण भाउखाड में रामबरन के घर के पास | Completed | 1390000 | 1258140.89 | 2009-10-11 | 2016-09-07
URTI | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Stop Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1715008/WC/85 — उर्ती एकपई नाला पर स्‍टापडैम कम रपटा निर्माण | Completed | 2092000 | 1954652.46 | 2009-11-14 | 2013-01-20
AMILIYA | 2006-2007 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1715008/WC/9 — तालाब निर्माण कमल शाहू के ध्घर के पास अमिलिया | Completed | 0 | 0 | 2006-06-05 | 2016-08-08
PONDIPATH | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1715008/WC/90 — तालाब निर्माण पोडीपाठ हरिराम के घर के पास | Completed | 0 | 258106 | 2009-12-25 | 2016-08-22
PONDIPATH | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1715008/WC/91 — तालाब निर्माण जैपाल सिंह गोड के घर के पास | Completed | 0 | 12558 | 2010-01-18 | 2016-08-22
PONDIPATH | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1715008/WC/92 — नवीन तालाब निर्माण बुदुलपति के घर के पास पोडीपाठ | Completed | 0 | 103090 | 2010-01-25 | 2016-08-22
BINDOOL | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1715008/WC/93 — नवीन तालाब निर्माण बिन्‍दूल दलदली नाला के पास | Completed | 0 | 300286.7 | 2009-12-22 | 2016-08-23
DHOTITOLA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Mini Percolation Tank / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1715008/WC/94 — पाला गडई निस्‍तारी तालाब ढोढीटोला | Completed | 0 | 2027798.45 | 2010-05-16 | 2012-10-10
BINDOOL | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1715008/WC/95 — Talab Nirman Mahesh Prasad Ke Ghar Ke Paas Churipaath | Completed | 0 | 362441.6 | 2009-12-21 | 2016-08-23
DHANGARH | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1715008/WC/96 — Talab Niraman Surajdeen Ke ghar ke Pass Dhangdar | Completed | 0 | 235053 | 2010-02-03 | 2016-08-29
JEER | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1715008/WC/97 — talab nirman shamylal ke home ke pas jeer | Completed | 0 | 85200 | 2010-01-02 | 2016-08-31
BHAISABOODA | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Mini Percolation Tank / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1715008/WC/98 — Nistari Talab Nirman Raudagadai Bhaisabuda | Completed | 0 | 2039524 | 2010-01-01 | 2013-06-10
LANGHADOL | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Gabions / Construction of Gabion Check Dam for Individuals | Constr of Gabion | 1715008/WC/99 — Jalpani Nistari Talab Nirman Langhadol | Completed | 0 | 1570668 | 2010-01-01 | 2013-07-10
BHADAILI | 2009-2010 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1715008/WC/9993621589 — talab nirmand baditawar k pass bhadali | Deleted | 0 | 0 | 2009-10-02
CHINGITOLA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Sunken Pond / Construction of Community Water Harvesting Ponds | Farm Pond | 1715008/WC/9993621613 — Jamuniya Nala Nistari Talab | Completed | 1426000 | 72480 | 2010-05-17 | 2011-11-11
JEER | 2010-2011 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1715008/WC/9993621614 — Kachara Nala Nistari Tank Nirman | Completed | 2713000 | 517900 | 2010-05-17 | 2011-11-11
TELDAH | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Feeder Channel / Construction of Feeder Canal for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1715008/WC/9993622263 — Tildah tank me water course, feild channel coloba fixing ka nirman | Deleted | 0 | 0 | 2009-04-01
TELDAH | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Feeder Channel / Construction of Feeder Canal for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1715008/WC/9993622264 — Tildah Tank me water course, field channel coloba fixing ka Nirman | Deleted | 0 | 0 | 2009-04-01
JEER | 2009-2010 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1715008/WC/9993622620 — talab nirmand lachan dhari ke ghar ke pass jeer | Deleted | 0 | 0 | 2009-10-02
JEER | 2009-2010 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1715008/WC/9993622632 — talabnirmad lachandhari ke ghar ke pass jeer | Completed | 34800348 | 46980 | 2010-01-22 | 2012-12-12
BHADAILI | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1715008/WC/9993623772 — talab nirmand baditawar ke pass bhadeli | Deleted | 0 | 0 | 2009-10-02
BANDHA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1715008/WC/9993624511 — Dasharatha Nalla Rapta Cum Stop Dam | Completed | 2255000 | 208620 | 2011-05-14 | 2013-05-10
KHANUANAWATOLA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1715008/WC/9993625707 — khanuya nistari talab(ghoghawa nala) | Completed | 4998000 | 193621 | 2012-06-04 | 2012-06-30
BIHARA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1715008/WC/9993627324 — WUA Bihara 49002 Water Course Field Chanel | Completed | 1666520 | 0 | 2012-06-03 | 2016-08-08
KHUTAR | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1715008/WC/9993627326 — WUA Khutar 49003 water course Field chanel | Completed | 1625320 | 0 | 2012-09-15 | 2016-08-08
LANGHADOL | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Dam / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1715008/WC/9993638962 — Construction of Nistari Tank at Dewnar | Deleted | 0 | 0 | 2013-10-02
LANGHADOL | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Dam / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1715008/WC/9993650341 — Deonar Nistari Talab | Deleted | 3497000 | 0 | 2013-06-12
MAJHAULIPATH | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Stop Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1715008/WC/9993650625 — talab nirman thuthawa dharwa | Deleted | 1768000 | 0 | 2014-01-22
MAJHAULIPATH | 2014-2015 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Mini Percolation tank / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1715008/WC/9993653217 — Talab Nirman Thudhwadhavara Gram Belwar | Completed | 1768000 | 822176.8 | 2014-10-17 | 2015-03-26
GADERIYA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1715008/WH/19952279 — WUA Pipra 49001 | Completed | 1778040 | 55962 | 2012-07-12 | 2015-10-15
RAUHAL | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Excavation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1715008/WH/8 — जल भण्‍डारण पौण्‍ड निर्माण रौहाल | Completed | 0 | 35581 | 2009-11-06 | 2016-08-23
BASODA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Micro Irrigation Works | Lining of minor Canal for Community / Lining of minor Canal for Community | Lining of Canal | 1715/IC/22012034387269 — Resectioning and Linning of main Canal Basauda Tank | Closed | 2400002 | 0 | 2020-06-19
OKHARAWAL | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Bitumen Top / Construction of Bitumen Top Roads for Community | Construction of Road and Culvert | 1715/RC/22012034210786 — Okharawal se Kumhiya Wahya Dhodhi Tola Me Mitti Moorum Ka Karya | Completed | 7785000 | 4903735.82 | 2014-03-06 | 2018-10-17
BHAOOKHAND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1715/RC/22012034612941 — Gram Bhaukand Ke Chameli mod Se Gram Malgo Pahuch Marg Me Nakdrra Nadi Par Pul Nirman | Closed | 3758000 | 0 | 2022-01-04
MALAGO | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1715/RC/22012034613051 — Gram Malgo Hanuman Mandir Se Ram Kailash Pal Ke Ghar Hote Huye Mayar Nadi Danhra Tak Marg Avam CD | Ongoing | 4143000 | 2809830.23 | 2023-06-06
JOGIYANI | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1715/RC/22012034613055 — Gram Panchayat Jogiyani me Shri Satanand Shah ke Ghar hote huye Bhandahwa tola hatka pahuch Marg Nir | Ongoing | 4872000 | 3642910.96 | 2023-02-22
BADGAD | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1715/RC/22012034613056 — Gram Panchayat Badgad Antergat Middile School Se Hote Huye Makraduari Pahuch Marg Nirman Avam CD | Ongoing | 4721000 | 3905307.58 | 2023-01-16
KOYALKHOONTH | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1715/RC/22012034613058 — Gram Panchayat Koyalkunth Antergat Bajar Se Gram Budkud Mayar Nadi Tak Marg Nirman | Closed | 4872000 | 0 | 2022-01-04
CHAURA | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1715/RC/22012034613459 — Gram Bandhaura Chauki Kudiya Nala Chaura Suhira Pahuch Marg Ka Nirman | Closed | 4709000 | 0 | 2022-04-11
RAUHAL | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1715/WC/22012034856186 — CTR - Talab nirman Belgadai Rauhal | Completed | 6708000 | 5302584.96 | 2021-11-15 | 2026-05-21
SITULKHURD | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Brushwood Check Dam for Community / Construction of Brushwood Check Dam for Community | Construction of Check Dam/Stop Dam | 1715/WC/22012034898849 — CTR - Stopdam Nirman Murgi Form Ke Pass Situlkurd | Ongoing | 4702000 | 1356899 | 2022-04-09
GADAHARA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1715/WC/22012034964499 — Kachan Nadi par Gabion cum stone massonary nirman karya GP Gadahara | Deleted | 0 | 0 | 2022-04-01
GADAHARA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1715/WC/22012035217111 — Kachan Nadi par Gabion cum stone massonary nirman karya GP Gadahara | Deleted | 0 | 0 | 2024-04-14
GADAHARA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1715/WC/22012035217113 — Kachan Nadi par Gabion cum stone massonary nirman karya GP Gadahara | Ongoing | 1080000 | 758472.25 | 2024-07-20
GADERIYA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1715/WC/22012035246613 — Gabion cum masonry Structure Kachan Nadi par Gaderiya Part 02 | Ongoing | 260000 | 136764 | 2025-06-03
DIGTHI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1715/WC/22012035255269 — सुदधरीकरण एवं बोल्‍डर पिचिंग एवं गैविनय मेशोनरी स्‍ट्रक्‍चर निर्माण कॉचन नदी पर ग्राम चाेकरा | Ongoing | 400000 | 323598.06 | 2025-04-02
GADERIYA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1715/WC/22012035256787 — Gabion cum massonary structure kachan nadi par gaderiya Part 01 Gaderiya | Closed | 497000 | 0 | 2025-05-27
BADGAD | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Land Development / Levelling/shaping of Wasteland Land for Community | Land Development | 1750/DP/9926688774 — TALAB | Deleted | 0 | 0 | 2009-05-13
JEER | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1750/LD/3799380646 — Mendha Bandhan Pappoo Singh ke Ghar ke pass Jeer | Deleted | 491000 | 0 | 2009-10-02
BIHARA | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1750/RC/22012034151060 — 1715008/RC/69 | Deleted | 0 | 0 | 2010-04-25
BIHARA | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Bitumen Top / Construction of Bitumen Top Roads for Community | Construction of Road and Culvert | 1750/RC/22012034151062 — bihra to dhuskari | Deleted | 0 | 0 | 2010-04-25
BIHARA | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1750/RC/22012034151063 — bihra | Deleted | 3161000 | 0 | 2010-04-25
BIHARA | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1750/RC/22012034151081 — UP GRADETION ROAD | Deleted | 0 | 0 | 2010-04-25
BIHARA | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1750/RC/22012034151082 — BIHRA | Deleted | 0 | 0 | 2010-04-24
BIHARA | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1750/RC/22012034151158 — bihra | Deleted | 0 | 0 | 2010-04-25
BIHARA | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1750/RC/22012034151212 — bihra | Deleted | 0 | 0 | 2010-04-25
BUCHARO | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1750/RC/22012034151223 — road | Deleted | 0 | 0 | 2009-04-25
BIHARA | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1750/RC/22012034151393 — Upgradation from Khutar Bihra to Badma | Deleted | 2596000 | 0 | 2010-04-01
CHINGITOLA | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Desilting / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 8094/wh/3 — Talab Nirman Bhamariya tola chhingitola | Completed | 0 | 0 | 2007-06-05 | 2007-03-31