## Work List
Exported on: 2026-09-06 16:10:27
Filters applied:
Data source: MGNREGA + VBGRAMG
District: UJJAIN
Block: UJJAIN
Panchayat: KANDARIYA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
| 2015-2016 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | AWC / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1718005004/AV/3732 — Aanganbadi/Other Rural Infrastructure,UJJAIN | Completed | 195000 | 195347.66 | 2015-09-28 | 2018-05-01
| 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1718005004/DP/1163 — कण्डारिया निर्मलवाटिका गीताबई अम्बाराम | Completed | 4500 | 2074 | 2011-12-22 | 2011-12-28
| 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1718005004/DP/1164 — कण्डारिया निर्मलवाटिका बलीराम कैशरसिंह | Completed | 4500 | 2074 | 2011-12-22 | 2011-12-28
| 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1718005004/DP/1165 — कण्डारिया निर्मलवाटिका आशराम घीसाजी | Deleted | 0 | 0 | 2010-04-14
| 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1718005004/DP/1166 — कण्डारिया निर्मलवाटिका आशराम घीसाजी= | Completed | 4500 | 2074 | 2011-12-22 | 2011-12-28
| 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1718005004/DP/22012034610215 — vraksha ropan shantidham kandariya | Closed | 427106.07 | 0 | 2023-09-25
| 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1718005004/DP/631 — कण्‍डारिया निर्मलवाटिका मोहन अम्‍बाराम | Completed | 4500 | 6124.2 | 2010-12-22 | 2011-03-20
| 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1718005004/DP/632 — कण्‍डारिया निर्मलवाटिका अमरसिंह बद्रीलाल | Completed | 4500 | 6124.2 | 2010-12-22 | 2011-03-20
| 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1718005004/DP/633 — कण्‍डारिया निर्मलवाटिका अम्‍बाराम भगीरथ | Completed | 4500 | 4942.39 | 2010-12-22 | 2011-03-20
| 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1718005004/DP/634 — कण्‍डारिया निर्मलवाटिका कमलाबाई रणछोड | Completed | 4500 | 6124.2 | 2010-12-22 | 2011-03-20
| 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1718005004/DP/635 — कण्‍डारिया निर्मलवाटिका मानसिंह रणछोड | Completed | 4500 | 6124.2 | 2010-12-22 | 2011-03-20
| 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1718005004/DP/636 — कण्‍डारिया निर्मलवाटिका बालू घीसाजी | Completed | 4500 | 6124.2 | 2010-12-22 | 2011-03-20
| 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1718005004/DP/637 — कण्‍डारिया निर्मलवाटिका सीताबाई जगदीश | Completed | 4500 | 6124.2 | 2010-12-22 | 2011-03-20
| 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1718005004/DP/638 — कण्‍डारिया निर्मलवाटिका राजाराम भागीरथ | Completed | 4500 | 6124.2 | 2010-12-22 | 2011-03-20
| 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1718005004/DP/639 — कण्‍डारिया निर्मलवाटिका जालमसिंह शंकरलाल | Completed | 4500 | 6124.2 | 2010-12-22 | 2011-03-20
| 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1718005004/DP/640 — कण्‍डारिया निर्मलवाटिका प्रभुबाई जगदीश | Completed | 4500 | 6124.2 | 2010-12-22 | 2011-03-20
| 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1718005004/DP/641 — कण्‍डारिया निर्मलवाटिका रामेश्‍वर अम्‍बाराम | Completed | 4500 | 6124.2 | 2010-12-22 | 2011-03-20
| 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1718005004/DP/979 — कण्‍डारिया निर्मलवाटिका मोहनलाल केसरसिंह | Completed | 4500 | 4099 | 2010-12-22 | 2011-12-28
| 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1718005004/DP/980 — कण्‍डारिया निर्मलवाटिका जानीबाई मांगीलाल | Completed | 4500 | 4099 | 2010-12-22 | 2011-12-28
| 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1718005004/DP/981 — कण्‍डारिया निर्मलवाटिका मुन्‍नालाल रामसिंह | Completed | 4500 | 4099 | 2010-12-22 | 2011-12-28
| 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1718005004/DP/982 — कण्‍डारिया निर्मलवाटिका गब्‍बा अम्‍बाराम | Completed | 4500 | 4099 | 2010-12-22 | 2011-12-28
| 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1718005004/DP/983 — कण्‍डारिया निर्मलवाटिका गजराम अम्‍बाराम | Completed | 4500 | 4099 | 2010-12-22 | 2011-12-28
| 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1718005004/IF/22012034340962 — VRAKSHAROPAN KARY PRADHANMANTRI ROAD SE TAKWASA KI OR EVAM SHANTIDHAM PAHUCH MARG | Completed | 335000 | 25944 | 2017-05-22 | 2018-12-26
| 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1718005004/IF/22012034341605 — Vraksha ropan gram kandariya me pradhanmantri rod v panchayat bhavan | Completed | 335000 | 25772 | 2017-05-22 | 2018-12-26
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1718005004/IF/22012035454601 — JGSA-2025 KHET TALAB SITARAM PITA NANDRAM GRAM KANDARIYA | Physically Completed | 147621.16 | 147123.14 | 2025-05-03 | 2026-03-30
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1718005004/IF/22012035516010 — KHET TALAB NIRMAN KARYA SURESH PITA BAHADUR GRAM KANDARIYA MAJRA PARDIKHEDA | Deleted | 0 | 0 | 2025-04-24
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1718005004/IF/22012035516138 — KHET TALAB NIRMAN KARYA SURESH PITA BAHADUR GRAM PANCHAYAT KANDARIYA MAJRA PARDIKHEDA | Deleted | 0 | 0 | 2025-04-24
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1718005004/IF/22012035519384 — KHET TALAB NIRMAN KARYA SURESH PITA BAHADUR GRAM PANCHAYAT KANDARIYA MAJRA PARDIKHEDA | Physically Completed | 147621.16 | 139416.14 | 2025-05-17 | 2026-03-30
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1718005004/IF/22012035623744 — EK BAGIYA MAA KE NAAM LILA BAI SEWARAM AJRANA | Approved | 0 | 0 | 2025-06-14
| 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718005004/IF/9993677542 — IAY(geeta bai/chhoga bai) | Completed | 14310 | 8261 | 2015-10-11 | 2016-11-07
| 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718005004/IF/9993677547 — IAY(chandesna bai/jeetsingh) | Completed | 14310 | 8267 | 2015-10-11 | 2016-11-07
| 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718005004/IF/9993677551 — iay(sandeshbai/rachkiya) | Completed | 14310 | 8261 | 2015-10-14 | 2016-11-07
| 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718005004/IF/IAY/300032 — Construction of IAY House -IAY REG. NO. MP1025635 | Completed | 15030 | 15215 | 2017-02-06 | 2017-10-30
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718005004/IF/IAY/3804032 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115777688 | Completed | 18360 | 18156 | 2022-10-15 | 2023-08-16
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718005004/IF/IAY/3804033 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115777797 | Completed | 18360 | 18052 | 2022-09-16 | 2023-08-16
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718005004/IF/IAY/3804037 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115778146 | Completed | 18360 | 18048 | 2022-10-15 | 2023-08-16
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718005004/IF/IAY/3831335 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116780253 | Completed | 18360 | 18048 | 2022-10-15 | 2023-08-16
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718005004/IF/IAY/3831336 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116780619 | Completed | 18360 | 17952 | 2022-10-15 | 2023-08-22
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718005004/IF/IAY/3831337 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116780705 | Completed | 18360 | 17952 | 2022-10-15 | 2023-08-22
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718005004/IF/IAY/3926369 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115777432 | Completed | 18360 | 17896 | 2022-08-19 | 2023-08-22
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718005004/IF/IAY/4155187 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115778175 | Completed | 18360 | 17925 | 2022-11-30 | 2023-08-22
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718005004/IF/IAY/4328106 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118181193 | Completed | 18360 | 18360 | 2022-09-16 | 2023-08-16
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718005004/IF/IAY/4328112 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118201773 | Completed | 18360 | 18048 | 2022-11-30 | 2023-08-16
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718005004/IF/IAY/4570780 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116780211 | Completed | 23490 | 22194 | 2025-01-10 | 2026-02-19
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718005004/IF/IAY/4570781 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116780291 | Completed | 23490 | 22194 | 2025-01-10 | 2026-02-19
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718005004/IF/IAY/4570782 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116780333 | Completed | 23490 | 22194 | 2025-01-10 | 2026-02-19
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718005004/IF/IAY/4581671 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118180904 | Completed | 23490 | 21870 | 2024-11-20 | 2026-02-24
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718005004/IF/IAY/4754031 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117763279 | Completed | 23490 | 22194 | 2025-01-10 | 2026-02-19
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718005004/IF/IAY/4754032 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117763373 | Completed | 23490 | 22194 | 2025-01-10 | 2026-02-21
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718005004/IF/IAY/4754160 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118190177 | Completed | 23490 | 22572 | 2025-02-05 | 2026-02-19
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718005004/IF/IAY/4765776 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115777753 | Ongoing | 27000 | 17874 | 2025-02-05
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718005004/IF/IAY/4996037 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115777650 | Completed | 23490 | 23490 | 2025-07-02 | 2026-02-07
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718005004/IF/IAY/4996040 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115777908 | Physically Completed | 23490 | 23490 | 2026-01-21 | 2026-05-17
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718005004/IF/IAY/4997319 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116780912 | Physically Completed | 23490 | 23490 | 2025-10-25 | 2025-12-21
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718005004/IF/IAY/5003032 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117763105 | Ongoing | 27000 | 23490 | 2026-02-06
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718005004/IF/IAY/5003033 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117763314 | Completed | 23490 | 23189 | 2025-12-11 | 2026-02-19
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718005004/IF/IAY/5003034 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117763455 | Ongoing | 27000 | 23490 | 2026-01-28
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718005004/IF/IAY/5004881 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118178574 | Completed | 23490 | 23490 | 2025-12-20 | 2026-02-19
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718005004/IF/IAY/5017637 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116801114 | Physically Completed | 23490 | 23490 | 2025-09-25 | 2025-12-21
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718005004/IF/IAY/5082383 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118202073 | Physically Completed | 23490 | 23490 | 2026-01-28 | 2026-08-23
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718005004/IF/IAY/5082391 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118203251 | Physically Completed | 23490 | 21924 | 2026-01-29 | 2026-08-02
| 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718005004/IF/IAY/5435687 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116780526 | Ongoing | 27000 | 0 | 2025-02-28
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718005004/IF/IAY/5436987 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117763427 | Completed | 23490 | 23490 | 2026-01-24 | 2026-08-04
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718005004/IF/IAY/5690214 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115777875 | Completed | 23490 | 23490 | 2026-02-06 | 2026-08-04
| 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718005004/IF/IAY/92480 — Construction of IAY House -IAY REG. NO. MP-18-005-004-002/34 | Approved | 27000 | 0 | 2015-07-20
| 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1718005004/LD/20 — शांतिधाम समतलीयकरण = कंडारिया | Completed | 226000 | 80256.39 | 2012-05-08 | 2014-01-30
| 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1718005004/LD/22012034304404 — SHANTI DHAM SHED NIRMAN GRAM AJRANA | Completed | 180000 | 177704.2 | 2017-03-11 | 2017-11-22
| 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1718005004/LD/22012034313972 — SHANTI DHAM SHED NIRMAN KANDARIYA | Completed | 180000 | 177309.75 | 2017-05-22 | 2017-11-22
| 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1718005004/LD/3799386409 — ग्रामीण क्रीडागण में समालियकरण 780 | Completed | 560000 | 31812 | 2012-06-19 | 2012-06-30
| 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718005004/RC/100 — विधायक निधि आंतरिक मार्ग सीमेंट कांक्रीट निर्माण क | Completed | 65000 | 103619.98 | 2012-05-27 | 2012-06-02
| 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718005004/RC/101 — पंचपरमेश्वर सी,सी,कार्य कृष्णपाल के घर से बहादुरसि | Completed | 75000 | 120232 | 2012-05-27 | 2012-09-10
| 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718005004/RC/22012034159555 — पंचपरमेश्वर सीमेंट कंक्रीट कार्य एवं नाली निर्माण | Deleted | 108000 | 0 | 2012-10-09
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718005004/RC/22012034186468 — पंचपरमेश्वर चन्दरसिंह के माकन से हनुमान मंदिर की औ | Completed | 126000 | 100582 | 2013-12-26 | 2014-05-09
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718005004/RC/22012034186484 — पंचपरमेश्वर बनेसिंह के मकान से हरिराम के मकान की औ | Completed | 85000 | 67480 | 2014-02-25 | 2014-05-25
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718005004/RC/22012034208359 — पंचपरमेश्वर बनेसिंह के मकान से हरिराम के मकान की औ | Deleted | 85000 | 0 | 2013-06-12
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1718005004/RC/22012034212970 — खेत सड़क निर्माण शंकर के मकान से चंद्रशेखर पालीवाल | Completed | 1189000 | 82774 | 2014-03-06 | 2016-10-22
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718005004/RC/22012034214919 — panchparmeshwar vishnu ke makan se D.P. ki or 279 | Completed | 74900 | 64818 | 2014-03-20 | 2014-05-25
| 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718005004/RC/22012034263839 — पंचपरमेश्वर हनुमान जी मंदिर से गंगाराम के घर की और | Deleted | 0 | 0 | 2014-10-02
| 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718005004/RC/22012034263842 — पंचपरमेश्वर स्कूल से शेतान बाई के घर की और | Deleted | 0 | 0 | 2014-10-02
| 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1718005004/RC/22012034294358 — शांतिधाम पहुँच मार्ग अजराना | Deleted | 0 | 0 | 2015-10-02
| 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1718005004/RC/22012034294514 — शांतिधाम पहुँच मार्ग अजराना | Completed | 300000 | 99822.34 | 2015-12-31 | 2017-11-08
| 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718005004/RC/22012034312031 — सीमेंट कंक्रीट जुवान सिंह के घर से पुनाजी के घर तक | Deleted | 0 | 0 | 2015-10-02
| 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718005004/RC/22012034312032 — सीमेंट कंक्रीट रोड चडी के घर भारत के घर तक | Deleted | 0 | 0 | 2015-10-02
| 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718005004/RC/22012034312033 — सीमेंट कंक्रीट रोड गंगाराम के घर से हनुमान मंदिर की ओर | Deleted | 0 | 0 | 2015-10-02
| 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718005004/RC/22012034312034 — सीमेंट कंक्रीट रोड तेजराम के घर से चोकीदार के घर तक | Deleted | 0 | 0 | 2015-10-02
| 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718005004/RC/22012034333149 — सी.सी. रोड तेजराम कनीराम के मकान से चंदर रामजी के मकान की और | Completed | 96292 | 104366 | 2017-03-24 | 2017-12-07
| 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718005004/RC/22012034335850 — सी सी रोड तेजराम कनीराम के मकान से चंदर पिता रामजी के मकान की और | Deleted | 0 | 0 | 2017-01-26
| 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718005004/RC/22012034335851 — सी सी रोड भूरालाल पिता भोलाराम के मकान से बद्रीलाल नंदराम के मकान तक | Closed | 0 | 0 | 2017-01-26
| 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718005004/RC/22012034344064 — शासकीय हेंडपंप से रमेश चोकीदार के मकान की और | Completed | 17000 | 17544 | 2017-07-12 | 2017-12-07
| 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718005004/RC/22012034344067 — C.C ROAD NANURAM PITA BHGIRATH KE MAKAN SE RAMLAL PITA BHERULAL KE MAKAN KI OR | Completed | 4164000000 | 39904 | 2017-07-12 | 2017-12-07
| 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718005004/RC/22012034347692 — Dulesigh pita omsingh ke makan se raees pita rukhmani ke makan ki aur | Completed | 15615 | 13998 | 2017-07-31 | 2018-09-05
| 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718005004/RC/22012034347697 — Raees pita rukhmani ke makan se chadi pita mirakh singh ke makan ki aur | Completed | 15615 | 14346 | 2017-07-31 | 2018-09-05
| 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718005004/RC/22012034347699 — BHuralal pita Bbholaram ke makan se bdrilal nandram ke makan tak | Completed | 80678 | 75690 | 2017-07-31 | 2018-07-19
| 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718005004/RC/22012034373669 — kandariya me shankarlal pita bhagirath ke makan se rajaram bhagirath ke makan tak | Closed | 0 | 0 | 2017-10-02
| 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718005004/RC/22012034373695 — sewaram kaniram ke makan se bajrangbali bholenath ke mandir ki orh | Closed | 0 | 0 | 2017-10-02
| 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718005004/RC/22012034373707 — hakam singh pita sitaram ke makan se men road ki or nali | Closed | 0 | 0 | 2017-10-02
| 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718005004/RC/22012034373728 — C.C.road and nali nirman pardikheda me punaji pita ghisa ji ke makan se pmgsy men road ki or | Closed | 0 | 0 | 2017-10-02
| 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718005004/RC/22012034373732 — nali nirman pardikheda me bahadur singh pita mayaram ke makan se puna ji pita ghisaji ke makan ki or | Closed | 0 | 0 | 2017-10-02
| 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718005004/RC/22012034373758 — nali nirman pardikheda me bahadur singh pita mayaram ke makan se puna ji pita ghisaji ke makan ki or | Closed | 0 | 0 | 2017-10-02
| 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718005004/RC/22012034373767 — nali nirman pardikheda me bahadur singh pita mayaram ke makan se puna ji pita ghisaji ke makan ki or | Closed | 0 | 0 | 2017-10-02
| 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718005004/RC/22012034373773 — nali nirman pardikheda me bahadur singh pita mayaram ke makan se puna ji pita ghisaji ke makan ki or | Closed | 0 | 0 | 2017-10-02
| 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718005004/RC/22012034373776 — C.C.road and nali nirman mohan pita kashi ke makan se bhagirath pita nagji ke makan ki or | Closed | 0 | 0 | 2017-10-02
| 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718005004/RC/22012034373781 — C.C.road and nali nirman Omprakash pita ramchadra ke makan se shivmaharaj ke makan ki or | Closed | 0 | 0 | 2017-10-02
| 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718005004/RC/22012034373787 — C.C.road and nali nirman men road se kailash pita kaniram ke makan ki or ajrana | Closed | 0 | 0 | 2017-10-02
| 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718005004/RC/22012034390127 — C.C. ROAD NALI NIRMAN SHANKARLAL PITA BHAGIRATH KE MAKAN SE RAJARAM BHAGIRATH KE MAKAN TAK | Completed | 23423 | 18618 | 2018-06-13 | 2019-01-05
| 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718005004/RC/22012034394365 — C C ROAD EVAM NALI NIRMAN BHERU MAHARAJ KE MANDIR SE TEJULAL GABBU JI KE GHAR KI OR GRAM AJRANA | Completed | 53865 | 52722 | 2018-10-05 | 2019-08-07
| 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718005004/RC/22012034394366 — C C ROAD EVAM NALI NIRMAN MAIN ROAD SE KELASH PITA KANIRAM KE MAKAN KI OR GRAM AJRANA | Completed | 30823 | 30480 | 2019-01-07 | 2019-08-07
| 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718005004/RC/22012034441208 — C C NALINIRMAN BHARAT PITA GORESINGH KE MAKAN SE DULE SINGH PITA OMSINGH KE MAKAN KI OR | Closed | 0 | 0 | 2018-10-02
| 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718005004/RC/22012034449101 — C C ROAD EVAM NALI NIRMAN PARDIKHEDA ME PUNA JI PITA GHISA JI KE GHAR SE PMGSY MAIN ROAD KI OR | Completed | 7440 | 7080 | 2019-03-09 | 2020-12-14
| 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718005004/RC/22012034449104 — C C ROAD EVAM NALI NIRMAN OMPRAKSH PITA RAMCHANDR KE MAKAN SE SHIV MAHRAJ KE MAKAN KI OR | Completed | 8370 | 7629 | 2019-03-08 | 2019-08-24
| 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718005004/RC/22012034449107 — C C ROAD EVAM NALI NIRMAN MOHAN PITA KASHI KE MAKAN SE BHAGIRATH PITA NAGJI KE MAKAN KI OR | Closed | 20925 | 0 | 2019-01-26
| 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718005004/RC/22012034530507 — c.c.rod prathmik vidhyalay se madanlal ke makan ki or | Closed | 22950 | 0 | 2020-04-26
| 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718005004/RC/22012034530520 — C.c.rod pradhanmantri rod se lakhan ke makan tak | Completed | 17850 | 17700 | 2020-08-07 | 2020-12-02
| 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718005004/RC/22012034531178 — C C ROAD NIRMAN SANTOSH TAILOR KE NAKAN SE RAMLAL KE MAKAN KI OR | Completed | 25500 | 25260 | 2020-08-25 | 2020-12-02
| 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718005004/RC/22012034544788 — OMPRAKASH JI KE MAKAM SE SHERI RAM MANDIR CHOWK C.C. ROAS AVM NALI NIRMAN | Completed | 30225 | 30110 | 2020-10-15 | 2021-09-20
| 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718005004/RC/22012034544790 — PRADHAN MANTRI ROAD SE SHANTILALJI KE MAKAN KI OR C.C. ROAD | Completed | 37867 | 37776 | 2020-12-08 | 2021-09-20
| 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718005004/RC/22012034554404 — MAYARAM KE MAKAN SE TEJU PITA GABBUJI KE MAKAN KI OR C.C. ROAD | Completed | 25500 | 8374 | 2020-12-29 | 2023-12-16
| 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1718005004/RC/22012034557710 — SUDUR SADAK KANDARIYA SE AJRANA PAHUNCH MARG TAK | Completed | 974411.91 | 944330.51 | 2021-02-11 | 2023-08-09
| 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718005004/RC/22012034562058 — C C ROAD & NALI NIRMAN PRADHANMANTRI ROAD SE EAHMAD KE MAKAN KI OR | Completed | 156000 | 155184 | 2021-03-10 | 2022-03-14
| 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718005004/RC/22012034562063 — C C ROAD & NALI NIRMAN BHOLE NATH MANDIR CHOUCK | Completed | 17000 | 20354 | 2021-03-13 | 2022-03-14
| 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718005004/RC/22012034562064 — C C ROAD & NALI NIRMAN HANUMAN MANDIR SE RAVI KE GHAR KI OR | Completed | 35000 | 34200 | 2021-03-10 | 2022-03-14
| 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718005004/RC/22012034562065 — C C ROAD & NALI NIRMAN INDAR KE GHAR SE KALIKA MATA MANDIR TAK | Completed | 35600 | 34704 | 2021-03-10 | 2022-03-14
| 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718005004/RC/22012034562066 — C C ROAD & NALI NIRMAN PANNALAL KE MAKAN SE MANUKLAL KE MAKAN TAK | Completed | 28000 | 27889 | 2021-03-10 | 2022-03-14
| 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718005004/RC/22012034562068 — C C ROAD & NALI NIRMAN SITLA MATA CHOUCK | Completed | 15000 | 16661 | 2021-03-10 | 2022-03-14
| 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718005004/RC/22012034562069 — C C ROAD & NALI NIRMAN DOULAT SINGH KE MAKAN SE GAJRAJ KE MAKAN TAK | Completed | 120000 | 121397 | 2021-07-16 | 2022-03-14
| 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718005004/RC/22012034664630 — CC Road Avam nali Nirman karya Tejaji Mandir se Rameshwar ke Ghar ki or Ajrana | Completed | 75000 | 72537.81 | 2023-10-07 | 2026-03-08
| 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1718005004/RC/3???????? — 1718005004/RC/3 | Completed | 0 | 26532 | 2012-09-18 | 2013-02-28
| 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718005004/RC/3कंडारिया — कंडारिया अर्थवर्क कंडारिया से अजराना तक | Completed | 500000 | 91385.72 | 2008-10-08 | 2013-02-28
| 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718005004/RS/22012034239585 — निर्मल भारत बनेसिंह | Completed | 4400 | 2512 | 2014-06-13 | 2016-06-18
| 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718005004/RS/22012034239617 — निर्मल भारत लालसिंह | Completed | 4400 | 2512 | 2014-06-13 | 2016-06-18
| 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718005004/RS/22012034239623 — निर्मल भारत रामनारायण | Completed | 4400 | 2512 | 2014-06-13 | 2014-06-19
| 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718005004/RS/22012034241057 — निर्मल भारत रामेश्वर | Completed | 4400 | 2512 | 2014-06-13 | 2016-06-18
| 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718005004/RS/22012034241084 — निर्मल भारत हरिराम | Completed | 4400 | 2512 | 2014-06-13 | 2014-06-19
| 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718005004/RS/22012034241087 — निर्मल भारत शांतिलाल | Completed | 4400 | 2512 | 2014-06-13 | 2015-05-16
| 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718005004/RS/22012034241088 — निर्मल भारत संतोष | Completed | 4400 | 2512 | 2014-06-13 | 2016-06-18
| 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718005004/RS/22012034241199 — निर्मल भारत मांगू बाई | Completed | 4400 | 2512 | 2014-06-17 | 2014-06-23
| 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718005004/RS/22012034242579 — निर्मल भारत राधा बाई | Deleted | 0 | 0 | 2012-06-16
| 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718005004/RS/22012034242736 — निर्मल भारत राधा बाई | Deleted | 0 | 0 | 2012-06-16
| 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718005004/RS/22012034242738 — निर्मल भारत राकेश | Completed | 4400 | 2512 | 2014-06-18 | 2014-06-24
| 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718005004/RS/22012034274563 — निर्मल भारत यूनिट 01 कंडारिया | Deleted | 51070 | 0 | 2014-10-07
| 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Drainage Channel / Construction of Flood/ Diversion Channel for Community | Solid and Liquid Waste Management | 1718005004/RS/22012034292377 — शान्तिधाम पहुँच मार्ग ग्राम अजराना | Deleted | 0 | 0 | 2015-10-02
| 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1718005004/RS/22012034568576 — SAMUDAYEK SWACCHATA PARISHER PRIMARY SCHOOL KE PASS GRAM KANDARIYA | Completed | 88000 | 41516 | 2021-11-23 | 2024-01-20
| 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1718005004/RS/22012035117127 — RCC Nali Nirman Karya Gopal ke Ghar se School ki Or Kandariya | Ongoing | 71000 | 68197.3 | 2023-10-07
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718005004/RS/64362 — निर्मल भारत सीता बाई मांगीलाल | Completed | 4300 | 2482 | 2013-09-12 | 2013-09-18
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718005004/RS/64852 — निर्मल भारत सोदराबाई मांगीलाल | Completed | 4300 | 2482 | 2013-09-12 | 2013-09-18
| 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1718005004/WC/22012034444696 — NALA TRANCHING KARY GRAM AJARANA | Completed | 90000 | 75668 | 2019-03-08 | 2022-04-19
| 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718005004/WC/22012034480226 — RECHRGE PIT CHANDER KE GHER KE PASS AJARANA | Closed | 7235.72 | 0 | 2019-06-22
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1718005004/WC/22012034760046 — सोख्ता गड्ढ़ा कालु महाराज के घर के पास अजराना | Closed | 5515.76 | 0 | 2021-05-22
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1718005004/WC/22012034760055 — सोख्ता गड्ढ़ा गोवर्धन गंभीर के घर के पास | Closed | 5515.76 | 0 | 2021-05-22
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1718005004/WC/22012034760061 — सोख्ता गड्ढ़ा किरमलाल के घर के सामने | Closed | 5515.76 | 0 | 2021-05-22
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1718005004/WC/22012034760071 — सोख्ता गड्ढ़ा रामचंद्र के घर के पास मजरा पारदीखेड़ा | Completed | 5515.76 | 2160 | 2021-10-02 | 2023-12-16
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1718005004/WC/22012034760078 — वॉरहरवेस्टिंग कार्य पंचायत भवन कंडारिया | Closed | 22229.14 | 0 | 2021-05-22
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1718005004/WC/22012034760085 — वॉरहरवेस्टिंग कार्य राजीव गांधी भवन कंडारिया | Closed | 22229.14 | 0 | 2021-05-22
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718005004/WC/22012034847369 — Sokta gadda viju ganga singh ke ghar ke pass | Closed | 2578.75 | 0 | 2021-10-02
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718005004/WC/22012034847378 — Sokta gadda bhagat singh ke ghar ke pass | Closed | 2578.75 | 0 | 2021-10-02
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718005004/WC/22012034847389 — Sokta gadda dashrat ke ghar ke pass | Closed | 2578.75 | 0 | 2021-10-02
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718005004/WC/22012034847396 — Sokta gadda kamal ke ghar ke pass | Closed | 2578.75 | 0 | 2021-10-02
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718005004/WC/22012034847404 — Sokta gadda shankar ke ghar ke pass | Closed | 2578.75 | 0 | 2021-10-02
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718005004/WC/22012034847413 — Sokta gadda manuklal ke ghar ke pass | Closed | 0 | 0 | 2021-10-02
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718005004/WC/22012034847421 — Sokta gadda ramchandra ke ghar ke pass | Closed | 0 | 0 | 2021-10-02
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718005004/WC/22012034847430 — Sokta gadda mohan ke ghar ke pass | Closed | 0 | 0 | 2021-10-02
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718005004/WC/22012034847436 — Sokta gadda vikram ke ghar ke pass | Closed | 0 | 0 | 2021-10-02
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718005004/WC/22012034847449 — Sokta gadda bahadur ke ghar ke pass | Closed | 0 | 0 | 2021-10-02
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718005004/WC/22012034847456 — Sokta gadda hate singh ke ghar ke pass | Closed | 0 | 0 | 2021-10-02
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718005004/WC/22012034847468 — Sokta gadda gyarshi bai ke ghar ke pass | Closed | 0 | 0 | 2021-10-02
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718005004/WC/22012034847482 — Sokta gadda gyarshi bai ke ghar ke pass | Closed | 0 | 0 | 2021-10-02
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718005004/WC/22012034847489 — Sokta gadda aatmaram ke ghar ke pass | Closed | 0 | 0 | 2021-10-02
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718005004/WC/22012034847494 — Sokta gadda bhagwan singh ke ghar ke pass | Closed | 0 | 0 | 2021-10-02
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718005004/WC/22012034847499 — Sokta gadda indar ke ghar ke pass | Closed | 0 | 0 | 2021-10-02
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718005004/WC/22012034847512 — Sokta gadda aandlal ke ghar ke pass | Closed | 0 | 0 | 2021-10-02
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718005004/WC/22012034847521 — Sokta gadda panna sher singh ke ghar ke pass | Closed | 0 | 0 | 2021-10-02
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718005004/WC/22012034847530 — Sokta gadda mahendar singh ke ghar ke pass | Closed | 0 | 0 | 2021-10-02
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718005004/WC/22012034847540 — Sokta gadda aplasha bai ke ghar ke pass | Closed | 0 | 0 | 2021-10-02
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718005004/WC/22012034847547 — Sokta gadda kamu bai ke ghar ke pass | Closed | 0 | 0 | 2021-10-02
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718005004/WC/22012034847559 — Sokta gadda biba singh ke ghar ke pass | Closed | 0 | 0 | 2021-10-02
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1718005004/WC/22012034899605 — Nala trenching ajrana 2 | Closed | 0 | 0 | 2022-01-12
| 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718005004/WC/22012035127277 — Nala trenching ramesh ke khet se mohan ke khet ki or | Physically Completed | 140489.51 | 47287.1 | 2023-10-05 | 2026-04-15
| 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1718005004/WH/22012034934780 — Nala trenching mahendar suresh ke makan se sardar singh ke khet ki or kandariya | Closed | 0 | 0 | 2022-05-14
| 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1718005004/WH/22012034934782 — nala trenching nahendra ke makan se sardar singh ke khet ki or | Completed | 241949.3 | 137917 | 2022-05-28 | 2024-08-01
| 2015-2016 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construct building for federation of women SHG / Construction of SHG/Federation Building for Groups | Construction of building/workshed for SHG | 1718005031/AV/3711 — Aanganbadi/Other Rural Infrastructure,UJJAIN | Deleted | 195000 | 0 | 2015-06-12
| 2013-2014 | D--RURAL INFRASTUCTURE / Bharat Nirman Sewa Kendra | New Construction / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | /SK/23 — Bharat Nirman Rajeev Gandhi Sewa Kendra,KANDARIYA | Completed | 1251000 | 1004690.18 | 2013-06-03 | 2018-10-29