## Work List
Exported on: 2026-08-28 07:02:12
Filters applied:
Data source: MGNREGA
District: UJJAIN
Block: UJJAIN
Panchayat: DAUDKHEDI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
| 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | AWC / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1718005044/AV/5598 — ANGANWADI EVAM BOUNDARY WALL (DAUDKHEDI) | Completed | 195000 | 187001.86 | 2016-09-15 | 2019-07-02
| 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1718005044/AV/7057 — शांतिधाम शेड निर्माण (दाऊदखेड़ी ) | Completed | 180000 | 175938.87 | 2017-01-26 | 2017-11-10
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Gov blding premises-Block Plantation-Horticulture / Block Plantation of Horticulture Trees in Government building premises for Community | Plantation | 1718005044/DP/22012034536108 — MA KI BAGIYA PRATHMIK VIDHYALAY DAUDKHEDI | Closed | 4972.44 | 0 | 2021-08-15
| 2015-2016 | D--RURAL INFRASTUCTURE / Rural Drinking Water | Soak Pits / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1718005044/DW/9993654140 — Sokta Gadda शा,प्रा. के पास | Completed | 3100 | 2067 | 2015-06-26 | 2016-07-21
| 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1718005044/FP/22012034637261 — RCC NALI NIRMAN MANDIR SE MOHAN KE GHAR TAK DAUDKHEDI | Closed | 33000 | 0 | 2023-10-06
| 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1718005044/IF/22012034340322 — vraksharopan kary sadak kinare DAUDKHEDI SE CHINTAMAN MARG | Completed | 335000 | 208822 | 2017-05-25 | 2023-08-05
| 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation - Shelter Belt for Individuals / Block Plantation of Shelter Belt Trees for Individuals | Plantation | 1718005044/IF/22012034603792 — NANDANFALODHYAN DEEPAK CHENA JI | Deleted | 0 | 0 | 2020-08-15
| 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1718005044/IF/22012034822600 — NADEF NIRMAN MAYARAM SUKHRAM | Completed | 10956.77 | 8516.07 | 2021-10-09 | 2023-08-05
| 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1718005044/IF/22012034822601 — NADEF NIRMAN MEHARBAN MANNA JI | Completed | 10956.77 | 8498.07 | 2021-11-20 | 2023-08-25
| 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1718005044/IF/22012034822604 — NADEF NIRMAN CHANDAR BHUWAN | Closed | 10956.77 | 0 | 2021-04-14
| 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1718005044/IF/22012034822605 — NADEF NIRMAN CHAMPALAL MANGEELAL | Completed | 10956.77 | 8498.07 | 2021-11-20 | 2023-08-05
| 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1718005044/IF/22012034822612 — SOKHTA GADDA MAYARAM SUKHRAM | Closed | 5718.26 | 0 | 2021-04-14
| 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1718005044/IF/22012034822614 — SOKHTA GADDA MEHARBAN MANNAJI | Closed | 5718.26 | 0 | 2021-04-14
| 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1718005044/IF/22012034822616 — SOKHTA GADDA CHANDAR BHUWAN | Deleted | 0 | 0 | 2021-04-14
| 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1718005044/IF/22012034822619 — SOKHTA GADDA CHAMPALAL MANGEELAL | Closed | 5718.26 | 0 | 2021-04-14
| 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718005044/IF/9993688480 — IAY हेमूबाई तकेसिंह | Completed | 14310 | 8274 | 2015-11-23 | 2016-10-22
| 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718005044/IF/9993689458 — IAY राजूबाई दिलीप | Completed | 14310 | 8271 | 2015-11-23 | 2016-10-22
| 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1718005044/IF/9993739476 — पशु शेड मेहरबान मन्नाजी | Deleted | 0 | 0 | 2015-10-02
| 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1718005044/IF/9993739477 — पशु शेड गणेश चंदेरलाल | Deleted | 0 | 0 | 2015-10-02
| 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1718005044/IF/9993739478 — पशु शेड गणेश चंदेरलाल | Deleted | 0 | 0 | 2015-10-02
| 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1718005044/IF/9993739479 — पशु शेड गणेश चंदेरलाल | Deleted | 0 | 0 | 2015-10-02
| 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1718005044/IF/9993739484 — पशु शेड कालू देवाजी | Deleted | 0 | 0 | 2015-10-02
| 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1718005044/IF/9993739485 — पशु शेड मेहरबान मन्नाजी | Deleted | 0 | 0 | 2015-10-02
| 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1718005044/IF/9993739486 — पशु शेड मायाराम सुखराम | Deleted | 0 | 0 | 2015-10-02
| 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1718005044/IF/9993739487 — पशु शेड बालू मांगीलाल | Deleted | 0 | 0 | 2015-10-02
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718005044/IF/IAY/3791128 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106903516 | Completed | 18360 | 17136 | 2022-09-24 | 2023-06-16
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718005044/IF/IAY/3791538 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100486404 | Completed | 18360 | 17136 | 2022-09-24 | 2023-08-22
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718005044/IF/IAY/3791553 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100490790 | Completed | 18360 | 17136 | 2022-09-16 | 2023-08-22
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718005044/IF/IAY/3802340 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106680944 | Physically Completed | 23490 | 19108 | 2023-01-10 | 2025-04-10
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718005044/IF/IAY/3804917 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105362465 | Completed | 18360 | 17136 | 2022-09-24 | 2023-06-16
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718005044/IF/IAY/3849000 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127488093 | Completed | 18360 | 15912 | 2022-07-16 | 2023-09-13
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718005044/IF/IAY/4000473 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116678741 | Completed | 18360 | 17732 | 2023-01-03 | 2024-07-29
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718005044/IF/IAY/4000474 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116679132 | Ongoing | 23490 | 7523 | 2022-12-20
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718005044/IF/IAY/4240989 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103554638 | Completed | 18360 | 16184 | 2022-10-29 | 2023-08-22
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718005044/IF/IAY/4535793 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102683830 | Completed | 23490 | 16954 | 2024-11-23 | 2026-03-09
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718005044/IF/IAY/4536887 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100753180 | Completed | 23490 | 21412 | 2025-02-04 | 2025-04-24
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718005044/IF/IAY/4543489 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105362501 | Completed | 23490 | 17924 | 2024-12-08 | 2025-04-17
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718005044/IF/IAY/4547573 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106691793 | Completed | 21870 | 15398 | 2024-11-24 | 2025-04-24
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718005044/IF/IAY/4933336 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100753139 | Ongoing | 23490 | 16704 | 2025-10-22
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718005044/IF/IAY/4933337 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100753199 | Ongoing | 23490 | 7308 | 2025-09-18
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718005044/IF/IAY/4933997 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102079721 | Completed | 23490 | 20785 | 2025-04-10 | 2025-12-12
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718005044/IF/IAY/4933998 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102079736 | Completed | 23490 | 21690 | 2025-05-12 | 2025-12-12
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718005044/IF/IAY/4933999 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102079777 | Physically Completed | 23490 | 17430 | 2025-05-12 | 2026-02-08
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718005044/IF/IAY/4934000 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102079790 | Completed | 23490 | 16870 | 2025-04-10 | 2025-12-12
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718005044/IF/IAY/4934487 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100486426 | Approved | 23490 | 0 | 2025-02-22
| 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718005044/IF/IAY/4934488 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100486439 | Ongoing | 23490 | 3654 | 2026-05-17
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718005044/IF/IAY/4934494 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100490765 | Completed | 23490 | 22540 | 2025-05-12 | 2025-12-12
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718005044/IF/IAY/4935111 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100753227 | Completed | 23490 | 21243 | 2025-05-26 | 2025-12-12
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718005044/IF/IAY/4935669 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103554754 | Ongoing | 23490 | 21364 | 2025-05-26
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718005044/IF/IAY/4937390 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106687170 | Ongoing | 23490 | 16870 | 2025-04-10
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718005044/IF/IAY/4938267 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106900845 | Completed | 23490 | 21924 | 2025-06-23 | 2026-03-09
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718005044/IF/IAY/4938283 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106907490 | Completed | 23490 | 20804 | 2025-04-17 | 2025-12-12
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718005044/IF/IAY/4938284 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106907523 | Completed | 23490 | 22389 | 2025-05-12 | 2026-03-09
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718005044/IF/IAY/4938935 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102684206 | Completed | 23490 | 22408 | 2025-05-26 | 2026-03-09
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718005044/IF/IAY/4938937 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102685000 | Completed | 23490 | 21364 | 2025-05-26 | 2025-12-12
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718005044/IF/IAY/4939344 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113444823 | Ongoing | 23490 | 3374 | 2025-05-12
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718005044/IF/IAY/4940726 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113679719 | Ongoing | 23490 | 0 | 2026-02-13
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718005044/IF/IAY/4941083 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113513267 | Ongoing | 23490 | 20524 | 2025-04-10
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718005044/IF/IAY/4941125 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113529257 | Approved | 23490 | 0 | 2025-02-22
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718005044/IF/IAY/4941142 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113537099 | Approved | 23490 | 0 | 2025-02-22
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718005044/IF/IAY/4946472 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116667858 | Ongoing | 23490 | 19518 | 2025-05-12
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718005044/IF/IAY/4968018 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128097078 | Completed | 23490 | 21364 | 2025-05-26 | 2025-12-12
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718005044/IF/IAY/4968037 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128114732 | Completed | 23490 | 14616 | 2025-05-26 | 2025-12-12
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718005044/IF/IAY/4968038 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128115284 | Completed | 23490 | 22949 | 2025-04-17 | 2026-02-19
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718005044/IF/IAY/4968039 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128115715 | Ongoing | 23490 | 10905 | 2025-04-10
| 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718005044/IF/IAY/530646 — Construction of IAY House -IAY REG. NO. MP2814621 | Completed | 15030 | 14964 | 2017-03-22 | 2017-10-16
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718005044/IF/IAY/5710728 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106676827 | Ongoing | 23490 | 16704 | 2026-01-30
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718005044/IF/IAY/5717249 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123878719 | Ongoing | 23490 | 6264 | 2026-01-30
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718005044/IF/IAY/5976547 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113527002 | Approved | 23490 | 0 | 2025-02-22
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718005044/IF/IAY/92486 — Construction of IAY House -IAY REG. NO. MP-18-005-044-002/65 | Completed | 14310 | 2448 | 2022-08-27 | 2024-07-02
| 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1718005044/LD/22012034305907 — शांतिधाम शेड निर्माण (सांवराखेड़ी ) | Completed | 180000 | 175769.81 | 2017-03-16 | 2017-11-10
| 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718005044/RC/1दाउदखेडी — दाउदखेडी अर्थर्वक तेजाजी मंदिर से जीवनखेडी तक | Deleted | 715200 | 0 | 2008-10-13
| 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718005044/RC/22012034159761 — सीमेंट कांक्रीट एवं नाली निर्माण कार्य, पुलिया से | Completed | 108000 | 42185 | 2013-03-04 | 2013-03-31
| 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718005044/RC/22012034160459 — सी.का.एवं नाली निर्माण राममंदिर से चोधरी घर की और | Completed | 130000 | 85184 | 2012-08-21 | 2013-08-26
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718005044/RC/22012034169557 — Sansad nidhi AAntrik KAry Daudkhedi | Completed | 300000 | 7884 | 2013-06-03 | 2014-04-27
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718005044/RC/22012034193644 — सांसद निधि आंतरिक सीमेंट कांक्रीट रोड निर्माण दौद | Completed | 300000 | 186474 | 2013-12-10 | 2014-11-30
| 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718005044/RC/22012034226474 — पंचपरमेश्वर कालू माली के घर से हरिकिशन के घर की और | Completed | 100000 | 83210.9 | 2014-08-02 | 2016-07-21
| 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718005044/RC/22012034230367 — पंचपर्मेस्वर उमराव सिंह के घर से बहादुर सिंह के घर | Deleted | 100000 | 0 | 2014-06-07
| 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718005044/RC/22012034264030 — पंचपरमेश्वर मोहन के घर से प्रेमसिंह के घर की और | Completed | 58000 | 16941 | 2016-09-22 | 2017-10-06
| 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718005044/RC/22012034264031 — पंचपरमेश्वर देवेन्द्र के घर से टंकी की और | Deleted | 0 | 0 | 2014-10-02
| 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718005044/RC/22012034291043 — हनुमान मंदिर से ram मंदिर की और | Completed | 53900 | 50691 | 2015-12-03 | 2017-10-06
| 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718005044/RC/22012034312523 — सीमेंट कंक्रीट रोड रमेश के घर से पप्पू के घर तक | Closed | 0 | 0 | 2015-10-02
| 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718005044/RC/22012034326898 — सी सी रोड़ लालबाई फूलबाई मंदिर से रायसिंह के मकान कि ओर | Completed | 28800 | 21900 | 2017-05-04 | 2018-06-20
| 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718005044/RC/22012034328451 — सी सी रोड़ जगदीश के मकान से शंकर्लाल के मकान की ओर | Completed | 57105 | 48726 | 2017-02-23 | 2018-06-20
| 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718005044/RC/22012034330184 — सी सी रोड़ +नाली निर्माण शंकरलाल छेताजी के मकान से प्रेमभागीरथ के मकान एवं मांगलिक भवन रोड़ की ओर | Completed | 84375 | 71280 | 2017-03-09 | 2017-12-15
| 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718005044/RC/22012034335754 — C C ROAD HIRALAL THAWAR JI KE MANKAN SE AMBARAM PITA MANGILAL KE MAKAN KI OR | Completed | 15360 | 14616 | 2019-01-20 | 2019-02-25
| 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718005044/RC/22012034336474 — सी सी रोड़ +नाली निर्माण जसवंतसिंह के मकान से जीवनसिंह के मकान तक | Completed | 13012.5 | 10320 | 2017-04-27 | 2018-02-06
| 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718005044/RC/22012034337576 — gulab sinh ke makan se men road tak | Completed | 14400 | 14364 | 2017-05-18 | 2018-02-06
| 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718005044/RC/22012034337577 — tufansinh ke makan se jasvant ke makan ki or | Completed | 19272 | 18384 | 2017-05-25 | 2018-02-06
| 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718005044/RC/22012034350722 — C C ROAD CHINTAMAN BAIPAS SE RAMESH KALURAM KE GHAR TAK (SANWRAKHEDI) | Completed | 53611.1 | 42312 | 2017-08-24 | 2018-02-06
| 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718005044/RC/22012034374574 — C C ROAD NIRMAN MANGLIK BHAWAN SE AAGE HANDPUMP SE CHAMPA MANGILAL KE GHAR KI OR GRAM DAUDKHEDI | Completed | 15300 | 13572 | 2019-01-06 | 2019-02-25
| 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718005044/RC/22012034392265 — C C ROAD MALKHAN SINGH KE GHAR KE SAMNE | Completed | 10512 | 8874 | 2018-08-16 | 2019-01-07
| 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718005044/RC/22012034397122 — C C NALI NIRMAN MANGLIK BHAWAN SE LALBAI FULBAI MANDIR TAK GRAM DAUDKHEDI | Completed | 19388 | 11928 | 2019-03-10 | 2020-10-12
| 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718005044/RC/22012034433209 — C C ROAD EVAM NALI NIRMAN RAJAL KE GHAR SE KAMAL PITA RAJARAM KE GHAR TAK GRAM DAUDKHEDI | Completed | 23711 | 20882 | 2018-12-29 | 2019-02-25
| 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718005044/RC/22012034440260 — C C ROAD NIRMAN TEJAJI KE MANDIR SE SANTOSH KE GHAR TAK | Closed | 0 | 0 | 2018-10-02
| 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718005044/RC/22012034449438 — DPR NALI NIRMAN MANGLIK BHAWAN SE LALBAI FULBAI MANDIR (DAUDKHEDI) | Closed | 19387.5 | 0 | 2018-04-14
| 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718005044/RC/22012034472019 — C C ROAD NALI NIRMAN BHADAR ZUJARSINH KE GHAR SE PREM AMBARAM KE GHAR TAK | Completed | 46569 | 41004 | 2019-08-28 | 2019-12-10
| 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718005044/RC/22012034529924 — C C ROAD NALI NIRMAN DHANNALAL MANGILAL KR MAKAN SE KALURAM DEVAJI KE MAKAN TAK | Completed | 41475 | 41166 | 2020-10-05 | 2022-03-07
| 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Repair & maint of Gravel Road Roads for Comm / Repair and maintenance of Gravel Road Roads for Community | Repair & maint of Road | 1718005044/RC/22012034536949 — Sudur Sampark (Aproch Road) Karansingh Ke Makan Se Kanhaiyalal Ke Khet Tak | Closed | 0 | 0 | 2020-08-15
| 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718005044/RC/22012034538149 — C C ROAD NALI NIRMAN CHATARSINH KE GHAR SE MORSINH KE GHAR TAK (DAUDKHEDI) | Completed | 28680 | 27360 | 2020-09-26 | 2020-12-05
| 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718005044/RC/22012034542098 — C C ROAD NALI NIRMAN SHANI MANDEER ROAD SE GOURDHAN SARPANCH KE GHAR KI OR | Completed | 60435 | 57000 | 2020-10-01 | 2020-12-05
| 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718005044/RC/22012034544114 — C C ROAD NALI NIRMAN GHANSHYAM KE MAKAN SE PANNALAAL KE MAKAN KI OR (DAUDKHEDI) | Completed | 13387 | 11665 | 2020-11-04 | 2022-03-07
| 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718005044/RC/22012034615075 — C C ROAD MARAMMAD KARY LALBAI FULBAI MANDEER WALA CHOUK | Deleted | 0 | 0 | 2022-04-14
| 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718005044/RC/22012034615076 — C C ROAD MARAMMAD KARY LALBAI FULBAI MANDEER WALA CHOUK | Deleted | 0 | 0 | 2022-04-14
| 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718005044/RC/22012034615262 — C C ROAD MARAMMAD LALBAI FULBAI MANDEER WALA CHOUK | Completed | 35129 | 17136 | 2023-02-15 | 2023-08-22
| 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718005044/RC/22012034622980 — C C ROAD NIRMAN SHANI MANDEER ROAD SE PANCHAYAT BHAWAN KI OR | Completed | 20858 | 15096 | 2023-05-30 | 2023-08-05
| 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718005044/RC/22012034625324 — C C ROAD NIRMAN BALU MANGEELAL KE GHAR SE DHARMENDRA RATANLAL KE GHAR KI OR | Completed | 18989 | 18539 | 2023-05-23 | 2023-08-05
| 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718005044/RC/22012034631552 — C C ROAD NALI NIRMAN BAHADUR SINGH KE GHAR SE SAMUDAIK SHOUCHALAY KI OR | Completed | 49350 | 22396 | 2023-06-13 | 2023-08-22
| 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718005044/RC/22012034648641 — C C ROAD NIRMAN MEN ROAD SE PRATHMIK VIDHYALAY KI OR SANWRAKHEDI | Completed | 119000 | 116446 | 2023-08-30 | 2024-02-28
| 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718005044/RC/22012034660827 — C C ROAD NIRMAN KUNDAN MALI KE GHAR SE VIJAY MALI KE GHAR TAK DAUDKHEDI | Completed | 51000 | 49934 | 2023-10-09 | 2024-12-01
| 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718005044/RC/22012034666071 — C C ROAD MANGUSINGH KE GHAR SE BANESINGH KE GHAR OUR NIRMAN | Completed | 29000 | 23690.06 | 2023-10-09 | 2024-11-11
| 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718005044/RC/22012034669038 — CC ROAD PANCHAYAT BHAWAN SE BAHADUR SINGH KE GHAR KI OR DAUDKHEDI | Completed | 32000 | 25808 | 2023-10-09 | 2024-11-11
| 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718005044/RC/22012034669208 — CC ROAD AVAM NALI NIRMAN KARYA SADARSINGH CHOUDHARI KE GHAR SE RAMSINGH KE GHAR TAK DAUDKHEDI | Completed | 42000 | 32396.38 | 2023-10-09 | 2026-03-10
| 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718005044/RC/22012034823155 — CC ROAD NIRMAN KARYA RAMESHWAR KE GHAR SE LALBAI FULBAI MANDIR KI OR DAUDKHEDI | Approved | 98000 | 0 | 2024-06-10
| 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718005044/RC/22012034823163 — CC ROAD NIRMAN KARYA MAIN ROAD SE JIVAN SINGH KE GHAR KI OR DAUDKHEDI | Approved | 68000 | 0 | 2024-06-10
| 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718005044/RC/22012034823171 — CC ROAD NIRMAN KARYA MATA MANDIR SE RAYSINGH KE MAKAN KI OR DAUDKHEDI | Completed | 49000 | 18876.08 | 2024-10-03 | 2026-02-01
| 2007-2008 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718005044/RC/3दाउदखेडी — दाउदखेडी अर्थवर्क तेजाजी मंदिर से सांवराखेडी से जी | Deleted | 788000 | 0 | 2008-02-10
| 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1718005044/RS/22012034496315 — SWACCHATA PARISHER GRAM DAUDKHEDI | Completed | 48000 | 43700 | 2020-10-05 | 2021-07-10
| 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1718005044/RS/22012034528565 — NADEF NIRMAN LALBAI FULBAI MANDEER KE PAS DAUDKHEDI | Completed | 10956.77 | 8480.07 | 2021-08-17 | 2023-08-05
| 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of NADEP Compost structure for Groups / Construction of NADEP Compost structure for Groups | Construction of NADEP/Vermi Compost Pit | 1718005044/RS/22012034528567 — NADEF NIRMAN HENDPUMP KE PAS AJA BASTI | Completed | 10956.77 | 8834.07 | 2021-10-09 | 2023-08-05
| 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of NADEP Compost structure for Groups / Construction of NADEP Compost structure for Groups | Construction of NADEP/Vermi Compost Pit | 1718005044/RS/22012034528570 — SAMUDAIK NADEF NIRMAN 1 | Completed | 10956.77 | 8834.07 | 2021-10-09 | 2023-08-05
| 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of NADEP Compost structure for Groups / Construction of NADEP Compost structure for Groups | Construction of NADEP/Vermi Compost Pit | 1718005044/RS/22012034528571 — SAMUDAIK NADEF NIRMAN 2 | Completed | 10956.77 | 8834.07 | 2021-10-09 | 2023-08-05
| 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of NADEP Compost structure for Groups / Construction of NADEP Compost structure for Groups | Construction of NADEP/Vermi Compost Pit | 1718005044/RS/22012034528573 — SAMUDAIK NADEF NIRMAN 3 | Closed | 0 | 0 | 2021-04-14
| 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1718005044/RS/22012034683898 — C C NALI NIRMAN NATHU NANURAM KE GHAR SE RAYSINH PITA BALU JI KE GHAR TAK | Completed | 7817 | 6931 | 2023-08-30 | 2024-04-30
| 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1718005044/RS/22012034697378 — C C NALA NIRMAN NATHU KE GHAR SE RAKESH KE GHAR KI OR DAUDKHEDI | Completed | 41400 | 34255 | 2023-08-15 | 2024-04-30
| 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1718005044/RS/22012035121843 — NALI NIRMAN KARYA RAJESH KE GHAR SE DARBAR SINGH KE GHAR TAK GRAM DAUDKHEDI | Completed | 54000 | 47385 | 2024-02-04 | 2024-07-29
| 2015-2016 | D--RURAL INFRASTUCTURE / Bharat Nirman Sewa Kendra | New Construction / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1718005044/SK/9993648163 — Bharat Nirman Rajeev Gandhi Sewa Kendra,DAUDKHEDI | Completed | 1285000 | 897874.03 | 2015-12-03 | 2019-01-01
| 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1718005044/WC/22012034355517 — BORI BANDHAN DOUDKHEDI | Completed | 26000 | 1548 | 2017-09-27 | 2018-06-20
| 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1718005044/WC/22012034430070 — CHECK DEM EVAM NALA TRANCHING GRAM DAUDKHEDI | Completed | 512000 | 433643.11 | 2019-01-06 | 2019-09-25
| 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1718005044/WC/22012034445682 — CHECK DEM EVAM NALA TRANCHING KARY BHERUMAHARAJ KE MANDIR KE PASS DAUDKHRDI | Completed | 724000 | 527885.5 | 2019-03-10 | 2020-05-26
| 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718005044/WC/22012034480522 — RICHARGE PIT SAJAN KE GHAR KE SAMNE (DAUDKHEDI) | Completed | 4662.57 | 176 | 2019-08-16 | 2020-11-05
| 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718005044/WC/22012034480525 — RICHARGE PIT AJA BASTI (DAUDKHEDI) | Closed | 4720.6 | 0 | 2019-07-28
| 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Brushwood Check Dam for Community / Construction of Brushwood Check Dam for Community | Construction of Check Dam/Stop Dam | 1718005044/WC/22012034547855 — NALA TRENCHING DAUDKHEDI | Completed | 197838.19 | 167285 | 2020-05-24 | 2023-08-22
| 2020-2021 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Renovation of Flood/ Diversion Channel for Comm / Renovation of Flood/ Diversion Channel for Community | Terracing | 1718005044/WC/22012034580479 — NALA TRECHING ARJUNSINGH KE KHET KE PAS | Closed | 0 | 0 | 2020-08-15
| 2023-2024 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1718005044/WC/22012034648006 — NALA TRECHING PULIYA KE PAS WALA NALA (DAUDKHEDI) | Completed | 168521.04 | 52512 | 2023-10-09 | 2025-12-28
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718005044/WC/22012034729035 — SOKHTA GADDA ANGANWADI BHAWAN KE PAS | Completed | 5515.76 | 2123 | 2021-07-13 | 2022-02-11
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718005044/WC/22012034729041 — SOKHTA GADDA ANGANWADI HENDPUMP KE PAS | Completed | 5515.76 | 2123 | 2021-07-06 | 2022-02-11
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718005044/WC/22012034729045 — SOKHTA GADDA KICHANSHED KE PAS | Completed | 5515.76 | 2316 | 2021-07-13 | 2022-02-11
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718005044/WC/22012034729051 — SOKHTA GADDA PRATHMIK VIDHYALAY KE PAS | Completed | 5515.76 | 2316 | 2021-07-13 | 2022-02-11
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718005044/WC/22012034729058 — SOKHTA GADDA BAUNDREEWAL KE PAS | Closed | 5718.26 | 0 | 2021-04-14
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1718005044/WC/22012034787303 — ROOF WATAR HARWESTING ANGANWADI BHAWAN DAUDKHEDI | Closed | 22229.14 | 0 | 2021-04-14
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1718005044/WC/22012034787306 — ROOF WATAR HARWESTING VIDHYALAY BHAWAN DAUDKHEDI | Closed | 22229.14 | 0 | 2021-04-14
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1718005044/WC/22012034794641 — ROOF WATAR HARWESTING SHCOOL BHAWAN SANWRAKHEDI | Closed | 22229.14 | 0 | 2021-04-14
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718005044/WC/22012034846101 — सोख्ता गड्ढा स्कूल के पास | Closed | 2578.75 | 0 | 2021-10-02
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718005044/WC/22012034846126 — सोख्ता गड्ढा स्कूल के पास 1 | Closed | 2578.75 | 0 | 2021-10-02
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718005044/WC/22012034846145 — सोख्ता गड्ढा स्कूल के पास 2 | Closed | 2578.75 | 0 | 2021-10-02
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718005044/WC/22012034846177 — सोख्ता गड्ढा स्कूल के पास 3 | Closed | 2578.75 | 0 | 2021-10-02
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718005044/WC/22012034846211 — सोख्ता गड्ढा स्कूल शौचालय के पासके पास 1 | Closed | 2578.75 | 0 | 2021-10-02
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718005044/WC/22012034846236 — सोख्ता गड्ढा स्कूल शौचालय के पासके पास 2 | Closed | 2578.75 | 0 | 2021-10-02
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718005044/WC/22012034846262 — सोख्ता गड्ढा पंचायत भवन के पास 1 | Closed | 2578.75 | 0 | 2021-10-02
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718005044/WC/22012034846278 — सोख्ता गड्ढा पंचायत भवन के पास 2 | Closed | 2578.75 | 0 | 2021-10-02
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718005044/WC/22012034846289 — सोख्ता गड्ढा पंचायत भवन के पास 3 | Closed | 2578.75 | 0 | 2021-10-02
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718005044/WC/22012034846301 — सोख्ता गड्ढा पंचायत भवन के पास 4 | Closed | 2578.75 | 0 | 2021-10-02
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718005044/WC/22012034846532 — प्राथमिक स्कूल सांवरा खेड़ीके पास | Closed | 0 | 0 | 2021-10-02
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718005044/WC/22012034846534 — प्राथमिक स्कूल सांवरा खेड़ीके पास 1 | Closed | 0 | 0 | 2021-10-02
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718005044/WC/22012034846538 — प्राथमिक स्कूल के पास 1 | Closed | 0 | 0 | 2021-10-02
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718005044/WC/22012034846544 — प्राथमिक स्कूल के पास 2 | Closed | 0 | 0 | 2021-10-02
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718005044/WC/22012034846547 — सामुदायिक शौचालय के पास 1 | Closed | 0 | 0 | 2021-10-02
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718005044/WC/22012034846553 — सामुदायिक शौचालय के पास 2 | Closed | 0 | 0 | 2021-10-02
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718005044/WC/22012034846561 — सोख्ता गड्ढा राकेश के घर के सामने 1 | Closed | 2578.75 | 0 | 2021-10-02
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718005044/WC/22012034846563 — सोख्ता गड्ढा राकेश के घर के सामने 2 | Closed | 2578.75 | 0 | 2021-10-02
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718005044/WC/22012034846657 — sokta gadda प्राथमिक स्कूल सांवरा खेड़ीके पास 1 | Closed | 0 | 0 | 2021-10-02
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718005044/WC/22012034846666 — sokta gadda प्राथमिक स्कूल सांवरा खेड़ीके पास 2 | Closed | 0 | 0 | 2021-10-02
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718005044/WC/22012034846677 — sokta gadda प्राथमिक स्कूल के पास 1 | Closed | 0 | 0 | 2021-10-02
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718005044/WC/22012034846679 — sokta gadda प्राथमिक स्कूल के पास 1 | Closed | 0 | 0 | 2021-10-02
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718005044/WC/22012034846684 — sokta gadda प्राथमिक स्कूल के पास 2 | Closed | 0 | 0 | 2021-10-02
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718005044/WC/22012034846698 — sokta gadda सामुदायिक शौचालय के पास 1 | Closed | 0 | 0 | 2021-10-02
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718005044/WC/22012034846706 — sokta gadda सामुदायिक शौचालय के पास 2 | Closed | 0 | 0 | 2021-10-02
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718005044/WC/22012034880165 — सामुदायिक नाडेप निर्माण मांगलिक भवन के पास सांवरा खेड़ी | Closed | 10320.66 | 0 | 2021-11-19
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718005044/WC/22012034880172 — सोख्ता गड्ढा मांगलिक भवन के पास सांवरा खेड़ी | Closed | 2578.75 | 0 | 2021-11-19
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Wasteland Block Plantation-Horticulture-Community / Wasteland Block Plantation of Horticulture Trees for Community | Plantation | 1718005044/WC/22012034899356 — नरेगा से नाला ट्रैकिंग मोड़ सिंह के खेत से उदय सिंह के खेत की ओर | Closed | 0 | 0 | 2022-01-12
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Wasteland Block Plantation-Horticulture-Community / Wasteland Block Plantation of Horticulture Trees for Community | Plantation | 1718005044/WC/22012034899357 — नरेगा से नाला ट्रैकिंग मोड़ सिंह के खेत से उदय सिंह के खेत की ओर | Closed | 0 | 0 | 2022-01-12
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Wasteland Block Plantation-Horticulture-Community / Wasteland Block Plantation of Horticulture Trees for Community | Plantation | 1718005044/WC/22012034899360 — नरेगा से नाला ट्रैकिंग मोड़ सिंह के खेत से उदय सिंह के खेत की ओर | Closed | 0 | 0 | 2022-01-12
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Wasteland Block Plantation-Horticulture-Community / Wasteland Block Plantation of Horticulture Trees for Community | Plantation | 1718005044/WC/22012034899361 — नरेगा से नाला ट्रैकिंग मोड़ सिंह के खेत से उदय सिंह के खेत की ओर | Closed | 0 | 0 | 2022-01-12
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Wasteland Block Plantation-Horticulture-Community / Wasteland Block Plantation of Horticulture Trees for Community | Plantation | 1718005044/WC/22012034899363 — नरेगा से नाला ट्रैकिंग मोड़ सिंह के खेत से उदय सिंह के खेत की ओर | Closed | 161206.56 | 0 | 2022-01-12
| 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1718005044/WC/22012034953841 — अमृत सरोवर नवीन तालाब दाऊद खेड़ी | Deleted | 0 | 0 | 2022-04-14
| 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Canal Line Plantation of Forestry-Community / Canal Line Plantation of Forestry Trees for Community | Plantation | 1718005044/WC/22012035125563 — संकीर्ण पॉइंट सांवरा खेड़ी | Closed | 0 | 0 | 2023-09-27
| 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1718005044/WC/22012035127166 — SANKIRN POND SANWARAKHEDI | Physically Completed | 252616.75 | 84011.2 | 2023-10-09 | 2026-04-10
| 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1718005044/WH/19961991 — तालाब जिर्नोदार एवम पाल विस्तार दाउदखेडी | Completed | 79266 | 58852 | 2017-06-15 | 2018-08-09
| 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1718/RC/22012034152714 — Gravel Road Nirman daudkhedi se sikandri sadak | Completed | 1755000 | 170257.3 | 2011-04-10 | 2015-03-23