SARSI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719001061/IF/IAY/6021646 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105296485 | Ongoing | 27000 | 9396 | 2026-06-06
SARSI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719001061/IF/IAY/6021868 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113508753 | Ongoing | 27000 | 17928 | 2026-04-09
SARSI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719001061/IF/IAY/6023055 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106088365 | Ongoing | 27000 | 17226 | 2026-05-05
SARSI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719001061/IF/IAY/6023944 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113504670 | Ongoing | 27000 | 5400 | 2026-02-19
SARSI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719001061/IF/IAY/6023998 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113505043 | Approved | 27000 | 0 | 2026-02-19
SARSI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719001061/IF/IAY/6024001 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113501853 | Ongoing | 27000 | 5400 | 2026-02-19
SARSI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719001061/IF/IAY/6024181 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113505156 | Approved | 27000 | 0 | 2026-02-19
SARSI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719001061/IF/IAY/6024628 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105325719 | Ongoing | 27000 | 21402 | 2026-05-15
SARSI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719001061/IF/IAY/6024918 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116788851 | Ongoing | 27000 | 18972 | 2026-05-15
SARSI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719001061/IF/IAY/6024996 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106134436 | Ongoing | 27000 | 13464 | 2026-04-12
SARSI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719001061/IF/IAY/6025231 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106134383 | Ongoing | 27000 | 23229 | 2026-04-16
SARSI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719001061/IF/IAY/6026020 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114025489 | Ongoing | 27000 | 13932 | 2026-06-18
SARSI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719001061/IF/IAY/6026489 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114057187 | Ongoing | 27000 | 21924 | 2026-04-09
SARSI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719001061/IF/IAY/6026621 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114023502 | Ongoing | 27000 | 12366 | 2026-06-18
SARSI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719001061/IF/IAY/6026756 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113984940 | Ongoing | 27000 | 5400 | 2026-02-19
SARSI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719001061/IF/IAY/6026905 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114025229 | Ongoing | 27000 | 10800 | 2026-02-19
SARSI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719001061/IF/IAY/6026943 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114057128 | Ongoing | 27000 | 12420 | 2026-04-12
SARSI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719001061/IF/IAY/6034432 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113502239 | Ongoing | 27000 | 10800 | 2026-02-19
SARSI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719001061/IF/IAY/6036214 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114057174 | Ongoing | 27000 | 5400 | 2026-06-20
SARSI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719001061/IF/IAY/6036496 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114902929 | Ongoing | 27000 | 15138 | 2026-05-16
SARSI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719001061/IF/IAY/6040876 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147591492 | Ongoing | 27000 | 10098 | 2026-06-03
SARSI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719001061/IF/IAY/6040974 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113502149 | Ongoing | 27000 | 7200 | 2026-02-19
SARSI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719001061/IF/IAY/6041056 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113984756 | Ongoing | 27000 | 21924 | 2026-04-09
SARSI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719001061/IF/IAY/6041057 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113984985 | Ongoing | 27000 | 8532 | 2026-04-12
SARSI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719001061/IF/IAY/6041074 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106040004 | Ongoing | 27000 | 9864 | 2026-04-03
SARSI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719001061/IF/IAY/6041075 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106040077 | Ongoing | 27000 | 5400 | 2026-02-19
SARSI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719001061/IF/IAY/6041124 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114024395 | Ongoing | 27000 | 10800 | 2026-02-19
SARSI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719001061/IF/IAY/6041125 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114025660 | Ongoing | 27000 | 16074 | 2026-05-26
SARSI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719001061/IF/IAY/6041126 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114027445 | Ongoing | 27000 | 11664 | 2026-04-16
SARSI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719001061/IF/IAY/6041127 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114029688 | Ongoing | 27000 | 8532 | 2026-06-18
SARSI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719001061/IF/IAY/6041208 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114057239 | Ongoing | 27000 | 3132 | 2026-04-12
SARSI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719001061/IF/IAY/6041288 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114903675 | Ongoing | 27000 | 5400 | 2026-06-20
SARSI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719001061/IF/IAY/6041487 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106134303 | Ongoing | 27000 | 14796 | 2026-04-14
SARSI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719001061/IF/IAY/6041488 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106134529 | Ongoing | 27000 | 3300 | 2026-02-19
SARSI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719001061/IF/IAY/6041654 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150582351 | Ongoing | 27000 | 3600 | 2026-02-19
SARSI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719001061/IF/IAY/6041705 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113502201 | Ongoing | 27000 | 0 | 2026-02-19
SARSI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719001061/IF/IAY/6041914 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114030261 | Ongoing | 27000 | 14400 | 2026-02-19
SARSI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719001061/IF/IAY/6041951 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113502646 | Ongoing | 27000 | 23424 | 2026-04-21
SARSI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719001061/IF/IAY/6042045 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114903768 | Ongoing | 27000 | 12366 | 2026-06-18
SARSI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719001061/IF/IAY/6042641 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113505081 | Ongoing | 27000 | 11664 | 2026-05-27
SARSI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719001061/IF/IAY/6042689 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114029754 | Ongoing | 27000 | 5400 | 2026-06-20
SARSI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719001061/IF/IAY/6043106 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114057104 | Ongoing | 27000 | 1566 | 2026-06-18
SARSI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719001061/IF/IAY/6043107 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114057140 | Ongoing | 27000 | 5400 | 2026-02-19
SARSI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719001061/IF/IAY/6043108 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114057153 | Ongoing | 27000 | 5400 | 2026-06-20
SARSI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719001061/IF/IAY/6043109 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114057164 | Ongoing | 27000 | 6600 | 2026-02-19
SARSI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719001061/IF/IAY/6043134 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114024312 | Ongoing | 27000 | 17928 | 2026-04-14
SARSI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719001061/IF/IAY/6231093 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114027544 | Ongoing | 27000 | 7200 | 2026-02-19
SARSI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719001061/IF/IAY/6231094 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113984877 | Ongoing | 27000 | 0 | 2026-02-19
SARSI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719001061/IF/IAY/6231340 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106040020 | Ongoing | 27000 | 12600 | 2026-02-19
SARSI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719001061/IF/IAY/6231353 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113502590 | Ongoing | 27000 | 13932 | 2026-06-23
SARSI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719001061/IF/IAY/6231533 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113501925 | Approved | 27000 | 0 | 2026-02-19
SARSI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719001061/IF/IAY/6231755 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150582137 | Ongoing | 23490 | 0 | 2026-04-27
SARSI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719001061/IF/IAY/6231756 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150582239 | Approved | 27000 | 0 | 2026-02-19
SARSI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719001061/IF/IAY/6231864 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119650009 | Ongoing | 27000 | 7200 | 2026-02-19
SARSI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719001061/IF/IAY/6231900 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114903555 | Ongoing | 27000 | 7200 | 2026-02-19
SARSI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719001061/IF/IAY/6231902 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114903637 | Ongoing | 23490 | 10800 | 2026-05-05
SARSI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719001061/IF/IAY/6231981 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114057207 | Ongoing | 27000 | 14400 | 2026-02-19
SARSI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719001061/IF/IAY/6232328 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114944773 | Ongoing | 27000 | 0 | 2026-02-19
SARSI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719001061/IF/IAY/6232404 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124198163 | Ongoing | 27000 | 14400 | 2026-02-19
SARSI | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719001061/RC/22012034664590 — नाली निर्माण कार्य केशरसिह के मकान से नाला व होकमसिह के मकान से नाला तक | Closed | 49627 | 0 | 2023-08-15
SARSI | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719001061/RC/22012034664601 — सी.सी रोड निर्माण कार्य केशरसिह के मकान से नाला की ओर सारसी | Completed | 49495 | 48357 | 2024-07-12 | 2024-11-25
SARSI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1719001061/WC/22012035054732 — डग आऊट पौण्ड निर्माण कार्य नवल जी के खेत के पास सारसी | Completed | 385261.22 | 332313.49 | 2023-06-17 | 2024-10-28
SARSI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1719001061/WC/22012035174870 — सामुदायिक डगआउट पोण्ड निर्माण कार्य चन्द्रर के खेत के पास सारसी | Completed | 568588.78 | 528167.95 | 2024-03-14 | 2024-11-05
SARSI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1719001061/WC/22012035235934 — परकोलेसन टेंक शिवलाल राघुसिह के खेत के पास सारसी | Completed | 199490.09 | 160155 | 2025-02-28 | 2025-06-14
SARSI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1719001061/WC/22012035262291 — JGSA 2025 रिचार्ज स्ट्रक्चर सामुदायिक कूप स्वच्छता परिसर के पास सारसी | Physically Completed | 25899.46 | 24094.94 | 2025-04-30 | 2026-04-15
SARSI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1719001061/WH/22012034939812 — तालाब जीर्णोद्वार कार्य शिवलाल के खेत के पास सारसी | Completed | 211196.49 | 204014.8 | 2024-06-14 | 2025-07-14
SARSI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1719001061/WH/22012034944169 — JGSA 2025 तालाब मरम्मत कार्य भगवान जमादार के खेत के पास सारसी | Completed | 230940.9 | 222859.34 | 2025-04-29 | 2026-02-02
PALDA | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1719001/LD/1पालडा P6 — वनवर्धन कार्य पालडा P6 (2009-2010) | Completed | 151000 | 76660 | 2010-03-02 | 2011-08-24
GUNDLAWADA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1719001/LD/1रीछडीया P — वनवर्धन कार्य रीछडीया P3 (2009-2010) | Completed | 158000 | 39798 | 2010-06-01 | 2011-08-24
SOYATKHURD | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1719001/LD/1वनवर्धन क — वनवर्धन कार्य सोयतखुर्द P2 (2009-2010) | Deleted | 34000 | 0 | 2009-03-01
KHANOTA | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1719001/LD/खनोटा P9 — वनवर्धन कार्य खनोटा P9,10(2009-2010) | Completed | 30000 | 1400 | 2010-02-02 | 2011-08-24
PALDA | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1719001/LD/पालडा P7 — वनवर्धन कार्य पालडा P7 (2009-2010) | Completed | 222000 | 113164 | 2010-03-16 | 2011-08-24
SOYATKHURD | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1719001/LD/वनवर्धन का — वनवर्धन कार्य सोयतखुर्द P1 (2009-2010) | Completed | 453000 | 251048 | 2010-02-23 | 2011-08-24
SALARIYA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1719001/WC/22012034781112 — ग्राम सालरीया मे स्‍थिति गोअभ्‍यारण के पास दुपीया का तालाब निमार्ण | Closed | 9101000 | 0 | 2021-04-14
KANTHALIYAKHEDA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Raising of Nursery for Community / Raising of Nursery for Community | Nursery Development | 1719/DP/22012034576856 — नर्सरी विस्‍तार कार्य शासकीय संजय नर्सरी ग्राम कंठालीया | Ongoing | 5266000 | 67018.52 | 2023-12-14
PALDA | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1719/RC/22012034154135 — Sadak Nirman | Completed | 4433000 | 367006 | 2012-03-01 | 2016-09-15
LODHAKHEDI | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1719/RC/22012034154136 — Sadak Nirman | Completed | 14143000 | 716076 | 2012-03-09 | 2016-09-02
LODHAKHEDI | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1719/RC/22012034154137 — Sadak Nirman | Completed | 11830000 | 832413 | 2012-03-01 | 2016-09-02
PARSULYAKALAN | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1719/RC/22012034154138 — sadak Nirman | Completed | 5322000 | 556849 | 2012-02-20 | 2016-09-02
AMARKOT | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Repair & maint of Gravel Road Roads for Comm / Repair and maintenance of Gravel Road Roads for Community | Repair & maint of Road | 1719/RC/22012034611222 — मुख्यमंत्री ग्राम सडक योजना ग्रेवल मार्ग में संधारण कार्य इन्दौर कोटा रोड से त्रिलोकपुरा | Completed | 1319000 | 478772 | 2022-03-26 | 2026-06-05
GUNDLAWADA | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1719/RC/BM/100/SUS — Sadak Nirman | Completed | 4767000 | 29000 | 2010-11-22 | 2016-09-02
KOTHADA | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1719/RC/BM/101/SUS — Sadak Nirman | Completed | 5564000 | 4524577.8 | 2010-11-21 | 2016-09-02
LALAKHEDI | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1719/RC/BM/102/SUS — Sadak Nirman | Completed | 3368000 | 2085954 | 2010-11-20 | 2016-09-02
KHEJDAKHEDI | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1719/RC/BM/103/SUS — Sadak Nirman | Completed | 1700000 | 1121711.6 | 2010-10-25 | 2016-09-02
KOTHADA | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1719/RC/BM/104/SUS — Sadak Nirman | Completed | 2344000 | 1325420 | 2010-10-24 | 2016-09-02
SHRIPATPURA | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1719/RC/BM/105/SUS — Sadak Nirman | Completed | 2183000 | 1706542.6 | 2011-02-26 | 2016-09-02
AMARKOT | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1719/RC/BM/106/SUS — SADAK NIRMAN | Completed | 8188000 | 4880375 | 2011-01-01 | 2016-09-02
GUNDLAWADA | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Bitumen Top / Construction of Bitumen Top Roads for Community | Construction of Road and Culvert | 1719/RC/BM/201/GLD — Sadak Nirman | Deleted | 0 | 0 | 2010-05-05
GUNDLAWADA | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1719/RC/BM/210/GLD — Sadak Nirman | Completed | 4767000 | 3187654.26 | 2011-03-22 | 2016-09-02
SALARIYA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1719/WC/22012034785480 — CTR गो अभयारण्य के पास दुपिया का तालाब | Ongoing | 9101000 | 3457858.51 | 2021-07-18
KARKDIYASOYAT | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | कुप निर्माण कार्य रामलाल फत्‍ता — कुप निर्माण कार्य रामलाल फत्‍ता | Completed | 107464 | 0 | 2008-05-11 | 2016-08-24
KARKDIYASOYAT | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | कूप निर्माण कार्य दुर्गालाल फत्‍ता — कूप निर्माण कार्य दुर्गालाल फत्‍ता | Completed | 107464 | 42136.36 | 2008-05-11 | 2011-03-28
KARKDIYASOYAT | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Desilting / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | तालाब गहरीकरण कार्य करकडिया सोयत — तालाब गहरीकरण कार्य करकडिया सोयत | Deleted | 99481 | 550 | 2008-04-02
SALARIYA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य अंदरसिंह अमरसिंह — नंदन फलोद्यान कार्य अंदरसिंह अमरसिंह | Completed | 190627 | 132068.24 | 2008-08-13 | 2013-03-31
SALARIYA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य अंदरसिंह नाथूसिंह — नंदन फलोद्यान कार्य अंदरसिंह नाथूसिंह | Completed | 190627 | 127778.34 | 2008-08-13 | 2013-03-31
DEHARIYASUSNER | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य अमरसिंह भंवरसिंह — नंदन फलोद्यान कार्य अमरसिंह भंवरसिंह | Completed | 190627 | 150602.84 | 2008-08-12 | 2012-12-16
MEHATPUR | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य ईश्‍वरसिंह कालूसिंह — नंदन फलोद्यान कार्य ईश्‍वरसिंह कालूसिंह | Deleted | 190627 | 30572.84 | 2008-08-08
MALANWASA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य उकार भेरू — नंदन फलोद्यान कार्य उकार भेरू | Completed | 190627 | 45523.84 | 2008-08-14 | 2012-12-12
NAHARKHEDA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य उदा हीराजी — नंदन फलोद्यान कार्य उदा हीराजी | Deleted | 190627 | 9533.84 | 2008-08-27
KAYRA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य करणसिंह — नंदन फलोद्यान कार्य करणसिंह | Completed | 190627 | 17073.11 | 2008-08-17 | 2012-12-18
SALARIYA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य करणसिंह अनारसिंह — नंदन फलोद्यान कार्य करणसिंह अनारसिंह | Completed | 190627 | 138630.34 | 2008-08-13 | 2013-03-31
BAMNIYAKHEDI | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य करणसिंह कालूसिंह — नंदन फलोद्यान कार्य करणसिंह कालूसिंह | Deleted | 190627 | 12128.84 | 2008-09-03
BAMNIYAKHEDI | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य करणसिंह हरीसिंह जी — नंदन फलोद्यान कार्य करणसिंह हरीसिंह जी | Deleted | 190627 | 9932 | 2008-09-03
KHERANA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य करणसिंह हिन्‍दुसिंह — नंदन फलोद्यान कार्य करणसिंह हिन्‍दुसिंह | Completed | 190627 | 82548.04 | 2008-08-15 | 2012-12-16
LODHAKHEDI | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य कान्‍हा उकारजी — नंदन फलोद्यान कार्य कान्‍हा उकारजी | Completed | 190627 | 16860.84 | 2008-08-13 | 2012-12-12
MEHATPUR | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य कालुसिंह अमरसिंह — नंदन फलोद्यान कार्य कालुसिंह अमरसिंह | Deleted | 190627 | 23735.84 | 2008-08-19
SALARIYA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य कालुसिंह लालसिंह — नंदन फलोद्यान कार्य कालुसिंह लालसिंह | Completed | 190627 | 131634.5 | 2008-09-03 | 2013-03-31
DIWANKHEDI | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य कालूराम लक्ष्‍मणसिंह — नंदन फलोद्यान कार्य कालूराम लक्ष्‍मणसिंह | Completed | 190627 | 67976.04 | 2008-08-14 | 2012-12-11
MEHATPUR | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य कालू रामाजी — नंदन फलोद्यान कार्य कालू रामाजी | Deleted | 190627 | 23735.84 | 2008-08-18
BAMNIYAKHEDI | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य कालूसिंह धुलाजी — नंदन फलोद्यान कार्य कालूसिंह धुलाजी | Completed | 190627 | 92803.84 | 2008-08-10 | 2012-12-15
PAYALI | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य कैलाशचंद मांगीलाल — नंदन फलोद्यान कार्य कैलाशचंद मांगीलाल | Completed | 190627 | 56527.79 | 2008-08-13 | 2012-12-18
SALARIYA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य गंगाबाई करणसिंह — नंदन फलोद्यान कार्य गंगाबाई करणसिंह | Completed | 190627 | 128193.34 | 2008-08-13 | 2013-03-31
SALARIYA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य गंगाबाई मांगीलाल — नंदन फलोद्यान कार्य गंगाबाई मांगीलाल | Completed | 190627 | 121190.34 | 2008-08-13 | 2013-03-31
SALARIYA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य गंगाबाई लालसिंह — नंदन फलोद्यान कार्य गंगाबाई लालसिंह | Completed | 190627 | 132491.24 | 2008-08-13 | 2013-03-31
PAYALI | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य गंगाराम जगन्‍नाथ — नंदन फलोद्यान कार्य गंगाराम जगन्‍नाथ | Completed | 190627 | 26669.78 | 2008-08-13 | 2012-12-18
KHANOTA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य गंगाराम लालंसिंह — नंदन फलोद्यान कार्य गंगाराम लालंसिंह | Deleted | 190627 | 21319.67 | 2008-08-16
KAYRA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य गजराजसिंह — नंदन फलोद्यान कार्य गजराजसिंह | Completed | 190627 | 70133.93 | 2008-08-17 | 2012-12-18
ANTRALIYA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य गिरीराज भागीरथ — नंदन फलोद्यान कार्य गिरीराज भागीरथ | Completed | 190627 | 67657.84 | 2008-09-03 | 2013-02-28
PAYALI | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य गिरीश रामचंदर — नंदन फलोद्यान कार्य गिरीश रामचंदर | Deleted | 190627 | 0 | 2008-04-01
DEHARIYASUSNER | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य गीताबाई लालसिंह — नंदन फलोद्यान कार्य गीताबाई लालसिंह | Completed | 190627 | 146389.84 | 2008-08-12 | 2012-12-16
PAYALI | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य गीताबाई हरीनारायण — नंदन फलोद्यान कार्य गीताबाई हरीनारायण | Completed | 190627 | 53129.74 | 2008-08-27 | 2012-12-18
KAWARAKHEDI | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य गुमानसिंह कालुसिंह — नंदन फलोद्यान कार्य गुमानसिंह कालुसिंह | Completed | 190627 | 27497.84 | 2008-08-19 | 2012-12-14
KHANOTA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य गोपाल हीरालाल — नंदन फलोद्यान कार्य गोपाल हीरालाल | Deleted | 190627 | 26519.67 | 2008-08-16
SHYAMPURA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य गोवर्धन भेरूलाल — नंदन फलोद्यान कार्य गोवर्धन भेरूलाल | Completed | 190627 | 42608.05 | 2008-08-13 | 2012-12-13
DEHARIYASUSNER | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य चंदरलाल धुलाजी — नंदन फलोद्यान कार्य चंदरलाल धुलाजी | Completed | 190627 | 155104.84 | 2008-08-12 | 2012-12-16
SALARIYA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य चंदरसिंह अंदरसिंह — नंदन फलोद्यान कार्य चंदरसिंह अंदरसिंह | Completed | 190627 | 123992.34 | 2008-08-13 | 2013-03-31
DEHARIYASUSNER | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य चेनसिंह दुलेसिंह — नंदन फलोद्यान कार्य चेनसिंह दुलेसिंह | Completed | 190627 | 153710.8 | 2008-08-12 | 2012-12-16
DEHARIYASUSNER | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य जालमसिंह नाहरसिंह — नंदन फलोद्यान कार्य जालमसिंह नाहरसिंह | Completed | 190627 | 152994.84 | 2008-08-12 | 2012-12-16
DEHARIYASUSNER | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य जितेन्‍द्रसिंह अर्जुनसिंह — नंदन फलोद्यान कार्य जितेन्‍द्रसिंह अर्जुनसिंह | Completed | 190627 | 148258.84 | 2008-08-12 | 2012-12-16
SALARIYA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य जीतनारायण दुलेसिंह — नंदन फलोद्यान कार्य जीतनारायण दुलेसिंह | Completed | 190627 | 126986.34 | 2008-08-13 | 2013-03-31
DEHARIYASUSNER | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य ञीभुवन बनेसिंह — नंदन फलोद्यान कार्य ञीभुवन बनेसिंह | Completed | 190627 | 152727.82 | 2008-08-12 | 2012-12-16
PAYALI | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य तुलसीराम गंगाधर — नंदन फलोद्यान कार्य तुलसीराम गंगाधर | Deleted | 190627 | 0 | 2008-04-01
PAYALI | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य दिनेश बंशीलाल — नंदन फलोद्यान कार्य दिनेश बंशीलाल | Completed | 190627 | 55690.79 | 2008-08-27 | 2012-12-18
SHYAMPURA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य दिनेश लालचंद — नंदन फलोद्यान कार्य दिनेश लालचंद | Completed | 190627 | 38103.05 | 2008-08-13 | 2012-12-13
PAYALI | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य देवीलाल हीरालाल — नंदन फलोद्यान कार्य देवीलाल हीरालाल | Completed | 190627 | 52535.74 | 2008-08-27 | 2012-12-18
MEHATPUR | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य देवीसिंह रूगनाथसिंह — नंदन फलोद्यान कार्य कालुसिंह देवीसिंह रूगनाथसिंह | Deleted | 190627 | 30382.84 | 2008-08-18
MALANWASA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य धनसिंह कालूजी — नंदन फलोद्यान कार्य धनसिंह कालूजी | Deleted | 176250.8 | 0 | 2008-04-01
MALANWASA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य धनसिंह घीसुजी — नंदन फलोद्यान कार्य धनसिंह घीसुजी | Completed | 190627 | 45362.04 | 2008-08-12 | 2012-12-12
DEHARIYASUSNER | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य धर्मेन्‍द्रसिंह कालुसिंह — नंदन फलोद्यान कार्य धर्मेन्‍द्रसिंह कालुसिंह | Completed | 190627 | 140809.82 | 2008-08-12 | 2012-12-16
DEHARIYASUSNER | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य नटवरसिंह शिवसिंह — नंदन फलोद्यान कार्य नटवरसिंह शिवसिंह | Completed | 190627 | 139688.84 | 2008-08-12 | 2012-12-16
SALARIYA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य नरवरसिंह परथीसिंह — नंदन फलोद्यान कार्य नरवरसिंह परथीसिंह | Completed | 190627 | 127779.34 | 2008-08-13 | 2013-03-31
SHYAMPURA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य नरवरसिंह भगवानसिंह — नंदन फलोद्यान कार्य नरवरसिंह भगवानसिंह | Completed | 190627 | 42673.05 | 2008-08-13 | 2012-12-13
DEHARIYASUSNER | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य नारायण मांगुसिंह — नंदन फलोद्यान कार्य नारायण मांगुसिंह | Completed | 190627 | 153595.34 | 2008-08-12 | 2012-12-16
SALARIYA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य नारायणसिंह करणसिंह — नंदन फलोद्यान कार्य नारायणसिंह करणसिंह | Completed | 190627 | 127778.34 | 2008-08-13 | 2013-03-31
MALANWASA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य नारायणसिंह चंदर — नंदन फलोद्यान कार्य नारायणसिंह चंदर | Completed | 190627 | 44996.84 | 2008-08-14 | 2012-12-12
SALARIYA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य नारायणसिंह भगवानसिंह — नंदन फलोद्यान कार्य नारायणसिंह भगवानसिंह | Completed | 190627 | 123512.34 | 2008-08-13 | 2013-03-31
MEHATPUR | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | नंदन फलोद्यान कार्य नारायणसिंह हरीसिंह — नंदन फलोद्यान कार्य नारायणसिंह हरीसिंह | Deleted | 190627 | 3523 | 2008-08-19
KHANOTA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य नैनसिंह भेरूसिंह — नंदन फलोद्यान कार्य नैनसिंह भेरूसिंह | Deleted | 190627 | 32586.67 | 2008-08-16
SALARIYA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य पर्वतसिंह दाणुसिंह बालुसिंह — नंदन फलोद्यान कार्य पर्वतसिंह दाणुसिंह बालुसिंह | Completed | 190627 | 122238.34 | 2008-08-13 | 2013-03-31
SALARIYA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोंद्यान कार्य पर्वतसिंह शिवलाल — नंदन फलोंद्यान कार्य पर्वतसिंह शिवलाल | Completed | 190627 | 130946.34 | 2008-08-13 | 2013-03-31
SALARIYA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य पीरूलाल मोतीलाल — नंदन फलोद्यान कार्य पीरूलाल मोतीलाल | Completed | 190627 | 124115.34 | 2008-08-13 | 2013-03-31
KHANOTA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य पुरालाल नाथूलाल — नंदन फलोद्यान कार्य पुरालाल नाथूलाल | Deleted | 190627 | 26434.74 | 2008-08-16
KHANOTA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य पूरा अमरा — नंदन फलोद्यान कार्य पूरा अमरा | Deleted | 190627 | 30763.67 | 2008-08-16
MALANWASA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य फुलीबाई रामसिंह — नंदन फलोद्यान कार्य फुलीबाई रामसिंह | Completed | 190627 | 45364.04 | 2008-08-14 | 2012-12-12
LODHAKHEDI | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य बद्रीलाल भुवान — नंदन फलोद्यान कार्य बद्रीलाल भुवान | Completed | 190627 | 17214.74 | 2008-08-19 | 2012-12-12
DEHARIYASUSNER | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य बनेसिंह पर्वतसिंह — नंदन फलोद्यान कार्य बनेसिंह पर्वतसिंह | Completed | 190627 | 147940.73 | 2008-08-12 | 2012-12-16
PAYALI | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य बाइसाथ भंवरलाल — नंदन फलोद्यान कार्य बाबुलाल भंवरलाल | Completed | 190627 | 56670.74 | 2008-09-03 | 2012-12-18
NAHARKHEDA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य बापूलाल पुराजी — नंदन फलोद्यान कार्य बापूलाल पुराजी | Completed | 190627 | 13927.84 | 2008-08-27 | 2012-12-12
SALARIYA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य बालुसिंह करणसिंह — नंदन फलोद्यान कार्य बालुसिंह करणसिंह | Completed | 190627 | 120422.34 | 2008-08-13 | 2013-03-31
MEHATPUR | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य बालुसिंह देवीसिंह — नंदन फलोद्यान कार्य बालुसिंह देवीसिंह मेहतपुर | Deleted | 190627 | 34095.84 | 2008-08-08
MEHATPUR | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | नंदन फलोद्यान कार्य बालूसिंह देवीसिंह — नंदन फलोद्यान कार्य बालूसिंह देवीसिंह | Deleted | 190627 | 8135.84 | 2008-08-19
KHANOTA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य भंवरकुंवर गो‍कलसिंह — नंदन फलोद्यान कार्य भंवरकुंवर गो‍कलसिंह | Deleted | 190627 | 19689.67 | 2008-08-16
KHANOTA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य भंवरकुंवर नेपालसिंह — नंदन फलोद्यान कार्य भंवरकुंवर नेपालसिंह | Deleted | 190627 | 29989.67 | 2008-08-16
KAYRA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य भंवरसिंह — नंदन फलोद्यान कार्य भंवरसिंह | Completed | 190627 | 71269.11 | 2008-08-17 | 2012-12-18
SALARIYA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य भेरू पुराजी — नंदन फलोद्यान कार्य भेरू पुराजी | Completed | 190627 | 125456.34 | 2008-08-13 | 2013-03-31
KAWARAKHEDI | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य भेरूसिंह परथी — नंदन फलोद्यान कार्य भेरूसिंह परथी | Completed | 190627 | 26447.84 | 2008-08-19 | 2012-12-15
LODHAKHEDI | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोंद्यान कार्य मदनलाल उकारजी — नंदन फलोंद्यान कार्य मदनलाल उकारजी | Completed | 190627 | 16160.84 | 2008-08-11 | 2012-12-12
MEHATPUR | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य मांगीलाल नंदराम — नंदन फलोद्यान कार्य मांगीलाल नंदराम | Deleted | 190627 | 8164.74 | 2008-08-18
KHANOTA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य माधू अमराजी — नंदन फलोद्यान कार्य माधू अमराजी | Completed | 190627 | 66339.27 | 2008-08-16 | 2012-12-13
SHYAMPURA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य मानसिंह कालुसिंह — नंदन फलोद्यान कार्य मानसिंह कालुसिंह श्‍यामपुरा | Completed | 190627 | 42539.05 | 2008-09-03 | 2012-12-13
BAMNIYAKHEDI | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य मानसिंह कालूसिंह — नंदन फलोद्यान कार्य मानसिंह कालूसिंह | Completed | 190627 | 14548.84 | 2008-08-13 | 2012-12-11
DEHARIYASUSNER | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य मानसिंह पर्वतसिंह — नंदन फलोद्यान कार्य मानसिंह पर्वतसिंह | Completed | 190627 | 149684.84 | 2008-08-12 | 2012-12-16
KHANOTA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य मानसिंह लालसिंह — नंदन फलोद्यान कार्य मानसिंह लालसिंह | Deleted | 190627 | 28478.67 | 2008-08-16
BAMNIYAKHEDI | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य रतनसिंह भोरूसिंह — नंदन फलोद्यान कार्य रतनसिंह भोरूसिंह | Completed | 190627 | 50489.84 | 2008-08-16 | 2012-12-15
PAYALI | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य रामगोपाल देवीलालजी — नंदन फलोद्यान कार्य रामगोपाल देवीलालजी | Completed | 190627 | 55000.79 | 2008-08-13 | 2012-12-18
DEHARIYASUSNER | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य रामनाथसिंह गुलाबसिंह — नंदन फलोद्यान कार्य रामनाथसिंह गुलाबसिंह | Completed | 190627 | 151444.84 | 2008-08-12 | 2012-12-16
PAYALI | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य रामनारायण फुलचंद — नंदन फलोद्यान कार्य रामनारायण फुलचंद | Completed | 190627 | 57419.65 | 2008-08-27 | 2012-12-18
PAYALI | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य रामलाल कीशन — नंदन फलोद्यान कार्य रामलाल कीशन | Deleted | 190627 | 0 | 2008-04-01
SALARIYA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य रामलाल परथी — नंदन फलोद्यान कार्य रामलाल परथी | Completed | 190627 | 122463.34 | 2008-08-13 | 2013-03-31
CHHAPARIYA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य रामलाल माधु — नंदन फलोद्यान कार्य रामलाल माधु | Completed | 190627 | 96243.84 | 2008-08-27 | 2012-12-11
MEHATPUR | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य रामसिंह दुलेसिंह — नंदन फलोद्यान कार्य रामसिंह दुलेसिंह | Deleted | 190627 | 23611.84 | 2008-08-13
BAMNIYAKHEDI | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य रामसिंह धुलाजी — नंदन फलोद्यान कार्य रामसिंह धुलाजी | Completed | 190627 | 100117.74 | 2008-08-13 | 2012-12-15
SALARIYA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य रामसिंह मोतीजी — नंदन फलोद्यान कार्य रामसिंह मोतीजी | Completed | 190627 | 130534.34 | 2008-08-13 | 2013-03-31
PAYALI | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य राम्रप्रसाद पन्‍नालाल — नंदन फलोद्यान कार्य राम्रप्रसाद पन्‍नालाल | Completed | 190627 | 54598.79 | 2008-08-27 | 2012-12-18
KHANOTA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य रूखमाकुंवर गजराजसिंह — नंदन फलोद्यान कार्य रूखमाकुंवर गजराजसिंह | Completed | 190627 | 65204.67 | 2008-08-16 | 2012-12-17
KHANOTA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य रोडीबाई अमरा — नंदन फलोद्यान कार्य रोडीबाई अमरा | Deleted | 190627 | 30570.57 | 2008-08-16
SALARIYA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य लक्ष्‍मण रामा रूपाजी — नंदन फलोद्यान कार्य लक्ष्‍मण रामा रूपाजी | Completed | 190627 | 127046.34 | 2008-08-13 | 2013-03-31
DEHARIYASUSNER | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य लक्ष्‍मणसिंह अर्जुनसिंह — नंदन फलोद्यान कार्य लक्ष्‍मणसिंह अर्जुनसिंह | Completed | 190627 | 144248.84 | 2008-08-12 | 2012-12-16
CHHAPARIYA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य लालसिंह शिवसिंह — नंदन फलोद्यान कार्य लालसिंह शिवसिंह | Completed | 190627 | 95845.84 | 2008-08-27 | 2012-12-11
ANTRALIYA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य विक्रम बालचंद — नंदन फलोद्यान कार्य विक्रम बालचंद | Completed | 190627 | 58782.84 | 2008-09-03 | 2013-02-28
KHANOTA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य विष्‍णु भगवानसिंह — नंदन फलोद्यान कार्य विष्‍णु भगवानसिंह | Completed | 190627 | 68671.67 | 2008-08-16 | 2012-12-17
PAYALI | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य शांतिबाई हीरालाल — नंदन फलोद्यान कार्य शांतिबाई हीरालाल | Completed | 190627 | 53297.79 | 2008-08-27 | 2012-12-18
DEHARIYASUSNER | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य शिवलाल कालूसिंह — नंदन फलोद्यान कार्य शिवलाल कालूसिंह | Deleted | 190627 | 18910.99 | 2008-10-30
SALARIYA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य शिवलाल रूगनाथ — नंदन फलोद्यान कार्य शिवलाल रूगनाथ | Completed | 190627 | 122970.34 | 2008-08-13 | 2013-03-31
SALARIYA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य शिवलाल लालसिंह — नंदन फलोद्यान कार्य शिवलाल लालसिंह | Completed | 190627 | 122419.34 | 2008-08-13 | 2013-03-31
KHANOTA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य श्‍यामकुंवर भारतसिंह — नंदन फलोद्यान कार्य श्‍यामकुंवर भारतसिंह | Deleted | 190627 | 33407.63 | 2008-08-16
DEHARIYASUSNER | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य सजनसिंह रूगनाथसिंह — नंदन फलोद्यान कार्य सजनसिंह रूगनाथसिंह | Completed | 190627 | 134009.8 | 2008-08-13 | 2012-12-16
BAMNIYAKHEDI | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य सोहनबाई गोकुलसिंह — नंदन फलोद्यान कार्य सोहनबाई गोकुलसिंह | Deleted | 190627 | 12157.74 | 2008-08-10
SALARIYA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य हरीराम चंदरसिंह — नंदन फलोद्यान कार्य हरीराम चंदरसिंह | Completed | 190627 | 127171.84 | 2008-08-13 | 2013-03-31
ANTRALIYA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलोद्यान कार्य हैमराज गिरीराज — नंदन फलोद्यान कार्य हैमराज गिरीराज | Completed | 190627 | 50190.84 | 2008-09-03 | 2013-03-05
PAYALI | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नंदन फलो्द्यान कार्य गिरीराज लक्ष्‍तीनारायण — नंदन फलो्द्यान कार्य गिरीराज लक्ष्‍तीनारायण | Completed | 190627 | 52908.79 | 2008-08-13 | 2012-12-18
KHANOTA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | वनवर्धन कार्य खनौटा — वनवर्धन कार्य खनौटा | Deleted | 11890 | 0 | 2008-09-01
PALDA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | वनवर्धन कार्य पालडा p7 — वनवर्धन कार्य पालडा p7 | Completed | 187000 | 17094 | 2008-09-01 | 2011-02-04
SOYATKHURD | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | वनवर्धन कार्य सोयतखुर्द — वनवर्धन कार्य सोयतखुर्द P2 | Completed | 245310 | 12821 | 2008-09-09 | 2011-02-04
PAYALI | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | ाल — कूप निर्माण कार्य देवीलाल हीरालाल | Deleted | 0 | 0 | 2008-04-01