## Work List
Exported on: 2026-08-26 19:54:09
Filters applied:
Data source: MGNREGA
District: SHAJAPUR
Block: SHUJALPUR
Panchayat: MOHAMMADOURPAVADIYA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
| 2019-2020 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1719007051/AV/22012034465628 — Goshala Nirman work Mohmmadourpaviday me | Completed | 2771628.29 | 2748131.7 | 2019-07-12 | 2021-01-30
| 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1719007051/AV/22012034598033 — DYNING HALL ARRANGMENT MIDDLE SCHOOL GP Mohammdourpavadiya | Closed | 0 | 0 | 2021-08-18
| 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1719007051/AV/22012034628115 — आंगनवाडी भवन निर्माण कार्य मो.पवाडीया | Closed | 500000 | 0 | 2022-08-16
| 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1719007051/AV/22012034661932 — आंगनवाड़ी भवन बाउंड्री वॉल निर्माण कार्य ग्राम मोहम्मदपुर पवाडीया | Ongoing | 500000 | 144422 | 2024-11-28
| 2015-2016 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | AWC / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1719007051/AV/2808 — Aanganbadi/Other Rural Infrastructure,SHUJALPUR | Completed | 180000 | 180159 | 2015-06-15 | 2016-06-18
| 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1719007051/DP/22012034432780 — Sarvjanik Kup Nirman Work Pani ki Tjanki ke pas | Closed | 535000 | 0 | 2018-09-01
| 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1719007051/DP/22012034455415 — Gaushala Varcharopan work Mohmmad pawdiya | Closed | 0 | 0 | 2019-07-25
| 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1719007051/DP/22012034481709 — Sarvjanik Kup Nirman work Gaushala parisar me | Closed | 0 | 0 | 2019-08-15
| 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1719007051/DP/22012034520646 — Samudayik Kup Nirman Work Gaushala ke pas | Completed | 567610.07 | 579419 | 2020-11-11 | 2021-09-13
| 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Coastal Line Plantation-Horticulture-Community / Along the coast Line Plantation of Horticulture Trees for Community | Plantation | 1719007051/DP/22012034560894 — Samudayik Vraksharopan Amrit Sarovar GP Moh. Pavadiya | Closed | 230120.31 | 0 | 2022-04-14
| 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1719007051/DP/22012034602837 — वसुधा वंदन मेरी माटी मेरा देश ग्राम पंचायत मो.पवाडीया | Closed | 55847.4 | 0 | 2023-09-27
| 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719007051/IF/22012034336173 — HITESHI KAPILDHARA KUP/ KHET TALAB OF SUMAN BAI W/o RAMESHCHAND | Closed | 234600 | 0 | 2017-04-14
| 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719007051/IF/22012034350200 — plantation gp mo pawadiya road side kelash malviya | Completed | 335000 | 21128 | 2017-07-07 | 2024-10-25
| 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719007051/IF/22012034352805 — PLANTATION GP MO PWADIYA | Deleted | 335000 | 0 | 2017-04-14
| 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719007051/IF/22012034454341 — HITESHI KAPIL DHARA GYAYATRI BAI MOTILAL | Completed | 214200 | 195090 | 2019-02-05 | 2020-03-10
| 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719007051/IF/22012034454462 — HITESHI KAPILDHARA KUP NIRMAN ARJUN SIMGH NAR SINGH | Completed | 214200 | 198078 | 2019-02-05 | 2020-03-10
| 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719007051/IF/22012034459519 — Hitesh kalipdhra kup nirman Tarachandra/kuwarlal | Completed | 214200 | 202512 | 2019-02-20 | 2020-03-10
| 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719007051/IF/22012034459673 — Hiteshi kapildhra kup nirman work Hemraj/Bapulal | Completed | 214200 | 215676 | 2019-03-05 | 2020-08-01
| 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719007051/IF/22012034466998 — हितेषी कपिलधारा कूप निर्माण लाडसिह/भेरूलाल | Completed | 214200 | 198996 | 2019-03-05 | 2020-08-01
| 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1719007051/IF/22012034471484 — Khet Talab nirman work Santosh /shiv narayan | Closed | 295000 | 0 | 2019-01-25
| 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1719007051/IF/22012034471494 — Khet Talab Nirman work Devbaksh /Motilal | Closed | 295000 | 0 | 2019-01-25
| 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1719007051/IF/22012034472055 — Khet Talab Nirman work Premnarayan /Gangaram | Closed | 295000 | 0 | 2019-01-25
| 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1719007051/IF/22012034579639 — Khet samtlikaran work mo. Pavdiys | Deleted | 0 | 0 | 2020-04-01
| 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1719007051/IF/22012034589193 — lAND Levellingh@Shaping Work Shokin Vishnuprasad | Closed | 0 | 0 | 2020-07-01
| 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1719007051/IF/22012034764907 — Khet Talab nirman work Shetan bai -Babulal | Completed | 307568.12 | 270546 | 2021-06-05 | 2022-08-26
| 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1719007051/IF/22012034765341 — Khet Talab Nirman Work Gopal bai- Khushilal | Completed | 307568.12 | 185047 | 2021-05-31 | 2022-08-26
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719007051/IF/22012034956590 — संयुक्त कपिलधारा कूप ओमप्रकाश पिता छगन लाल एवं अन्य | Completed | 250732.62 | 199384.77 | 2022-04-11 | 2024-02-12
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719007051/IF/22012034956592 — संयुक्त कपिलधारा कूप देवराज पिता मूलचंद एवं अन्य | Completed | 250732.62 | 196352.28 | 2022-04-11 | 2023-08-25
| 2024-2025 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1719007051/IF/22012035206824 — नाडेप कार्य निर्माण | New | 0 | 0 | 2024-04-14
| 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1719007051/IF/22012035363084 — JGSA 2025 Dugwell recharge pit sarwajanik kup goshala ke pash mo pawadiya | Approved | 0 | 0 | 2025-04-18
| 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1719007051/IF/9993714816 — khet talab suman ramesh | Completed | 100000 | 68303 | 2016-06-03 | 2017-07-20
| 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Horticulture / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719007051/IF/9993720018 — pasusetvisunudaas tulsiram | Deleted | 0 | 0 | 2016-01-26
| 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Horticulture / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719007051/IF/9993720022 — pasusetvisuman bai ramesh chandra | Deleted | 0 | 0 | 2016-01-26
| 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Sericulture / Block Plantation of Sericulture Trees in fields for Individuals | Plantation | 1719007051/IF/9993720027 — pasushedsuman bai ramesh chand | Deleted | 0 | 0 | 2016-01-26
| 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Horticulture / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719007051/IF/9993720030 — pasushedsuman bai ramesh chand | Deleted | 0 | 0 | 2016-01-26
| 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007051/IF/IAY/1918446 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4228667 | Completed | 15660 | 15660 | 2018-08-13 | 2019-03-13
| 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007051/IF/IAY/1918821 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4079645 | Completed | 15660 | 15660 | 2018-08-13 | 2019-01-08
| 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007051/IF/IAY/1919080 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5101645 | Completed | 15660 | 15312 | 2018-08-13 | 2019-01-18
| 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007051/IF/IAY/1923615 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4563133 | Completed | 15660 | 15660 | 2018-08-13 | 2019-01-08
| 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007051/IF/IAY/1925482 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5467832 | Completed | 15660 | 15672 | 2018-08-13 | 2019-05-21
| 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007051/IF/IAY/2097689 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4079565 | Completed | 15840 | 15488 | 2019-07-14 | 2020-03-15
| 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007051/IF/IAY/2143207 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5091098 | Completed | 15840 | 14432 | 2019-07-14 | 2020-06-20
| 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007051/IF/IAY/2143830 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5107204 | Completed | 15840 | 15136 | 2019-07-14 | 2020-03-15
| 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007051/IF/IAY/2158659 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5479328 | Completed | 15840 | 14784 | 2019-07-14 | 2020-03-15
| 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007051/IF/IAY/2166368 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5680644 | Closed | 15840 | 0 | 2019-06-27
| 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007051/IF/IAY/332227 — Construction of IAY House -IAY REG. NO. MP1096303 | Completed | 15030 | 15128 | 2017-02-22 | 2018-04-21
| 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007051/IF/IAY/352061 — Construction of IAY House -IAY REG. NO. MP1130944 | Completed | 15030 | 15116 | 2017-02-22 | 2018-03-14
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007051/IF/IAY/3682529 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115118685 | Completed | 18360 | 17544 | 2022-07-16 | 2023-01-08
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007051/IF/IAY/3682545 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115119711 | Completed | 18360 | 16320 | 2022-07-16 | 2023-07-07
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007051/IF/IAY/3686126 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113758593 | Completed | 18360 | 18156 | 2022-07-16 | 2023-01-08
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007051/IF/IAY/3719734 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114000914 | Completed | 18360 | 16728 | 2022-07-16 | 2023-07-22
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007051/IF/IAY/3719737 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114001015 | Completed | 18360 | 13668 | 2022-07-16 | 2023-07-22
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007051/IF/IAY/3719738 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114001045 | Completed | 18360 | 17952 | 2022-07-16 | 2023-01-08
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007051/IF/IAY/3727375 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121359785 | Completed | 18360 | 18360 | 2022-07-16 | 2023-08-25
| 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007051/IF/IAY/378642 — Construction of IAY House -IAY REG. NO. MP1676436 | Completed | 15030 | 15460 | 2017-02-22 | 2018-03-08
| 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007051/IF/IAY/378824 — Construction of IAY House -IAY REG. NO. MP1696855 | Completed | 15030 | 15534 | 2018-11-15 | 2019-05-28
| 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007051/IF/IAY/378825 — Construction of IAY House -IAY REG. NO. MP1696863 | Completed | 15030 | 15460 | 2017-02-22 | 2018-03-14
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007051/IF/IAY/3807740 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114000444 | Completed | 18360 | 17952 | 2022-07-16 | 2023-01-08
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007051/IF/IAY/4222677 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114071360 | Completed | 18360 | 14304 | 2022-07-23 | 2023-07-07
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007051/IF/IAY/4226898 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118747302 | Completed | 18360 | 15708 | 2022-07-23 | 2023-08-25
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007051/IF/IAY/4228342 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121353661 | Completed | 18360 | 16932 | 2022-07-23 | 2023-07-07
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007051/IF/IAY/4242451 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114000281 | Completed | 18360 | 16728 | 2022-07-23 | 2023-07-07
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007051/IF/IAY/4678416 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126829804 | Ongoing | 21870 | 17928 | 2025-01-25
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007051/IF/IAY/4679799 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131391471 | Completed | 21870 | 20169 | 2024-11-04 | 2025-10-09
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007051/IF/IAY/4691101 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114071380 | Completed | 21870 | 20412 | 2024-11-04 | 2025-10-09
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007051/IF/IAY/4746078 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113782392 | Completed | 21870 | 17496 | 2024-12-25 | 2025-10-09
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007051/IF/IAY/4861851 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115118302 | Completed | 23490 | 19170 | 2024-12-25 | 2025-10-09
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007051/IF/IAY/5253836 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121364937 | Completed | 23490 | 20358 | 2025-04-17 | 2025-10-09
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007051/IF/IAY/5254036 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113758484 | Completed | 23490 | 20358 | 2025-04-17 | 2025-10-09
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007051/IF/IAY/5257972 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114071294 | Completed | 23490 | 18531 | 2025-04-17 | 2025-10-09
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007051/IF/IAY/5260636 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113782453 | Completed | 23490 | 20358 | 2025-04-17 | 2025-10-09
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007051/IF/IAY/5267109 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114071515 | Completed | 23490 | 19053 | 2025-04-17 | 2025-10-09
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007051/IF/IAY/5268838 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118723405 | Completed | 23490 | 19053 | 2025-04-17 | 2025-10-09
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007051/IF/IAY/5275037 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114071249 | Completed | 23490 | 20358 | 2025-04-17 | 2025-10-09
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007051/IF/IAY/5283617 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113758301 | Completed | 23490 | 20358 | 2025-04-17 | 2025-10-09
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007051/IF/IAY/5283764 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119857567 | Completed | 23490 | 14094 | 2025-04-17 | 2026-02-11
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007051/IF/IAY/5285668 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114000060 | Completed | 23490 | 20358 | 2025-04-17 | 2025-12-06
| 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007051/IF/IAY/528944 — Construction of IAY House -IAY REG. NO. MP2772827 | Completed | 15030 | 15460 | 2017-02-22 | 2018-03-14
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007051/IF/IAY/5292148 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118729425 | Completed | 23490 | 14094 | 2025-04-17 | 2025-10-09
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007051/IF/IAY/5293184 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114000926 | Completed | 23490 | 20358 | 2025-04-17 | 2025-10-09
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007051/IF/IAY/5295622 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115119174 | Completed | 23490 | 14094 | 2025-04-17 | 2025-10-09
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007051/IF/IAY/5300572 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121356505 | Completed | 23490 | 20358 | 2025-04-17 | 2025-11-25
| 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007051/IF/IAY/530991 — Construction of IAY House -IAY REG. NO. MP2822733 | Completed | 15030 | 16548 | 2017-02-22 | 2018-05-03
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007051/IF/IAY/5313768 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119762196 | Completed | 23490 | 17226 | 2025-04-17 | 2026-02-11
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007051/IF/IAY/5317210 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114071196 | Completed | 23490 | 21924 | 2025-05-01 | 2025-10-09
| 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007051/IF/IAY/531844 — Construction of IAY House -IAY REG. NO. MP2845347 | Completed | 15030 | 15164 | 2017-02-22 | 2018-05-03
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007051/IF/IAY/5319910 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114071205 | Completed | 23490 | 21663 | 2025-05-19 | 2026-02-11
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007051/IF/IAY/5324480 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114749763 | Completed | 23490 | 20358 | 2025-04-17 | 2025-10-09
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007051/IF/IAY/5324922 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121355253 | Completed | 23490 | 20358 | 2025-04-17 | 2025-10-09
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007051/IF/IAY/5337232 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115118608 | Completed | 23490 | 20358 | 2025-04-17 | 2025-10-09
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007051/IF/IAY/5338364 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121365677 | Completed | 23490 | 14094 | 2025-04-17 | 2025-10-09
| 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007051/IF/IAY/544752 — Construction of IAY House -IAY REG. NO. MP3206466 | Completed | 15030 | 15552 | 2017-02-22 | 2018-05-03
| 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007051/IF/IAY/54632 — Construction of IAY House -IAY REG. NO. MP-19-007-051-001/017 | Approved | 23490 | 0 | 2015-12-16
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007051/IF/IAY/5591714 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121847959 | Completed | 23490 | 20880 | 2025-05-15 | 2025-10-09
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007051/IF/IAY/5613509 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121847535 | Completed | 23490 | 21924 | 2025-05-15 | 2025-10-09
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007051/IF/IAY/5678883 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114071560 | Ongoing | 23490 | 22446 | 2025-08-01
| 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007051/IF/IAY/57125 — Construction of IAY House -IAY REG. NO. MP-19-007-051-001/0107 | Approved | 23490 | 0 | 2015-12-22
| 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007051/IF/IAY/57579 — Construction of IAY House -IAY REG. NO. MP-19-007-051-001/023 | Ongoing | 23490 | 7308 | 2026-05-14
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007051/IF/IAY/5813455 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114000107 | Physically Completed | 23490 | 19470 | 2025-09-22 | 2026-02-18
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007051/IF/IAY/5813464 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121361237 | Completed | 23490 | 21663 | 2025-09-22 | 2026-02-11
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007051/IF/IAY/5813465 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121367391 | Completed | 23490 | 21663 | 2025-09-22 | 2026-02-11
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007051/IF/IAY/5813645 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121354296 | Physically Completed | 23490 | 15660 | 2025-09-22 | 2026-02-05
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007051/IF/IAY/5813753 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113782540 | Completed | 23490 | 22458 | 2025-09-22 | 2025-12-06
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007051/IF/IAY/5813896 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114071317 | Completed | 23490 | 21663 | 2025-09-26 | 2026-02-11
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007051/IF/IAY/5813897 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114071408 | Completed | 23490 | 21948 | 2025-09-22 | 2025-12-06
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007051/IF/IAY/5813898 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114071480 | Completed | 23490 | 21663 | 2025-09-22 | 2026-02-11
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007051/IF/IAY/5814005 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113782790 | Completed | 23490 | 20880 | 2025-09-26 | 2026-02-11
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007051/IF/IAY/5814061 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119762086 | Completed | 23490 | 21663 | 2025-09-22 | 2026-02-11
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007051/IF/IAY/5814227 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119758465 | Ongoing | 23490 | 12528 | 2025-10-25
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007051/IF/IAY/5814228 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119758500 | Physically Completed | 23490 | 12528 | 2025-09-22 | 2026-03-15
| 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007051/IF/IAY/784854 — Construction of IAY House -IAY REG. NO. MP1465116 | Completed | 15480 | 15516 | 2017-12-04 | 2018-05-03
| 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007051/IF/IAY/788341 — Construction of IAY House -IAY REG. NO. MP1676364 | Completed | 15480 | 15528 | 2017-12-04 | 2018-05-03
| 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007051/IF/IAY/801097 — Construction of IAY House -IAY REG. NO. MP2772992 | Completed | 15480 | 15528 | 2017-12-04 | 2018-05-02
| 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007051/IF/IAY/803997 — Construction of IAY House -IAY REG. NO. MP3200797 | Completed | 15480 | 15492 | 2018-01-12 | 2018-05-02
| 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007051/IF/IAY/804035 — Construction of IAY House -IAY REG. NO. MP3206513 | Completed | 15480 | 15492 | 2017-10-10 | 2018-05-03
| 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007051/IF/IAY/804095 — Construction of IAY House -IAY REG. NO. MP3214285 | Completed | 15480 | 14644 | 2017-10-03 | 2018-05-02
| 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007051/IF/IAY/804560 — Construction of IAY House -IAY REG. NO. MP3293075 | Completed | 15480 | 15492 | 2017-10-04 | 2018-05-02
| 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007051/IF/IAY/804561 — Construction of IAY House -IAY REG. NO. MP3293084 | Completed | 15480 | 15492 | 2017-10-04 | 2018-05-02
| 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007051/IF/IAY/804574 — Construction of IAY House -IAY REG. NO. MP3294354 | Completed | 15480 | 15480 | 2017-10-04 | 2018-03-15
| 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007051/IF/IAY/804575 — Construction of IAY House -IAY REG. NO. MP3294451 | Completed | 15480 | 14976 | 2017-10-03 | 2018-05-02
| 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719007051/IF/नवीनकूप निमा्रण डुंगाजी हरचंद मोहम्‍ — नवीनकूप निमा्रण डुंगाजी हरचंद मोहम्‍मदपुर पवाडिया | Completed | 44000 | 20508 | 2008-10-08 | 2013-03-22
| 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719007051/IF/नवीनकूप निर्माण विष्‍णुदास तुलसीदास — नवीनकूप निर्माण विष्‍णुदास तुलसीदास मोहम्‍मदपुर पवाडिया | Completed | 44000 | 16959 | 2008-10-09 | 2013-03-22
| 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1719007051/LD/22012034305713 — MO PAWADIYA ME SHANTIDHAM SHED NIRMAN SHAMSHAN PARISAR | Completed | 180000 | 178551.5 | 2017-04-22 | 2018-01-06
| 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Development of chaur Land for Community | Land Development | 1719007051/LD/22012034467044 — Chargrah Vikash nirman work | Ongoing | 750924.38 | 147454 | 2020-01-22
| 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1719007051/LD/22012034535102 — Chargah Vikash Land Levilling Work | Completed | 246579.95 | 137014 | 2020-12-28 | 2023-12-11
| 2016-2017 | D--RURAL INFRASTUCTURE / Other Works | Infrastructure for NADEP composting / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1719007051/OP/9425891400 — MO PAWADIYA ME SAMUDAYIK BHAWAN ME NIRMAN KARYA SATSANG BHAWAN | Completed | 183000 | 178718 | 2016-12-30 | 2017-03-28
| 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007051/RC/22012034155839 — panch parmeshwar+manrega se CC road antrik marg sapera basti se pawadiya tak pawadiya | Deleted | 0 | 0 | 2012-11-20
| 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007051/RC/22012034155840 — panch parmeshwar+manrega se nali o dewar nale par panchayat bhawan se mukhya sadak ki aur mohammadpu | Deleted | 0 | 0 | 2012-11-20
| 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007051/RC/22012034155841 — panch parmeshwar+manrega se CC road and nali nirman pawadiya se guru maharaj tak pawadiya | Deleted | 0 | 0 | 2012-11-20
| 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007051/RC/22012034155842 — panch parmeshwar+manrega se CC road and nali nirman pawadiya se pani ki tanki tak pawadiya | Deleted | 0 | 0 | 2012-11-20
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007051/RC/22012034194430 — MOHD PAWADIA ME CC ROAD BHAGWAN SINGH KE MAKAN SE | Completed | 164000 | 164000 | 2013-12-18 | 2014-03-13
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007051/RC/22012034194433 — MOHD PAWADIA ME CC ROAD RAMSINGH KE MAKAN SE ANARB | Completed | 123000 | 122972 | 2013-12-18 | 2014-03-20
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1719007051/RC/22012034206971 — MO PAWADIYA ME KHET SADAK NIRMAN MAIN ROAD SE SHIV | Completed | 1440000 | 1275477.9 | 2014-02-22 | 2016-06-03
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007051/RC/22012034221914 — pp+manrega se cc road and nali nirman | Deleted | 0 | 0 | 2014-01-26
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007051/RC/22012034221915 — pp+manrega se cc road and nali nirman | Deleted | 0 | 0 | 2014-01-26
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007051/RC/22012034221916 — pp+manrega se cc road and nali nirman | Deleted | 0 | 0 | 2014-01-26
| 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007051/RC/22012034230269 — पंच परमेश्‍वर व मनरेगा से सी सी रोड एवं नाली निर्माण शंकरलाल के मकान से हेमराज के मकान तक | Completed | 150000 | 73928 | 2014-09-28 | 2014-10-12
| 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007051/RC/22012034283768 — cc road and nali nirman manubai ke makan se hanuman mandir tak | Completed | 110000 | 109980 | 2015-09-08 | 2015-10-02
| 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007051/RC/22012034298359 — cc road nali nirman | Completed | 90000 | 76335 | 2016-02-06 | 2016-06-15
| 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007051/RC/22012034304269 — cc road nali nirman | Closed | 0 | 0 | 2016-01-26
| 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007051/RC/22012034320868 — new cc road nn nirman karya | Closed | 0 | 0 | 2016-08-15
| 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1719007051/RC/22012034321402 — SUDUR KHET SADAK | Closed | 0 | 0 | 2017-01-14
| 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1719007051/RC/22012034341009 — MO PAWADIYA ME SUDUR GRAM SADAK SAMPARK SUNDARLAL KE MAKAN SE SAPERA BASTI TAK | Completed | 707800 | 575410.22 | 2017-06-13 | 2019-06-25
| 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1719007051/RC/22012034368346 — khet sadak | Closed | 0 | 0 | 2017-11-23
| 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007051/RC/22012034395701 — C C Road And nirman work Shaskiya School se dhram singh ke makan Tak | Completed | 60500 | 42947 | 2018-12-26 | 2019-01-27
| 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007051/RC/22012034439953 — C C Raod Nirman work | Closed | 0 | 0 | 2017-01-26
| 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007051/RC/22012034447142 — सी सी रोड एवं नाली निर्माण कार्य हनुमान मंदिर व प्रधानमंत्री रोड तक | Completed | 141171 | 141090.96 | 2019-03-05 | 2019-08-26
| 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007051/RC/22012034478623 — C C Road And Nali Nirman Work Ramcharan Se Murali Das beragi ke Makan tak | Completed | 64766 | 64690 | 2019-10-01 | 2020-06-08
| 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1719007051/RC/22012034502891 — G.S.B. Road Nirman Work Sapera Basti Se Gaushala Tak | Closed | 0 | 0 | 2019-08-15
| 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1719007051/RC/22012034504738 — जी एस बी रोड सपेरा बस्ती से गौशाला तक ग्राम पंचायत मोहम्मदपुर पवाड़िया | Completed | 1178056.3 | 1091830.02 | 2019-12-20 | 2021-09-13
| 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1719007051/RC/22012034505815 — G.S.B. Road Nirman Work Sapera Basti Se Gaushala Tak | Closed | 0 | 0 | 2019-08-25
| 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Repair & maint of Mitti Murram Roads for Comm / Repair and maintenance of Mitti Murram Roads for Community | Repair & maint of Road | 1719007051/RC/22012034513337 — c c rod | Closed | 0 | 0 | 2020-01-01
| 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007051/RC/22012034513338 — c c rod | Closed | 0 | 0 | 2020-01-01
| 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007051/RC/22012034513339 — c c rod | Closed | 0 | 0 | 2020-01-01
| 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007051/RC/22012034513340 — c crod | Closed | 0 | 0 | 2020-01-01
| 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007051/RC/22012034527611 — C C Road And nali Nirman Work Main Marga Se Bhagwan Das Ke Makan Tak | Completed | 51075 | 51110 | 2020-07-03 | 2020-10-26
| 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007051/RC/22012034535942 — C C Road And nali Nirman Work Jagdish Vishvkarma Se Hemraj Pathel And Laxminarayan Se Shivnarayan | Closed | 82230 | 0 | 2020-07-01
| 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007051/RC/22012034542879 — C C Road And Nali Nirman Work Sundarlal Ke Makan Se Samudyik Bhvan Tak | Completed | 50643 | 50520 | 2020-10-12 | 2020-11-09
| 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007051/RC/22012034542886 — C C Road And Nali Nirman Work Laxmi pathel Ke Makan Se Shivnarayan Ke Makan Tak | Completed | 15810 | 18074 | 2020-10-12 | 2020-12-21
| 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1719007051/RC/22012034548346 — सुदूर सड्क सह खेत सड्क मेंन रोड अव.बडोदिया से राजेंद्र प्र्जापत के मकान तक ग्राम पचायत मोह.पवाडिया | Completed | 1496537.78 | 1429887.83 | 2020-11-23 | 2021-09-13
| 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007051/RC/22012034612754 — सीसी नाली निर्माण कार्य मुख्य मार्ग से नवीन के घर तक | Closed | 0 | 0 | 2022-01-26
| 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007051/RC/22012034612755 — सीसी नाली निर्माण कार्य मुख्य मार्ग से नवीन के घर तक | Completed | 14895 | 14894 | 2022-08-19 | 2023-04-20
| 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007051/RC/22012034622081 — C C. Road or nali nirman work Pramri School se Middil School Tak graam mo.pavadiya | Completed | 32100 | 30276 | 2023-06-07 | 2024-06-27
| 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007051/RC/22012034652460 — C C ROD NALI NIRMAN DINESH KE MAKAN SE SANKARLAL KE MAKAN TAK MO.PAWADIYA | Closed | 0 | 0 | 2023-06-26
| 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007051/RC/22012034652957 — सी सी रोड दिनेश के घर से संकर के घर तक | Completed | 39700 | 36873 | 2023-10-04 | 2024-11-07
| 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007051/RC/22012034821719 — सी सी रोड निर्माण कार्य मिडील स्कूल से शमसान तक | Approved | 147900 | 0 | 2024-04-04
| 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007051/RC/22012034827746 — सीसी रोड निर्माण कार्य मिडिल स्कूल का समसान तक मोहम्मदपुर पवाडिया | Completed | 147200 | 143463 | 2024-12-05 | 2025-07-14
| 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007051/RC/22012034833100 — सीसी रोड एवं नाली निर्माण कार्य मुख्य मार्ग बड़ोदिया से शिवनारायण के घर तक | Completed | 45100 | 44163 | 2025-01-13 | 2025-06-17
| 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007051/RC/22012034846466 — CC Road And Nali Nirman Kary Prathmik School se laxman ke ghar tak Sapera Basti me | Ongoing | 67713 | 66294 | 2025-12-04
| 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007051/RC/22012034846471 — CC Road And Nali nirman kary krshna se mungalal Jagnnath ke ghr tak Sapera Basti | Ongoing | 76642 | 72036 | 2025-12-04
| 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007051/RC/22012034851614 — C C Road And Nali Nirman Kary Harijan Mohalle Se Choukse Narayan se ram mandir tak | Ongoing | 59464 | 46980 | 2026-02-06
| 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007051/RC/65 — पंच परमेश्‍वर व मनरेगा से सीसी रोड एवं नाली निर्मा | Completed | 216000 | 120270 | 2012-05-29 | 2013-03-30
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719007051/RS/22012034212062 — MOHAMMADPUR PAWADIYA ME MARYADA VIKRAM SINGH NATHU | Deleted | 4400 | 0 | 2013-08-15
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719007051/RS/22012034212067 — MOHAMMADPUR PAWADIYA ME MARYADA MOTILAL MAKHAN SIN | Completed | 4400 | 4377 | 2014-03-05 | 2014-03-12
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719007051/RS/22012034212069 — MOHAMMADPUR PAWADIYA ME MARYADA DHARM SINGH DEVBAX | Completed | 4400 | 4377 | 2014-03-05 | 2014-03-12
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719007051/RS/22012034212071 — MOHAMMADPUR PAWADIYA ME MARYADA NARENDRA BHANWAR S | Completed | 4400 | 4377 | 2014-03-05 | 2014-03-12
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719007051/RS/22012034212073 — MOHAMMADPUR PAWADIYA ME MARYADA SHRIKANT SAWAI SIN | Completed | 4400 | 4377 | 2014-03-05 | 2014-03-12
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719007051/RS/22012034212075 — MOHAMMADPUR PAWADIYA ME MARYADA SANTOSH THAKUR PRA | Completed | 4400 | 4377 | 2014-03-05 | 2014-03-12
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719007051/RS/22012034212077 — MOHAMMADPUR PAWADIYA ME MARYADA JITENDRA KUMER SIN | Completed | 4400 | 4377 | 2014-03-05 | 2014-03-12
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719007051/RS/22012034212079 — MOHAMMADPUR PAWADIYA ME MARYADA OMPRAKASH CHAGANLA | Completed | 4400 | 4377 | 2014-03-05 | 2014-03-12
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719007051/RS/22012034212082 — MOHAMMADPUR PAWADIYA ME MARYADA KHUMAN SINGH BHAWA | Completed | 4400 | 4377 | 2014-03-05 | 2014-03-12
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719007051/RS/22012034212083 — MOHAMMADPUR PAWADIYA ME MARYADA LEELADHAR RAMESH | Completed | 4400 | 4377 | 2014-03-05 | 2014-03-12
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719007051/RS/22012034212084 — MOHAMMADPUR PAWADIYA ME MARYADA MANOHAR CHAGANLAL | Completed | 4400 | 4377 | 2014-03-05 | 2014-03-12
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719007051/RS/22012034212087 — MOHAMMADPUR PAWADIYA ME MARYADA DINESH MANGILAL | Completed | 4400 | 4377 | 2014-03-05 | 2014-03-12
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719007051/RS/22012034212088 — MOHAMMADPUR PAWADIYA ME MARYADA TULSIRAM RAMLAL | Completed | 4400 | 4377 | 2014-03-05 | 2014-03-12
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719007051/RS/22012034212089 — MOHAMMADPUR PAWADIYA ME MARYADA SIDDHANATH KHUSHIL | Completed | 4400 | 4377 | 2014-03-05 | 2014-03-12
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719007051/RS/22012034212090 — MOHAMMADPUR PAWADIYA ME MARYADA SHIVNARAYAN NATHUL | Completed | 4400 | 4377 | 2014-03-05 | 2014-03-12
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719007051/RS/22012034212092 — MOHAMMADPUR PAWADIYA ME MARYADA SOHAN PRABHULAL | Completed | 4400 | 4377 | 2014-03-05 | 2014-03-12
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719007051/RS/22012034212093 — MOHAMMADPUR PAWADIYA ME MARYADA SURAJ SINGH NATHUL | Completed | 4400 | 4377 | 2014-03-05 | 2014-03-12
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719007051/RS/22012034212095 — MOHAMMADPUR PAWADIYA ME MARYADA HAJARILAL DEVBAX | Completed | 4400 | 4377 | 2014-03-05 | 2014-03-12
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719007051/RS/22012034212097 — MOHAMMADPUR PAWADIYA ME MARYADA JAGDISH BHAGIRATH | Completed | 4400 | 4377 | 2014-03-05 | 2014-03-12
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719007051/RS/22012034212098 — MOHAMMADPUR PAWADIYA ME MARYADA RAMESH RUGNATH | Completed | 4400 | 4377 | 2014-03-05 | 2014-03-12
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719007051/RS/22012034212100 — MOHAMMADPUR PAWADIYA ME MARYADA PREMNARAYAN BALDEV | Completed | 4400 | 4377 | 2014-03-05 | 2014-03-12
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719007051/RS/22012034212101 — MOHAMMADPUR PAWADIYA ME MARYADA GIRIRAJ BHAGIRATH | Completed | 4400 | 4377 | 2014-03-05 | 2014-03-12
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719007051/RS/22012034212103 — MOHAMMADPUR PAWADIYA ME MARYADA MAKHAN SINGH RAMLA | Completed | 4400 | 4377 | 2014-03-05 | 2014-03-12
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719007051/RS/22012034212105 — MOHAMMADPUR PAWADIYA ME MARYADA MANGILAL NATHULAL | Completed | 4400 | 4377 | 2014-03-05 | 2014-03-12
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719007051/RS/22012034212106 — MOHAMMADPUR PAWADIYA ME MARYADA TARACHAND KANWARLA | Completed | 4400 | 4377 | 2014-03-05 | 2014-03-12
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719007051/RS/22012034212107 — MOHAMMADPUR PAWADIYA ME MARYADA SIDDHANATH DARIYAV | Completed | 4400 | 4377 | 2014-03-05 | 2014-03-12
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719007051/RS/22012034212112 — MOHAMMADPUR PAWADIYA ME MARYADA VIKRAM SINGH NATHU | Completed | 4400 | 4377 | 2014-03-05 | 2014-03-12
| 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719007051/RS/22012034348722 — HITGRAHI MULAK SOCHALAY | Completed | 24000 | 23792 | 2017-07-20 | 2018-04-05
| 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1719007051/RS/22012034506810 — R C C Nali Nirman Work Premnarayan Se Lakhan Patel Ke Makan Tak | Completed | 33905 | 33894 | 2021-02-22 | 2021-09-13
| 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1719007051/RS/22012034689862 — Nali nirman work harinaraya se bapulal ke ghar tk | Completed | 41000 | 40356 | 2023-06-07 | 2024-06-27
| 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1719007051/RS/22012034700430 — नाली निर्माण कार्य देवीसिंह के माकन से स्तकुल तक | Closed | 20200 | 0 | 2023-04-04
| 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1719007051/RS/22012035113899 — नाली निर्माण कार्य देवकरण से पुलिया तक ग्राम मो.पवाडीया | Completed | 64100 | 63125.45 | 2024-07-04 | 2025-11-05
| 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1719007051/RS/22012035113902 — सीसी एवं नाली निर्माण कार्य देवबक्ष के मकान से चक्की तक ग्राम मो.पवाडिया | Completed | 39000 | 38899.92 | 2024-02-14 | 2024-08-11
| 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1719007051/RS/22012035126894 — नाली निर्माण सुंदरलाल के घर से मक्खन के घर तक मोहम्मदपुर पवाड़िया | Closed | 0 | 0 | 2024-01-26
| 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1719007051/RS/22012035126895 — नाली निर्माण सुंदरलाल के घर से मक्खन के घर तक मोहम्मदपुर पवाड़िया | Completed | 37000 | 36777 | 2024-07-04 | 2024-09-23
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719007051/RS/39233 — jagdish mangilal manrega+maryada | Completed | 4400 | 4377 | 2013-06-27 | 2013-07-08
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719007051/RS/39234 — murlidas prabhudas manrega+maryada | Completed | 4400 | 4377 | 2013-06-27 | 2014-07-08
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Anganwadi Toilets / Construction of Anganwadi Multi Unit Toilets for Community | Construction of Toilets | 1719007051/RS/39235 — devbaksh motilal manrega+maryada | Completed | 4400 | 4377 | 2013-06-27 | 2014-07-08
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719007051/RS/39237 — ramesh chandra nathulal manrega+maryada | Completed | 4400 | 4377 | 2013-06-27 | 2014-07-08
| 2016-2017 | D--RURAL INFRASTUCTURE / Bharat Nirman Sewa Kendra | New Construction / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1719007051/SK/9993648762 — Bharat Nirman Rajeev Gandhi Sewa Kendra,MOHAMMADOURPAVADIYA | Completed | 514000 | 425626 | 2016-11-25 | 2018-01-25
| 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1719007051/WC/14 — सार्वजनिक कूप निर्माण मोहम्‍मद पवाडिया | Completed | 126000 | 238732 | 2008-04-02 | 2013-03-30
| 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1719007051/WC/15 — सार्वजनिक कूप निर्माण पेयजल हेतु ग्राम मोहम्‍मदपुर | Completed | 126000 | 12221 | 2008-04-09 | 2010-02-10
| 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1719007051/WC/18सार्वजनि — सार्वजनिक कूप निर्माण पवाडिया गांव मोहम्‍मदपूर | Deleted | 315000 | 0 | 2009-01-27
| 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Mini Percolation tank / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1719007051/WC/22012034327397 — MO PAWADIYA ME TALAB JIRNODHAR | Completed | 331000 | 289409.96 | 2017-05-30 | 2017-07-07
| 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1719007051/WC/22012034423862 — नाला टेन्‍चस निर्माण कार्य | Completed | 254336 | 165486.54 | 2018-09-27 | 2019-05-30
| 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1719007051/WC/22012034480805 — Soka pit Gagdde work Sarvajik Parisar me | Closed | 0 | 0 | 2019-07-25
| 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1719007051/WC/22012034480969 — Soka Pit Gadde work Nirman Savjanik Parisar me | Closed | 0 | 0 | 2019-07-25
| 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1719007051/WC/22012034481089 — Soka Pit gadde Sarvajnik Parisar Me | Closed | 0 | 0 | 2019-07-25
| 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1719007051/WC/22012034487706 — Soka pit Gagdde work Panchyat Bhwan ke pas | Closed | 0 | 0 | 2019-08-16
| 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1719007051/WC/22012034487707 — Soka pit Gagdde work Samudyika bhwan ke pas | Closed | 0 | 0 | 2019-08-15
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1719007051/WC/22012034645601 — Water Absorption Trench Kheda Ke pas Vala Nala par Pavadiya | Completed | 376136.3 | 239380 | 2021-05-13 | 2025-03-10
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1719007051/WC/22012034645602 — Water Absorption Trench Kheda Ke pas Vala Nala par Pavadiya | Closed | 0 | 0 | 2021-04-01
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1719007051/WC/22012034659849 — Roof Water Harvesting Roof Water Harvesting Panchyat Bhavan Me | Completed | 12300 | 12407 | 2021-09-08 | 2022-06-15
| 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1719007051/WC/22012034659860 — Roof Water Harvesting Roof Water Harvesting Samudyik Bhavan Me | Completed | 12300 | 11016 | 2022-04-11 | 2022-08-26
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1719007051/WC/22012034659872 — Roof Water Harvesting Roof Water Harvesting E Kksha Bhvan Me | Completed | 12300 | 9699 | 2021-09-08 | 2022-08-26
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1719007051/WC/22012034732265 — Hendpamp Recharge pits Main Road 1 | Deleted | 0 | 0 | 2021-05-01
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1719007051/WC/22012034732269 — Hendpamp Recharge pits Main Road 2 | Deleted | 0 | 0 | 2021-05-01
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1719007051/WC/22012034732285 — Hendpamp Recharge pits Main Road 3 | Deleted | 0 | 0 | 2021-05-01
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1719007051/WC/22012034736292 — Hendapampa Recharge pits Sapera Basti | Completed | 14467.3 | 11313 | 2021-06-25 | 2024-03-09
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1719007051/WC/22012034736295 — Hendapampa Recharge pits Dhalmau | Completed | 14467.3 | 11198 | 2021-06-25 | 2024-03-09
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1719007051/WC/22012034736309 — Hendapampa Recharge pits Jod Par | Completed | 14467.3 | 10520 | 2021-06-25 | 2024-03-09
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1719007051/WC/22012034986114 — Amrat sarovar Navin Talba nirman Pavadiya | Closed | 0 | 0 | 2022-04-01
| 2022-2023 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1719007051/WC/22012034990714 — डग पोण्ड निर्माण खारचा मो. पवड़िया | Completed | 1488203.27 | 1475779 | 2022-11-18 | 2024-10-18
| 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1719007051/WC/22012034995330 — रिचार्ज ट्रेंज ग्राम मोहम्मदपुर पवड़िया | Closed | 0 | 0 | 2022-08-18
| 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1719007051/WC/22012035171553 — construction of gabion structure Mo. Pawadiya | Completed | 61630.49 | 58427 | 2024-03-11 | 2024-11-05
| 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1719007051/WC/22012035197116 — वेस्टवियर निर्माण कार्य ख़ार्चा अमृत ​​सरोवर पवाडिया | Completed | 41000 | 40671 | 2024-07-04 | 2024-08-11
| 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1719007051/WC/22012035271840 — JGSA 2025 Dugwell recharge pit sarwajanik kup goshala ke pash mo pawadiya | Completed | 23899.46 | 21753.26 | 2025-05-02 | 2026-01-07
| 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1719007051/WC/22012035271874 — JGSA 2025 Dugwell recharge pit sarwajanik kup goshala ke pash mo pawadiya | New | 0 | 0 | 2025-04-22
| 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1719007051/WC/22012035271911 — JGSA 2025 Dugwell recharge pit sarwajanik kup goshala ke pash | New | 0 | 0 | 2025-04-19
| 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1719007051/WC/22012035296111 — JGSA 2025 Dugwell recharge pit sarwajanik kup pawadiya GP mo pawadiya | Completed | 23899.46 | 20189 | 2025-05-07 | 2026-01-07
| 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1719007051/WC/22012035296127 — JGSA 2025 Dugwell recharge pit sarwajanik kup mohmdpur GP mo pawadiya | Completed | 23899.46 | 20711 | 2025-05-07 | 2026-01-07
| 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1719007051/WC/22012035305480 — JGA 2025 रीचार्ज सार्वजनिक कुंडी G P MO.PAWADIYA | Completed | 23899.46 | 19143.26 | 2025-05-19 | 2026-01-07
| 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1719007051/WC/22012035314520 — Amrit Sarovar Nirman Karya GoShala Ke Pas GP Mo Pawadiya | Approved | 1928924.11 | 0 | 2025-04-14
| 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1719007051/WC/सार्वजनिक — सार्वजनिक कूप निर्माण गांव पवाडिया मोहम्‍मदपूर | Completed | 315000 | 65510 | 2008-12-27 | 2015-05-20
| 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Excavation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1719007051/WH/19956070 — Talab Gehrikaran Karye NANA TALAB Gram mohhamadpur Pawadiya | Completed | 100000 | 22044 | 2016-05-30 | 2016-08-10
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1719007051/WH/22012034447314 — Talab Renovation Nana Talab par Mohammapur | Deleted | 0 | 0 | 2021-04-01
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1719007051/WH/22012034447343 — Pal sudrikarsn work Nana Talab par | Closed | 464498.34 | 0 | 2021-04-01
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation of Fisheries Ponds for Community / Renovation of Fisheries Ponds for Community | Repair & maint of Pond/ Tank | 1719007051/WH/22012034908595 — तालाब पाल जीर्णोधर मोहम्मदपुर पवाडिया | Completed | 311000 | 239777 | 2022-03-05 | 2024-12-14