## Work List
Exported on: 2026-08-21 18:11:05
Filters applied:
Data source: MGNREGA
District: DHAR
Block: DHAR
Panchayat: KALSADA KHURD
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
| 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1722004020/DP/22012034584411 — VASUDHA VANDAN PLANTATION FUTA TALAB KE PAS KALSADAKHURD | Completed | 54564.94 | 27861 | 2023-09-26 | 2025-04-16
| 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Forest Protection / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1722004020/DP/6006 — तारफेंसि‍ग व़क्षारोपण कलसाडाखुर्द | Deleted | 0 | 0 | 2008-08-02
| 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1722004020/DP/6028 — व़क्षारोपण कार्य कलसाडाखुर्द | Completed | 0 | 5400 | 2010-07-30 | 2010-08-13
| 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1722004020/IF/22012034357961 — vraksharopan kary kalsada khurd bhagu bai babulal | Closed | 335000 | 0 | 2017-06-28
| 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1722004020/IF/22012034368962 — Vraksharopan Kaneeram | Closed | 335000 | 0 | 2017-04-01
| 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1722004020/IF/22012034370573 — Podharopan samshan ghat | Completed | 335000 | 2064 | 2017-07-05 | 2021-03-31
| 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1722004020/IF/22012034370576 — podharopan shamshan road ke pas hukumsingh | Completed | 335000 | 217013 | 2017-07-05 | 2022-11-18
| 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1722004020/IF/22012034370579 — shamshan me varksharopan bhagirath | Completed | 335000 | 182568 | 2017-08-10 | 2022-07-23
| 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004020/IF/22012034417033 — IAY REG. NO. MP1543197 PM AVAS SORAM BAI | Completed | 15700 | 14442 | 2018-07-02 | 2018-11-29
| 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1722004020/IF/22012034440660 — souchalay nirman mukesh devaji kalsada khurd | Completed | 12000 | 11181 | 2019-02-01 | 2021-01-01
| 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Mini Percolation Tank for Individuals / Construction of Mini Percolation Tank for Individuals | Construction of Percolation Tank | 1722004020/IF/22012034467169 — Khet Talab Prahalad Rajaram | Closed | 0 | 0 | 2019-01-26
| 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Mini Percolation Tank for Individuals / Construction of Mini Percolation Tank for Individuals | Construction of Percolation Tank | 1722004020/IF/22012034467176 — Khet Talab Suner Parihar | Closed | 0 | 0 | 2019-01-26
| 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Mini Percolation Tank for Individuals / Construction of Mini Percolation Tank for Individuals | Construction of Percolation Tank | 1722004020/IF/22012034471726 — Khet Talab Sunersingh Tolaram | Completed | 253000 | 242794 | 2019-03-10 | 2021-02-17
| 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1722004020/IF/22012034496976 — sock pit kaniram ggabbaji kasalakhurd | Physically Completed | 2649 | 176 | 2019-08-25 | 2021-01-01
| 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1722004020/IF/22012034497522 — Sick pit nirman mukesh devaji kalsadakhurd | Completed | 2649 | 176 | 2019-08-25 | 2021-12-30
| 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1722004020/IF/22012034497552 — sock pit nirman hukum gbbaji kalsadakhurd | Completed | 2649 | 176 | 2019-08-25 | 2020-01-01
| 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1722004020/IF/22012034497554 — sock pit nirman babulal gbbaji kalsadakhurd | Completed | 2649 | 176 | 2019-08-25 | 2021-01-01
| 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1722004020/IF/22012034497556 — sock pit nirman rajesh khimaji kalsadakhurd | Completed | 2649 | 176 | 2019-08-25 | 2021-01-01
| 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1722004020/IF/22012034497557 — sock pit nirman narayan badrilal kalsadakhurd | Completed | 2649 | 176 | 2019-08-25 | 2021-01-01
| 2019-2020 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1722004020/IF/22012034497966 — sock pit nirman punamchand gabbaji kalsadakhurd | Completed | 2649 | 352 | 2019-08-29 | 2021-01-01
| 2019-2020 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1722004020/IF/22012034497984 — Sock pit nirman bhagirath shankar sing kalsadakhurd | Completed | 2649 | 352 | 2019-08-29 | 2021-01-01
| 2019-2020 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1722004020/IF/22012034497986 — Sock pit nirman munna kal khilaji kalsadakhurd | Completed | 2649 | 176 | 2019-08-29 | 2021-01-01
| 2019-2020 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1722004020/IF/22012034497987 — Sock pit nirman ramesh somani kalsadakhurd | Closed | 2649 | 0 | 2019-08-15
| 2019-2020 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1722004020/IF/22012034497988 — Sock pit nirman prakash ramani kalsadakhurd | Completed | 2649 | 176 | 2019-08-29 | 2021-01-01
| 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722004020/IF/22012034719108 — Kapildhara kup Nirman Prahlad Rajaram | Deleted | 0 | 0 | 2021-04-01
| 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722004020/IF/22012034930382 — Kapildhara kup Nirman Prahlad Rajaram Kalsadakhurd | Completed | 250732.62 | 239476.7 | 2022-02-18 | 2023-10-08
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1722004020/IF/22012035448359 — KHET TALAB VISHAL KAILASH | Physically Completed | 450885.64 | 417093 | 2025-05-02 | 2026-04-14
| 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1722004020/IF/22012035448392 — DUGWELL RICHARGE PRAHALAD RAJARAM KE KUP PE | Physically Completed | 25899.46 | 25060 | 2025-05-02 | 2026-04-14
| 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1722004020/IF/22012035496093 — DUGWELL RICHARGE VISHAL KAILASH KE KUP PE | Physically Completed | 25899.46 | 25063 | 2025-05-21 | 2026-04-15
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722004020/IF/22012035646713 — PM AAWAS PRABHU SINGHAD 100905835 | Approved | 24000 | 0 | 2025-04-01
| 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722004020/IF/9993681927 — iNDIRA aVAS LAKHAN Mangoji | Closed | 14310 | 0 | 2015-10-15
| 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004020/IF/9993706126 — Indira Avas Bindabai Chunneelal | Completed | 14310 | 13527 | 2016-06-04 | 2017-11-01
| 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722004020/IF/9993742604 — C M Avas Rajesh Babu | Completed | 14310 | 14195 | 2016-05-26 | 2016-12-20
| 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722004020/IF/9993742607 — C M Avas Radheshyam Ambaram | Closed | 0 | 0 | 2016-04-14
| 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722004020/IF/9993742608 — C M Avas Radheshyam Ambaram | Closed | 0 | 0 | 2016-04-14
| 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722004020/IF/9993742609 — C M Avas Radheshyam Ambaram | Completed | 14310 | 14195 | 2016-05-26 | 2016-12-20
| 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722004020/IF/9993742617 — C M Avas Jitendra Gattu | Closed | 0 | 0 | 2016-04-14
| 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722004020/IF/9993742618 — C M Avas Jitendra Gattu | Completed | 14310 | 14195 | 2016-05-26 | 2016-09-26
| 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722004020/IF/9993742624 — C M Avas Kamalabai Bajeshingh | Completed | 14310 | 14195 | 2016-05-26 | 2016-09-26
| 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722004020/IF/9993742628 — C M Avas Sohan Pappu | Completed | 14310 | 14195 | 2016-05-26 | 2016-12-20
| 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004020/IF/9993746073 — Indira Avas Lakhan Sukharam | Completed | 14310 | 14195 | 2016-06-08 | 2016-09-26
| 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722004020/IF/9993748426 — C M Avas Mohan Dayaram | Completed | 14310 | 14195 | 2016-06-21 | 2016-12-20
| 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722004020/IF/9993748428 — C M Avas Bhagirath Shankarlal | Completed | 14310 | 14195 | 2016-06-21 | 2016-12-20
| 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004020/IF/IAY/2402628 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4447186 | Completed | 17100 | 15960 | 2020-05-26 | 2021-02-17
| 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004020/IF/IAY/2402899 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4453237 | Completed | 17100 | 17100 | 2020-06-02 | 2020-08-06
| 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004020/IF/IAY/2483037 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4109667 | Completed | 17100 | 16720 | 2020-05-26 | 2021-02-17
| 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004020/IF/IAY/2507867 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4449254 | Completed | 17100 | 15960 | 2020-05-26 | 2021-02-17
| 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004020/IF/IAY/2509407 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4470156 | Completed | 17100 | 15960 | 2020-05-26 | 2021-02-17
| 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004020/IF/IAY/2509423 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4470428 | Completed | 17100 | 15960 | 2020-05-26 | 2021-02-17
| 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004020/IF/IAY/2516611 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4553839 | Completed | 17100 | 16530 | 2020-06-02 | 2021-02-17
| 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004020/IF/IAY/2521610 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4616342 | Completed | 17100 | 16530 | 2020-06-02 | 2021-02-17
| 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004020/IF/IAY/2521798 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4618939 | Completed | 17100 | 15960 | 2020-05-26 | 2021-02-17
| 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004020/IF/IAY/2865485 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4440448 | Completed | 17100 | 9264 | 2021-04-15 | 2021-09-13
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004020/IF/IAY/3677603 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105058103 | Completed | 18360 | 18224 | 2022-11-14 | 2023-11-15
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004020/IF/IAY/3687127 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102428108 | Completed | 18360 | 17935 | 2023-01-07 | 2024-01-11
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004020/IF/IAY/3820422 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117396524 | Completed | 18360 | 17646 | 2022-07-15 | 2024-09-18
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004020/IF/IAY/4038656 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102147777 | Completed | 18360 | 17136 | 2022-06-14 | 2022-11-14
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004020/IF/IAY/4207436 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106233615 | Completed | 18360 | 18207 | 2022-07-15 | 2023-08-14
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004020/IF/IAY/4543252 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105054182 | Ongoing | 23490 | 20358 | 2025-04-23
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004020/IF/IAY/4560549 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115105240 | Completed | 23490 | 21276 | 2025-01-20 | 2026-02-28
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004020/IF/IAY/4859233 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102147818 | Ongoing | 23490 | 13833 | 2025-04-16
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004020/IF/IAY/5148533 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102427455 | Completed | 23490 | 21924 | 2025-08-13 | 2026-02-17
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004020/IF/IAY/5192918 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100905598 | Completed | 23490 | 21663 | 2025-04-16 | 2026-05-15
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004020/IF/IAY/5196798 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102427365 | Ongoing | 23490 | 5481 | 2025-08-09
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004020/IF/IAY/5202219 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115103972 | Ongoing | 23490 | 20358 | 2025-05-07
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004020/IF/IAY/5216938 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105059600 | Ongoing | 23490 | 16443 | 2025-08-13
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004020/IF/IAY/5218113 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102428010 | Ongoing | 23490 | 5220 | 2025-09-10
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004020/IF/IAY/5227119 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102147032 | Ongoing | 23490 | 18792 | 2025-05-07
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004020/IF/IAY/5238011 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102427545 | Completed | 23490 | 22185 | 2025-05-07 | 2026-02-17
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004020/IF/IAY/5239396 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102428271 | Completed | 23490 | 23490 | 2025-05-21 | 2025-09-09
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004020/IF/IAY/5350692 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117397070 | Completed | 23490 | 23490 | 2025-05-21 | 2025-09-09
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004020/IF/IAY/5352134 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141852366 | Completed | 23490 | 22446 | 2025-05-07 | 2026-02-17
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004020/IF/IAY/5555061 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106224095 | Ongoing | 23490 | 12789 | 2026-01-20
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004020/IF/IAY/5564447 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143739333 | Ongoing | 23490 | 16443 | 2025-08-20
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004020/IF/IAY/5638654 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105056914 | Ongoing | 23490 | 14616 | 2025-08-13
| 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004020/IF/IAY/5642101 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105055128 | Physically Completed | 23490 | 20097 | 2026-05-30 | 2026-06-07
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004020/IF/IAY/5657780 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102427951 | Ongoing | 23490 | 16443 | 2025-09-10
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004020/IF/IAY/5658531 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105058887 | Ongoing | 23490 | 21402 | 2025-09-22
| 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004020/IF/IAY/82895 — Construction of IAY House -IAY REG. NO. MP-22-004-020-001/016 | Approved | 23490 | 0 | 2015-12-29
| 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004020/IF/IAY/82896 — Construction of IAY House -IAY REG. NO. MP-22-004-020-001/7 | Approved | 23490 | 0 | 2015-12-29
| 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1722004020/LD/28 — ग्रामीण कीडांगन खेल मैदान समतलीकरण प्रावि कलसाडाखुर्द | Completed | 88000 | 82500 | 2011-11-29 | 2012-09-21
| 2006-2007 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722004020/RC/02 — ग्रेवल मार्ग कलसाडा. से पिपल्‍दा 1कि.मी. सी.सी. 300 मी. पुलिया नग एवं प्रोटेशन कार्य RES | Completed | 0 | 35615 | 2006-11-17 | 2007-12-10
| 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722004020/RC/20-01 — ग्रेवल मार्ग कलसाडाखुर्द से सेजवानी मार्ग | Completed | 0 | 131374 | 2008-05-08 | 2011-01-25
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722004020/RC/22012034157145 — सीमेंट कांक्रीट आंतर‍िक मांर्ग कलसाडा खुर्द | Deleted | 0 | 0 | 2013-04-14
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722004020/RC/22012034157146 — सीमेंट कांक्रीट आंतर‍िक मांर्ग कलसाडा खुर्द | Deleted | 0 | 0 | 2013-04-14
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722004020/RC/22012034157147 — सीमेंट कांक्रीट आंतर‍िक मांर्ग कलसाडा खुर्द | Deleted | 0 | 0 | 2013-04-14
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722004020/RC/22012034195497 — सीमेंट कांक्रीट अांतरीक मार्ग अरूण दा के घर से मां | Completed | 53000 | 52974 | 2014-01-08 | 2014-10-26
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722004020/RC/22012034205837 — cement concreet intarnal road samandar ke ghar se | Completed | 53000 | 50880 | 2014-03-05 | 2015-05-10
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722004020/RC/22012034207237 — खेत सड़क नंदकिशोर शर्मा के खेत से विक्रम डा के खेत | Completed | 1491000 | 825639 | 2014-02-26 | 2016-12-30
| 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722004020/RC/22012034229761 — C.C.Road Kaniram Ke Makan Se Bheru Ke Makan Tak | Completed | 136000 | 86111 | 2014-09-24 | 2016-06-20
| 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722004020/RC/22012034289757 — khet sadak nirmadjivan mukati ke khet se padam singh ke khet tak | Completed | 643000 | 391216.4 | 2015-11-25 | 2016-12-30
| 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722004020/RC/22012034293058 — C C Road Meharban Ke Makan Se Kaniram Ke Makan | Completed | 80000 | 79977 | 2015-12-19 | 2016-06-20
| 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722004020/RC/22012034318091 — सुदुर ग्राम सडक नई आबादी से माताजी मंदिर तक | Completed | 1100000 | 1074784.67 | 2016-12-20 | 2020-10-10
| 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722004020/RC/22012034371903 — khet sadak | Closed | 0 | 0 | 2017-10-02
| 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722004020/RC/22012034533844 — GRAVEL ROAD SAMSAN ROAD SE BABUSINGH PATEL KE KHET TAK | Physically Completed | 1168924.34 | 4398 | 2020-09-29 | 2021-10-03
| 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722004020/RC/22012034553396 — Cement concrete road nirman shamshan pahut marg | Completed | 69000 | 58900 | 2020-12-23 | 2021-04-25
| 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722004020/RC/22012034583564 — cement concrete road nirman vijay pandit ke ghar se narayan singh ke ghar tak | Completed | 26000 | 25476 | 2021-11-03 | 2021-12-30
| 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722004020/RC/22012034658643 — CC ROAD SAMSAN GHAT MARG | Completed | 33000 | 29172 | 2024-01-16 | 2024-09-18
| 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722004020/RC/22012034832046 — CC ROAD KANIRAM KE GHAR SE HANDPUMP TAK | Completed | 30000 | 25272 | 2025-02-06 | 2026-02-28
| 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722004020/RC/22012034846753 — CC ROAD PS BHAWAN PRAGAN | Ongoing | 55000 | 13050 | 2025-08-06
| 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722004020/RC/25340 — ग्रेवल रोड पि‍पल्‍दा रोड से नेशनल हाईवे बग्‍गड | Completed | 498000 | 306859 | 2009-02-04 | 2011-01-25
| 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722004020/RC/25461 — खरंजा नि‍माण कलसाडाखुर्द | Completed | 0 | 98492 | 2009-07-03 | 2009-05-14
| 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722004020/RC/25499 — आंतरि‍क ग्रेवल मार्ग शि‍व मंदि‍र से क़ष्‍ण मंदि‍र तक कलसाडाखुर्द | Completed | 0 | 71472.92 | 2009-12-18 | 2009-01-26
| 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722004020/RC/25510 — बग्‍गड से एकलदूना मार्ग पर पुलि‍या र्नि‍माण बग्‍गड | Completed | 0 | 359470 | 2009-11-07 | 2010-05-31
| 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722004020/RC/25579 — ग्रेवल मार्ग निर्माण कलसाडा खुर्द से मगर देवला ग्राम पंचायत कलसाडा खुर्द | Completed | 0 | 383424 | 2010-07-06 | 2011-12-24
| 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722004020/RC/25674 — मुरम सडक निर्माण मुख्‍य मार्ग से चोकीदार के खेत तक कलसाडाखुर्द | Completed | 500000 | 219666 | 2012-01-13 | 2012-09-21
| 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722004020/RC/25738 — सीमेंट कांक्रीट आंतरिक मार्ग निर्माण तेजराम के घर से रामसिंह के घर तक कलसाडाखुर्द | Completed | 120000 | 104780 | 2012-08-16 | 2013-11-27
| 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722004020/RC/25831 — सीमेंट कांक्रीट आंतर‍िक मार्ग राधेश्‍याम के मकान से देवीसिंह के मकान तक भाग 2 | Completed | 48000 | 47408 | 2013-03-11 | 2013-11-27
| 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722004020/RC/25832 — सीमेंट कांक्रीट आंतरिक मार्ग राधेश्‍याम के घर से मांगु के घर व देवसिंग के मकान तक | Completed | 190000 | 113712 | 2013-03-18 | 2013-11-27
| 2006-2007 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722004020/RC/501 — बग्‍गड से एकलदुना पहुंच मार्ग पार्ट 1 | Completed | 400000 | 0 | 2007-01-29 | 2008-01-01
| 2007-2008 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722004020/RC/5026 — ग्रेवल मार्ग कलसाडा से नील फैक्‍टी ii | Deleted | 0 | 0 | 2007-11-03
| 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722004020/RC/5027 — ग्रेवल मार्ग एन एच 59 से एकलदुना कलसाडाखुर्द | Completed | 0 | 59478 | 2009-06-01 | 2006-02-02
| 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722004020/RC/5028 — पुलि‍या र्नि‍माण ग्रेवल मार्ग बग्‍गड् कलसाडाखुर्द | Deleted | 0 | 0 | 2008-05-04
| 2006-2007 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722004020/RC/55 — ग्रेवल रोड् बग्‍गड | Completed | 500059.6 | 170810 | 2006-10-10 | 2007-02-20
| 2006-2007 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722004020/RC/601 — कलसाडाखुर्द से बग्‍गड् पहुंच मार्ग | Completed | 500000 | 0 | 2006-11-10 | 2007-04-15
| 2006-2007 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722004020/RC/602 — कलसाडाखुर्द से नील फैक्‍टी पहुंच मार्ग | Completed | 500000 | 0 | 2006-12-15 | 2009-02-02
| 2006-2007 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722004020/RC/603 — कलसाडाखुर्द से बग्‍गड ग्रेवल मार्ग अतिरिक्‍त | Completed | 400000 | 0 | 2007-01-18 | 2007-12-05
| 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Anganwadi Multi Unit Toilets for Comm / Construction of Anganwadi Multi Unit Toilets for Community | Construction of Toilets | 1722004020/RS/22012034524922 — RCC NALI RAMESHWER PATIDAR KE MAKAN SE SHIV MANDIR | Closed | 0 | 0 | 2021-06-13
| 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1722004020/RS/22012034525973 — R c c nali nirman rameshwar ke ghar se shiv mandir kalsadakhurd | Completed | 17000 | 13896 | 2021-07-08 | 2022-07-18
| 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Community / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1722004020/RS/22012034534245 — SBM SCP COMMUNITY COMPOST PIT-KALSADKHURD | Completed | 47000.06 | 47561.5 | 2021-10-16 | 2022-04-15
| 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1722004020/RS/22012034536634 — SBM SSP SAMUDAYIK SOAK PIT-10 UNIT KALSADAKHURD | Completed | 59999.77 | 48948 | 2021-10-01 | 2022-04-15
| 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1722004020/RS/22012034537878 — SBM ISP KALSADAKHURD 50 UNIT | Completed | 99999.74 | 74517 | 2021-09-08 | 2022-07-22
| 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1722004020/RS/22012034587215 — COMUNITY TOILET MAIN ROAD KALSADAKHURD | Closed | 0 | 0 | 2021-09-10
| 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1722004020/RS/22012034587216 — COMUNITY TOILET MAIN ROAD KALSADAKHURD | Closed | 44000 | 0 | 2021-10-09
| 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Multi Unit Toilets for School / Construction of Multi Unit Toilets for School | Construction of Toilets | 1722004020/RS/22012034631693 — COMUNITY TOILET KALSADAKHURD | Completed | 44000 | 50322 | 2022-02-03 | 2022-07-19
| 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1722004020/RS/22012035113595 — NALI JITENDRA KE GHAR SE MOHAN BHAT KE GHAR TAK | Completed | 17000 | 15691 | 2024-01-31 | 2024-08-27
| 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1722004020/RS/22012035113607 — NALI NIRMAN JEEVAN KE GHAR SEMUNNALAL KE GHAR TAK | Completed | 24000 | 20774 | 2024-01-16 | 2024-08-27
| 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1722004020/RS/22012035129632 — RCC NALI KAILASH KE GHAR SE CHAPRA TAK | Completed | 34000 | 32175 | 2024-08-25 | 2024-12-30
| 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1722004020/RS/22012035132149 — NALI NIRMAN JAGDISH KE GHAR SE MANGILAL BAJESING KE GHAR TAK | Completed | 27000 | 24660 | 2024-10-12 | 2024-11-26
| 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1722004020/RS/22012035132687 — NALI NIRMAN CHADAR THAKUR KE GHAR SE NALA TAK | Completed | 12000 | 9720 | 2024-11-04 | 2025-04-30
| 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1722004020/RS/22012035133019 — NALI NIRMAN DILIP PATEL KE GHAR SE RAMESHWAR PATIDAR KE GHAR TAK | Completed | 12000 | 11664 | 2024-11-18 | 2024-12-04
| 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1722004020/RS/22012035134661 — NALI AMIR KE GHAR SE KAILASH KE GHAR TAK | Completed | 8000 | 7776 | 2025-03-12 | 2025-05-19
| 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1722004020/WC/22012034313348 — Jal Sangrahan Sanrachana Resham Kandra Road Ke Pas | Completed | 214000 | 196281 | 2016-11-23 | 2017-10-14
| 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Dam / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1722004020/WC/22012034327164 — nstar talab jirnodhar kalsada khurd | Completed | 302000 | 287711.79 | 2017-06-03 | 2019-08-18
| 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Dam / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1722004020/WC/22012034356570 — bori bandhan(gujrat nale par )kalsada khurd) | Completed | 27000 | 172 | 2017-10-06 | 2020-10-10
| 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1722004020/WC/22012034442033 — nala tranchig kary kalsadakhurd | Closed | 0 | 0 | 2019-04-01
| 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Trench for Community | Construction of Trench | 1722004020/WC/22012034442232 — Nala Trenching Kalasada Khurd Gaw Ke Pas | Closed | 0 | 0 | 2019-01-26
| 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1722004020/WC/22012034482799 — Richarg Pit Dharmshala Marg Hend Pump | Completed | 5099.07 | 176 | 2019-08-19 | 2021-01-01
| 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1722004020/WC/22012034482800 — Richarg Pit Panchayat Ke Pas Handpump | Completed | 5134.63 | 176 | 2019-08-19 | 2021-01-01
| 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1722004020/WC/22012034482801 — Richarg Pit Banjara Bastee Handpump | Completed | 5061.42 | 176 | 2019-08-19 | 2021-01-01
| 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1722004020/WC/22012034518637 — nala tranching kalsadakhurd | Closed | 0 | 0 | 2019-10-02
| 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1722004020/WC/22012034605277 — NALA TENCH MOHINI NADI PAS NALA KALSADA KHURD | Completed | 313318.8 | 273406 | 2020-12-30 | 2021-08-23
| 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1722004020/WC/22012034632655 — nala tranching mohni nala | Closed | 0 | 0 | 2021-03-22
| 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1722004020/WC/22012034632661 — Bhu sankalan pond brij ke pass | Closed | 0 | 0 | 2021-03-22
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1722004020/WC/22012034633316 — CTRA WORK SANKAN POND BRIJ KE PAS KALSADAKHURD | Completed | 279083.82 | 287576 | 2021-04-10 | 2022-09-23
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1722004020/WC/22012034635779 — CTRA WORK NALA TRENCH SHIV MANDIR SE BANESINGH KE KHET TAK | Completed | 413478 | 352258 | 2021-04-10 | 2024-06-17
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1722004020/WC/22012034650433 — CTRA RWH E-PANCHAYAT BHAWAN KALSADA | Completed | 5500 | 5597 | 2021-04-17 | 2021-07-17
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1722004020/WC/22012034672372 — CTRA WORK SANKAN POND AADIWASI BASTI KE PAS PIPALDA ROAD | Completed | 192767.79 | 162003 | 2021-04-29 | 2021-11-18
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1722004020/WC/22012034682465 — CTRA NALA TRENCH DAM SE KRISHNA KE KHET TAK PART-1 | Physically Completed | 212040 | 4632 | 2021-05-13 | 2021-07-31
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1722004020/WC/22012034682466 — CTRA NALA TRENCH DAM SE KRISHNA KE KHET TAK PART-2 | Suspended | 159030 | 0 | 2021-05-21
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1722004020/WC/22012034682903 — CTRA RICHARGE PIT-1 SHIVMANDIR WALA NALA | Completed | 13133.77 | 13057 | 2021-05-08 | 2021-07-02
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1722004020/WC/22012034682920 — CTRA RICHARGE PIT-2 SHIVMANDIR WALA NALA | Completed | 13133.77 | 12864 | 2021-05-13 | 2021-07-02
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1722004020/WC/22012034682927 — CTRA RICHARGE PIT-3 SHIVMANDIR WALA NALA | Completed | 13133.77 | 13057 | 2021-05-08 | 2021-07-03
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1722004020/WC/22012034682935 — CTRA RICHARGE PIT-1 MOHINI NALA | Completed | 13133.77 | 12864 | 2021-05-13 | 2021-07-03
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1722004020/WC/22012034682945 — CTRA RICHARGE PIT-2 MOHINI NALA | Completed | 13133.77 | 12864 | 2021-05-13 | 2021-07-03
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1722004020/WC/22012034682984 — CTRA RICHARGE PIT-3 MOHINI NALA | Completed | 13133.77 | 12864 | 2021-05-13 | 2021-07-04
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Coastal Block Plantation - Farm Forestry-Community / Along the coast Block Plantation of Farm Forestry Trees for Community | Plantation | 1722004020/WC/22012034900083 — ADDITIONAL WORK OF TORANDWAR KALSADAKHURD | Closed | 0 | 0 | 2022-01-23
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Coastal Block Plantation - Farm Forestry-Community / Along the coast Block Plantation of Farm Forestry Trees for Community | Plantation | 1722004020/WC/22012034900084 — ADDITIONAL WORK OF TORANDWAR KALSADAKHURD | Closed | 0 | 0 | 2022-01-23
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1722004020/WC/22012034904075 — NALA TRENCH CHITU KE MAKAN SE MAHENRA KE MAKAN | Closed | 0 | 0 | 2022-01-29
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1722004020/WC/22012034904078 — NALA TRENCH BABU KE KHET SE MUKESH KE KHET | Closed | 0 | 0 | 2022-01-29
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1722004020/WC/22012034908575 — NALA TRENCH CHITU KE MAKAN SE MAHENDRA KE MAKAN TAK | Closed | 0 | 0 | 2022-01-26
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1722004020/WC/22012034908579 — NALA TRENCHBABU SINHG KE KHET SE MUKESH KE KHET | Closed | 0 | 0 | 2022-01-26
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1722004020/WC/22012034908586 — BHU SANKAN POND GOPAL KE KHET KE PAS | Closed | 0 | 0 | 2022-01-26
| 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1722004020/WC/22012034934872 — NSP BHUSANKAN POND GOPAL KE KHET KE PAS | Completed | 231439.57 | 191199 | 2022-05-29 | 2024-06-11
| 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1722004020/WC/22012034951341 — NPS NALA TRENCH BABUSINGH KE KHET SE MUKESH KE KHET | Closed | 0 | 0 | 2022-04-14
| 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1722004020/WC/22012034951525 — NSP Nala trenching babu singh k khet se mukesh k khet tak kalsadakhurag | Closed | 0 | 0 | 2022-04-14
| 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1722004020/WC/22012035099976 — NALA TRENCH PANI KI TANKI SE FUTA TALAB | Completed | 121116.4 | 92551.2 | 2024-06-10 | 2025-05-26
| 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1722004020/WC/22012035165835 — Nala trenching karya | New | 0 | 0 | 2024-01-26
| 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1722004020/WC/22012035227994 — NALA TRENCH JIVAN KE GHAR SE TALAB TAK | Completed | 167670.29 | 135530.55 | 2024-11-27 | 2025-05-19
| 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1722004020/WC/4005 — नि‍स्‍तारी तालाब र्नि‍माण कलसाडाखुर्द RES | Deleted | 0 | 0 | 2007-04-13
| 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1722004020/WC/4006 — नि‍स्‍तारी तालाब कलसाडाखुर्द RES | Completed | 0 | 1540863.5 | 2007-05-17 | 2007-04-13
| 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1722004020/WC/4070 — जल संगहण संरचना कलसाडाखुर्द | Completed | 80000 | 52800 | 2010-04-29 | 2011-01-25
| 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1722004020/WC/4072 — जल संग्रहण सरंचना कलसाडाखूर्द | Completed | 0 | 15600 | 2010-05-06 | 2011-01-25
| 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1722004020/WC/4104 — जल ग्रहण ढांचा (तलाई र्नि‍माण) गा पं बग्‍गड | Completed | 80000 | 23100 | 2010-06-10 | 2010-06-10
| 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1722004020/WC/4106 — जल ग्रहण ढाचा कलसाडाखुर्द | Completed | 0 | 45600 | 2010-06-03 | 2011-01-25
| 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Sunken Pond / Construction of Community Water Harvesting Ponds | Farm Pond | 1722004020/WC/9993627342 — जल संग्रहण संरचना | Deleted | 0 | 0 | 2013-04-14
| 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Sunken Pond / Construction of Community Water Harvesting Ponds | Farm Pond | 1722004020/WC/9993634192 — जल संग्रहण संरचना कलसाडाखुर्द भाग 3 | Completed | 258000 | 215239 | 2013-06-19 | 2014-06-18
| 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1722004020/WC/9993667907 — Jalsangrahan Sanrachana | Deleted | 0 | 0 | 2016-01-26
| 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1722004020/WC/9993667916 — Jalsangrahan Sanrchana | Deleted | 0 | 0 | 2016-01-26