## Work List
Exported on: 2026-08-31 18:12:56
Filters applied:
Data source: VBGRAMG
District: VIDISHA
Block: SIRONJ
Panchayat: BISHEPUR
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
| 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1727002009/DP/22012034625775 — वृक्षारोपण निर्माण अमृत सरोवर के पास ग्राम युसुफपुर | Ongoing | 498181.71 | 0 | 2024-08-13
| 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1727002009/DP/22012034627779 — वृक्षारोपण निर्माण खेरापति माता मंदिर के पास युसुफपुर | Ongoing | 504193.94 | 0 | 2024-09-20
| 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Coastal Afforestation using forstry Trees for Comm / Along the coast Afforestation using forestry Trees for Community | Plantation | 1727002009/DP/GIS/36338 — Dry Boulder Wall गजराज सिंह के खेत के पास पहाडी पर युसुफपुर | Ongoing | 357085.06 | 0 | 2023-10-06
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1727002009/IC/22012034885413 — सिंचाई कार्य सामुदायिक कूप निर्माण समन्‍दरसिंह के खेत के पास ग्राम युसुफपुर | New | 0 | 0 | 2024-06-08
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1727002009/IC/22012034885414 — सिंचाई कार्य सामुदायिक कूप निर्माण नीलेश के घर के पास ग्राम विशेपुर | New | 0 | 0 | 2024-06-08
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1727002009/IC/22012034885415 — सिंचाई कार्य सामुदायिक कूप निर्माण अजबसिंह के घर के पास ग्राम विशेपुर | New | 0 | 0 | 2024-06-08
| 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1727002009/IF/22012035504196 — Dug Well Recharge मुकेश / कुबेर सिंह ग्राम विशेपुर | Approved | 25899.46 | 0 | 2025-04-14
| 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1727002009/IF/22012035504292 — Dug Well Recharge कूप संजेश / लालसिंह ग्राम यूसुफपुर | Approved | 0 | 0 | 2025-04-14
| 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1727002009/IF/22012035504299 — Dug Well Recharge कूप पदम / मोहनलाल ग्राम यूसुफपुर | Approved | 0 | 0 | 2025-04-14
| 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1727002009/IF/22012035504307 — Dug Well Recharge कूप जितेंद्र / रघुबीर सिंह ग्राम यूसुफपुर | Approved | 0 | 0 | 2025-04-14
| 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1727002009/WC/22012035236975 — कन्‍टूर ट्रैंच निर्माण बजीरपुर वाली पहाडी पर ग्राम युसुुफपुर | Approved | 0 | 0 | 2024-10-02
| 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1727002009/WC/VB/22012035330248 — बोल्‍डर चैक डेम निर्माण बजीरपुर नाले पर पार्ट 02 ग्राम युसुफपुर | Approved | 0 | 0 | 2026-07-01
| 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Trench for Community | Construction of Trench | 1727002009/WC/VB/22012035330251 — कन्‍टूर ट्रैंच निर्माण युसुफपुर पहाडी पर पार्ट 02 ग्राम युसुफपुर | Approved | 0 | 0 | 2026-07-01
| 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1727002009/WC/VB/22012035331874 — कन्‍टूर ट्रैंच निर्माण युसुफपुर पहाडी पर पार्ट 0३ ग्राम युसुफपुर | Approved | 0 | 0 | 2026-07-01
| 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1727002009/WC/VB/22012035331876 — कन्‍टूर ट्रैंच निर्माण युसुफपुर पहाडी पर पार्ट 01 ग्राम युसुफपुर | Ongoing | 179224.06 | 63600 | 2026-08-09
| 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1727002009/WC/VB/22012035331877 — गेवियन स्‍ट्रेक्‍चर निर्माण युसुफपुर वाली पहाडी पर पार्ट 02 ग्राम युसुुफपुर | Ongoing | 94884.65 | 600 | 2026-08-09
| 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1727002009/WC/VB/22012035331879 — गेवियन स्‍ट्रेक्‍चर निर्माण युसुफपुर वाली पहाडी पर पार्ट 01 ग्राम युसुुफपुर | Ongoing | 95416.75 | 0 | 2026-08-11
| 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1727002009/WC/VB/22012035331881 — गेवियन स्‍ट्रेक्‍चर निर्माण युसुफपुर वाली पहाडी पर पार्ट 04 ग्राम युसुुफपुर | Ongoing | 94352.55 | 9000 | 2026-08-18
| 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1727002009/WC/VB/22012035331882 — गेवियन स्‍ट्रेक्‍चर निर्माण युसुफपुर वाली पहाडी पर पार्ट 03 ग्राम युसुुफपुर | Ongoing | 95561.86 | 0 | 2026-08-18
| 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1727002009/WC/VB/22012035331883 — बोल्‍डर चैक डेम निर्माण बजीरपुर नाले पर पार्ट 01 ग्राम युसुफपुर | Approved | 0 | 0 | 2026-07-01
| 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1727002009/WC/VB/22012035331893 — गेवियन स्‍ट्रेक्‍चर निर्माण युसुफपुर वाली पहाडी पर पार्ट 16 ग्राम युसुुफपुर | Approved | 93820.47 | 0 | 2026-07-01
| 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1727002009/WC/VB/22012035331957 — गेवियन स्‍ट्रेक्‍चर निर्माण युसुफपुर वाली पहाडी पर पार्ट 15 ग्राम युसुुफपुर | Ongoing | 97013.03 | 600 | 2026-08-09
| 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1727002009/WC/VB/22012035331958 — गेवियन स्‍ट्रेक्‍चर निर्माण युसुफपुर वाली पहाडी पर पार्ट 13 ग्राम युसुुफपुर | Approved | 95416.75 | 0 | 2026-07-01
| 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1727002009/WC/VB/22012035331959 — गेवियन स्‍ट्रेक्‍चर निर्माण युसुफपुर वाली पहाडी पर पार्ट 11 ग्राम युसुुफपुर | Approved | 47794.21 | 0 | 2026-07-01
| 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1727002009/WC/VB/22012035331960 — गेवियन स्‍ट्रेक्‍चर निर्माण युसुफपुर वाली पहाडी पर पार्ट 17 ग्राम युसुुफपुर | Ongoing | 98222.34 | 600 | 2026-08-09
| 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1727002009/WC/VB/22012035331961 — गेवियन स्‍ट्रेक्‍चर निर्माण युसुफपुर वाली पहाडी पर पार्ट 18 ग्राम युसुुफपुर | Ongoing | 95561.86 | 0 | 2026-08-18
| 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1727002009/WC/VB/22012035331962 — गेवियन स्‍ट्रेक्‍चर निर्माण युसुफपुर वाली पहाडी पर पार्ट 19 ग्राम युसुुफपुर | Ongoing | 97708.39 | 0 | 2026-08-18
| 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1727002009/WC/VB/22012035331963 — गेवियन स्‍ट्रेक्‍चर निर्माण युसुफपुर वाली पहाडी पर पार्ट 20 ग्राम युसुुफपुर | Approved | 0 | 0 | 2026-07-01
| 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1727002009/WC/VB/22012035331964 — गेवियन स्‍ट्रेक्‍चर निर्माण युसुफपुर वाली पहाडी पर पार्ट 21 ग्राम युसुुफपुर | Ongoing | 47528.15 | 600 | 2026-08-09
| 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1727002015/WC/VB/22012035331891 — गेवियन स्‍ट्रेक्‍चर निर्माण युसुफपुर वाली पहाडी पर पार्ट 14 ग्राम युसुुफपुर | Ongoing | 95948.84 | 0 | 2026-08-18