## Work List
District / Block / Panchayat | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Start / completed date
BHOPAL / PHANDA / KHEJDADEO | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Kitchen Shed / Construction of Kitchen shed Building for Community | Constr of Kitchen Shed | 1728002017/AV/22012034580332 — डायनिंग हॉल में बेंच निर्माण कार्य ग्राम पंचायत खेजडादेव | Closed | 26881.94 | 0 | 2021-04-14 -
BHOPAL / PHANDA / KHEJDADEO | C--COMMON INFRASTRUCTURE FOR NRLM COMPLIANT SELF HELP GROUPS / Anganwadi/Other Rural Infrastructure | Constr of workshed for Livelihood activity (Grps) / Construction of workshed for Livelihood activity for Groups | Construction of building/workshed for SHG | 1728002017/AV/22012034621450 — सेग्रीगेशन शेड निर्माण कार्य मनरेगा+15 वॉं वित्‍त ग्राम पंचायत खेजडादेव | Completed | 20000 | 19584 | 2022-10-04 - 2022-11-11
BHOPAL / PHANDA / KHEJDADEO | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1728002017/DP/02 — वाटिका में व़क्षारोपण खेजडादेव | Completed | 132000 | 36055 | 2008-07-24 - 2016-08-20
BHOPAL / PHANDA / KHEJDADEO | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1728002017/DP/03 — व़क्षारोपण रोड के किनारे | Completed | 875000 | 179235 | 2008-07-24 - 2016-08-20
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1728002017/DP/22012034440654 — सामुदायिक कूप निर्माण कार्य डोबरा, खेजडादेव | Closed | 0 | 0 | 2019-04-14 -
BHOPAL / PHANDA / KHEJDADEO | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1728002017/DP/22012034488724 — सामुदायिक व़क्षारोपण कार्य शमशान घाट, खेजडादेव | Ongoing | 390826.48 | 199551 | 2020-06-16 -
BHOPAL / PHANDA / KHEJDADEO | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1728002017/DP/22012034488725 — सामुदायिक व़क्षारोण्‍प कार्य शमशान घाट, डोबरा, खेजडादेव | Ongoing | 390826.48 | 198713 | 2020-06-16 -
BHOPAL / PHANDA / KHEJDADEO | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1728002017/DP/22012034491297 — सामुदायिक व़क्षारोपण कार्य मंदिर प्रांगण, चांदपुर, खेजडादेव | Ongoing | 390826.48 | 149840 | 2020-08-25 -
BHOPAL / PHANDA / KHEJDADEO | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1728002017/DP/475 — बांस व्रक्षारोपण/ विशनखेडी पंचायत खेजडादेव | Completed | 120000 | 8528 | 2010-07-15 - 2016-08-20
BHOPAL / PHANDA / KHEJDADEO | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1728002017/DP/9926693136 — निर्मल वाटिका ग्राम पंचायत खेजडादेव | Completed | 301000 | 271660 | 2012-01-20 - 2013-03-28
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Horticulture / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1728002017/IF/20 — नंदन फलोधान पूरनसिंह/रेवाराम खेजडादेव | Completed | 132000 | 12350 | 2008-07-24 - 2016-09-23
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1728002017/IF/22012034340793 — वृक्षारोपण कार्य तालाब के पास, खेल मैदान, स्कूल के पास डोबरा ग्रामपंचायत खेजड़ादेव | Completed | 335000 | 10948 | 2017-05-23 - 2018-06-02
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1728002017/IF/22012034340794 — वृक्षारोपण कार्य शमशान के पास खेजड़ादेव | Completed | 335000 | 11278 | 2017-05-23 - 2018-06-02
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1728002017/IF/22012034340798 — वृक्षारोपण कार्य स्कूल, खेल मैदान, शमशान के पास विशनखेड़ी खेजड़ादेव | Completed | 335000 | 10590 | 2017-08-02 - 2018-01-23
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1728002017/IF/22012034340800 — वृक्षारोपण कार्य खेल मैदान, शमशान, स्कूल के पास चांदपुर खेजड़ादेव | Completed | 335000 | 10590 | 2017-08-02 - 2018-04-28
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1728002017/IF/22012034342949 — व्रक्छारोपण कार्य तालाब किनारे ग्राम डोबरा ग्राम पंचायत खेजड़ादेव | Closed | 84000 | 0 | 2017-05-22 -
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1728002017/IF/22012034715979 — कपिलधारा कूप सह खेततालाब निर्माण कार्य गुलाब सिंह / रामप्रसाद, खेजडादेव | Completed | 294161.33 | 278331.56 | 2021-05-04 - 2026-06-05
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1728002017/IF/47 — कूप निर्माण पूरनसिंह/रेवाराम | Completed | 180000 | 18109 | 2009-04-01 - 2014-04-02
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1728002017/IF/9926700949 — कूप निमार्ण कार्य उमेद सिंह/पूरन सिंह ग्रा पं खेजड | Completed | 331700 | 286231 | 2014-02-11 - 2014-07-07
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/1008430 — Construction of IAY House -IAY REG. NO. MP1493332 | Completed | 15480 | 14448 | 2017-08-01 - 2017-11-01
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/1892410 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4195900 | Completed | 15660 | 14616 | 2018-07-24 - 2018-12-20
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/1892533 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4262192 | Completed | 15660 | 15486 | 2018-07-24 - 2019-02-21
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/1893788 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4864328 | Completed | 15660 | 14616 | 2018-07-24 - 2018-12-05
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/1893838 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4893568 | Completed | 15660 | 15486 | 2018-07-24 - 2019-02-21
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/1893899 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4917316 | Completed | 15660 | 15660 | 2018-07-24 - 2019-01-08
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/1894197 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5102712 | Completed | 15660 | 13572 | 2018-07-24 - 2018-11-27
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/1894198 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5102747 | Completed | 15660 | 14616 | 2018-07-24 - 2019-02-28
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/1894199 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5102916 | Completed | 15660 | 15660 | 2018-07-24 - 2019-01-08
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/1902100 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5103367 | Completed | 15660 | 14616 | 2018-07-24 - 2018-11-20
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/1902461 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5103353 | Completed | 15660 | 15660 | 2018-08-21 - 2019-01-08
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/1902538 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5158705 | Completed | 15660 | 14616 | 2018-08-14 - 2019-02-28
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/1902545 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5163566 | Completed | 15660 | 14616 | 2018-08-14 - 2018-12-19
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/1902547 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5164495 | Completed | 15660 | 13572 | 2018-07-24 - 2018-11-13
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/1947517 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5123793 | Completed | 15840 | 13728 | 2019-07-02 - 2020-03-10
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/2099074 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4108567 | Completed | 15840 | 13728 | 2019-07-16 - 2020-03-10
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/2104407 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4232728 | Completed | 15840 | 14784 | 2019-07-16 - 2020-02-12
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/2105687 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4252409 | Completed | 15840 | 14784 | 2019-07-23 - 2020-02-19
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/2107971 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4297943 | Completed | 15840 | 14784 | 2019-07-16 - 2020-03-05
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/2137325 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4945468 | Completed | 15840 | 14784 | 2019-07-09 - 2020-03-10
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/2142548 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5084458 | Completed | 15840 | 14784 | 2019-07-16 - 2020-04-23
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/2143660 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5102824 | Completed | 15840 | 13728 | 2019-07-16 - 2020-03-05
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/2143995 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5111175 | Completed | 15840 | 13728 | 2019-07-23 - 2020-03-05
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/2144504 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5123361 | Completed | 15840 | 14784 | 2019-07-02 - 2020-03-06
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/2145641 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5154809 | Completed | 15840 | 13728 | 2019-07-02 - 2019-12-25
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/2145998 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5163664 | Completed | 15840 | 13728 | 2019-07-02 - 2020-03-10
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/3700478 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106146599 | Completed | 18360 | 18360 | 2022-07-26 - 2022-11-16
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/3732341 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124341555 | Completed | 18360 | 17544 | 2022-07-15 - 2022-12-19
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/3745308 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124534823 | Completed | 18360 | 18156 | 2022-07-15 - 2022-11-16
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/3751997 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125539169 | Completed | 18360 | 17340 | 2022-06-21 - 2023-12-20
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/3754531 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125561861 | Completed | 18360 | 18156 | 2022-07-15 - 2022-11-28
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/3759708 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120306956 | Completed | 18360 | 18156 | 2022-07-15 - 2022-11-10
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/3759963 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127231671 | Completed | 18360 | 18156 | 2022-07-15 - 2022-11-16
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/3761205 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124810563 | Completed | 18360 | 14688 | 2022-07-15 - 2024-05-13
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/3792534 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106146612 | Completed | 18360 | 18156 | 2022-07-26 - 2022-11-16
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/3844253 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124178880 | Completed | 18360 | 18156 | 2022-07-15 - 2022-11-16
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/3845280 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124179614 | Completed | 18360 | 18156 | 2022-07-15 - 2022-11-10
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/3852130 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122377853 | Completed | 18360 | 18156 | 2022-07-15 - 2022-11-16
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/3855489 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128971655 | Completed | 18360 | 18156 | 2022-07-15 - 2022-11-16
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/3862246 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144266880 | Completed | 18360 | 18156 | 2022-07-15 - 2022-11-10
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/3871972 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145206352 | Completed | 18360 | 17748 | 2022-07-26 - 2023-12-20
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/3880469 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141833820 | Completed | 18360 | 17748 | 2022-07-15 - 2022-12-05
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/3880477 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141838428 | Completed | 18360 | 18360 | 2022-07-15 - 2022-11-21
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/3920740 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117271110 | Completed | 18360 | 18310 | 2022-07-15 - 2024-05-01
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/3942088 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120308569 | Completed | 18360 | 18360 | 2022-07-15 - 2022-12-06
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/3945192 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128972553 | Completed | 18360 | 18326 | 2022-09-27 - 2023-10-19
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/3946997 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141833843 | Completed | 18360 | 15944 | 2022-08-09 - 2024-05-13
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/3946998 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141838324 | Completed | 18360 | 18156 | 2022-07-15 - 2022-11-07
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/3946999 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141838411 | Completed | 18360 | 17136 | 2022-07-15 - 2023-01-10
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/4024484 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144266862 | Completed | 18360 | 18156 | 2022-07-15 - 2022-11-10
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/4260603 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103634197 | Completed | 18360 | 17989 | 2022-10-04 - 2024-05-01
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/4262797 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100884350 | Completed | 18360 | 18360 | 2022-07-15 - 2022-12-25
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/4262798 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100884410 | Completed | 18360 | 18360 | 2022-08-02 - 2022-11-16
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/4264034 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115188909 | Completed | 18360 | 17544 | 2022-07-15 - 2022-11-21
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/4267744 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124528088 | Completed | 18360 | 18360 | 2022-07-15 - 2022-11-21
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/4533300 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100851386 | Completed | 23490 | 21697.16 | 2024-11-08 - 2025-05-07
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/4539520 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103627356 | Ongoing | 23490 | 18297.98 | 2025-03-18 -
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/4545929 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106146623 | Completed | 23490 | 21698.36 | 2024-11-08 - 2025-05-07
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/4557767 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115212634 | Completed | 23490 | 21425 | 2025-03-18 - 2026-05-07
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/4570733 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116773229 | Completed | 23490 | 21698.36 | 2024-11-08 - 2026-03-26
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/4644137 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141833752 | Completed | 23490 | 21698.36 | 2024-11-08 - 2025-05-07
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/4646262 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142532659 | Completed | 23490 | 21698.36 | 2024-11-08 - 2026-03-26
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/4652352 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145220539 | Completed | 23490 | 21698.36 | 2024-11-08 - 2025-05-07
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/4935243 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100811459 | Completed | 23490 | 23229 | 2025-07-15 - 2025-11-11
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/4935756 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103625632 | Completed | 23490 | 23482.02 | 2025-05-20 - 2026-02-19
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/4937520 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106146645 | Completed | 23490 | 23449.92 | 2025-06-10 - 2026-02-19
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/4941360 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113886393 | Completed | 23490 | 23478 | 2025-06-10 - 2026-02-19
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/4941362 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113886433 | Ongoing | 23490 | 4698 | 2025-06-10 -
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/4943005 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114095539 | Completed | 23490 | 23143.8 | 2025-05-27 - 2026-02-23
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/4946522 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116704751 | Completed | 23490 | 23452.92 | 2025-06-10 - 2026-02-27
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/4956520 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120307316 | Completed | 23490 | 23449.92 | 2025-06-10 - 2026-02-19
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/4956521 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120308216 | Completed | 23490 | 23223 | 2025-06-10 - 2026-02-23
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/4956522 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120308398 | Completed | 23490 | 22880.8 | 2025-04-08 - 2026-02-27
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/4956524 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120308914 | Completed | 23490 | 23220 | 2025-06-10 - 2026-02-23
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/4957521 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122377119 | Physically Completed | 23490 | 21663 | 2025-12-23 - 2026-06-12
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/4958630 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124170179 | Completed | 23490 | 23217 | 2025-06-10 - 2026-02-23
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/4958631 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124171570 | Completed | 23490 | 23223 | 2025-06-10 - 2025-11-11
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/4959115 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124535420 | Completed | 23490 | 23220 | 2025-06-10 - 2025-11-11
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/4961224 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125537559 | Completed | 23490 | 23220 | 2025-06-10 - 2026-02-23
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/4961228 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125537931 | Completed | 23490 | 23490 | 2025-09-23 - 2026-02-27
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/4961229 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125538274 | Completed | 23490 | 23212.02 | 2025-05-20 - 2026-02-23
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/4962770 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125313616 | Completed | 23490 | 21654 | 2025-06-10 - 2026-03-26
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/4963400 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125579479 | Completed | 23490 | 23217 | 2025-05-27 - 2026-02-23
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/4969732 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128971142 | Completed | 23490 | 23196 | 2025-04-08 - 2026-02-23
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/4969736 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128974743 | Completed | 23490 | 23220 | 2025-06-10 - 2026-02-23
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/4976493 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142023575 | Completed | 23490 | 22437 | 2025-05-27 - 2026-03-26
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/4977836 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141833794 | Completed | 23490 | 23220 | 2025-06-10 - 2025-11-11
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/4981198 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145199141 | Physically Completed | 23490 | 21141 | 2025-07-29 - 2026-02-03
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/5123098 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142023035 | Physically Completed | 23490 | 21402 | 2025-07-15 - 2026-01-02
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/5129392 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116460244 | Physically Completed | 23490 | 23490 | 2025-08-12 - 2026-02-03
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/5131041 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113886508 | Completed | 23490 | 23214 | 2025-05-20 - 2026-02-23
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/5388707 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120623123 | Physically Completed | 23490 | 21402 | 2025-06-10 - 2026-06-16
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/5393076 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106339709 | Completed | 23490 | 22968 | 2025-12-23 - 2026-05-04
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/5395159 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142532629 | Physically Completed | 23490 | 23490 | 2025-08-19 - 2026-02-03
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/5399745 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120622583 | Physically Completed | 23490 | 22968 | 2025-08-12 - 2026-02-04
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/5402434 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116773431 | Completed | 23490 | 22913.88 | 2025-06-10 - 2025-11-11
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/5594171 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105456739 | Completed | 23490 | 23217 | 2025-06-10 - 2026-02-23
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/5595563 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125308862 | Completed | 23490 | 22950.96 | 2025-06-10 - 2026-03-26
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/5596293 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116705187 | Completed | 23490 | 22965 | 2025-06-10 - 2025-11-11
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/5641186 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127232704 | Completed | 23490 | 23217 | 2025-06-03 - 2026-02-23
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/5642422 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145224530 | Completed | 23490 | 23229 | 2025-10-14 - 2026-05-07
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/5732982 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147923225 | Physically Completed | 23490 | 23229 | 2026-01-20 - 2026-06-12
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/5796450 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124170891 | Approved | 23490 | 0 | 2025-08-26 -
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/585477 — Construction of IAY House -IAY REG. NO. MP1882960 | Completed | 15030 | 14448 | 2017-05-23 - 2017-10-24
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/585688 — Construction of IAY House -IAY REG. NO. MP2022387 | Completed | 15030 | 14388 | 2017-03-22 - 2017-12-19
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/587307 — Construction of IAY House -IAY REG. NO. MP3576278 | Completed | 15030 | 15008 | 2017-03-01 - 2017-10-06
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/5902775 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120307650 | Ongoing | 23490 | 5742 | 2026-06-02 -
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/5902903 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106339565 | Ongoing | 23490 | 7308 | 2026-05-26 -
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/5907273 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119862880 | Approved | 23490 | 0 | 2026-01-28 -
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/5908103 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116704822 | Approved | 23490 | 0 | 2026-01-22 -
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/5909354 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105453011 | Approved | 23490 | 0 | 2026-01-28 -
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/5910085 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113689889 | Approved | 23490 | 0 | 2026-01-22 -
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/5913312 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128974339 | Ongoing | 23490 | 6264 | 2026-05-19 -
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/5916304 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113728804 | Ongoing | 23490 | 2088 | 2026-06-16 -
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/5916630 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113692230 | Ongoing | 23490 | 6264 | 2026-05-19 -
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/5920485 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116705505 | Ongoing | 23490 | 4698 | 2026-05-26 -
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/5922623 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116704689 | Ongoing | 23490 | 2610 | 2026-06-16 -
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/5925632 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113728920 | Ongoing | 23490 | 1044 | 2026-06-16 -
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/5926791 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113443872 | Approved | 23490 | 0 | 2026-01-28 -
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/5931815 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106434542 | Approved | 23490 | 0 | 2026-01-28 -
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/594715 — Construction of IAY House -IAY REG. NO. MP2599645 | Completed | 15030 | 14268 | 2017-03-01 - 2017-11-01
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/595113 — Construction of IAY House -IAY REG. NO. MP3446684 | Completed | 15030 | 14620 | 2017-05-09 - 2017-12-19
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/614401 — Construction of IAY House -IAY REG. NO. MP1882981 | Completed | 15030 | 14792 | 2017-05-09 - 2017-12-19
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/6156683 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119280195 | Ongoing | 23490 | 4698 | 2026-06-02 -
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/6159589 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122442244 | Approved | 23490 | 0 | 2025-02-18 -
BHOPAL / PHANDA / KHEJDADEO | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002017/IF/IAY/806324 — Construction of IAY House -IAY REG. NO. MP3576332 | Completed | 15480 | 14104 | 2017-08-01 - 2018-01-09
BHOPAL / PHANDA / KHEJDADEO | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Land Leveling / Levelling/shaping of Wasteland Land for Community | Land Development | 1728002017/LD/22012034299910 — khel maidan khejdadev | Closed | 0 | 0 | 2017-04-14 -
BHOPAL / PHANDA / KHEJDADEO | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1728002017/LD/3799380090 — खेल मैदान चांदपुर ग्राम पंचायत खेजडादेव | Completed | 412000 | 397436 | 2010-12-12 - 2011-07-04
BHOPAL / PHANDA / KHEJDADEO | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1728002017/LD/3799381948 — शांति धाम विकास कार्य ग्राम पंचायत खेजडादेव | Completed | 470245 | 341007 | 2012-06-29 - 2014-11-17
BHOPAL / PHANDA / KHEJDADEO | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1728002017/PG/22012034312672 — खेल मैदान निर्माण कार्य विशनखेडी खेजडादेव | Completed | 186600 | 137574.91 | 2017-06-13 - 2020-05-29
BHOPAL / PHANDA / KHEJDADEO | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1728002017/PG/22012034312673 — खेल मैदान निर्माण कार्य डोबरा,खेजडादेव | Completed | 186600 | 136282.91 | 2017-06-13 - 2020-05-28
BHOPAL / PHANDA / KHEJDADEO | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002017/RC/22012034154503 — सी सी रोड निर्माण पंचपरमेश्‍वर ग्राम पंचायत खेजडाद | Completed | 136000 | 130020.05 | 2012-05-27 - 2012-07-13
BHOPAL / PHANDA / KHEJDADEO | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002017/RC/22012034162292 — सी सी रोड निर्माण कार्य लक्ष्‍मीनारायण के घर ये बा | Completed | 177000 | 152678 | 2013-03-07 - 2013-11-22
BHOPAL / PHANDA / KHEJDADEO | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002017/RC/22012034175997 — सी सी रोड लक्ष्‍मीनारायण के घर से बाबूलाल के घर त | Completed | 79000 | 61584 | 2013-07-24 - 2013-11-23
BHOPAL / PHANDA / KHEJDADEO | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002017/RC/22012034195468 — सी सी रोड पंचपरमेश्‍वर लक्ष्‍मीनारायण से अवधनारायण | Completed | 77300 | 64857 | 2013-12-24 - 2014-03-18
BHOPAL / PHANDA / KHEJDADEO | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002017/RC/22012034200290 — सी सी रोड पंचपरमेश्‍वर अवधनारायण से अजब के घर तक | Completed | 149200 | 133977 | 2014-01-27 - 2014-03-29
BHOPAL / PHANDA / KHEJDADEO | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1728002017/RC/22012034211425 — सुदूर ग्राम संपर्क खेजडादेव से छोटी पठार तक, ग्राम | Completed | 1493000 | 452311 | 2014-03-05 - 2016-06-29
BHOPAL / PHANDA / KHEJDADEO | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002017/RC/22012034329004 — सी सी रोड निर्माण मनरेगा +पंचपरमेस्वर अशोक मीना के घर से संजीव के घर तक ग्राम पंचायत खेजड़ादेव | Completed | 92000 | 92390 | 2017-03-01 - 2017-05-12
BHOPAL / PHANDA / KHEJDADEO | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1728002017/RC/22012034334609 — सुदूर ग्राम संपर्क खेजडादेव से मनीखेडी छोटी पटार की ओर, खेजडादेव | Completed | 325000 | 295032.14 | 2017-04-25 - 2019-06-22
BHOPAL / PHANDA / KHEJDADEO | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1728002017/RC/22012034375496 — खेत सडक उमेद से हिम्‍मतसिंह के खेत तक डोबरा, खेजडादेव | Closed | 0 | 0 | 2018-04-14 -
BHOPAL / PHANDA / KHEJDADEO | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002017/RC/22012034437190 — C C ROAD NIRMAN KARYA NARESH SE MAHESH KI GHAR KI AUR | Closed | 0 | 0 | 2019-04-14 -
BHOPAL / PHANDA / KHEJDADEO | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002017/RC/22012034438637 — c c road panchpermeshwar | Closed | 0 | 0 | 2019-04-14 -
BHOPAL / PHANDA / KHEJDADEO | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1728002017/RC/22012034439016 — सुदुर सडक शेर ि‍सिंह के घर से मंदिर तक | Closed | 0 | 0 | 2019-04-14 -
BHOPAL / PHANDA / KHEJDADEO | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002017/RC/22012034503050 — सी सी रोड अभिसरण मनरेगा +14वां वित्‍त सीताराम से मन्‍नू के घर तक, विशनखेडी, खेजडादेव | Completed | 90625 | 89760 | 2019-10-29 - 2020-02-04
BHOPAL / PHANDA / KHEJDADEO | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1728002017/RC/22012034527924 — खेत सडक ग्रेवल रोड डोबरा मंदिर से शेर सिंह के खेत तक, खेजडादेव | Completed | 1721422.85 | 1461426.1 | 2020-07-14 - 2022-06-13
BHOPAL / PHANDA / KHEJDADEO | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1728002017/RC/22012034527925 — सुदूर ग्राम संपर्क सडक ग्रेवल रोड डोबरा मेन रोड से शमशान तक, खेजडादेव | Ongoing | 1271265.51 | 382805.79 | 2020-07-07 -
BHOPAL / PHANDA / KHEJDADEO | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002017/RC/22012034535056 — सी सी रोड निर्माण मनरेगा+14 वां वित्‍त रामस्‍वरूप से अशोक के घर तक, चांदपुर, खेजडादेव | Completed | 44179 | 43320 | 2020-08-25 - 2020-09-10
BHOPAL / PHANDA / KHEJDADEO | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002017/RC/22012034535057 — सी सी रोड निर्माण मनरेगा+14 वां वित्‍त नरेश से अशोक के घर तक, चांदपुर, खेजडादेव | Completed | 87975 | 87780 | 2020-08-25 - 2020-10-01
BHOPAL / PHANDA / KHEJDADEO | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002017/RC/22012034679821 — सी सी रोड निर्माण कार्य डोबरा मंदिर से नदी तक, खेजडादेव | New | 0 | 0 | 2024-04-14 -
BHOPAL / PHANDA / KHEJDADEO | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002017/RC/22012034823783 — सी सी रोड निर्माण मनरेगा +15 वां वित्त जगदीश से शैतान के घर तक, डोबरा, खेजडादेव | Completed | 21312 | 20646.6 | 2024-08-12 - 2024-12-06
BHOPAL / PHANDA / KHEJDADEO | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002017/RC/22012034823786 — सी सी रोड निर्माण मनरेगा +15 वां वित्त कोमल के घर से मेन रोड तक, डोबरा, खेजडादेव | Completed | 44650 | 39594 | 2024-08-06 - 2026-06-05
BHOPAL / PHANDA / KHEJDADEO | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002017/RC/22012034840172 — सी सी रोड निर्माण कार्य मनरेगा +15 वां वित्‍त स्‍कूल परिसर, खेजडादेव | Approved | 42000 | 0 | 2024-10-02 -
BHOPAL / PHANDA / KHEJDADEO | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1728002017/RC/4 — सी सी रोड चांदपुर, खेजडादेव | Completed | 280000 | 272523 | 2008-08-23 - 2008-08-23
BHOPAL / PHANDA / KHEJDADEO | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1728002017/RC/51 — सी सी रोड डोबरा, खेजडादेव | Completed | 294000 | 271689 | 2009-04-01 - 2009-04-01
BHOPAL / PHANDA / KHEJDADEO | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1728002017/RC/52 — सी सी रोड विशनखेडी, खेजडादेव | Completed | 294000 | 281615 | 2008-11-15 - 2009-04-01
BHOPAL / PHANDA / KHEJDADEO | D--RURAL INFRASTUCTURE / Rural Sanitation | Compost Pit / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1728002017/RS/22012034383787 — सार्वजनिक नाडेप निर्माण कार्य खेजडादेव | Closed | 0 | 0 | 2018-04-14 -
BHOPAL / PHANDA / KHEJDADEO | D--RURAL INFRASTUCTURE / Rural Sanitation | Compost Pit / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1728002017/RS/22012034384100 — नाडेप निर्माण कार्य खेजडादेव | Closed | 0 | 0 | 2018-04-14 -
BHOPAL / PHANDA / KHEJDADEO | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1728002017/RS/22012034497718 — सामुदायिक स्वच्छता परिसर, अभिसरण मनरेगा,15 वां वित्त, एसबीएम खेल ग्राउंड के पास, चांदपुर, खेजडादेव | Completed | 44000 | 43320 | 2020-11-10 - 2021-03-01
BHOPAL / PHANDA / KHEJDADEO | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1728002017/RS/22012034501119 — नाली निर्माण कार्य मनरेगा 15 वां वित्त मेन रोड राधेश्‍याम के घर से राम मंदिर, डोबरा, खेजडादेव | Completed | 84375 | 83980 | 2021-01-05 - 2021-02-10
BHOPAL / PHANDA / KHEJDADEO | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1728002017/RS/22012034501120 — नाली निर्माण कार्य मनरेगा 14 वां वित्त पवर्त से नर्वदा मीना के घर तक, खेजडादेव | Completed | 41612 | 41040 | 2021-01-05 - 2021-01-30
BHOPAL / PHANDA / KHEJDADEO | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1728002017/RS/22012034601946 — सामुदायिक नाडेप निर्माण कार्य (संख्‍या 10) ग्राम पंचायत खेजडादेव | Completed | 145420.01 | 110847.31 | 2021-11-30 - 2023-09-12
BHOPAL / PHANDA / KHEJDADEO | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1728002017/RS/22012034601953 — लीच पीट निर्माण कार्य (संख्‍या 10) ग्राम पंचायत खेजडादेव | Closed | 102498.68 | 0 | 2021-10-02 -
BHOPAL / PHANDA / KHEJDADEO | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1728002017/RS/22012034617234 — लीच पिट निर्माण कार्य (संख्या 25), ग्राम पंचायत खेजडादेव | Completed | 195942.48 | 103436.67 | 2022-02-01 - 2023-07-07
BHOPAL / PHANDA / KHEJDADEO | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1728002017/RS/22012035113943 — पाइप नाली निर्माण कार्य मनरेगा +15 वां वित्‍त, मेन रोड से स्‍कूल तक, डोबरा, खेजडादेव | Completed | 25700 | 24752 | 2023-10-05 - 2024-07-15
BHOPAL / PHANDA / KHEJDADEO | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1728002017/RS/22012035113953 — पाइप नाली निर्माण मनरेगा+15वां वित्‍त,मेन रोड से अचल के घर तक, डोबरा, खेजडादेव | Completed | 18215 | 17459 | 2023-10-05 - 2024-07-15
BHOPAL / PHANDA / KHEJDADEO | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1728002017/RS/22012035130812 — सामुदायिक लीच पिट निर्माण मनरेगा + 15 वां वित्त, मनोज के घर से शास.हेंडपपं तक, खेजडादेव | Physically Completed | 61095 | 45817.14 | 2024-11-06 - 2026-06-16
BHOPAL / PHANDA / KHEJDADEO | D--RURAL INFRASTUCTURE / Bharat Nirman Sewa Kendra | New Construction / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1728002017/SK/9993648605 — Bharat Nirman Rajeev Gandhi Sewa Kendra,KHEJDADEO | Completed | 1363000 | 543785 | 2016-06-21 - 2017-11-30
BHOPAL / PHANDA / KHEJDADEO | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1728002017/WC/2 — कन्‍टूर टेन्‍ज चांदपुर , खेजडादेव | Completed | 67000 | 40672 | 2009-01-07 - 2009-01-07
BHOPAL / PHANDA / KHEJDADEO | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1728002017/WC/22012034325837 — तालाब मरम्मत कार्य डोबरा ग्राम पंचायत खेजड़ादेव | Completed | 168000 | 41452 | 2017-05-23 - 2017-12-20
BHOPAL / PHANDA / KHEJDADEO | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1728002017/WC/22012034379778 — MWCचेक डेम निर्माण महेंद्र मीणा, सुरेंद्र मीणा के खेत के पास खेजडादेव | Completed | 1358002 | 1265556.6 | 2017-12-19 - 2020-10-29
BHOPAL / PHANDA / KHEJDADEO | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1728002017/WC/22012034472085 — सोख्‍ता गढढा निर्माण कार्य शमशान के पास, खेजडादेव | Completed | 13427.22 | 9504 | 2019-08-06 - 2020-02-27
BHOPAL / PHANDA / KHEJDADEO | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1728002017/WC/22012034472087 — सोख्‍ता गढढा निर्माण कार्य स्‍कूल के पास, विशनखेडी खेजडादेव | Completed | 13427.22 | 7392 | 2019-08-06 - 2019-09-11
BHOPAL / PHANDA / KHEJDADEO | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1728002017/WC/22012034472088 — सोख्‍ता गढढा निर्माण कार्य स्‍कूल के पास, डोबरा, खेजडादेव | Completed | 13427.22 | 8448 | 2019-08-06 - 2019-10-01
BHOPAL / PHANDA / KHEJDADEO | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1728002017/WC/22012034474409 — सोख्‍ता गढढा निर्माण कार्य शासकीय स्‍कूल के पास, खेजडादेव | Completed | 13427.22 | 8448 | 2019-08-06 - 2019-10-03
BHOPAL / PHANDA / KHEJDADEO | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1728002017/WC/22012034474411 — सोख्‍ता गढढा निर्माण कार्य गीताचरण के घर के पास, खेजडादेव | Completed | 13427.22 | 7392 | 2019-08-13 - 2019-10-10
BHOPAL / PHANDA / KHEJDADEO | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1728002017/WC/22012034474412 — सोख्‍ता गढढा निर्माण कार्य प्राइवेट स्‍कूल के पास, चांदपुर, खेजडादेव | Completed | 13427.22 | 9504 | 2019-08-13 - 2019-10-04
BHOPAL / PHANDA / KHEJDADEO | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1728002017/WC/22012034474413 — सोख्‍ता गढढा निर्माण कार्य शासकीय स्‍कूल के पास,चांदपुर, खेजडादेव | Completed | 13427.22 | 9504 | 2019-07-30 - 2019-09-05
BHOPAL / PHANDA / KHEJDADEO | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1728002017/WC/22012034474417 — सोख्‍ता गढढा निर्माण कार्य खेल मैदान के पास, चांदपुर खेजडादेव | Completed | 13427.22 | 8448 | 2019-07-30 - 2019-09-04
BHOPAL / PHANDA / KHEJDADEO | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1728002017/WC/22012034474418 — सोख्‍ता गढढा निर्माण कार्य तालाब के पास, डोबरा खेजडादेव | Completed | 13427.22 | 7392 | 2019-08-20 - 2019-09-11
BHOPAL / PHANDA / KHEJDADEO | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1728002017/WC/22012034474419 — सोख्‍ता गढढा निर्माण कार्य शमशान के पास, डोबरा, खेजडादेव | Completed | 13427.22 | 6336 | 2019-07-30 - 2019-08-29
BHOPAL / PHANDA / KHEJDADEO | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1728002017/WC/22012034474420 — सोख्‍ता गढढा निर्माण कार्य आंगनबाडी के पास, डोबरा, खेजडादेव | Completed | 13427.22 | 8448 | 2019-08-13 - 2019-09-04
BHOPAL / PHANDA / KHEJDADEO | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1728002017/WC/22012034527765 — पोण्‍ड निर्माण कार्य शमशान के पास ग्राम विशनखेडी, खेजडादेव | Completed | 310386.65 | 267099.99 | 2020-04-28 - 2020-11-26
BHOPAL / PHANDA / KHEJDADEO | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1728002017/WC/22012034547006 — MWC चेक डेम निर्माण कार्य ग्राम पंचायत खेजडादेव | Closed | 0 | 0 | 2020-01-30 -
BHOPAL / PHANDA / KHEJDADEO | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1728002017/WC/22012034566400 — सोख्‍ता गढढा निर्माण कार्य पंचायत भवन के पास, खेजडादेव | Completed | 14283.77 | 10260 | 2020-07-14 - 2020-09-20
BHOPAL / PHANDA / KHEJDADEO | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1728002017/WC/22012034566401 — सोख्‍ता गढढा निर्माण कार्य शेरू के घर के पास, खेजडादेव | Completed | 14283.77 | 10260 | 2020-07-14 - 2020-09-20
BHOPAL / PHANDA / KHEJDADEO | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1728002017/WC/22012034566402 — सोख्‍ता गढढा निर्माण कार्य पंचायत भवन के पास, खेजडादेव | Completed | 14283.77 | 10260 | 2020-07-14 - 2020-09-20
BHOPAL / PHANDA / KHEJDADEO | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1728002017/WC/22012034566403 — सोख्‍ता गढढा निर्माण कार्य शमशान के पास, चांदपुर, खेजडादेव | Completed | 14283.77 | 10260 | 2020-07-28 - 2020-09-20
BHOPAL / PHANDA / KHEJDADEO | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1728002017/WC/22012034566404 — सोख्‍ता गढढा निर्माण कार्य शमशान के पास, डोबरा, खेजडादेव | Completed | 14283.77 | 9500 | 2020-07-14 - 2020-09-20
BHOPAL / PHANDA / KHEJDADEO | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1728002017/WC/22012034566405 — सोख्‍ता गढढा निर्माण कार्य नदी के पास, डाेबरा, खेजडादेव | Completed | 14283.77 | 10260 | 2020-08-11 - 2020-09-20
BHOPAL / PHANDA / KHEJDADEO | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1728002017/WC/22012034615311 — चेक डेम निर्माण कार्य खेजडादेव | Closed | 0 | 0 | 2020-10-02 -
BHOPAL / PHANDA / KHEJDADEO | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone boulder Gully Plugs for Comm / Construction of Stone boulder Gully Plugs for Community | Boulder Check/Gully Plug | 1728002017/WC/22012034695779 — गली प्‍लग / बोल्‍डर चेक निर्माण्‍ा कार्य, बाबडिया नाला, (संख्‍या10), खेजडादेव | Closed | 184565.52 | 0 | 2021-04-14 -
BHOPAL / PHANDA / KHEJDADEO | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone boulder Gully Plugs for Comm / Construction of Stone boulder Gully Plugs for Community | Boulder Check/Gully Plug | 1728002017/WC/22012034695781 — गली प्‍लग / बोल्‍डर चेक निर्माण्‍ा कार्य, बाबडिया नाला, (संख्‍या10), खेजडादेव | Deleted | 0 | 0 | 2021-04-14 -
BHOPAL / PHANDA / KHEJDADEO | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone boulder Gully Plugs for Comm / Construction of Stone boulder Gully Plugs for Community | Boulder Check/Gully Plug | 1728002017/WC/22012034695802 — गली प्‍लग / बोल्‍डर चेक निर्माण्‍ा कार्य, विशनखेडीनाला, (संख्‍या 10),खेजडादेव | Closed | 184565.52 | 0 | 2021-04-14 -
BHOPAL / PHANDA / KHEJDADEO | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1728002017/WC/22012034717671 — MWC चेक डेम निर्माण कार्य दूधी नदी पंचायत भवन के सामने, खेजडादेव | Completed | 1270665.3 | 1234748.23 | 2021-05-25 - 2021-11-12
BHOPAL / PHANDA / KHEJDADEO | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1728002017/WC/22012034839159 — चेकडेम निर्माण कार्य खेजडादेव | Closed | 0 | 0 | 2021-04-14 -
BHOPAL / PHANDA / KHEJDADEO | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1728002017/WC/22012034951071 — चेक डेम निर्माण कार्य भागदिया नदी पर ग्राम पंचायत खेजडादेव | Deleted | 0 | 0 | 2022-03-18 -
BHOPAL / PHANDA / KHEJDADEO | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1728002017/WC/22012034951078 — चेक डेम निर्माण कार्य दिवितिया ग्राम पंचायत खेजडादेव | Closed | 0 | 0 | 2022-03-18 -
BHOPAL / PHANDA / KHEJDADEO | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1728002017/WC/22012034951079 — चेक डेम निर्माण कार्य भागदिया नदी पर ग्राम पंचायत खेजडादेव | Closed | 0 | 0 | 2022-03-18 -
BHOPAL / PHANDA / KHEJDADEO | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1728002017/WC/22012034959344 — चेक डेम निर्माण कार्य मनरेगा+ 15 वां वित्त, बागड़िया नदी पर, खेजडादेव | Completed | 745000 | 741959.12 | 2022-05-03 - 2023-07-07
BHOPAL / PHANDA / KHEJDADEO | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1728002017/WC/22012034959345 — चेक डेम निर्माण कार्य द्वितीय, मनरेगा+ 15 वां वित्त+जनभागीदारी, खेजडादेव | Deleted | 0 | 0 | 2022-04-08 -
BHOPAL / PHANDA / KHEJDADEO | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1728002017/WC/22012034959346 — चेक डेम निर्माण कार्य द्वितीय, मनरेगा+ 15 वां वित्त, खेजडादेव | Completed | 780000 | 779163.4 | 2022-05-03 - 2023-07-07
BHOPAL / PHANDA / KHEJDADEO | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1728002017/WC/22012035181533 — सोख्ता गढढा निर्माण कार्य (संख्या 5) डोबरा, ग्राम पंचायत खेजडादेव | Closed | 0 | 0 | 2024-01-25 -
BHOPAL / PHANDA / KHEJDADEO | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1728002017/WC/22012035197453 — चेक डेम निर्माण कार्य हलाली नदी, ग्राम पंचायत खेजडादेव | Closed | 0 | 0 | 2024-01-24 -
BHOPAL / PHANDA / KHEJDADEO | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1728002017/WC/69 — हलाली नदी गाद निकालना गहरीकरण | Completed | 500000 | 485401 | 2009-05-19 - 2009-04-01
BHOPAL / PHANDA / KHEJDADEO | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1728002017/WC/9993623291 — नाला सफाई चौडीकरण ग्राम पंचायत खेजडादेव | Completed | 480000 | 435440 | 2011-05-19 - 2012-07-06