## Work List
Exported on: 2026-08-26 13:33:19
Filters applied:
Data source: MGNREGA
District: BHOPAL
Block: PHANDA
Panchayat: KHAM KHEDA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
| 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1728002022/DP/22012034582370 — व़क्षाराेपण कार्य अम़त सरोवर के पास, खामखेडा | Ongoing | 427106.07 | 60035 | 2023-07-29
| 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1728002022/DP/353 — बांस व्रक्षारोपण खामखेडा | Completed | 127000 | 8800 | 2010-08-01 | 2010-07-01
| 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1728002022/DP/9926693480 — नि‍र्मल वाटि‍का 20 हितग्राही ग्राम पंचायत खामखेडा | Completed | 110000 | 109572 | 2012-07-14 | 2012-07-28
| 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1728002022/IF/22012034341807 — वृक्षारोपण कार्य शमशान ग्राम खामखेड़ा ग्रामपंचायत खामखेड़ा | Completed | 335000 | 279994 | 2017-07-15 | 2020-11-08
| 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1728002022/IF/22012034364454 — वृक्षारोपण कार्य तालाब ग्राम पंचायत खामखेडा | Completed | 335000 | 279976 | 2017-07-15 | 2020-08-12
| 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Block Plantation of Farm Forestry Trees in Fields for Individuals | Plantation | 1728002022/IF/22012034426766 — व़क्षारोपण कार्य पर्वत सिंह के खेत की मेढ पर, खामखेडा | Completed | 189600 | 143010 | 2018-08-25 | 2020-08-28
| 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Block Plantation of Farm Forestry Trees in Fields for Individuals | Plantation | 1728002022/IF/22012034426767 — व़क्षारोपण कार्य दीपक कुमार के खेत की मेढ पर, खामखेडा | Completed | 189200 | 143775 | 2018-09-29 | 2024-05-13
| 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Block Plantation of Farm Forestry Trees in Fields for Individuals | Plantation | 1728002022/IF/22012034624845 — व़क्षारापेण कार्य मलखान / मांगीलाल के खेत की मेढ पर, खामखेडा | Closed | 0 | 0 | 2020-01-26
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1728002022/IF/22012034635288 — पशु शेड निर्माण कार्य लक्ष्‍मीनारायण / किशोरी लाल, खामखेडा | Ongoing | 63830.2 | 6120 | 2022-05-21
| 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1728002022/IF/22012034660270 — FRA खेत समतलीकरण कार्य लखन सिंह / नन्‍नू लाल, खामखेडा | Closed | 62263.53 | 0 | 2020-10-02
| 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1728002022/IF/9926710537 — पशु शेड निर्माण मलखान / मांगीलाल, खामखेडा | Completed | 58000 | 56059 | 2014-03-01 | 2014-06-30
| 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1728002022/IF/9926710547 — पशु शेड निर्माण कमल सिंह / रामसिंह खामखेडा | Completed | 58000 | 56059 | 2014-03-01 | 2014-06-30
| 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1728002022/IF/9926713323 — पशु शेड निर्माण लखन / श्‍याम लाल, खामखेडा | Deleted | 57870 | 0 | 2014-02-03
| 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1728002022/IF/9926713340 — पशु शेड निर्माण नंद लाल / लक्ष्‍मण सिंह खामखेडा | Deleted | 57870 | 0 | 2014-02-03
| 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1728002022/IF/9926743439 — मवेशी शेड निमार्ण नंदलाल / लक्ष्‍मण सिंह, खामखेडा | Deleted | 57875 | 0 | 2014-02-03
| 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1728002022/IF/9926743458 — मवेशी शेड निर्माण लखन / श्‍यामलाल, खामखेडा | Deleted | 57875 | 0 | 2014-02-03
| 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1728002022/IF/9993672321 — पशु शेड निर्माण लखन सिंह / श्‍यामलाल ग्राम पंचायत खामखेडा | Completed | 57876 | 53917 | 2015-08-22 | 2016-05-07
| 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1728002022/IF/9993672774 — पशु शेड निर्माण अवधनारायण /भंवरलाल खामखेडा | Completed | 57876 | 53916.35 | 2015-08-29 | 2016-07-05
| 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1728002022/IF/9993674682 — pashu sed nirman karya Vikram singh s/o dashrath singh | Completed | 57876 | 53916.35 | 2015-09-19 | 2016-07-05
| 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/9993749056 — मनरेगा +अभिसरण रामप्‍यारी बाई / नंदराम ग्रामपंचायत खामखेडा | Completed | 16000 | 8684 | 2016-07-30 | 2016-08-26
| 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/1093222 — Construction of IAY House -IAY REG. NO. MP3297699 | Completed | 15480 | 15480 | 2017-12-09 | 2018-03-21
| 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/113882 — Construction of IAY House -IAY REG. NO. MP-28-002-022-001/052 | Approved | 23490 | 0 | 2016-01-16
| 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/1144773 — Construction of IAY House -IAY REG. NO. MP1370681 | Completed | 15480 | 15516 | 2017-12-23 | 2018-07-28
| 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/1149697 — Construction of IAY House -IAY REG. NO. MP2018396 | Completed | 15480 | 15480 | 2017-12-09 | 2018-03-12
| 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/1149720 — Construction of IAY House -IAY REG. NO. MP2021711 | Completed | 15480 | 15480 | 2017-12-16 | 2018-02-24
| 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/1149815 — Construction of IAY House -IAY REG. NO. MP2036412 | Completed | 15480 | 15480 | 2017-12-09 | 2018-02-02
| 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/1149852 — Construction of IAY House -IAY REG. NO. MP2042861 | Deleted | 15480 | 0 | 2017-05-25
| 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/1149854 — Construction of IAY House -IAY REG. NO. MP2042908 | Completed | 15480 | 15480 | 2017-11-18 | 2018-03-12
| 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/1149855 — Construction of IAY House -IAY REG. NO. MP2042981 | Completed | 15480 | 15480 | 2017-12-16 | 2018-02-02
| 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/1150072 — Construction of IAY House -IAY REG. NO. MP2072188 | Completed | 15480 | 15480 | 2017-12-23 | 2018-02-16
| 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/1150149 — Construction of IAY House -IAY REG. NO. MP2082091 | Completed | 15480 | 15480 | 2017-11-18 | 2018-01-16
| 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/1150150 — Construction of IAY House -IAY REG. NO. MP2082105 | Completed | 15480 | 15480 | 2017-12-16 | 2018-02-09
| 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/1150151 — Construction of IAY House -IAY REG. NO. MP2082138 | Deleted | 15480 | 0 | 2017-05-25
| 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/1150294 — Construction of IAY House -IAY REG. NO. MP2097698 | Completed | 15480 | 15480 | 2017-10-14 | 2018-01-16
| 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/1150295 — Construction of IAY House -IAY REG. NO. MP2097716 | Completed | 15480 | 15480 | 2017-10-14 | 2018-02-09
| 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/1150298 — Construction of IAY House -IAY REG. NO. MP2097734 | Completed | 15480 | 15480 | 2017-10-14 | 2018-02-16
| 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/1153654 — Construction of IAY House -IAY REG. NO. MP2645290 | Completed | 15480 | 14472 | 2017-12-23 | 2018-08-19
| 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/1153932 — Construction of IAY House -IAY REG. NO. MP2695296 | Completed | 15480 | 15480 | 2017-11-18 | 2018-01-22
| 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/1294308 — Construction of IAY House -IAY REG. NO. MP2658684 | Ongoing | 23490 | 8178 | 2018-10-27
| 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/1677744 — Construction of IAY House -IAY REG. NO. MP1631207 | Completed | 15660 | 15660 | 2018-06-09 | 2018-09-17
| 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/1678800 — Construction of IAY House -IAY REG. NO. MP2036886 | Completed | 15660 | 14616 | 2018-07-07 | 2018-11-02
| 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/1678940 — Construction of IAY House -IAY REG. NO. MP2082147 | Completed | 15660 | 15486 | 2018-07-07 | 2018-10-22
| 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/1681110 — Construction of IAY House -IAY REG. NO. MP2695205 | Completed | 15660 | 14616 | 2018-06-30 | 2018-11-02
| 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/1691232 — Construction of IAY House -IAY REG. NO. MP3901002 | Completed | 15660 | 15660 | 2018-06-09 | 2018-08-24
| 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/1904778 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4448302 | Completed | 15660 | 14616 | 2018-08-25 | 2018-12-01
| 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/1904930 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4788510 | Completed | 15660 | 14616 | 2018-09-29 | 2018-11-16
| 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/1905080 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5232891 | Completed | 15660 | 14616 | 2018-08-25 | 2018-12-01
| 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/1905215 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5586925 | Completed | 15660 | 13572 | 2018-08-25 | 2018-10-26
| 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/1922915 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4439563 | Completed | 15660 | 15660 | 2018-09-29 | 2018-11-24
| 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/2031212 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3238189 | Completed | 15840 | 14784 | 2019-07-13 | 2019-12-18
| 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/2147402 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5201696 | Completed | 15840 | 14784 | 2019-07-13 | 2019-11-30
| 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/290690 — Construction of IAY House -IAY REG. NO. MP1275310 | Completed | 15030 | 15030 | 2017-01-28 | 2017-03-31
| 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/290940 — Construction of IAY House -IAY REG. NO. MP1370675 | Completed | 15030 | 15080 | 2017-02-11 | 2017-04-07
| 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/291761 — Construction of IAY House -IAY REG. NO. MP2041739 | Completed | 15030 | 15128 | 2017-01-28 | 2017-08-02
| 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/291992 — Construction of IAY House -IAY REG. NO. MP2072325 | Completed | 15030 | 15060 | 2017-01-28 | 2017-07-07
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/3679474 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106519166 | Completed | 18360 | 17238 | 2022-07-16 | 2023-04-30
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/3681600 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114186330 | Completed | 18360 | 18360 | 2022-07-02 | 2022-12-27
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/3701101 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115280770 | Completed | 18360 | 18360 | 2022-07-02 | 2023-01-27
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/3713741 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114878261 | Completed | 18360 | 17850 | 2022-06-25 | 2023-07-26
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/3732935 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119855996 | Completed | 18360 | 18360 | 2022-06-25 | 2022-12-27
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/3739324 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122810956 | Approved | 23490 | 0 | 2022-04-27
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/3751659 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126454306 | Completed | 18360 | 17340 | 2022-06-04 | 2023-05-10
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/3762621 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127283385 | Completed | 18360 | 18360 | 2022-07-16 | 2023-07-05
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/3785275 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122114875 | Completed | 18360 | 18360 | 2022-06-25 | 2022-12-27
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/3813820 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114877138 | Completed | 18360 | 16116 | 2022-07-02 | 2024-07-25
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/3834665 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126270243 | Completed | 18360 | 13668 | 2022-06-04 | 2024-05-13
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/3841625 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116991316 | Completed | 18360 | 17136 | 2022-06-25 | 2023-07-26
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/3901816 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126252405 | Completed | 18360 | 18360 | 2022-06-04 | 2022-12-26
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/4149544 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127282548 | Completed | 18360 | 18326 | 2022-07-16 | 2023-05-10
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/4189959 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115280575 | Completed | 18360 | 17136 | 2022-07-16 | 2023-07-26
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/4190976 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116991484 | Completed | 18360 | 18360 | 2022-07-02 | 2022-12-27
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/4196922 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125808929 | Completed | 18360 | 17238 | 2022-07-16 | 2023-05-05
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/4735576 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100596049 | Completed | 23490 | 20898 | 2025-01-11 | 2026-03-11
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/4744806 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114878015 | Completed | 23490 | 21600 | 2025-01-11 | 2025-11-11
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/4748278 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115280686 | Ongoing | 23490 | 16182 | 2026-01-16
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/4760305 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119855936 | Completed | 23490 | 21492 | 2025-01-11 | 2026-03-11
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/4764153 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121533293 | Ongoing | 23490 | 19602 | 2025-03-01
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/4771965 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124946151 | Approved | 23490 | 0 | 2024-10-04
| 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/526820 — Construction of IAY House -IAY REG. NO. MP2720041 | Completed | 15030 | 15255 | 2017-02-25 | 2017-12-30
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/5384444 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114187179 | Approved | 23490 | 0 | 2025-02-17
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/5385977 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102106145 | Approved | 23490 | 0 | 2025-02-17
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/5387669 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105287708 | Ongoing | 23490 | 18792 | 2025-05-03
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/5387670 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105288352 | Ongoing | 23490 | 16965 | 2026-01-02
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/5387731 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121533124 | Ongoing | 23490 | 20358 | 2025-05-31
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/5387988 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119855734 | Approved | 23490 | 0 | 2025-02-21
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/5389092 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122406038 | Approved | 23490 | 0 | 2025-02-21
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/5391189 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115280481 | Physically Completed | 23490 | 20358 | 2026-01-16 | 2026-05-10
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/5391190 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115280530 | Approved | 23490 | 0 | 2025-02-17
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/5391191 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115280656 | Approved | 23490 | 0 | 2025-03-03
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/5392314 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114877380 | Ongoing | 23490 | 10962 | 2025-05-31
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/5392316 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114877479 | Ongoing | 23490 | 20358 | 2026-01-02
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/5392317 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114877578 | Approved | 23490 | 0 | 2025-03-03
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/5394185 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122120421 | Ongoing | 23490 | 20619 | 2025-05-03
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/5394988 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124941438 | Approved | 23490 | 0 | 2025-03-03
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/5395477 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124863428 | Physically Completed | 23490 | 15660 | 2025-07-05 | 2026-02-08
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/5396657 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114185570 | Physically Completed | 23490 | 17226 | 2025-05-03 | 2026-03-22
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/5398159 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123456015 | Approved | 23490 | 0 | 2025-03-03
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/5398890 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123431641 | Approved | 23490 | 0 | 2025-03-03
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/5399199 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114186736 | Completed | 23490 | 23490 | 2025-11-12 | 2026-03-16
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/5399200 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114186837 | Ongoing | 23490 | 20358 | 2025-05-31
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/5399257 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126449246 | Physically Completed | 23490 | 17226 | 2025-05-03 | 2026-03-22
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/5399373 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140787267 | Physically Completed | 23490 | 17226 | 2025-05-03 | 2026-02-10
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/5399540 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126435690 | Physically Completed | 23490 | 20358 | 2025-05-03 | 2026-03-22
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/5399705 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119856125 | Approved | 23490 | 0 | 2025-03-04
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/5401777 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114185047 | Physically Completed | 23490 | 20358 | 2025-05-03 | 2026-03-22
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/5402395 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100733475 | Approved | 23490 | 0 | 2025-03-03
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/5402396 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100733494 | Physically Completed | 23490 | 9396 | 2025-12-19 | 2026-02-08
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/5402397 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100733519 | Ongoing | 23490 | 18792 | 2025-05-03
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/5403171 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140482855 | Completed | 23490 | 23229 | 2025-05-03 | 2026-05-07
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/5403172 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140483323 | Completed | 23490 | 20619 | 2025-05-03 | 2026-03-26
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/5403640 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124944302 | Approved | 23490 | 0 | 2025-03-03
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/5404482 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121533756 | Approved | 23490 | 0 | 2025-03-03
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/5404483 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121533941 | Approved | 23490 | 0 | 2025-02-17
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/5406027 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114877250 | Ongoing | 23490 | 20358 | 2025-05-03
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/5406028 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114878114 | Ongoing | 23490 | 21924 | 2025-05-31
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/5406029 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114878318 | Approved | 23490 | 0 | 2025-02-17
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/5406178 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124939532 | Ongoing | 23490 | 17226 | 2025-05-03
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/5406179 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124940753 | Physically Completed | 23490 | 20358 | 2025-05-03 | 2025-12-10
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/5406340 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140492944 | Physically Completed | 23490 | 20619 | 2025-07-05 | 2026-02-10
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/5407530 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124943119 | Physically Completed | 23490 | 21924 | 2025-05-03 | 2026-06-14
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/5408843 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106519289 | Physically Completed | 23490 | 19575 | 2025-07-19 | 2026-02-10
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/5409144 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125805352 | Ongoing | 23490 | 21924 | 2025-05-03
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/5410936 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102105959 | Completed | 23490 | 21924 | 2025-05-31 | 2026-05-25
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/5410937 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102106019 | Ongoing | 23490 | 17226 | 2025-05-03
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/5607611 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121532788 | Ongoing | 23490 | 6786 | 2026-01-16
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/5607612 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121532941 | Physically Completed | 23490 | 21924 | 2025-11-12 | 2026-06-16
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/5608135 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121533460 | Physically Completed | 23490 | 10962 | 2025-05-31 | 2025-12-11
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/5608521 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114185496 | Approved | 23490 | 0 | 2025-03-21
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/5608699 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126452850 | Approved | 23490 | 0 | 2025-03-03
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/5609602 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126455011 | Physically Completed | 23490 | 21924 | 2025-12-04 | 2026-03-03
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/5609770 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114186606 | Approved | 23490 | 0 | 2025-03-21
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/5609882 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102106243 | Approved | 23490 | 0 | 2025-02-21
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/5610056 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126275287 | Ongoing | 23490 | 6264 | 2026-02-13
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/5610182 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121532546 | Physically Completed | 23490 | 21924 | 2025-05-31 | 2026-02-24
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/5610250 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125806267 | Completed | 23490 | 21924 | 2025-05-31 | 2026-03-11
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/5610595 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114186933 | Approved | 23490 | 0 | 2025-02-17
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/5611196 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122406761 | Completed | 23490 | 21924 | 2025-06-28 | 2026-03-11
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/5611574 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106518995 | Approved | 23490 | 0 | 2025-02-21
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/5611707 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114186171 | Ongoing | 23490 | 0 | 2025-11-12
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/5611982 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119856057 | Ongoing | 23490 | 13572 | 2026-01-16
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/5612084 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114877798 | Approved | 23490 | 0 | 2025-02-21
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/5612101 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122406311 | Approved | 23490 | 0 | 2025-03-03
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/5612102 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122406537 | Approved | 23490 | 0 | 2025-02-21
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/5612120 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140786318 | Approved | 23490 | 0 | 2025-03-03
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/5612181 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115280616 | Approved | 23490 | 0 | 2025-02-17
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/5612182 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115280724 | Completed | 23490 | 21924 | 2025-11-12 | 2026-03-11
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/5720389 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100596034 | Approved | 23490 | 0 | 2025-05-09
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/5721787 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121535574 | Approved | 23490 | 0 | 2025-05-20
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/5723005 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105288555 | Ongoing | 23490 | 13572 | 2026-02-13
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/5723014 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125807301 | Ongoing | 23490 | 19314 | 2025-11-12
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/5725768 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121533606 | Approved | 23490 | 0 | 2025-06-25
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/5733099 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121532435 | Approved | 23490 | 0 | 2025-05-09
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/5830085 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115280796 | Completed | 23490 | 21924 | 2025-12-04 | 2026-03-11
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/5830392 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119855869 | Approved | 23490 | 0 | 2024-10-04
| 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/613400 — Construction of IAY House -IAY REG. NO. MP1654196 | Completed | 15030 | 15480 | 2017-03-04 | 2017-12-15
| 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/804232 — Construction of IAY House -IAY REG. NO. MP3238212 | Completed | 15480 | 15480 | 2017-07-15 | 2018-02-02
| 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/804525 — Construction of IAY House -IAY REG. NO. MP3286441 | Completed | 15480 | 15480 | 2017-05-27 | 2018-03-12
| 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/807681 — Construction of IAY House -IAY REG. NO. MP3903935 | Completed | 15480 | 15480 | 2017-05-27 | 2018-01-16
| 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002022/IF/IAY/85980 — Construction of IAY House -IAY REG. NO. MP-28-002-022-001/44 | Completed | 14310 | 9018 | 2016-11-26 | 2016-12-16
| 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Land Leveling / Levelling/shaping of Wasteland Land for Community | Land Development | 1728002022/LD/22012034294150 — शांतिधम विकाश कार्य ग्राम पंचायत खामखेड़ा | Completed | 500000 | 279564.2 | 2016-12-03 | 2017-04-24
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1728002022/LD/22012034571826 — खेत समतलीकरण कार्य ग्राम पंचायत खामखेडा | Closed | 64869.2 | 0 | 2021-10-02
| 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1728002022/LD/3799382041 — खेल मैदान निर्माण कार्य ग्राम पंचायत खामखेडा | Completed | 317000 | 172300 | 2012-10-04 | 2013-04-18
| 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002022/RC/22012034154180 — सी सी रोड पंचपरमेश्‍वर ग्राम पंचायत खामखेडा | Completed | 149800 | 146044 | 2012-05-22 | 2012-06-27
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002022/RC/22012034170673 — सी सी रोड पंचपरमेश्‍वर मनफूल के पास से खेडी की ओर, खामखेडा | Completed | 177000 | 156072 | 2013-06-09 | 2013-11-08
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002022/RC/22012034181053 — सी सी रोड पंचपरमेश्‍वर कार्य स्‍कूल के पास वाली सड | Completed | 47230 | 44367 | 2013-09-07 | 2013-11-08
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002022/RC/22012034188575 — सी सी रोड पंचपरमेश्‍वर चौक से बसोड घाट तक, ग्राम प | Completed | 88100 | 79622 | 2013-10-05 | 2014-01-31
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1728002022/RC/22012034209899 — खेत सडक योजना लखन से बाबूलाल के खेत तक, खामखेडा | Completed | 1493000 | 502038.5 | 2014-03-01 | 2016-10-26
| 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002022/RC/22012034303799 — सी सी रोड पंचपरमेश्‍वर नदी से अस्‍पताल की ओर, खामखेडा | Completed | 173500 | 163537 | 2016-04-09 | 2016-09-26
| 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002022/RC/22012034318838 — सी सी रोड पंच परमेश्वर +अभिसरण मनरेगा मानसिंह के घर से हेमराज के घर की और ग्राम पंचायत खामखेडा | Deleted | 156000 | 0 | 2016-12-26
| 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002022/RC/22012034321952 — सी सी रोड निर्माण मनरेगा+पंच परमेश्वर अभिसरण नवल सिंह के घर से गजराज सिंह के घर की ओर ग्राम पंचायत ख | Deleted | 28000 | 0 | 2017-01-28
| 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002022/RC/22012034323761 — सी सी रोड पंचपरमेश्‍वर बसोड घाट से शमशान की ओर, खामखेडा | Closed | 0 | 0 | 2017-04-14
| 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002022/RC/22012034337164 — सी सी रोड पंचपरमेश्वर मान सिंह के घर से तालाब तक खामखेडा | Completed | 163271 | 156004 | 2017-05-06 | 2018-02-19
| 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002022/RC/22012034369596 — सी सी रोड पंचपरमेश्‍वर खामखेडा | Closed | 0 | 0 | 2018-04-03
| 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1728002022/RC/22012034439014 — सुदुर संपर्क सडक श्‍यामलाल के खेत से ग्राम की ओर | Closed | 0 | 0 | 2019-04-14
| 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002022/RC/22012034468584 — सी सी रोड पंचपरमेश्‍वर भगवान सिंह से नवल सिंह के घर तक, नाली सहित, खामखेडा | Closed | 32550 | 0 | 2019-01-26
| 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002022/RC/22012034468585 — सी सी रोड पंचपरमेश्‍वर मंदिर से रामबाबू के घर तक नाली सहित, खामखेडा | Completed | 46500 | 45408 | 2019-08-03 | 2019-09-06
| 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1728002022/RC/22012034528213 — सुदूर ग्राम संपर्क सड़क निर्माण गाड़ाघाट से सुमेर खेड़ी की ओर, खामखेड़ा | Completed | 1740660.61 | 1700668.52 | 2020-07-25 | 2022-06-13
| 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002022/RC/22012034546117 — सी सी रोड सहनाली निर्माण अभिसरण मनरेगा + 14वां वित्‍त राजेश से नारायण सिंह के घर तक, खामखेडा | Completed | 79000 | 77520 | 2020-10-31 | 2020-12-19
| 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002022/RC/22012034553883 — सी सी रोड सहनाली निर्माण अभ्रिसरण मनरेगा + 14 वां वित्‍त मोहन से राजू के घर तक, खामखेडा | Completed | 18600 | 18528 | 2021-11-27 | 2021-12-17
| 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002022/RC/22012034595321 — सी सी रोड निर्माण मनरेगा +15 वां वित्त इशाक के घर से बंजारा बस्ती की ओर, खामखेडा | Completed | 71527 | 70638 | 2021-11-27 | 2022-02-10
| 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1728002022/RC/22012034644667 — ग्रेवल सडक निर्माण मनरेगा+विधायक निधि, राजू के खेत से रासलाखेडी पहुंच मार्ग तक, खामखेडा | Completed | 400000 | 391260.83 | 2023-10-07 | 2026-06-05
| 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1728002022/RC/22012034679818 — सुदूर सडक निर्माण पठार से वनदान की ओर ग्राम पंचायत खामखेडा | New | 0 | 0 | 2024-04-14
| 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1728002022/RC/22012034683822 — ग्रेवल रोड निर्माण मनरेगा +विधायक निधि सुजान बेदरा से खामखेडा मेढे तक, खामखेडा | Ongoing | 400000 | 119277 | 2025-05-17
| 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1728002022/RC/22012034837170 — ग्रेवल रोड निर्माण मनरेगा विधायक निधि श्री सुजान वेदरा से खामखेडा तक, खामखेडा | Deleted | 0 | 0 | 2025-02-04
| 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002022/RC/22012034845398 — सी सी रोड निर्माण कार्य मनरेगा +5 वां वित्त टपरों के मंदिर से शासकीय बाग की ओर, खामखेडा | Approved | 141199 | 0 | 2025-04-14
| 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002022/RC/22012034845456 — सी सी रोड निर्माण मनरेगा +15 वां वित्त टपरों के मंदिर से शासकीय बाग की ओर, खामखेडा | Approved | 141199 | 0 | 2025-04-14
| 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1728002022/RC/37 — मिटटी करण रोड, खामखेडा से अगरिया, खामखेडा | Completed | 969652 | 934960.6 | 2009-02-19 | 2009-02-19
| 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1728002022/RS/22012034289087 — मनरेगा+स्‍वच्‍छ भारत मिशन अभिसरण से शौचालय निर्माण 20 हितग्राही खामखेडा | Completed | 63600 | 3180 | 2015-10-16 | 2015-12-04
| 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Compost Pit / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1728002022/RS/22012034323266 — सार्वजनिक नाडेप निर्माण कार्य टपरा मोहल्ला ग्राम पंचायत खामखेडा | Deleted | 16900 | 0 | 2017-02-05
| 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Compost Pit / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1728002022/RS/22012034323271 — सार्वजनिक नाडेप कार्य खेडी श्मशान के पास ग्राम पंचायत खामखेडा | Deleted | 16900 | 0 | 2016-10-02
| 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1728002022/RS/22012034323559 — शोचालय निर्माण कार्य मनरेगा 21 हितग्राही ग्राम पंचायत खामखेड़ा | Completed | 252000 | 206073.68 | 2017-02-11 | 2018-04-28
| 2018-2019 | D--RURAL INFRASTUCTURE / Rural Sanitation | Compost Pit / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1728002022/RS/22012034384091 — नाडेप निर्माण कल्‍याणपुरा, खामखेडा | Closed | 0 | 0 | 2018-04-14
| 2018-2019 | D--RURAL INFRASTUCTURE / Rural Sanitation | Compost Pit / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1728002022/RS/22012034384326 — NADEP NIRMAN KARYA KHAMKHEDA | Closed | 0 | 0 | 2018-04-14
| 2018-2019 | D--RURAL INFRASTUCTURE / Rural Sanitation | Compost Pit / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1728002022/RS/22012034384331 — NADEP NIRMAN KARYA KALYANPURA KHAMKHEDA | Closed | 0 | 0 | 2018-04-14
| 2018-2019 | D--RURAL INFRASTUCTURE / Rural Sanitation | Compost Pit / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1728002022/RS/22012034384332 — NADEP NIRMAN KARYA KHAMKHEDA | Closed | 12236.71 | 0 | 2018-04-14
| 2018-2019 | D--RURAL INFRASTUCTURE / Rural Sanitation | Compost Pit / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1728002022/RS/22012034384333 — NADEP NIRMAN KARYA KALYANPURA KHAMKHEDA | Closed | 12236.71 | 0 | 2018-04-14
| 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1728002022/RS/22012034497549 — सामुदायिक स्वच्छता परिसर, अभिसरण मनरेगा, 15 वां वित्त, एसबीएम, सामुदायिक भवन के पास, खामखेडा | Completed | 44000 | 39900 | 2020-10-03 | 2020-11-30
| 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1728002022/RS/22012034622056 — लीच पिट निर्माण कार्य मनरेगा +15 वां वित्त(संख्या 25), खामखेडा | Completed | 31500 | 31266 | 2021-12-03 | 2021-12-17
| 2025-2026 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1728002022/RS/22012035138030 — नाली निर्माण कार्य मनरेगा +15 वां वित्त कमल नेता के घर से बसाेड घाट की ओर, खामखेडा | Approved | 30000 | 0 | 2025-04-14
| 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1728002022/WC/110 — नदी टेनिंग एवं गाद निकलाई | Completed | 485000 | 484415.08 | 2010-05-06 | 2010-04-01
| 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1728002022/WC/22012034326310 — तालाब बेस्ट वेयर निर्माण कार्य खामखेड़ा | Completed | 39147 | 38361.5 | 2017-05-27 | 2018-10-18
| 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1728002022/WC/22012034471968 — सोख्‍ता गढढा निर्माण कार्य तालाब के पास खामखेडा | Completed | 13427.22 | 9328 | 2019-10-05 | 2019-10-24
| 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1728002022/WC/22012034471969 — सोख्‍ता गढढा निर्माण कार्य मेन रोड बाडे में, खामखेडा | Completed | 13427.22 | 9328 | 2019-10-05 | 2019-10-24
| 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1728002022/WC/22012034471970 — सोख्‍ता गढढा निर्माण कार्य पप्‍पू सरपंच के घर के पास, खामखेडा | Completed | 13427.22 | 9152 | 2019-08-31 | 2019-09-20
| 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1728002022/WC/22012034471971 — सोख्‍ता गढढा निर्माण कार्य पर्वत सिंह के घर के पास, खामखेडा | Completed | 13427.22 | 9152 | 2019-08-31 | 2019-09-20
| 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1728002022/WC/22012034471972 — सोख्‍ता गढढा निर्माण कार्य मंदिर के पास कल्‍याणपुरा, खामखेडा | Closed | 13427.22 | 0 | 2019-06-24
| 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1728002022/WC/22012034547358 — सामुदायिक पोण्‍ड निर्माण कार्य बंजारा बस्‍ती खामखेडा | Completed | 108814.67 | 67260 | 2020-06-20 | 2020-08-25
| 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1728002022/WC/22012034579051 — सोख्‍ता गढढा निर्माण कार्य शमशान घाट में, खामखेडा | Completed | 14283.77 | 12863.41 | 2020-09-05 | 2020-11-26
| 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1728002022/WC/22012034579052 — सोख्‍ता गढढा निर्माण कार्य नलजल योजना के पास, खामखेडा | Completed | 14283.77 | 12863.41 | 2020-09-05 | 2020-11-26
| 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1728002022/WC/22012034579053 — सोख्‍ता गढढा निर्माण कार्य पूलिया के पास, खामखेडा | Completed | 14283.77 | 12863.41 | 2020-09-05 | 2020-11-26
| 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1728002022/WC/22012034579054 — सोख्‍ता गढढा निर्माण कार्य आंगनबाडी के पास, खामखेडा | Completed | 14283.77 | 12863.41 | 2020-09-05 | 2020-11-26
| 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1728002022/WC/22012034596487 — सामुदायिक पोण्‍ड निर्माण कार्य खेल मैदान के सामने, खामखेडा | Completed | 332962.02 | 265488 | 2020-11-28 | 2022-03-15
| 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1728002022/WC/22012034596488 — सामुदायिक पोण्‍ड निर्माण कार्य कल्‍याणपुर मार्ग के पास, खामखेडा | Completed | 332962.02 | 265964 | 2020-11-28 | 2022-03-10
| 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1728002022/WC/22012034615309 — चेक डेम निर्माण कार्य खामखेडा | Closed | 0 | 0 | 2020-10-02
| 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1728002022/WC/22012034950885 — तालाब जीर्णोद्वार एवं पाल मरम्‍मत कार्य ग्राम पंचायत खामखेडा | Completed | 968612.08 | 909303.72 | 2022-04-30 | 2023-07-05
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1728002022/WC/22012034951713 — चेक डेम निर्माण कार्य ग्राम पंचायत खामखेडा | Closed | 0 | 0 | 2022-03-18
| 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1728002022/WC/22012034959347 — चेक डैम निर्माण कार्य मनरेगा +15 वा वित्त +जनभागीदारी, खामखेड़ा | Completed | 399000 | 396653.36 | 2022-06-18 | 2025-01-21
| 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1728002022/WC/22012035008399 — परकोलेशन टेंक निर्माण कार्य ग्राम पंचायत खामखेडा | Physically Completed | 723391.85 | 329137 | 2022-11-12 | 2026-06-04
| 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1728002022/WC/22012035018606 — परकोलेशन टेंक निर्माण कार्य पार्ट - 2, खामखेडा | Closed | 0 | 0 | 2022-10-02
| 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1728002022/WC/22012035296062 — सामुदायिक पोंड निर्माण कार्य नदी के पास, खामखेड़ा | Approved | 570989.21 | 0 | 2025-04-14
| 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1728002022/WC/83 — निर्मल नीर सोख्‍ता गडडा होज निर्माण दूल्‍हा ेदव के पास खामखेडा | Completed | 12000 | 10070 | 2009-03-03 | 2009-03-03
| 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1728002022/WC/84 — निर्मल नीर सोख्‍ता गडडा नवल के घर के पास खामखेडा | Completed | 12000 | 10070 | 2009-03-03 | 2009-03-03
| 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1728002022/WC/85 — निर्मल नीर सोख्‍ता गडडा खेडी पर खामखेडा | Completed | 12000 | 10070 | 2009-03-03 | 2009-03-03
| 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1728002022/WC/86 — निर्मल नीर सोख्‍ता गडडा गोआ के पास खामखेडा | Completed | 12000 | 12170 | 2009-03-02 | 2009-02-01
| 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1728002022/WC/87 — निर्मल नीर सोख्‍ता गडडा पठार पर खामखेडा | Completed | 12000 | 10070 | 2009-03-02 | 2009-03-02