## Work List
Exported on: 2026-08-22 00:49:45
Filters applied:
Data source: MGNREGA
District: BHOPAL
Block: PHANDA
Panchayat: KHAJOORI SADAK
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
| 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Bharat Nirman Seva Kendra / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1728002076/AV/22012034375969 — राजीव गांधी सेवा केंद्र / पंचायत भवन ग्राम पंचायत खजूरीसडक | Completed | 700000 | 699630.3 | 2019-01-26 | 2020-05-06
| 2019-2020 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1728002076/AV/22012034470536 — शमश्‍ाान शेड एवं ग्राउंड समतलीकरण खारखेडी, खजूरीसडक | Completed | 281062.92 | 230233.84 | 2019-12-07 | 2021-03-04
| 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Kitchen Shed / Construction of Kitchen shed Building for Community | Constr of Kitchen Shed | 1728002076/AV/22012034573050 — डायनिंग हॉल में बेंच निर्माण कार्य मा.शाला ग्राम पंचायत खजूरीसडक | Completed | 26881.94 | 22465.86 | 2021-09-11 | 2022-06-06
| 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Kitchen Shed / Construction of Kitchen shed Building for Community | Constr of Kitchen Shed | 1728002076/AV/22012034587141 — डायनिंग हॉल में बेंच निर्माण कार्य माध्‍यमिक शाला, खजूरीसडक | Closed | 0 | 0 | 2021-04-14
| 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Repair & Maint of Anganwadi Building / Repair and Maintenance of Anganwadi Building for Community | Repair & Maint of Community infrastructure | 1728002076/AV/22012034611547 — आंगनबाडी में पुताई, फर्स एवं टायलेट सुधार कार्य, मनरेगा +15 वां वित्त, खारखेडी, खजूरीसडक | Completed | 17700 | 16212 | 2021-12-04 | 2021-12-21
| 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1728002076/AV/22012034622232 — शांतिधाम विकास कार्य ग्राम खामलाखेडी, ग्राम पंचायत खजूरीसडक | Deleted | 0 | 0 | 2022-08-16
| 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1728002076/AV/22012034622600 — शांतिधाम विकास कार्य, खामलाखेडी, ग्राम पंचायत खजूरीसडक | Ongoing | 290065.42 | 27684 | 2022-09-27
| 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert / cross drainage structues for Community | Culvert | 1728002076/AV/22012034637185 — पुलिया निर्माण कार्य मनरेगा +15 वां वित्‍त, खारखेडी मेन रोड, खजूरीसडक | Completed | 225000 | 167504 | 2023-07-08 | 2026-02-03
| 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert / cross drainage structues for Community | Culvert | 1728002076/AV/22012034639654 — पुलिया निर्माण कार्य मनरेगा + 15 वां वित्‍त खारखेडी, खजूरीसडक | Closed | 150000 | 0 | 2023-04-01
| 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1728002076/DP/22012034447699 — सार्वजनिक व़क्षारोपण कार्य शमशान घाट, खजूरीसडक | Completed | 373989.79 | 151341 | 2019-08-17 | 2026-02-13
| 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1728002076/DP/22012034580313 — सामुदायिक व़क्षारोपण कार्य गांव वाले तालाब के पास, खजूरीसडक | Ongoing | 160908.84 | 43644 | 2023-07-15
| 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1728002076/DP/22012034610096 — व़क्षारोपण कार्य शमशान परिसर, खेतलाखेडी, खजूरीसडक | Closed | 0 | 0 | 2023-08-16
| 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1728002076/DP/9926690019 — निर्मल वाटिका, 104 हितग्राही, खजूरी सडक | Completed | 457000 | 441959 | 2011-02-15 | 2012-11-05
| 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1728002076/IF/22012034341219 — वृक्षारोपण कार्य स्कूल के पास ग्राम खजूरी सड़क ग्राम पंचायत खजूरी सड़क | Completed | 335000 | 13528 | 2017-05-27 | 2018-01-23
| 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1728002076/IF/22012034342468 — वृक्षारोपड़ कार्य शांतिधाम के पास ग्राम खारखेडी ग्र.प. खजुरी सड़क | Completed | 335000 | 10500 | 2017-07-01 | 2018-01-23
| 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1728002076/IF/22012034342478 — वृक्षारोपड़ कार्य शांतिधाम कि मेड पर ग्राम खेतलाखेडी ग्र.प. खजुरी सड़क | Completed | 335000 | 12260 | 2017-07-01 | 2018-01-23
| 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1728002076/IF/22012034456463 — KUP NIRMAN | Closed | 0 | 0 | 2019-04-14
| 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1728002076/IF/22012034472844 — कूप निर्माण कार्य सह खेत तालाब दशरथ / पन्‍ना लाल खेतलाखेडी ग्राम पंचायत खजूरीसडक | Completed | 230400.79 | 165929.41 | 2019-05-25 | 2023-04-10
| 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1728002076/IF/22012034680635 — खेत समतलीकरण कार्य दशरथ सिंह / पन्‍नालाल, खेतलाखेडी, खजूरीसडक | Closed | 0 | 0 | 2021-01-21
| 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1728002076/IF/22012034680907 — कपिलधारा कूप निर्माण सह खेत तालाब सुमित्राबाई/रंजीत सिंह ग्राम खेतलाखेडी ग्राम पंचायत खजुरीसडक | Closed | 294161.33 | 0 | 2021-01-21
| 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1728002076/IF/22012034680919 — कपिलधारा कूप निर्माण सह खेत तालाब राहुल मेवाडा/ओमप्रकाश मेवाडा ग्राम पंचायत खजुरीसडक | Completed | 294161.33 | 288335.96 | 2021-04-24 | 2021-12-23
| 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1728002076/IF/22012034746707 — मेढ बंधान कार्य ओमप्रकाश / करण सिंह, खजूरीसडक | Completed | 32791.63 | 26634 | 2021-05-29 | 2021-06-30
| 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1728002076/IF/22012034982932 — कपिलधारा कूप निर्माण कार्य रितिक /मोर सिंह मेवाडा, खेतलाखेडी, खजूरीसडक | Ongoing | 306971.28 | 229776 | 2023-06-17
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1728002076/IF/22012035526582 — खेत तालाब निर्माण कार्य विष्‍णु प्रसाद / चंदन सिंह, खजूरी सडक | Ongoing | 260630.55 | 0 | 2025-05-22
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1728002076/IF/22012035544277 — खेत तालाब निर्माण कार्य वीरभान / श्‍याम लाल, खजूरी सडक | Physically Completed | 236851.21 | 67599 | 2025-05-28 | 2026-06-28
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1728002076/IF/22012035553618 — खेत तालाब निर्माण कार्य अवधनारायण / श्‍याम लाल, खजूरीसडक | Ongoing | 220210.87 | 522 | 2025-11-08
| 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002076/IF/9993724327 — मनरेगा+इंदिरा आवास अभिसरण सम्‍पत बाई /फूल सिंह, ,खजूरीसडक | Completed | 16000 | 14696 | 2016-05-07 | 2016-10-18
| 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002076/IF/9993751544 — मनरेगा+इंदिरा आवास अभिसरण गुडडी बाई /वीरसिंह,खजूरीसडक | Completed | 16000 | 14028 | 2016-07-23 | 2016-11-02
| 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002076/IF/IAY/1024931 — Construction of IAY House -IAY REG. NO. MP2150628 | Completed | 15480 | 14448 | 2017-05-27 | 2017-10-03
| 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002076/IF/IAY/1184830 — Construction of IAY House -IAY REG. NO. MP1084020 | Completed | 15480 | 14448 | 2017-12-09 | 2018-01-27
| 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002076/IF/IAY/1184831 — Construction of IAY House -IAY REG. NO. MP1121516 | Completed | 15480 | 14448 | 2017-12-09 | 2018-01-16
| 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002076/IF/IAY/1184833 — Construction of IAY House -IAY REG. NO. MP1184559 | Completed | 15480 | 14448 | 2017-12-30 | 2018-02-19
| 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002076/IF/IAY/1184834 — Construction of IAY House -IAY REG. NO. MP1199423 | Completed | 15480 | 14370 | 2017-12-30 | 2019-02-13
| 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002076/IF/IAY/1184842 — Construction of IAY House -IAY REG. NO. MP3358535 | Completed | 15480 | 14448 | 2017-12-09 | 2018-02-13
| 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002076/IF/IAY/1901857 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4900085 | Completed | 15660 | 15660 | 2018-07-21 | 2018-11-26
| 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002076/IF/IAY/1902693 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5706072 | Completed | 15660 | 14616 | 2018-07-21 | 2018-12-31
| 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002076/IF/IAY/1902694 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5706082 | Completed | 15660 | 13410 | 2018-07-21 | 2019-07-09
| 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002076/IF/IAY/2353575 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3799398 | Completed | 17100 | 17334 | 2021-03-20 | 2021-05-10
| 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002076/IF/IAY/2353590 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3358699 | Completed | 17100 | 15054 | 2021-04-03 | 2021-11-16
| 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002076/IF/IAY/288203 — Construction of IAY House -IAY REG. NO. MP1561830 | Completed | 15030 | 14664 | 2017-02-18 | 2018-01-06
| 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002076/IF/IAY/289915 — Construction of IAY House -IAY REG. NO. MP1143945 | Completed | 15030 | 14722 | 2017-02-25 | 2018-01-06
| 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002076/IF/IAY/2907855 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP1072835 | Completed | 17100 | 15054 | 2021-05-15 | 2021-12-01
| 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002076/IF/IAY/292853 — Construction of IAY House -IAY REG. NO. MP3788773 | Completed | 15030 | 14784 | 2019-08-31 | 2019-11-02
| 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002076/IF/IAY/292856 — Construction of IAY House -IAY REG. NO. MP3799422 | Completed | 15030 | 14978 | 2017-02-11 | 2017-07-25
| 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002076/IF/IAY/322601 — Construction of IAY House -IAY REG. NO. MP1075025 | Completed | 15030 | 14016 | 2017-04-08 | 2019-01-08
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002076/IF/IAY/3672166 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114144843 | Completed | 18360 | 17340 | 2022-05-21 | 2022-09-15
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002076/IF/IAY/3753884 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127139350 | Completed | 18360 | 18360 | 2022-05-21 | 2022-12-06
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002076/IF/IAY/3753895 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127140186 | Completed | 18360 | 18360 | 2022-07-16 | 2022-12-06
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002076/IF/IAY/3753929 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127144440 | Completed | 18360 | 18156 | 2022-05-21 | 2022-11-14
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002076/IF/IAY/3754304 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121649420 | Completed | 18360 | 18156 | 2022-05-21 | 2022-10-20
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002076/IF/IAY/3785296 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122117418 | Completed | 18360 | 18156 | 2022-05-21 | 2022-10-03
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002076/IF/IAY/3790243 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106448407 | Completed | 18360 | 18156 | 2022-05-21 | 2022-10-03
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002076/IF/IAY/4262233 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114201921 | Completed | 18360 | 15300 | 2022-07-16 | 2022-12-10
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002076/IF/IAY/4267951 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123882694 | Completed | 18360 | 17952 | 2022-07-16 | 2022-11-14
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002076/IF/IAY/4740182 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106441019 | Completed | 23490 | 23013 | 2025-03-15 | 2026-02-19
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002076/IF/IAY/4740217 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106451902 | Completed | 23490 | 21888 | 2025-02-15 | 2025-09-22
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002076/IF/IAY/4748828 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114167579 | Completed | 23490 | 22518 | 2025-02-15 | 2026-03-06
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002076/IF/IAY/4752743 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116735355 | Completed | 23490 | 22149 | 2025-02-15 | 2026-02-19
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002076/IF/IAY/5251632 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114188072 | Completed | 23490 | 22707 | 2025-04-12 | 2026-02-19
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002076/IF/IAY/5253293 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105797217 | Completed | 23490 | 22968 | 2025-04-12 | 2026-02-19
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002076/IF/IAY/5253554 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114191247 | Completed | 23490 | 22707 | 2025-04-12 | 2025-11-11
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002076/IF/IAY/5261780 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127135678 | Completed | 23490 | 22707 | 2025-04-12 | 2026-02-19
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002076/IF/IAY/5262909 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121671763 | Completed | 23490 | 23229 | 2025-04-12 | 2025-07-21
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002076/IF/IAY/5264334 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127147476 | Completed | 23490 | 21924 | 2025-04-12 | 2026-02-19
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002076/IF/IAY/5266061 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114126450 | Completed | 23490 | 21924 | 2025-04-12 | 2026-02-19
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002076/IF/IAY/5266259 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116734577 | Completed | 23490 | 21924 | 2025-04-12 | 2026-03-06
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002076/IF/IAY/5269832 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119676426 | Completed | 23490 | 22185 | 2025-04-12 | 2026-02-19
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002076/IF/IAY/5275508 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105806740 | Completed | 23490 | 21402 | 2025-04-12 | 2026-02-19
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002076/IF/IAY/5277764 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122116753 | Completed | 23490 | 23490 | 2025-04-12 | 2026-03-06
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002076/IF/IAY/5282359 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100860426 | Completed | 23490 | 23490 | 2025-04-12 | 2026-03-06
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002076/IF/IAY/5294014 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106462057 | Completed | 23490 | 22707 | 2025-04-12 | 2026-02-19
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002076/IF/IAY/5296422 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106486003 | Completed | 23490 | 22446 | 2025-04-12 | 2026-02-19
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002076/IF/IAY/5304653 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119676621 | Completed | 23490 | 23490 | 2025-04-12 | 2026-02-19
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002076/IF/IAY/5310691 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114204924 | Completed | 23490 | 23229 | 2025-04-12 | 2026-02-19
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002076/IF/IAY/5315122 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123504697 | Completed | 23490 | 23229 | 2025-04-12 | 2026-02-19
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002076/IF/IAY/5315727 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106724577 | Completed | 23490 | 22968 | 2025-04-12 | 2026-02-19
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002076/IF/IAY/5319608 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114197345 | Completed | 23490 | 23490 | 2025-04-12 | 2026-02-19
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002076/IF/IAY/5321814 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114176259 | Completed | 23490 | 21924 | 2025-04-12 | 2026-02-19
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002076/IF/IAY/5329167 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127138035 | Completed | 23490 | 23229 | 2025-04-12 | 2026-02-19
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002076/IF/IAY/5332465 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105832023 | Completed | 23490 | 23490 | 2025-04-12 | 2026-02-19
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002076/IF/IAY/5337046 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124189611 | Completed | 23490 | 21402 | 2025-04-12 | 2026-02-19
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002076/IF/IAY/5338974 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116785611 | Completed | 23490 | 22968 | 2025-04-12 | 2026-03-06
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002076/IF/IAY/5589553 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105791996 | Completed | 23490 | 22185 | 2025-07-12 | 2026-02-19
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002076/IF/IAY/5590695 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106715380 | Completed | 23490 | 21924 | 2025-05-24 | 2026-02-19
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002076/IF/IAY/5591089 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121654138 | Completed | 23490 | 23229 | 2025-05-17 | 2026-02-19
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002076/IF/IAY/5640155 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106442842 | Completed | 23490 | 22707 | 2025-06-14 | 2025-11-11
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002076/IF/IAY/5640335 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105785356 | Completed | 23490 | 22968 | 2025-07-12 | 2026-03-06
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002076/IF/IAY/5640491 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106488093 | Completed | 23490 | 22707 | 2025-07-12 | 2026-02-19
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002076/IF/IAY/5640923 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127143616 | Completed | 23490 | 22707 | 2026-01-10 | 2026-04-22
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002076/IF/IAY/5641177 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119626172 | Completed | 23490 | 22968 | 2025-07-12 | 2026-02-19
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002076/IF/IAY/5644052 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106718957 | Completed | 23490 | 22968 | 2025-07-12 | 2026-02-19
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002076/IF/IAY/5728969 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106723074 | Approved | 23490 | 0 | 2025-02-11
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002076/IF/IAY/5732865 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116785122 | Approved | 23490 | 0 | 2025-02-11
| 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002076/IF/IAY/573767 — Construction of IAY House -IAY REG. NO. MP1136697 | Completed | 15030 | 14036 | 2017-03-04 | 2017-07-25
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002076/IF/IAY/5845932 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144682486 | Completed | 23490 | 22968 | 2025-10-25 | 2026-02-19
| 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002076/IF/IAY/5929937 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127138606 | Ongoing | 23490 | 23490 | 2026-04-04
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002076/IF/IAY/6068355 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105804289 | Approved | 23490 | 0 | 2026-01-20
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002076/IF/IAY/6069085 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106477328 | Approved | 23490 | 0 | 2026-01-20
| 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002076/IF/IAY/6069428 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106726563 | Ongoing | 23490 | 22968 | 2026-05-09
| 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002076/IF/IAY/6079409 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119640446 | Ongoing | 23490 | 7830 | 2026-05-23
| 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002076/IF/IAY/85095 — Construction of IAY House -IAY REG. NO. MP-28-002-076-002/66 | Approved | 23490 | 0 | 2016-01-11
| 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1728002076/LD/22012034298547 — शांतिधाम विकास कार्य खजूरीसडक | Completed | 245000 | 238284 | 2017-01-21 | 2017-10-18
| 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1728002076/LD/22012034462414 — समतलीकरण कार्य नवीन सामुदायिक भवन के सामने खजूरीसडक | Completed | 78796.8 | 74493.94 | 2019-03-09 | 2020-09-23
| 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1728002076/LD/22012034462415 — समतलीकरण कार्य आंगनबाडी स्‍वराज भवन के सामने खेतलाखेडी, खजूरीसडक | Completed | 78796.8 | 74481.94 | 2019-03-09 | 2020-09-24
| 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1728002076/LD/22012034474341 — समतलीकरण कार्य शमशान घाट में, खारखेडी ग्राम पंचायत खजूरीसडक | Completed | 262318.98 | 246393.7 | 2020-01-25 | 2021-03-04
| 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1728002076/LD/22012034523891 — समतलीकरण कार्य शक्ति माता मंदिर खजूरीसडक | Completed | 206097.12 | 178977.47 | 2020-10-03 | 2021-12-23
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1728002076/LD/22012034572189 — समतलीकरण कार्य शमशान घाट, खेतलाखेडी, ग्राम पंचायत खजूरीसडक | Completed | 111242.16 | 13398 | 2021-11-13 | 2022-10-25
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1728002076/LD/22012034572190 — समतलीकरण कार्य सेग्रीगेशन शेड, ग्राम पंचायत खजूरीसडक | Completed | 60057.08 | 51941.26 | 2021-11-13 | 2021-12-10
| 2017-2018 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1728002076/PG/22012034311936 — खेल मैदान निर्माण कार्य खारखेड़ी खजूरी सड़क | Completed | 156000 | 29928 | 2017-05-27 | 2020-09-05
| 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1728002076/RC/121 — सी सी रोड, देवरा मंदिर से चौकीदार के घर तक, खातलाखेडी, खजूरी सडक | Completed | 500000 | 465979.78 | 2009-08-03 | 2009-04-01
| 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1728002076/RC/22012034151905 — ग्रेवल रोड खारखेडी से खारपा तक ग्राम पंचायत खजूरी सडक | Completed | 490000 | 400531 | 2011-01-03 | 2011-05-04
| 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002076/RC/22012034154231 — सी सी रोड पंचपरमेश्‍वर ग्राम पंचायत खजूरीसडक | Completed | 186000 | 179371.45 | 2012-05-18 | 2012-11-12
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002076/RC/22012034168937 — सी सी रोड पंचपरमेश्‍वर निर्माण कार्य पेट्रोल पंप स | Completed | 165300 | 155538 | 2013-06-01 | 2013-08-22
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002076/RC/22012034186431 — सी सी रोड पंचपरमेश्‍व मुख्‍य मार्ग से भाउसर के मका | Completed | 178000 | 168062 | 2013-09-28 | 2014-12-03
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002076/RC/22012034186457 — सी सी रोड पंचपरमेश्‍वर निमार्ण कार्य आगनवाडी से मु | Completed | 178000 | 138999 | 2013-09-28 | 2014-07-25
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002076/RC/22012034186473 — सी सी रोड पंचपरमेश्‍वर आगनवाडी से भावसार के घर तक | Completed | 178000 | 168470 | 2013-09-28 | 2014-04-14
| 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002076/RC/22012034220599 — सी सी रोड पाल्‍या बाबा से मुख्‍य मार्ग तक खारखेडी, | Completed | 114600 | 109876 | 2014-06-07 | 2014-07-11
| 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002076/RC/22012034266832 — सी सी रोड पंचपरमेश्‍वर गंगाराम से अनिल के घर तक खजूरीसडक | Completed | 130700 | 122002 | 2015-07-04 | 2015-08-31
| 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002076/RC/22012034289466 — सी सी रोड पंचपरमेश्‍वर रंजीत के मकान से मान सिंह के घर तक, खजूरीसडक | Completed | 100400 | 97308 | 2015-11-28 | 2016-06-14
| 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1728002076/RC/22012034293153 — खेत सड़क निर्माण धमनिया रोड से रामनारायण के खेत तक ग्र.पा.खजूरी सड़क | Completed | 1497000 | 236274 | 2015-12-26 | 2016-06-17
| 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002076/RC/22012034315131 — सी सी रोड पंचपरमेश्वर पेट्रोल पंप से लीलाकिशन के मकान तक, खजुरी सड़क | Completed | 173500 | 163537 | 2016-10-01 | 2017-03-31
| 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002076/RC/22012034317932 — सी सी रोड पंचपरमेश्‍वर अनोखीलाल से ज्ञान दास के घर तक खजूरीसडक | Completed | 250600 | 250430 | 2016-12-17 | 2017-05-30
| 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002076/RC/22012034319206 — सी.सी.रोड निर्माण मनरेगा+पंचपरमेशवर पेट्रोल पंप से लीलाकिशन के मकान तक ग्राम पंचायत खजूरी सड़क | Deleted | 173100 | 0 | 2016-12-30
| 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002076/RC/22012034323349 — c.c.road panchparmeshwar khajoori sadak | Closed | 0 | 0 | 2017-04-14
| 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1728002076/RC/22012034339489 — सुदूर सड़क खजूरी बकानिया मार्ग से खारखेडी की ओर, खजूरी सड़क | Completed | 1259600 | 1206758.36 | 2017-06-10 | 2019-06-22
| 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002076/RC/22012034343805 — सी सी रोड पंचपरमेश्वर जगदीश खंडेलवाल से रामस्वरुप के मकान तक खजूरीसड़क | Completed | 257100 | 256800 | 2017-07-08 | 2018-03-12
| 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002076/RC/22012034362225 — सी सी रोड पंचपरमेश्वर, रोड से शान्तिधाम, खजूरी सड़क | Closed | 51728 | 0 | 2017-04-19
| 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002076/RC/22012034370609 — C C ROAD GANESH RAM SE BHANDAR SINGH | Closed | 0 | 0 | 2018-04-14
| 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1728002076/RC/22012034375511 — सुदूर संपर्क सडक ग्राम पंचायत खजूरीसडक | Closed | 0 | 0 | 2018-04-14
| 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1728002076/RC/22012034377113 — सुदूर ग्राम संपर्क सडक खेतलाखेडी से हाइवे की ओर, खजूरीसडक | Closed | 636000 | 0 | 2017-08-15
| 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002076/RC/22012034437276 — C C ROAD NIRMAN KARYA KHAJURISADAK | Closed | 0 | 0 | 2019-04-14
| 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002076/RC/22012034438640 — C.C.ROAD PANCHPERMESWE | Closed | 0 | 0 | 2019-04-14
| 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002076/RC/22012034438642 — C.C.ROAD PANCHPERMEASWER | Closed | 0 | 0 | 2019-04-14
| 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002076/RC/22012034470310 — सी सी रोड पंचपरमेवश्‍र करन सिंह के घर से धामनिया रोड, खजूरीसडक | Closed | 46500 | 0 | 2019-01-12
| 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002076/RC/22012034470313 — सी सी रोड निर्माण मांगीलाल के घर से धामनिया रोड, खजूरीसडक | Closed | 20925 | 0 | 2019-01-12
| 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002076/RC/22012034470316 — सी सी रोड पंचपरमेश्‍वर धामनिया रोड से शांतिलाल के घर तक, खजूरीसडक | Closed | 55800 | 0 | 2019-01-12
| 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002076/RC/22012034470317 — सी सी रोड पंचपरमेश्‍वर मांगीलाल के घर से धामनिया रोड, खजूरीसडक | Closed | 20925 | 0 | 2019-01-12
| 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002076/RC/22012034470692 — सी सी रोड अभिसरण मनरेगा +14वां वित्‍त चरन सिंह के घर से धामनिया रोड, खजूरीसडक | Completed | 46500 | 46464 | 2019-07-27 | 2019-09-16
| 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002076/RC/22012034470696 — सी सी रोड अभिसरण मनरेगा +14वां वित्‍त मांगी लाल के घर से धामनिया रोड, खजूरीसडक | Completed | 20925 | 20768 | 2019-07-27 | 2019-08-31
| 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002076/RC/22012034470700 — सी सी रोड अभिसरण मनरेगा +14वां वित्‍त धामनिया रोड से शांतिलाल के घर तक, खजूरीसडक | Completed | 55800 | 55616 | 2019-07-27 | 2019-09-16
| 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002076/RC/22012034470702 — सी सी रोड अभिसरण मनरेगा +14वां वित्‍त अमर सिंह से तुलसी बाई मेंबर के घर तक, खजूरीसडक | Completed | 20925 | 20064 | 2019-08-31 | 2019-09-24
| 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002076/RC/22012034475404 — सी सी रोड अभिसरण मनरेगा +14वां वित्‍त धामनिया रोड से राकेश के घर की ओर, खजूरीसडक | Completed | 13500 | 13200 | 2019-09-21 | 2019-10-05
| 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002076/RC/22012034475407 — सी सी रोड अभिसरण मनरेगा +14वां वित्‍त भूरी बाई से राजाराम के घर की ओर, खजूरीसडक | Completed | 14996 | 14784 | 2019-09-21 | 2019-10-14
| 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002076/RC/22012034475409 — सी सी रोड अभिसरण मनरेगा +14वां वित्‍त धामनिया रोड से मिथलेश के घर की ओर, खजूरीसडक | Completed | 13500 | 13376 | 2019-09-21 | 2019-10-26
| 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002076/RC/22012034526317 — सीसी रोड निर्माण 14वां वित्त अभिसरण केसर सिंह से प्रेम सिंह के घर तक, खारखेड़ी, खजूरी सड़क | Completed | 21855 | 19380 | 2020-08-29 | 2020-09-21
| 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002076/RC/22012034526515 — सी सी रोड निर्माण मनरेगा 14 वां वित्‍त अभिसरण दिलीप से मनोज के घर तक, खजूरीसडक‍ | Completed | 15000 | 13680 | 2020-06-20 | 2020-08-15
| 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002076/RC/22012034526524 — सी सी रोड अभिसरण मनरेगा +14वां वित्‍त सीताराम शर्मा से सज्‍जन के घर तक, खारखेडी, खजूरीसडक | Completed | 74865 | 72960 | 2020-09-12 | 2020-10-30
| 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1728002076/RC/22012034526536 — सुदुर ग्राम संपर्क सडक खजूरी सडक मुख्‍य मार्ग से खेतलाखेडी, ग्राम पंचायत खजूरीसडक | Completed | 1422808.36 | 1304882.16 | 2020-06-24 | 2020-12-10
| 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1728002076/RC/22012034528115 — खेत सड़क निर्माण खेतलाखेड़ी सड़क से मनोहर सिंह के खेत की ओर, खजूरी सड़क | Completed | 1426808.36 | 563706.58 | 2020-07-08 | 2020-11-28
| 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002076/RC/22012034545146 — सी सी रोड निर्माण अभिसरण मनरेगा + 14 वां वित्‍त मेन रोड से कमलसिंह के घर की ओर, खारखेडी, खजूरीसडक | Completed | 18600 | 17100 | 2020-10-24 | 2020-11-16
| 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002076/RC/22012034559289 — सी सी रोड निर्माण कार्य मनरेगा अभिसरण खजुरीसडक | Closed | 0 | 0 | 2020-10-02
| 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002076/RC/22012034569228 — सी सी रोड निर्माण कार्य मनरेगा + 15 वां वित्‍त आंगनबाडी से नारायण सिंह के घर तक, खजूरीसडक | Deleted | 0 | 0 | 2021-04-14
| 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1728002076/RC/22012034575849 — सुदूर ग्राम संपर्क सडक निर्माण हाइवे मेन रोड से संजय जोशी के खेत तक, खजूरीसडक | Completed | 1386860.15 | 1016111.97 | 2021-07-10 | 2022-08-15
| 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Kharanja (brick/stone) Roads for Comm / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1728002076/RC/22012034651063 — खडंजा निर्माण कार्य गणेश राम के घ्‍ार से पप्‍पू की डेयरी तक, खजूरीसडक | Closed | 0 | 0 | 2023-04-14
| 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Kharanja (brick/stone) Roads for Comm / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1728002076/RC/22012034661198 — खंड़ंजा निर्माण कार्य गणेश राम के घर से पप्पू की डेयरी तक, खजूरी सड़क | Closed | 0 | 0 | 2023-04-14
| 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1728002076/RC/22012034663697 — सुदूर सडक निर्माण कार्य मनरेगा+जनभागीदारी, मेन रोड से दुर्गाप्रसाद जी के खेत तक, खजूरीसडक | Completed | 4240000 | 3367684.46 | 2023-10-07 | 2026-06-05
| 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002076/RC/22012034679817 — सी सी रोड निर्माण कार्य ग्राम पंचायत खजूरीसडक | New | 0 | 0 | 2024-04-14
| 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002076/RC/22012034682060 — सी सी रोड निर्माण मनरेगा + विधायक निधि विष्णु के घर से राहुल परिहार की डेरी तक, खजूरीसडक | Completed | 150000 | 144504 | 2024-08-03 | 2025-08-11
| 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1728002076/RC/43 — सडक मुरमीकरण मेनरोड से बकानिया की तरफ खजूरीसडक | Completed | 177000 | 121436.44 | 2009-05-01 | 2009-04-01
| 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1728002076/RC/92 — मुरमी करण कार्य मेन रोड से जूनापथ मार्ग खजूरी सडक | Completed | 177000 | 150460 | 2009-06-13 | 2009-06-01
| 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1728002076/RS/22012034305784 — शौचालय निर्माण 10 हितग्राही खारखेडी, खजूरीसडक | Completed | 102400 | 90733.7 | 2016-10-29 | 2016-12-26
| 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Compost Pit / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1728002076/RS/22012034321925 — सार्वजनिक नाडेप निर्माण कार्य ग्राम पंचायत खजुरी सड़क | Deleted | 16900 | 0 | 2017-01-29
| 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Compost Pit / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1728002076/RS/22012034321937 — सार्वजनिक नाडेप निर्माण कार्य ग्राम पंचायत खजुरी सड़क | Completed | 16900 | 16230 | 2017-02-04 | 2017-05-30
| 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Compost Pit / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1728002076/RS/22012034321941 — सार्वजनिक नाडेप निर्माण कार्य ग्राम पंचायत खजुरी सड़क | Completed | 16900 | 16397 | 2017-02-04 | 2017-10-18
| 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Compost Pit / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1728002076/RS/22012034322173 — सार्वजनिक नाडेप निर्माण कार्य बिजली ऑफिस की तरफ ग्राम पंचायत खजुरी सड़क | Completed | 16900 | 16397 | 2017-02-04 | 2017-05-30
| 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Compost Pit / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1728002076/RS/22012034322176 — सार्वजनिक नाडेप निर्माण कार्य गीता बाई के घर की ओर ग्राम पंचायत खजुरी सड़क | Completed | 16900 | 16397 | 2017-02-04 | 2017-05-30
| 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Compost Pit / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1728002076/RS/22012034322181 — सार्वजनिक नाडेप निर्माण कार्य हनुमान मंदिर वाला ग्राम पंचायत खजुरी सड़क | Completed | 16900 | 3173 | 2017-03-04 | 2020-09-05
| 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Compost Pit / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1728002076/RS/22012034322228 — सार्वजनिक नाडेप निर्माण कार्य प्रेम के मकान के तरफ पंचायत खजुरी सड़क | Completed | 16900 | 16397 | 2017-02-04 | 2017-05-22
| 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1728002076/RS/22012034323223 — शौचालय निर्माण10 हितग्राही ग्राम खेतलाखेडी ग्राम पंचायत खजुरी सड़क | Completed | 120000 | 86768.18 | 2017-02-04 | 2017-10-18
| 2018-2019 | D--RURAL INFRASTUCTURE / Rural Sanitation | Compost Pit / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1728002076/RS/22012034384120 — नाडेप निर्माण कार्य खजूरीसडक | Closed | 0 | 0 | 2018-04-14
| 2018-2019 | D--RURAL INFRASTUCTURE / Rural Sanitation | Compost Pit / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1728002076/RS/22012034384704 — NADEP NIRMAN KARYA KHAJURISADAK | Closed | 0 | 0 | 2018-04-14
| 2018-2019 | D--RURAL INFRASTUCTURE / Rural Sanitation | Compost Pit / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1728002076/RS/22012034384705 — NADEP NIRMAN KARYA KHARKHEDI KHAJURISADAK | Closed | 0 | 0 | 2018-04-14
| 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1728002076/RS/22012034526760 — SLWM लीच पिट निर्माण कार्य (संख्‍या 9) ग्राम पंचायत खजूरीसडक | Closed | 124620.82 | 0 | 2021-04-14
| 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1728002076/RS/22012034526761 — SLWM किचिन गार्डन निर्माण कार्य (संख्‍या 7) ग्राम पंचायत खजूरीसडक | Closed | 28853.06 | 0 | 2021-04-14
| 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Vermi Compost structure for Community / Construction of Vermi Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1728002076/RS/22012034526762 — SLWM वर्मी कम्‍पोस्‍ट निर्माण कार्य, (संख्‍या 15) ख्‍ाजूरीसडक | Closed | 200896.19 | 0 | 2021-04-14
| 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1728002076/RS/22012034597379 — नाडेप निर्माण कार्य (संख्या 12) ग्राम पंचायत खजूरीसडक | Completed | 158370.25 | 125978.56 | 2021-11-06 | 2021-12-07
| 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1728002076/RS/22012034597381 — नाडेप निर्माण कार्य (संख्या 4) खारखेडी ग्राम पंचायत खजूरीसडक | Completed | 54290.09 | 8616 | 2021-11-06 | 2026-06-05
| 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1728002076/RS/22012034624504 — लीच पिट निर्माण कार्य मनरेगा +15 वां वित्त (संख्या 10), खारखेडी, खजूरीसडक | Completed | 12300 | 11580 | 2021-12-04 | 2022-12-20
| 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1728002076/RS/22012034624509 — लीच पिट निर्माण कार्य मनरेगा +15 वां वित्त (संख्या 15), खजूरीसडक | Completed | 18500 | 17370 | 2021-12-04 | 2022-06-18
| 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1728002076/RS/22012034629766 — SLWM अंतर्गत लीच पिट निर्माण मनरेगा +एसबीएम (संख्या 25), खारखेडी, खजूरीसडक | Completed | 30600 | 27792 | 2021-12-04 | 2022-01-01
| 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1728002076/RS/22012034683229 — सामुदायिक लीच पिट निर्माण बाइ कार्य पाइप ड्रेनेज, मनरेगा + एसबीएम, खजूरीसडक | Completed | 222900 | 219674 | 2023-06-10 | 2023-11-02
| 2025-2026 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1728002076/RS/22012035136717 — नाली निर्माण कार्य मनरेगा +15 वां वित्त धर्मेंद्र से रामस्‍वरूप के घर तक, खजूरी सडक | Completed | 50000 | 48546 | 2025-04-11 | 2025-07-21
| 2025-2026 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1728002076/RS/22012035136853 — नाली निर्माण कार्य मनरेगा +15 वां वित्त रामस्‍वरूप से विक्रम के घर तक, खजूरी सडक | Completed | 100000 | 95265 | 2025-04-11 | 2025-07-21
| 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Gabions / Construction of Gabion Check Dam for Individuals | Constr of Gabion | 1728002076/WC/100 — गेवियन संरचना खजूरी सडक 2 | Completed | 79000 | 34868 | 2009-02-25 | 2008-04-01
| 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Dam / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1728002076/WC/22012034314036 — तालाब वेस्‍ट निर्माण कार्य खारखेडी, खजूरीसडक | Completed | 267000 | 257715 | 2016-12-10 | 2017-05-30
| 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Sub Surface Dam / Construction of Underground Dykes for Community | Underground Dyke for Ground Water Recharge | 1728002076/WC/22012034326180 — तालाब बेस्ट बियर निर्माण कार्य खारखेडी, खजूरी सड़क | Completed | 326400 | 321740 | 2017-05-27 | 2017-07-19
| 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & maint of Community Ponds for Comm / Repair and maintenance of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1728002076/WC/22012034391375 — तालाब बेस्‍ट वियर मरम्‍मत कार्य पुलिया सहित खेतलाखेडी, खजूरीसडक | Completed | 325000 | 324561.12 | 2018-06-09 | 2020-05-06
| 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1728002076/WC/22012034394102 — संकन तालाब गहरीकरण कार्य खारखेड़ी ग्राम पंचायत खजूरीसड़क | Completed | 967100 | 965840.05 | 2018-06-23 | 2020-08-29
| 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1728002076/WC/22012034435633 — talab nirman | Closed | 0 | 0 | 2019-04-14
| 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1728002076/WC/22012034471810 — सोख्‍ता गढढा निर्माण कार्य सती माता मंदिर के पास, खजूरीसडक | Completed | 13427.22 | 9504 | 2019-07-20 | 2020-05-02
| 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1728002076/WC/22012034471811 — सोख्‍ता गढढा निर्माण कार्य शा0मा0शाला भवन, खजूरीसडक | Completed | 13427.22 | 9504 | 2019-07-27 | 2019-08-24
| 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1728002076/WC/22012034471812 — सोख्‍ता गढढा निर्माण कार्य आंगनबाडी भवन क्रं0 2, खजूरीसडक | Completed | 13427.22 | 9504 | 2019-07-27 | 2019-08-24
| 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1728002076/WC/22012034495121 — MWC संकन तालाब निर्माण कार्य ग्राम पंचायत खजूरीसडक | Closed | 0 | 0 | 2019-08-15
| 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1728002076/WC/22012034495122 — MWC चेक डेम निर्माण कार्य रामचरण के खेत के पास, ग्राम पंचायत खजूरीसडक | Closed | 0 | 0 | 2019-08-15
| 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1728002076/WC/22012034547406 — सामुदायिक पोण्‍ड निर्माण कार्य शमशान में, खजूरीसडक | Completed | 108814.67 | 94180.32 | 2020-05-16 | 2020-11-27
| 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1728002076/WC/22012034595451 — MWC सामुदायिक तालाब निर्माण कार्य खारखेडी, ग्राम पंचायत खजूरीसडक | Closed | 0 | 0 | 2020-10-02
| 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1728002076/WC/22012034596454 — MWC सामुदायिक तालाब निर्माण कार्य खारखेडी, ग्राम पंचायत खजूरीसडक | Completed | 664269.76 | 545491.48 | 2020-11-28 | 2021-10-15
| 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & Maint of Earthen graded Bund for Com / Repair and Maintenance of Earthen graded Bund for Community | Repair & Maint of Bund | 1728002076/WC/22012034608940 — तालाब पाल (बंट) सुद़ढीकरण कार्य खजूरीसडक | Closed | 422925 | 0 | 2020-10-02
| 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1728002076/WC/22012034608942 — सामुदायिक पोण्‍ड निर्माण कार्य खारखेडी, खजूरीसडक | Closed | 0 | 0 | 2020-10-02
| 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1728002076/WC/22012034610682 — सामुदायिक पोण्‍ड निर्माण कार्य मरघट के पास, खेतलाखेडी, खजूरीसडक | Closed | 0 | 0 | 2020-10-02
| 2021-2022 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1728002076/WC/22012034754220 — फ्लड कंट्रोल एंड बंड स्टेबलाइजेशन कार्य, खजूरी सड़क | Closed | 0 | 0 | 2021-04-14
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & maint of Community Ponds for Comm / Repair and maintenance of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1728002076/WC/22012034926643 — तालाब जीर्णोद्धार एवं वेस्ट वियर निर्माण कार्य मनरेगा + 15 वां वित्त, खजूरीसडक | Completed | 225000 | 229236 | 2022-03-26 | 2022-07-12
| 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1728002076/WC/22012035001604 — सामुदायिक पोंड निर्माण कार्य पुराने शमशान के पास, ग्राम खामलाखेड़ी, खजूरी सड़क | Completed | 597866.63 | 475397.86 | 2022-09-27 | 2025-06-25
| 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1728002076/WC/22012035032416 — सामुदायिक पोण्ड निर्माण कार्य, खारखेडी, ग्राम पंचायत खजूरीसडक | Completed | 895047.39 | 515389 | 2023-04-15 | 2025-06-25
| 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1728002076/WC/22012035125913 — सामुदायिक पोण्‍ड निर्माण कार्य खेतलाखेडी, ग्राम पंचायत खजूरीसडक | Closed | 0 | 0 | 2023-08-16
| 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1728002076/WC/22012035125917 — सोख्‍ता गढढा निर्माण कार्य संख्‍या 2 बिजली आफिस के पीछे, खजूरीसडक | Completed | 43563.99 | 13673 | 2023-10-07 | 2026-04-18
| 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1728002076/WC/22012035129499 — सोख्‍ता गढढा निर्माण कार्य संख्‍या 2, आंगनबाडी व भैयालाल के घर के पास, खारखेडी खजूरीसडक | Closed | 0 | 0 | 2023-08-16
| 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1728002076/WC/22012035268160 — सामुदायिक पोण्‍ड निर्माण कार्य ग्राम पंचायत खजूरीसडक | Deleted | 0 | 0 | 2025-04-14
| 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1728002076/WC/22012035290874 — सोख्‍ता गढढा निर्माण कार्य पंचायत भवन के पास, खजूरीसडक | Approved | 25899.46 | 0 | 2025-04-14
| 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1728002076/WC/22012035290876 — सोख्‍ता गढढा निर्माण कार्य हनुमान मंदिर के पास, खजूरीसडक | Approved | 25899.46 | 0 | 2025-04-14
| 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1728002076/WC/22012035309075 — सामुदायिक पोण्‍ड निर्माण कार्य ग्राम पंचायत खजूरीसडक | Completed | 311654.15 | 154251 | 2025-06-09 | 2026-04-16
| 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1728002076/WC/97 — कोलास नदी केचमेंन्‍ट एरिया रूकावट दूर करना | Completed | 494000 | 102118 | 2009-05-17 | 2009-04-01
| 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Gabions / Construction of Gabion Check Dam for Individuals | Constr of Gabion | 1728002076/WC/99 — गेवियन संरचना खजूरी सडक 1 | Completed | 83000 | 37207 | 2009-02-14 | 2008-04-01
| 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Feeder Channel / Construction of Feeder Canal for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1728002076/WC/9993625065 — नदी चौडीकरण कार्य ग्राम पंचायत खजूरीसडक | Completed | 498500 | 134182 | 2012-05-25 | 2012-06-14