## Work List
Exported on: 2026-08-22 01:17:20
Filters applied:
Data source: MGNREGA
District: BHOPAL
Block: PHANDA
Panchayat: MUBARAKPUR
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
| 2022-2023 | C--COMMON INFRASTRUCTURE FOR NRLM COMPLIANT SELF HELP GROUPS / Anganwadi/Other Rural Infrastructure | Constr of workshed for Livelihood activity (Grps) / Construction of workshed for Livelihood activity for Groups | Construction of building/workshed for SHG | 1728002097/AV/22012034621783 — सेग्रीगेशन शेड निर्माण कार्य मनरेगा+15 वॉं वित्‍त ग्राम पंचायत मुबारिकपुर | Completed | 20000 | 19584 | 2022-12-20 | 2023-08-08
| 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1728002097/AV/22012034627152 — शांतिधाम विकास कार्य बदरखा सडक, मुबारकपुर | Completed | 328127.66 | 283229.58 | 2023-04-11 | 2023-12-20
| 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1728002097/AV/22012034648679 — Gram Panchayat Seva Kendra | Closed | 1100000 | 0 | 2023-08-15
| 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play field for Community | Construction of Play field | 1728002097/AV/22012034653645 — खेल मैदान निर्माण कार्य नई बस्ती, ग्राम पंचायत मुबारकपुर | Closed | 0 | 0 | 2024-01-24
| 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1728002097/DP/22012034583108 — व़क्षारोपण कार्य शांतिधाम परिसर, ग्राम पंचायत मुबारकपुर | Completed | 134212.69 | 86813 | 2023-08-08 | 2026-02-16
| 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1728002097/DP/22012034583109 — व़क्षारोपण कार्य शांतिधाम परिसर,बदरखासडक, ग्राम पंचायत मुबारकपुर | Ongoing | 134212.69 | 63414 | 2023-08-01
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002097/IF/IAY/4697391 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117898199 | Ongoing | 23490 | 16038 | 2024-11-26
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002097/IF/IAY/4703726 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120379491 | Completed | 23490 | 23229 | 2025-06-17 | 2025-11-12
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002097/IF/IAY/4710535 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123434933 | Ongoing | 23490 | 16038 | 2024-11-26
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002097/IF/IAY/4753403 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117897276 | Completed | 23490 | 20844 | 2024-11-26 | 2026-04-16
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002097/IF/IAY/4753405 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117897842 | Ongoing | 23490 | 17712 | 2024-11-26
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002097/IF/IAY/4883470 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151196968 | Ongoing | 23490 | 14094 | 2025-02-25
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002097/IF/IAY/5822052 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122204826 | Completed | 23490 | 20880 | 2025-10-07 | 2026-04-16
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002097/IF/IAY/5824027 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126825216 | Completed | 23490 | 21924 | 2025-10-07 | 2026-04-16
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002097/IF/IAY/5824447 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123798853 | Completed | 23490 | 22707 | 2025-12-09 | 2026-04-16
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002097/IF/IAY/5826314 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122032238 | Completed | 23490 | 23229 | 2025-12-09 | 2026-04-16
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002097/IF/IAY/5827439 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121647298 | Completed | 23490 | 22968 | 2025-10-07 | 2026-04-16
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002097/IF/IAY/5827535 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121649496 | Completed | 23490 | 21924 | 2025-10-07 | 2026-04-16
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002097/IF/IAY/5828026 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122727957 | Completed | 23490 | 22707 | 2025-12-09 | 2026-04-16
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002097/IF/IAY/5843544 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126578276 | Physically Completed | 23490 | 19314 | 2025-11-04 | 2026-01-23
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002097/IF/IAY/5843818 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117897558 | Completed | 23490 | 22446 | 2025-10-28 | 2026-04-16
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002097/IF/IAY/5843819 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117897955 | Completed | 23490 | 22446 | 2025-10-21 | 2026-04-16
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002097/IF/IAY/5844115 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121720631 | Approved | 23490 | 0 | 2025-02-07
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002097/IF/IAY/5844588 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142248488 | Completed | 23490 | 22446 | 2025-10-21 | 2026-04-16
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002097/IF/IAY/5844590 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142253193 | Completed | 23490 | 22707 | 2025-12-09 | 2026-04-16
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002097/IF/IAY/5844642 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121356826 | Completed | 23490 | 22446 | 2025-12-16 | 2026-04-16
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002097/IF/IAY/5844659 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145857136 | Completed | 23490 | 22446 | 2025-10-28 | 2026-04-16
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002097/IF/IAY/5844660 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145930557 | Completed | 23490 | 22446 | 2025-10-28 | 2026-04-16
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002097/IF/IAY/5845403 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117898027 | Completed | 23490 | 22446 | 2025-11-11 | 2026-04-16
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002097/IF/IAY/5845837 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130571512 | Completed | 23490 | 22446 | 2025-10-21 | 2026-04-16
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002097/IF/IAY/5845838 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130571531 | Approved | 23490 | 0 | 2025-02-07
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002097/IF/IAY/5845839 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130571552 | Completed | 23490 | 22446 | 2025-10-21 | 2026-04-16
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002097/IF/IAY/5845840 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130571574 | Approved | 23490 | 0 | 2025-02-21
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002097/IF/IAY/5904257 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122033627 | Approved | 23490 | 0 | 2026-01-22
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002097/IF/IAY/5905464 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124187545 | Approved | 23490 | 0 | 2026-01-22
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002097/IF/IAY/5908240 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123799318 | Approved | 23490 | 0 | 2026-01-22
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002097/IF/IAY/5910369 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123866144 | Approved | 23490 | 0 | 2026-01-22
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002097/IF/IAY/5911074 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130037392 | Approved | 23490 | 0 | 2026-01-29
| 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002097/IF/IAY/5912735 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122206284 | Physically Completed | 23490 | 21924 | 2026-04-14 | 2026-06-16
| 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002097/IF/IAY/5919338 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130571492 | Ongoing | 23490 | 23490 | 2026-05-05
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002097/IF/IAY/5919551 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145930436 | Approved | 23490 | 0 | 2026-01-22
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002097/IF/IAY/5919663 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121664385 | Approved | 23490 | 0 | 2026-01-29
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002097/IF/IAY/5919736 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142249214 | Approved | 23490 | 0 | 2026-01-29
| 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002097/IF/IAY/5921809 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118505308 | Ongoing | 23490 | 7830 | 2026-06-02
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002097/IF/IAY/5926832 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122628023 | Approved | 23490 | 0 | 2026-01-22
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002097/IF/IAY/5927093 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122609346 | Approved | 23490 | 0 | 2026-01-22
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002097/IF/IAY/5927639 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122612776 | Approved | 23490 | 0 | 2026-01-22
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002097/IF/IAY/5928244 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126826944 | Approved | 23490 | 0 | 2026-01-29
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002097/IF/IAY/5928744 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124186209 | Approved | 23490 | 0 | 2026-01-22
| 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002097/IF/IAY/5929819 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106516775 | Ongoing | 23490 | 10962 | 2026-06-02
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002097/IF/IAY/5930030 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145930343 | Approved | 23490 | 0 | 2026-01-22
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002097/IF/IAY/5930618 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113746919 | Approved | 23490 | 0 | 2026-01-22
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002097/IF/IAY/6058949 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120403341 | Approved | 23490 | 0 | 2026-01-22
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002097/IF/IAY/6060831 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122726625 | Approved | 23490 | 0 | 2026-01-22
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002097/IF/IAY/6063792 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121629618 | Approved | 23490 | 0 | 2026-01-22
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002097/IF/IAY/6064903 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122200962 | Approved | 23490 | 0 | 2026-01-22
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002097/IF/IAY/6065059 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122609646 | Approved | 23490 | 0 | 2026-01-22
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002097/IF/IAY/6069108 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106499329 | Approved | 23490 | 0 | 2026-01-22
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002097/IF/IAY/6069109 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106499397 | Approved | 23490 | 0 | 2026-01-22
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002097/IF/IAY/6069122 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106516866 | Approved | 23490 | 0 | 2026-01-22
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002097/IF/IAY/6082477 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122609101 | Approved | 23490 | 0 | 2026-01-22
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002097/IF/IAY/6084596 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124171987 | Approved | 23490 | 0 | 2026-01-22
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002097/IF/IAY/6090731 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127948120 | Approved | 23490 | 0 | 2026-01-29
| 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002097/IF/IAY/6090899 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128085207 | Ongoing | 23490 | 10962 | 2026-06-02
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002097/IF/IAY/6092460 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130037047 | Approved | 23490 | 0 | 2026-01-29
| 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002097/IF/IAY/6093073 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130580629 | Physically Completed | 23490 | 21924 | 2026-04-14 | 2026-06-16
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002097/IF/IAY/6096137 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142249105 | Approved | 23490 | 0 | 2026-01-29
| 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002097/IF/IAY/6096138 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142249382 | Ongoing | 23490 | 23490 | 2026-05-05
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002097/IF/IAY/6097350 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145847740 | Approved | 23490 | 0 | 2026-01-22
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002097/IF/IAY/6100456 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150193258 | Approved | 23490 | 0 | 2026-01-29
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002097/IF/IAY/6243888 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121755188 | Approved | 23490 | 0 | 2026-01-29
| 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002097/IF/IAY/6245257 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128771391 | Approved | 23490 | 0 | 2026-04-27
| 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1728002097/RS/22012034668668 — सामुदायिक लीच पिट निर्माण कार्य (संख्‍या 20), मुबारकपुर | Closed | 164494.04 | 0 | 2022-08-16
| 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1728002097/RS/22012034673861 — सामुदायिक सोक पिट मनरेगा+एसबीएम, हिद्रेश मीना से जगदीश मीना के घर तक, मुबा‍रकपुर | Completed | 63297 | 63240 | 2022-11-22 | 2022-12-25
| 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1728002097/RS/22012034673867 — सामुदायिक सोक पिट मनरेगा+एसबीएम, हनुमान मंदिर से अर्जुन मीना के घर तक, मुबा‍रकपुर | Completed | 63297 | 46512 | 2022-12-20 | 2025-05-20
| 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1728002097/RS/22012034673870 — सामुदायिक सोक पिट मनरेगा+एसबीएम, मस्जिद से सलीम मिया के घर तक, मुबा‍रकपुर | Completed | 63297 | 62424 | 2022-12-13 | 2023-08-22
| 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1728002097/RS/22012035121280 — सामुदायिक लीच पिट निर्माण कार्य (संख्या 10), बदरखासडक, मुबारिकपुर | Closed | 0 | 0 | 2023-10-02
| 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1728002097/RS/22012035121281 — सामुदायिक लीच पिट निर्माण कार्य (संख्या 10), मुबारिकपुर | Closed | 0 | 0 | 2023-10-02
| 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1728002097/RS/22012035129015 — ग्रेवाटर नाली निर्माण मनरेगा + 15 वां वित्त सलीम से उईके के घर तक, मुबारकपुर | Completed | 68088 | 23328 | 2024-08-19 | 2026-02-25
| 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1728002097/RS/22012035131393 — पाइप नाली निर्माण कार्य मनरेगा + 15 वां वित्त रविशंकर से हरी के घर तक, बदरखासडक, मुबारकपुर | Completed | 28382 | 20655 | 2024-10-21 | 2024-12-05
| 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1728002097/WC/22012035001522 — सामुदायिक सोख्‍ता गढढा निर्माण्‍ा कार्य (संख्‍या 5), मुबारकपुर | Closed | 113626.07 | 0 | 2022-08-16
| 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone boulder Gully Plugs for Comm / Construction of Stone boulder Gully Plugs for Community | Boulder Check/Gully Plug | 1728002097/WC/22012035001528 — गली प्‍लग / बोल्‍डर चेक डेम निर्माणनाले पर, (संख्‍या 10), मुबारकपुर | Closed | 0 | 0 | 2022-08-16
| 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone boulder Gully Plugs for Comm / Construction of Stone boulder Gully Plugs for Community | Boulder Check/Gully Plug | 1728002097/WC/22012035001530 — गली प्‍लग / बोल्‍डर चेक डेम निर्माण नाले पर (संख्‍या 15),बदरखासडक, मुबारकपुर | Closed | 0 | 0 | 2022-08-06
| 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone boulder Gully Plugs for Comm / Construction of Stone boulder Gully Plugs for Community | Boulder Check/Gully Plug | 1728002097/WC/22012035025921 — गली प्‍लग / बोल्‍डर चेक डेम निर्माण संख्‍या 10, मुबारिकपुर | Completed | 202554.54 | 159991.66 | 2023-04-11 | 2025-09-26
| 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone boulder Gully Plugs for Comm / Construction of Stone boulder Gully Plugs for Community | Boulder Check/Gully Plug | 1728002097/WC/22012035025924 — गली प्‍लग / बोल्‍डर चेक डेम निर्माण संख्‍या 15,बदरखासडक, मुबारिकपुर | Completed | 301831.82 | 237265.45 | 2023-04-11 | 2025-09-26
| 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1728002097/WC/22012035074163 — पोखर तालाब निर्माण कर्य बदरखासडक, मुबारकपुर | Completed | 648304.06 | 515895.68 | 2023-06-01 | 2026-04-16
| 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1728002097/WC/22012035153144 — सोख्‍ता गढढा निर्माण कार्य संख्याx 03 ग्राम पंचायत मुबारकपुर | Closed | 95226.77 | 0 | 2023-10-02
| 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1728002097/WC/22012035181441 — सोख्ता गडढा निर्माण कार्य मुबारकपुर | Approved | 116609.13 | 0 | 2024-04-14