## Work List
District / Block / Panchayat | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Start / completed date
BHOPAL / PHANDA / BISHANKHEDI | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1728002098/AV/22012034648684 — Gram Panchayat Seva Kendra | Ongoing | 1100000 | 196749.32 | 2025-04-22 -
BHOPAL / PHANDA / BISHANKHEDI | C--COMMON INFRASTRUCTURE FOR NRLM COMPLIANT SELF HELP GROUPS / Anganwadi/Other Rural Infrastructure | Constr of agri produce storage building for groups / Construction of Agricultural produce storage Building for Groups | Constr of Food Grain storage | 1728002098/AV/22012034650713 — सेग्रीगेशन शेड निर्माण मनरेगा+ 15वा वित्त चांदपुर, बिशनखेड़ी | Closed | 20000 | 0 | 2023-08-17 -
BHOPAL / PHANDA / BISHANKHEDI | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1728002098/AV/22012034663693 — Gram Panchayat Seva Kendra Bishan Khedi | New | 0 | 0 | 2024-08-15 -
BHOPAL / PHANDA / BISHANKHEDI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002098/IF/IAY/4577017 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118018196 | Completed | 23490 | 21861 | 2025-02-04 - 2026-03-10
BHOPAL / PHANDA / BISHANKHEDI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002098/IF/IAY/4585914 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119862678 | Completed | 23490 | 21816 | 2025-02-04 - 2026-03-10
BHOPAL / PHANDA / BISHANKHEDI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002098/IF/IAY/4603845 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124428216 | Ongoing | 23490 | 7830 | 2026-05-12 -
BHOPAL / PHANDA / BISHANKHEDI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002098/IF/IAY/4611756 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125555911 | Completed | 23490 | 21663 | 2025-04-22 - 2026-03-10
BHOPAL / PHANDA / BISHANKHEDI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002098/IF/IAY/4613346 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125585898 | Completed | 23490 | 21663 | 2025-02-25 - 2026-03-10
BHOPAL / PHANDA / BISHANKHEDI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002098/IF/IAY/4646260 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142532533 | Completed | 23490 | 21663 | 2025-02-04 - 2026-03-10
BHOPAL / PHANDA / BISHANKHEDI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002098/IF/IAY/4661731 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148978526 | Completed | 23490 | 21663 | 2025-02-25 - 2026-03-10
BHOPAL / PHANDA / BISHANKHEDI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002098/IF/IAY/4713537 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127168826 | Ongoing | 23490 | 9135 | 2026-05-26 -
BHOPAL / PHANDA / BISHANKHEDI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002098/IF/IAY/4781857 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128972035 | Completed | 23490 | 21816 | 2025-03-25 - 2025-09-30
BHOPAL / PHANDA / BISHANKHEDI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002098/IF/IAY/5821433 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125562340 | Completed | 23490 | 20358 | 2025-10-07 - 2026-03-10
BHOPAL / PHANDA / BISHANKHEDI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002098/IF/IAY/5822145 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151111738 | Completed | 23490 | 23490 | 2025-10-14 - 2026-03-10
BHOPAL / PHANDA / BISHANKHEDI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002098/IF/IAY/5822161 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116385959 | Completed | 23490 | 23490 | 2026-01-20 - 2026-05-13
BHOPAL / PHANDA / BISHANKHEDI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002098/IF/IAY/5822987 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125571642 | Completed | 23490 | 23490 | 2025-10-07 - 2026-03-10
BHOPAL / PHANDA / BISHANKHEDI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002098/IF/IAY/5822990 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124809010 | Ongoing | 23490 | 18792 | 2025-10-14 -
BHOPAL / PHANDA / BISHANKHEDI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002098/IF/IAY/5823000 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124810055 | Completed | 23490 | 23490 | 2025-10-07 - 2026-03-10
BHOPAL / PHANDA / BISHANKHEDI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002098/IF/IAY/5823316 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124177670 | Ongoing | 23490 | 7830 | 2026-05-12 -
BHOPAL / PHANDA / BISHANKHEDI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002098/IF/IAY/5823383 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124310763 | Completed | 23490 | 23490 | 2025-10-07 - 2026-03-09
BHOPAL / PHANDA / BISHANKHEDI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002098/IF/IAY/5823446 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124426468 | Approved | 23490 | 0 | 2025-03-03 -
BHOPAL / PHANDA / BISHANKHEDI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002098/IF/IAY/5823623 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125329277 | Approved | 23490 | 0 | 2025-03-03 -
BHOPAL / PHANDA / BISHANKHEDI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002098/IF/IAY/5823649 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142779926 | Completed | 23490 | 23490 | 2025-10-07 - 2026-03-10
BHOPAL / PHANDA / BISHANKHEDI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002098/IF/IAY/5824033 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122379388 | Completed | 23490 | 23490 | 2025-10-07 - 2026-03-10
BHOPAL / PHANDA / BISHANKHEDI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002098/IF/IAY/5824518 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118018131 | Completed | 23490 | 23490 | 2026-02-10 - 2026-06-16
BHOPAL / PHANDA / BISHANKHEDI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002098/IF/IAY/5824855 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124536669 | Completed | 23490 | 23490 | 2025-10-28 - 2026-03-10
BHOPAL / PHANDA / BISHANKHEDI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002098/IF/IAY/5824920 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124341706 | Ongoing | 23490 | 22185 | 2026-02-17 -
BHOPAL / PHANDA / BISHANKHEDI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002098/IF/IAY/5825029 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125563700 | Completed | 23490 | 23490 | 2025-10-07 - 2026-03-10
BHOPAL / PHANDA / BISHANKHEDI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002098/IF/IAY/5825167 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124426786 | Approved | 23490 | 0 | 2025-03-03 -
BHOPAL / PHANDA / BISHANKHEDI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002098/IF/IAY/5825610 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124425196 | Completed | 23490 | 23490 | 2025-10-07 - 2026-03-10
BHOPAL / PHANDA / BISHANKHEDI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002098/IF/IAY/5825614 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126455023 | Completed | 23490 | 23490 | 2025-10-07 - 2026-03-10
BHOPAL / PHANDA / BISHANKHEDI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002098/IF/IAY/5825725 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115188207 | Completed | 23490 | 23490 | 2025-10-07 - 2026-06-16
BHOPAL / PHANDA / BISHANKHEDI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002098/IF/IAY/5825771 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125564260 | Ongoing | 23490 | 7830 | 2025-10-07 -
BHOPAL / PHANDA / BISHANKHEDI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002098/IF/IAY/5825951 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124311451 | Completed | 23490 | 23490 | 2025-10-07 - 2026-03-10
BHOPAL / PHANDA / BISHANKHEDI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002098/IF/IAY/5826193 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124808488 | Approved | 23490 | 0 | 2025-02-18 -
BHOPAL / PHANDA / BISHANKHEDI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002098/IF/IAY/5826403 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125912598 | Completed | 23490 | 23490 | 2025-10-07 - 2026-03-10
BHOPAL / PHANDA / BISHANKHEDI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002098/IF/IAY/5826809 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124312756 | Approved | 23490 | 0 | 2025-02-18 -
BHOPAL / PHANDA / BISHANKHEDI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002098/IF/IAY/5827997 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127173874 | Completed | 23490 | 23490 | 2025-10-14 - 2026-03-10
BHOPAL / PHANDA / BISHANKHEDI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002098/IF/IAY/5828093 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124420046 | Approved | 23490 | 0 | 2025-03-20 -
BHOPAL / PHANDA / BISHANKHEDI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002098/IF/IAY/5828311 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119862623 | Completed | 23490 | 23490 | 2026-01-20 - 2026-05-25
BHOPAL / PHANDA / BISHANKHEDI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002098/IF/IAY/5828384 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122377463 | Completed | 23490 | 15660 | 2025-10-14 - 2026-02-09
BHOPAL / PHANDA / BISHANKHEDI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002098/IF/IAY/5843637 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126448294 | Completed | 23490 | 23490 | 2025-11-11 - 2026-03-10
BHOPAL / PHANDA / BISHANKHEDI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002098/IF/IAY/5843644 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125572676 | Approved | 23490 | 0 | 2025-03-03 -
BHOPAL / PHANDA / BISHANKHEDI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002098/IF/IAY/5843658 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142532592 | Completed | 23490 | 23490 | 2025-11-18 - 2026-03-10
BHOPAL / PHANDA / BISHANKHEDI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002098/IF/IAY/5843862 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128973161 | Completed | 23490 | 23490 | 2026-01-20 - 2026-06-16
BHOPAL / PHANDA / BISHANKHEDI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002098/IF/IAY/5843993 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149001198 | Completed | 23490 | 23490 | 2025-11-18 - 2026-03-10
BHOPAL / PHANDA / BISHANKHEDI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002098/IF/IAY/5844440 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144518477 | Ongoing | 23490 | 7830 | 2026-05-12 -
BHOPAL / PHANDA / BISHANKHEDI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002098/IF/IAY/5844442 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144528171 | Approved | 23490 | 0 | 2025-02-18 -
BHOPAL / PHANDA / BISHANKHEDI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002098/IF/IAY/5844540 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147925283 | Approved | 23490 | 0 | 2025-03-03 -
BHOPAL / PHANDA / BISHANKHEDI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002098/IF/IAY/5844546 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127171054 | Completed | 23490 | 23490 | 2025-11-11 - 2026-02-09
BHOPAL / PHANDA / BISHANKHEDI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002098/IF/IAY/5844679 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124307709 | Completed | 23490 | 23490 | 2026-01-20 - 2026-05-25
BHOPAL / PHANDA / BISHANKHEDI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002098/IF/IAY/5844734 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124315691 | Approved | 23490 | 0 | 2025-03-20 -
BHOPAL / PHANDA / BISHANKHEDI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002098/IF/IAY/5844735 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124316462 | Completed | 23490 | 23490 | 2026-01-06 - 2026-03-16
BHOPAL / PHANDA / BISHANKHEDI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002098/IF/IAY/5844781 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124178277 | Completed | 23490 | 23490 | 2025-11-11 - 2026-03-10
BHOPAL / PHANDA / BISHANKHEDI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002098/IF/IAY/5844811 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150161396 | Completed | 23490 | 23490 | 2025-11-18 - 2026-06-16
BHOPAL / PHANDA / BISHANKHEDI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002098/IF/IAY/5844913 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150152910 | Approved | 23490 | 0 | 2025-03-20 -
BHOPAL / PHANDA / BISHANKHEDI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002098/IF/IAY/5844914 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150152987 | Approved | 23490 | 0 | 2025-03-03 -
BHOPAL / PHANDA / BISHANKHEDI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002098/IF/IAY/5845050 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147347370 | Completed | 23490 | 23490 | 2025-11-11 - 2026-03-16
BHOPAL / PHANDA / BISHANKHEDI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002098/IF/IAY/5845428 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125574214 | Approved | 23490 | 0 | 2025-03-03 -
BHOPAL / PHANDA / BISHANKHEDI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002098/IF/IAY/5845429 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126280205 | Completed | 23490 | 23490 | 2025-11-11 - 2026-06-16
BHOPAL / PHANDA / BISHANKHEDI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002098/IF/IAY/5845532 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150130053 | Approved | 23490 | 0 | 2025-02-18 -
BHOPAL / PHANDA / BISHANKHEDI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002098/IF/IAY/5845576 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144233200 | Completed | 23490 | 22908 | 2025-11-11 - 2026-03-26
BHOPAL / PHANDA / BISHANKHEDI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002098/IF/IAY/5845584 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125575272 | Approved | 23490 | 0 | 2025-02-18 -
BHOPAL / PHANDA / BISHANKHEDI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002098/IF/IAY/5845751 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142532437 | Approved | 23490 | 0 | 2025-02-18 -
BHOPAL / PHANDA / BISHANKHEDI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002098/IF/IAY/5845759 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125581503 | Completed | 23490 | 23490 | 2025-12-02 - 2026-05-04
BHOPAL / PHANDA / BISHANKHEDI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002098/IF/IAY/5845773 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125582524 | Completed | 23490 | 23490 | 2025-11-11 - 2026-03-26
BHOPAL / PHANDA / BISHANKHEDI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002098/IF/IAY/5845780 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142858037 | Approved | 23490 | 0 | 2025-03-03 -
BHOPAL / PHANDA / BISHANKHEDI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002098/IF/IAY/5846118 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147407947 | Ongoing | 23490 | 18792 | 2026-01-06 -
BHOPAL / PHANDA / BISHANKHEDI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002098/IF/IAY/5846143 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144545353 | Completed | 23490 | 23490 | 2025-11-11 - 2026-03-26
BHOPAL / PHANDA / BISHANKHEDI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002098/IF/IAY/5905066 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125301470 | Ongoing | 23490 | 9135 | 2026-05-12 -
BHOPAL / PHANDA / BISHANKHEDI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002098/IF/IAY/5906885 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115188120 | Approved | 23490 | 0 | 2026-01-28 -
BHOPAL / PHANDA / BISHANKHEDI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002098/IF/IAY/5910016 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124313287 | Ongoing | 23490 | 3132 | 2026-05-26 -
BHOPAL / PHANDA / BISHANKHEDI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002098/IF/IAY/5916652 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124341999 | Ongoing | 23490 | 4437 | 2026-05-26 -
BHOPAL / PHANDA / BISHANKHEDI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002098/IF/IAY/5917845 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116622755 | Ongoing | 23490 | 7830 | 2026-05-12 -
BHOPAL / PHANDA / BISHANKHEDI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002098/IF/IAY/5917961 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142844210 | Approved | 23490 | 0 | 2026-01-28 -
BHOPAL / PHANDA / BISHANKHEDI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002098/IF/IAY/5918135 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144011201 | Ongoing | 23490 | 7830 | 2026-05-12 -
BHOPAL / PHANDA / BISHANKHEDI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002098/IF/IAY/5919046 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147363895 | Ongoing | 23490 | 4698 | 2026-05-26 -
BHOPAL / PHANDA / BISHANKHEDI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002098/IF/IAY/5920714 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127170125 | Ongoing | 23490 | 4437 | 2026-05-26 -
BHOPAL / PHANDA / BISHANKHEDI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002098/IF/IAY/5921291 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147368814 | Approved | 23490 | 0 | 2026-01-28 -
BHOPAL / PHANDA / BISHANKHEDI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002098/IF/IAY/5922012 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125765693 | Ongoing | 23490 | 4437 | 2026-05-26 -
BHOPAL / PHANDA / BISHANKHEDI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002098/IF/IAY/5922385 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125572716 | Ongoing | 23490 | 4437 | 2026-05-26 -
BHOPAL / PHANDA / BISHANKHEDI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002098/IF/IAY/5922474 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141715442 | Ongoing | 23490 | 14094 | 2026-04-21 -
BHOPAL / PHANDA / BISHANKHEDI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002098/IF/IAY/5923678 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115188434 | Approved | 23490 | 0 | 2026-01-28 -
BHOPAL / PHANDA / BISHANKHEDI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002098/IF/IAY/5924432 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147923487 | Ongoing | 23490 | 10962 | 2026-04-21 -
BHOPAL / PHANDA / BISHANKHEDI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002098/IF/IAY/5925015 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115188503 | Approved | 23490 | 0 | 2026-01-28 -
BHOPAL / PHANDA / BISHANKHEDI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002098/IF/IAY/5926711 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149626323 | Approved | 23490 | 0 | 2026-01-28 -
BHOPAL / PHANDA / BISHANKHEDI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002098/IF/IAY/5928967 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128975136 | Ongoing | 23490 | 7830 | 2026-05-12 -
BHOPAL / PHANDA / BISHANKHEDI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002098/IF/IAY/5929666 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126078089 | Ongoing | 23490 | 7830 | 2026-05-12 -
BHOPAL / PHANDA / BISHANKHEDI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002098/IF/IAY/5929740 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124312187 | Approved | 23490 | 0 | 2026-01-28 -
BHOPAL / PHANDA / BISHANKHEDI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002098/IF/IAY/6065051 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124427562 | Approved | 23490 | 0 | 2025-03-03 -
BHOPAL / PHANDA / BISHANKHEDI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002098/IF/IAY/6123133 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115188784 | Approved | 23490 | 0 | 2025-09-26 -
BHOPAL / PHANDA / BISHANKHEDI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002098/IF/IAY/6127583 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105751688 | Approved | 23490 | 0 | 2026-03-02 -
BHOPAL / PHANDA / BISHANKHEDI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002098/IF/IAY/6131512 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122379127 | Approved | 23490 | 0 | 2025-09-26 -
BHOPAL / PHANDA / BISHANKHEDI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002098/IF/IAY/6144440 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148970741 | Approved | 23490 | 0 | 2026-03-10 -
BHOPAL / PHANDA / BISHANKHEDI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002098/IF/IAY/6171245 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125569263 | Approved | 23490 | 0 | 2026-03-02 -
BHOPAL / PHANDA / BISHANKHEDI | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1728002098/RC/22012034656538 — खेत सडक निर्माण मनरेगा +जनभागीदारी, जीतेश चौकसे से अखिलेष के खेत तक, चांदपुर, बिसनखेडी | Ongoing | 2188000 | 1655925 | 2023-10-07 -
BHOPAL / PHANDA / BISHANKHEDI | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002098/RC/22012034680956 — सी सी रोड निर्माण कार्य मेन रोड से सरोज के घर तक विशनखेडी | New | 0 | 0 | 2024-04-14 -
BHOPAL / PHANDA / BISHANKHEDI | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1728002098/RS/22012034667812 — सामुदायिक नाडेप निर्माण कार्य (संख्‍या 10) ग्राम पंचायत विशनखेडी | Closed | 154807.11 | 0 | 2022-08-16 -
BHOPAL / PHANDA / BISHANKHEDI | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1728002098/RS/22012034672406 — सामुदायिक लीच पिट निर्माण कार्य (संख्‍या 20), ग्राम पंचायत विशनखेडी | Closed | 164494.04 | 0 | 2022-10-02 -
BHOPAL / PHANDA / BISHANKHEDI | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1728002098/RS/22012034701688 — सामुदायिक लीच पिट निर्माण ग्रेवाटर मेनेजमेंट मनरेगा+एसबीएम, मुकेश के घर से पुलिया की ओर, विशनखेडी | Closed | 0 | 0 | 2023-04-14 -
BHOPAL / PHANDA / BISHANKHEDI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1728002098/WC/22012034999834 — सामुदायिक सोख्‍ता गढढा निर्माण कार्य (संख्‍या 15) विशनखेडी | Physically Completed | 336177.63 | 144076.42 | 2022-12-13 - 2026-06-30
BHOPAL / PHANDA / BISHANKHEDI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1728002098/WC/22012035006421 — सामुदायिक पोण्‍ड निर्माण कार्य ग्राम पंचायत विशनखेडी | Deleted | 0 | 0 | 2022-10-02 -
BHOPAL / PHANDA / BISHANKHEDI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1728002098/WC/22012035008391 — सामुदायिक पोण्‍ड निर्माण कार्य ग्राम पंचायत विशनखेडी | Completed | 357840.1 | 212789 | 2022-12-13 - 2026-04-16
BHOPAL / PHANDA / BISHANKHEDI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1728002098/WC/22012035020606 — सामुदायिक पोण्‍ड निर्माण कार्य प्रथम, चांदपुर, ग्राम पंचायत विशनखेडी | Deleted | 0 | 0 | 2022-10-03 -
BHOPAL / PHANDA / BISHANKHEDI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1728002098/WC/22012035020607 — सामुदायिक पोण्‍ड निर्माण कार्य द्वितीय, चांदपुर, ग्राम पंचायत विशनखेडी | Deleted | 0 | 0 | 2022-10-03 -
BHOPAL / PHANDA / BISHANKHEDI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1728002098/WC/22012035025381 — सामुदायिक पोण्‍ड निर्माण कार्य प्रथम, चांदपुर, ग्राम पंचायत विशनखेडी | Completed | 361353.32 | 228463 | 2023-04-04 - 2026-04-16
BHOPAL / PHANDA / BISHANKHEDI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1728002098/WC/22012035025384 — सामुदायिक पोण्‍ड निर्माण कार्य द्वितीय, चांदपुर, ग्राम पंचायत विशनखेडी | Completed | 361353.32 | 221034 | 2023-04-04 - 2026-04-16