## Work List
Exported on: 2026-08-21 07:13:24
Filters applied:
Data source: MGNREGA
District: SEHORE
Block: ASHTA
Panchayat: ATRALIYA ASHTAA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
| 2025-2026 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1729002137/AV/22012034667994 — Shantidham Nirman Atraliya Ashta | Ongoing | 347299.31 | 293004.64 | 2026-02-15
| 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1729002137/DP/22012034573918 — Nirmal Neer Kup Nirman Kalaji ki imli ke pas Atraliya Ashta | Ongoing | 512819.59 | 214637.36 | 2023-05-24
| 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1729002137/DP/22012034597413 — वसुधा वंदन अमृत वाटिका ( स्कूल परिसर मे अतरालिया ) | Closed | 55847.4 | 0 | 2023-04-14
| 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Gov bldng premises Blck Plntation-Forestry-Comunty / Block Plantation of Forestry Trees in Government building premises for Community | Plantation | 1729002137/DP/22012034626972 — व्रक्षा रोपण (स्कूल परिसर मे अतरलिया ) | Ongoing | 58988.78 | 29754 | 2025-12-04
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729002137/IF/22012035068961 — kapil dhara kup nirman (gangu /harji) | Closed | 0 | 0 | 2023-01-25
| 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729002137/IF/22012035068965 — kapil dhara nirman (arjun sinh / moti) | Completed | 269004.17 | 258245.37 | 2023-06-07 | 2025-10-14
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729002137/IF/22012035070801 — khet talab nirman (murli singh / umrav singh) | Closed | 0 | 0 | 2023-01-25
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729002137/IF/22012035070926 — kapil dhara kup nirman (sundar bai / sidhdhu lal) | Closed | 0 | 0 | 2023-01-25
| 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729002137/IF/22012035090578 — kapil dhara kup nirman ( sundar bai /sidhdhu lal ) | Ongoing | 278238.64 | 223998.75 | 2023-06-01
| 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729002137/IF/22012035091958 — pokhar nirman atralia (murisingh / umrav singh) | Completed | 385261.22 | 120952 | 2023-05-31 | 2026-01-23
| 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729002137/IF/22012035109063 — khat talab (pratap singh /bhanvar ji) | Ongoing | 385261.22 | 121371.64 | 2023-10-06
| 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729002137/IF/22012035109065 — khet talab (mahesh / bheru singh) | Ongoing | 385261.22 | 78625.61 | 2023-10-06
| 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1729002137/IF/22012035163549 — khet talab (rajendra / radheshyam) | Ongoing | 385261.22 | 221 | 2023-10-06
| 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729002137/IF/22012035163560 — kapil dhara kup nirman (mangilal / harji) | Ongoing | 280370.56 | 256488 | 2023-10-06
| 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729002137/IF/22012035163575 — kapil dhara kup nirman (babulal / sidhnath singh ) | Closed | 277738.64 | 0 | 2023-08-17
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1729002137/IF/22012035229856 — नंदन फलों उद्यान (सरला बाई /दिनेश ) | Ongoing | 173308.58 | 243 | 2024-06-26
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1729002137/IF/22012035229868 — नंदन फलों उद्यान (कुंता बाई / भेरुलाल ) | Approved | 0 | 0 | 2024-06-08
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729002137/IF/22012035230162 — kapil dhara kup nirman kunta bai /bherulal | Approved | 0 | 0 | 2024-06-08
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1729002137/IF/22012035441811 — khet talab ( vikram / baldevsingh ) | Deleted | 0 | 0 | 2025-04-14
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729002137/IF/22012035442637 — dug well shubham /arjun singh | Deleted | 0 | 0 | 2025-04-14
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729002137/IF/22012035442690 — dug well ashok /ramcharan | Deleted | 0 | 0 | 2025-04-14
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729002137/IF/22012035442711 — dug well rahul /dinesh | Deleted | 0 | 0 | 2025-04-14
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729002137/IF/22012035442735 — dug well prabhu lal / ramcharan | Deleted | 0 | 0 | 2025-04-14
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729002137/IF/22012035442747 — dug well balvir singh /govind | Deleted | 0 | 0 | 2025-04-14
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729002137/IF/22012035443843 — dug well shubham /arjun singh (gp-atraliya ahta) | Physically Completed | 25899.46 | 21958.26 | 2025-05-01 | 2026-03-30
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729002137/IF/22012035443858 — dug well ashok /ramcharan (gp- atraliya ashta) | Physically Completed | 25899.46 | 21435.94 | 2025-05-01 | 2026-03-30
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729002137/IF/22012035443867 — dug well rahul /dinesh (gp- atraliya ashta ) | Completed | 25899.46 | 15904.64 | 2025-05-01 | 2026-04-08
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729002137/IF/22012035443878 — dug well prabhu lal / ramcharan (gp- atraliya ashta) | Physically Completed | 25899.46 | 21974.13 | 2025-05-01 | 2026-03-30
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729002137/IF/22012035443893 — dug well balvir singh /govind (gp- atraliya ashta) | Physically Completed | 25899.46 | 21957.5 | 2025-05-01 | 2026-03-30
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1729002137/IF/22012035443908 — khet talab ( vikram / baldevsingh ) gp- atraliya ashta | Physically Completed | 450885.64 | 105321.25 | 2025-05-01 | 2026-04-25
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1729002137/IF/22012035445663 — Khet talab govind / padam singh atraliya ashta | Closed | 55865.38 | 16730.54 | 2025-05-01
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1729002137/IF/22012035445857 — Khet talab dalip singh / chen atraliya ashta | Closed | 147621.16 | 31082 | 2025-05-01
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729002137/IF/22012035446057 — Dug well sundar bai / sidhshulal atraliya ashta | New | 0 | 0 | 2025-04-14
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729002137/IF/22012035446182 — Dug well sandip0/ prem sukh | Approved | 25899.46 | 0 | 2025-04-14
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729002137/IF/22012035446342 — Dug well chandar / ranjit atraliya ashta | Physically Completed | 25899.46 | 21956.84 | 2025-05-02 | 2026-03-30
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729002137/IF/22012035488087 — Kapil dhara kup nirma atraliya ashta ( rajaram / moti ) | Approved | 0 | 0 | 2025-04-14
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002137/IF/IAY/4582941 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118386730 | Completed | 23490 | 20169 | 2024-10-21 | 2025-06-16
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002137/IF/IAY/4742916 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113749105 | Completed | 23490 | 19683 | 2024-11-17 | 2025-06-16
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002137/IF/IAY/4766895 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123223092 | Completed | 21870 | 21627 | 2024-11-17 | 2025-06-16
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002137/IF/IAY/4805422 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146443489 | Completed | 21870 | 19683 | 2024-11-17 | 2025-06-16
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002137/IF/IAY/5821882 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120383288 | Ongoing | 23490 | 23490 | 2025-10-31
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002137/IF/IAY/5822186 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113765654 | Ongoing | 23490 | 22707 | 2025-10-15
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002137/IF/IAY/5822873 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119376320 | Completed | 23490 | 23490 | 2025-10-15 | 2026-01-12
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002137/IF/IAY/5822874 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119376763 | Ongoing | 23490 | 10962 | 2025-11-17
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002137/IF/IAY/5824436 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126711214 | Completed | 23490 | 23490 | 2025-10-15 | 2026-03-09
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002137/IF/IAY/5824437 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126711915 | Ongoing | 23490 | 18270 | 2025-11-17
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002137/IF/IAY/5825503 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118420645 | Physically Completed | 23490 | 22185 | 2025-10-15 | 2026-03-22
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002137/IF/IAY/5826495 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117821847 | Completed | 23490 | 23490 | 2025-10-15 | 2026-01-12
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002137/IF/IAY/5828114 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119428764 | Ongoing | 23490 | 22185 | 2025-10-31
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002137/IF/IAY/5844045 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126476957 | Completed | 23490 | 23490 | 2025-10-15 | 2026-03-09
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002137/IF/IAY/5844791 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149714489 | Ongoing | 23490 | 18792 | 2025-10-31
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002137/IF/IAY/5844866 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148317748 | Completed | 23490 | 23490 | 2025-10-31 | 2026-03-09
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002137/IF/IAY/5844981 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149411112 | Ongoing | 23490 | 22185 | 2025-10-31
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002137/IF/IAY/5844982 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149411165 | Completed | 23490 | 23490 | 2025-10-15 | 2026-01-12
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002137/IF/IAY/5844983 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149411195 | Completed | 23490 | 23490 | 2025-10-15 | 2026-07-10
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002137/IF/IAY/6179435 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149729474 | Approved | 23490 | 0 | 2026-03-17
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002137/IF/IAY/6206490 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149729305 | Approved | 23490 | 0 | 2026-03-17
| 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002137/IF/IAY/6207978 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149545994 | Ongoing | 23490 | 3654 | 2026-06-16
| 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729002137/RC/22012034653563 — 15 वित्त +मनरेगा सीमेंट कंक्रीट ( मंदिर से रोड तक ) | Completed | 34000 | 12595 | 2024-01-17 | 2025-02-06
| 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729002137/RC/22012034668816 — 15 वित्त +मनरेगा (c c raod man road se chok tak) | Ongoing | 86900 | 80190 | 2024-07-03
| 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Mitti Murram Roads for Community / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1729002137/RC/22012034824193 — c c road nirman hendpump se arjun ke ghar tak | Approved | 125698 | 0 | 2024-06-08
| 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1729002137/RS/22012034692666 — nali nirman atraliya (ajay singh ke makan se chok tak) | Completed | 58269 | 57239 | 2023-06-07 | 2023-09-10
| 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1729002137/RS/22012034694984 — सामुदायिक स्वच्छ्ता परिसर अतरालिया (sc बस्ती के पास ) | Completed | 44000 | 42337 | 2023-06-29 | 2025-01-10
| 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1729002137/RS/22012034697565 — 15 वित्त +मनरेगा (नाली निर्माण पुलिया से हमीर के घर तक ) | Completed | 89000 | 87074 | 2023-09-01 | 2024-05-23
| 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1729002137/RS/22012035119338 — pvc nali nirman atraliya men road se mandir tak | Completed | 27320 | 25935 | 2024-06-07 | 2025-02-09