## Work List
Exported on: 2026-08-26 13:31:18
Filters applied:
Data source: MGNREGA
District: SEHORE
Block: ICHHAWAR
Panchayat: RUGANATHPURA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
| 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1729003076/AV/22012034645159 — Shantidham nirman karya gram rupadeh gp Ruganathpura | Completed | 226381.46 | 205150.53 | 2023-10-08 | 2026-04-07
| 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1729003076/DP/22012034595782 — Vasdhu vandan ( varksha ropan karya no of plant 75 ) gp RUGANATHPURA | Closed | 55847.4 | 0 | 2023-07-30
| 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1729003076/IF/22012035102211 — Khet Talab nirman karya ( Chandar singh / Narvat singh kotawar ) gp Ruganathpura | Completed | 385261.22 | 358758 | 2023-06-02 | 2024-06-11
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1729003076/IF/22012035239652 — Nandan phaloudhan nirman karya vishnu prasad / badri prasad no of plants 250 GP Rugnathapura | Ongoing | 173308.58 | 43983 | 2024-07-20
| 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1729003076/IF/22012035446494 — JGSA Dugwell Recharge structure vishnuprasad/badriprasad | Physically Completed | 25899.46 | 23134.06 | 2025-05-03 | 2026-06-04
| 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1729003076/IF/22012035446564 — JGSA Dugwell Recharge structure gyansingh/banshilal | Physically Completed | 25899.46 | 23917.06 | 2025-05-03 | 2026-06-04
| 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1729003076/IF/22012035446655 — JGSA Dugwell Recharge structure prahalad/banshilal | Physically Completed | 25899.46 | 23917.06 | 2025-05-03 | 2026-06-04
| 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1729003076/IF/22012035446813 — JGSA Dugwell Recharge structure lakhanlal/mangilal | Physically Completed | 25899.46 | 22350.88 | 2025-05-03 | 2026-06-04
| 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1729003076/IF/22012035446905 — JGSA Dugwell Recharge structure devnarayan/meharvan | Physically Completed | 25899.46 | 23917.06 | 2025-05-03 | 2026-06-04
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1729003076/IF/22012035529966 — JGSA KHET talab nirman kary ritesh/shivmaresh gram rupadesh | Physically Completed | 147621.16 | 69165 | 2025-05-22 | 2026-05-11
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729003076/IF/22012035567803 — Kapil Dhara Kup nirman karya Ramcharan / Bhavar ji gp Ruganathpura | Approved | 0 | 0 | 2025-04-16
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1729003076/IF/22012035642009 — Ek Bagiya Maa Ke Naam Savantri bai/Kanverlal gram rupdi | New | 0 | 0 | 2025-08-15
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1729003076/IF/22012035642021 — Ek Bagiya Maa Ke Naam Bhagwati bai/Dinesh Gram Rupdi | Approved | 0 | 0 | 2025-08-15
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1729003076/IF/22012035642038 — Ek Bagiya Maa Ke Naam Sugan bai/Ramesh chendra gram rupdi | New | 0 | 0 | 2025-08-15
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1729003076/IF/22012035642057 — Ek Bagiya Maa Ke Naam Sunita bai/Bhojraj gram rupdi | New | 0 | 0 | 2025-08-15
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729003076/IF/IAY/4562616 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115684919 | Completed | 23490 | 23382 | 2025-01-18 | 2026-05-23
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729003076/IF/IAY/4564095 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115719980 | Completed | 23490 | 22968 | 2025-06-03 | 2026-05-23
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729003076/IF/IAY/4573537 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117839512 | Approved | 23490 | 0 | 2024-09-12
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729003076/IF/IAY/4694020 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115684802 | Completed | 23490 | 21735 | 2024-12-24 | 2026-05-23
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729003076/IF/IAY/4694021 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115684880 | Completed | 23490 | 22968 | 2025-01-18 | 2026-05-23
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729003076/IF/IAY/4694069 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115707343 | Physically Completed | 23490 | 11484 | 2025-08-15 | 2026-02-27
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729003076/IF/IAY/4698375 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115129095 | Ongoing | 23490 | 19170 | 2025-01-21
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729003076/IF/IAY/4698387 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115134963 | Ongoing | 23490 | 19494 | 2025-01-05
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729003076/IF/IAY/4698388 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115135007 | Ongoing | 23490 | 19710 | 2025-01-05
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729003076/IF/IAY/4698435 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115151788 | Ongoing | 23490 | 16038 | 2025-01-05
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729003076/IF/IAY/4698492 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115168331 | Ongoing | 23490 | 18711 | 2025-01-05
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729003076/IF/IAY/4701246 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115226454 | Ongoing | 23490 | 18954 | 2025-01-05
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729003076/IF/IAY/4745452 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115137319 | Ongoing | 23490 | 18360 | 2025-01-21
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729003076/IF/IAY/4745517 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115153586 | Ongoing | 23490 | 19062 | 2025-01-05
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729003076/IF/IAY/4747616 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115178908 | Ongoing | 23490 | 18576 | 2025-01-21
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729003076/IF/IAY/5823417 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115703893 | Approved | 23490 | 0 | 2025-02-28
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729003076/IF/IAY/5824128 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115700128 | Completed | 23490 | 22968 | 2026-01-19 | 2026-07-29
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729003076/IF/IAY/5824130 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117004184 | Ongoing | 23490 | 21141 | 2026-01-21
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729003076/IF/IAY/5826811 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115684828 | Completed | 23490 | 22185 | 2026-01-19 | 2026-07-29
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729003076/IF/IAY/5826812 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115684866 | Completed | 23490 | 23490 | 2026-01-22 | 2026-07-29
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729003076/IF/IAY/5826813 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115684899 | Physically Completed | 23490 | 0 | 2025-02-22 | 2026-06-07
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729003076/IF/IAY/5826814 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115685016 | Completed | 23490 | 23229 | 2026-01-21 | 2026-07-29
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729003076/IF/IAY/5826815 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115685057 | Completed | 23490 | 23490 | 2026-01-21 | 2026-07-29
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729003076/IF/IAY/5826822 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115685591 | Completed | 23490 | 22968 | 2026-01-19 | 2026-07-29
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729003076/IF/IAY/5826965 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115891170 | Ongoing | 23490 | 22968 | 2026-01-19
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729003076/IF/IAY/5826966 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115891346 | Ongoing | 23490 | 22968 | 2026-01-19
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729003076/IF/IAY/5827831 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115684477 | Approved | 23490 | 0 | 2025-02-28
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729003076/IF/IAY/5827832 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115684491 | Approved | 23490 | 0 | 2025-02-22
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729003076/IF/IAY/5827833 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115684661 | Completed | 23490 | 23490 | 2026-01-05 | 2026-07-29
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729003076/IF/IAY/5827834 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115684758 | Ongoing | 23490 | 23490 | 2026-01-19
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729003076/IF/IAY/5845734 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115684997 | Completed | 23490 | 23490 | 2026-01-21 | 2026-07-29
| 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729003076/IF/IAY/5912048 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117393289 | Ongoing | 23490 | 12528 | 2026-06-16
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729003076/IF/IAY/5914970 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115684971 | Approved | 23490 | 0 | 2026-02-09
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729003076/IF/IAY/5917527 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117365867 | Approved | 23490 | 0 | 2026-02-09
| 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729003076/IF/IAY/5917789 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117839602 | Ongoing | 23490 | 6264 | 2026-06-16
| 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729003076/IF/IAY/5924787 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117839639 | Ongoing | 23490 | 0 | 2026-06-16
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729003076/IF/IAY/5925320 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115684847 | Approved | 23490 | 0 | 2026-02-11
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729003076/IF/IAY/5929931 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117388476 | Approved | 23490 | 0 | 2026-02-09
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729003076/IF/IAY/5931376 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117839541 | Approved | 23490 | 0 | 2026-02-09
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729003076/IF/IAY/6207019 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117804445 | Approved | 23490 | 0 | 2026-02-28
| 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1729003076/LD/22012034589569 — Samtliya karan karya ( Shamshan mai ) gp Ruganathpura | Completed | 404770.66 | 398155 | 2023-05-24 | 2023-12-12
| 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1729003076/LD/22012034590879 — Samtliya karan karya ( Shamshan mai gram rupadeh) gp Ruganathpura | Completed | 558301.95 | 556032 | 2023-07-28 | 2023-12-20
| 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1729003076/LD/22012034596562 — Shamshan samtaliykaran kary gram Rupadeh gp Ruganathpua | Closed | 0 | 0 | 2023-08-16
| 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1729003076/LD/22012034597006 — Samtaliykaran nirman kary Shamshan mai gram Rupadi gp Ruganathpua | Ongoing | 713910.86 | 282625 | 2023-10-08
| 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1729003076/WC/22012035055381 — Amrat sarovar ( Navin Talab ) niraman karya ( kochang baba wali nali ) gp RUGANTHPURA | Closed | 1992638.57 | 0 | 2023-01-26
| 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1729003076/WC/22012035060019 — Nala vishatarikaran karya gram rupadheh mai gp Ruganathpura | Closed | 0 | 0 | 2023-04-14
| 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1729003076/WC/22012035066677 — Pokhar nirman karya ( Imarat lal ke khet ke pass gram Rupadeh ) gp Ruganathpura | Closed | 0 | 0 | 2023-04-14
| 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Grps / Construction of Sand filter for openwell recharge for Groups | Well Recharge | 1729003076/WC/22012035156000 — Nirmal neer kup nirman karya ( Shanti dham mai gram Rupdi ) gp Ruganathpura | Completed | 648891.55 | 459894.5 | 2024-02-09 | 2025-03-09
| 2023-2024 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1729003076/WC/22012035191563 — Samuday ke liye baad / daivarjan cheinal nirman ghatoee wala nala gram rupadeh gp ruganathpura | Closed | 0 | 0 | 2024-01-26
| 2023-2024 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1729003076/WC/22012035192628 — Samuday ke liye baad / diversion channel ka nirman ghatoee wala nala gram rupadeh gp ruganathpura | Completed | 489328.52 | 421473 | 2024-03-15 | 2024-08-27
| 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1729003076/WC/22012035201585 — Talab jinoudhar dharmsingh ke khet ke passgram rugnathpura | Deleted | 0 | 0 | 2024-04-14
| 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1729003076/WC/22012035201680 — Talab jinoudhar dharmsingh ke khet ke pass gram rugnathpura | Deleted | 0 | 0 | 2024-06-05
| 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1729003076/WC/22012035201682 — Talab jinoudhar dharmsingh ke khet ke pass gram rugnathpura | Ongoing | 469574.19 | 5832 | 2024-06-14
| 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1729003076/WC/22012035202788 — Samuday ke liyae baad / diversion channel ka nirman puliya se bhilt baba ki or gp Rugnathpura | Approved | 0 | 0 | 2024-06-05