## Work List
District / Block / Panchayat | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Start / completed date
RAISEN / SILWANI / RAMGARH | C--COMMON INFRASTRUCTURE FOR NRLM COMPLIANT SELF HELP GROUPS / Anganwadi/Other Rural Infrastructure | Constr of workshed for Livelihood activity (Grps) / Construction of workshed for Livelihood activity for Groups | Construction of building/workshed for SHG | 1730006072/AV/22012034633713 — Shantidham simriya kalan | Closed | 0 | 0 | 2023-04-14 -
RAISEN / SILWANI / RAMGARH | C--COMMON INFRASTRUCTURE FOR NRLM COMPLIANT SELF HELP GROUPS / Anganwadi/Other Rural Infrastructure | Constr of workshed for Livelihood activity (Grps) / Construction of workshed for Livelihood activity for Groups | Construction of building/workshed for SHG | 1730006072/AV/22012034633714 — Shantidham simriya kalan | Closed | 0 | 0 | 2023-04-14 -
RAISEN / SILWANI / RAMGARH | C--COMMON INFRASTRUCTURE FOR NRLM COMPLIANT SELF HELP GROUPS / Anganwadi/Other Rural Infrastructure | Constr of workshed for Livelihood activity (Grps) / Construction of workshed for Livelihood activity for Groups | Construction of building/workshed for SHG | 1730006072/AV/22012034633715 — Shantidham simriya kalan | Ongoing | 314000.05 | 110183.87 | 2023-06-12 -
RAISEN / SILWANI / RAMGARH | C--COMMON INFRASTRUCTURE FOR NRLM COMPLIANT SELF HELP GROUPS / Anganwadi/Other Rural Infrastructure | Constr of workshed for Livelihood activity (Grps) / Construction of workshed for Livelihood activity for Groups | Construction of building/workshed for SHG | 1730006072/AV/22012034634998 — Shantidham Nirmad | Closed | 0 | 0 | 2023-04-14 -
RAISEN / SILWANI / RAMGARH | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1730006072/AV/22012034634999 — School Bandri ball | Closed | 0 | 0 | 2023-04-14 -
RAISEN / SILWANI / RAMGARH | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1730006072/DP/22012034588670 — Amrit vatika gram panchyat ramgarh | Closed | 0 | 0 | 2023-04-14 -
RAISEN / SILWANI / RAMGARH | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1730006072/DP/22012034593433 — Amrit vatika gram Ramgarh gram panchyat ramgarh | Completed | 55847.4 | 36020 | 2023-08-14 - 2025-09-18
RAISEN / SILWANI / RAMGARH | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Shelter Belt Trees (Comm) / Boundary Line Plantation of Shelter Belt Trees for Community | Plantation | 1730006072/DP/22012034610584 — Gram Panchyat Ramgarh Ke Gram Salaiya Me Nali Ki Path Upchat Nirmad | Closed | 0 | 0 | 2023-08-16 -
RAISEN / SILWANI / RAMGARH | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Coastal Line Plantation-Horticulture-Community / Along the coast Line Plantation of Horticulture Trees for Community | Plantation | 1730006072/DP/22012034622266 — पौधरोपण कार्य आगनवाडी के पीछे | Approved | 0 | 0 | 2024-06-08 -
RAISEN / SILWANI / RAMGARH | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Coastal Line Plantation-Horticulture-Community / Along the coast Line Plantation of Horticulture Trees for Community | Plantation | 1730006072/DP/22012034622268 — पौधरोपण कार्य मंदिर किला | Approved | 0 | 0 | 2024-06-08 -
RAISEN / SILWANI / RAMGARH | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Const of Level Bench Terrace for Individual / Construction of Level Bench Terrace for Individual | Terracing | 1730006072/IF/22012035093465 — Kapildhara Cup Nirmad Balkishan | Physically Completed | 233820.75 | 102323 | 2023-10-04 - 2026-05-05
RAISEN / SILWANI / RAMGARH | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Const of Level Bench Terrace for Individual / Construction of Level Bench Terrace for Individual | Terracing | 1730006072/IF/22012035093471 — Kapildhara Cup Nirmad Vidhi Singh | Physically Completed | 233820.75 | 101660 | 2023-09-21 - 2026-05-05
RAISEN / SILWANI / RAMGARH | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Const of Level Bench Terrace for Individual / Construction of Level Bench Terrace for Individual | Terracing | 1730006072/IF/22012035093472 — Kapildhara Cup Nirmad Babu lal | Closed | 0 | 0 | 2023-04-14 -
RAISEN / SILWANI / RAMGARH | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Const of Level Bench Terrace for Individual / Construction of Level Bench Terrace for Individual | Terracing | 1730006072/IF/22012035093473 — Kapildhara Cup Nirmad Ajuddi Bai | Physically Completed | 223999.59 | 88842 | 2023-10-04 - 2026-05-05
RAISEN / SILWANI / RAMGARH | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Const of Level Bench Terrace for Individual / Construction of Level Bench Terrace for Individual | Terracing | 1730006072/IF/22012035094000 — Kapildhara Cup Nirmad Narayan Singh | Closed | 0 | 0 | 2023-04-14 -
RAISEN / SILWANI / RAMGARH | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Pebble graded Bund for Individuals / Construction of Pebble graded Bund for Individuals | Construction of Bund | 1730006072/IF/22012035106922 — Kapildhara Cup Nirmad munshi lal | Closed | 0 | 0 | 2023-04-14 -
RAISEN / SILWANI / RAMGARH | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1730006072/IF/22012035122736 — Gram panchyat ramgarh ke gram simriya kalan me dinesh ka med bandhan ka nirmad | Closed | 0 | 0 | 2023-04-14 -
RAISEN / SILWANI / RAMGARH | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1730006072/IF/22012035122740 — Gram panchyat ramgarh ke gram simriya kalan me Kalu ram ka med bandhan ka nirmad | Closed | 0 | 0 | 2023-04-14 -
RAISEN / SILWANI / RAMGARH | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen Check Dam for Individuals / Construction of Earthen Anicut Check Dam for Individuals | Construction of Check Dam/Stop Dam | 1730006072/IF/22012035122744 — Gram panchyat ramgarh ke gram simriya kalan me Bhagwan Singh ka med bandhan ka nirmad | Closed | 0 | 0 | 2023-04-14 -
RAISEN / SILWANI / RAMGARH | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Brushwood Check Dam for Individuals / Construction of Brushwood Check Dam for Individuals | Construction of Check Dam/Stop Dam | 1730006072/IF/22012035122749 — Gram panchyat ramgarh ke gram simriya kalan me halke veerka med bandhan ka nirmad | Closed | 0 | 0 | 2023-04-14 -
RAISEN / SILWANI / RAMGARH | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Berkeley Compost Pit for Individual / Construction of Berkeley Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1730006072/IF/22012035122751 — Gram panchyat ramgarh ke gram simriya kalan me kkhet singh ka med bandhan ka nirmad | Closed | 0 | 0 | 2023-04-14 -
RAISEN / SILWANI / RAMGARH | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Berkeley Compost Pit for Individual / Construction of Berkeley Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1730006072/IF/22012035122752 — Gram panchyat ramgarh ke gram simriya kalan me babulal ka med bandhan ka nirmad | Closed | 0 | 0 | 2023-04-14 -
RAISEN / SILWANI / RAMGARH | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Boulder Check Dam for Individuals / Construction of Boulder Check Dam for Individuals | Construction of Check Dam/Stop Dam | 1730006072/IF/22012035122756 — Gram panchyat ramgarh ke gram simriya kalan me munna lal ka med bandhan ka nirmad | Closed | 0 | 0 | 2023-04-14 -
RAISEN / SILWANI / RAMGARH | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Const of Level Bench Terrace for Individual / Construction of Level Bench Terrace for Individual | Terracing | 1730006072/IF/22012035122772 — Gram panchyat ramgarh ke gram salaiya kalan me haljeveer ka med bandhan ka nirmad | Closed | 0 | 0 | 2023-04-14 -
RAISEN / SILWANI / RAMGARH | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Const of Level Bench Terrace for Individual / Construction of Level Bench Terrace for Individual | Terracing | 1730006072/IF/22012035122774 — Kapildhara Cup Nirmad patiram gram ramgarh | Closed | 0 | 0 | 2023-04-14 -
RAISEN / SILWANI / RAMGARH | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Berkeley Compost Pit for Individual / Construction of Berkeley Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1730006072/IF/22012035122777 — Kapildhara Cup Nirmad laxmiprasad gram ramgarh | Closed | 0 | 0 | 2023-04-14 -
RAISEN / SILWANI / RAMGARH | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1730006072/IF/22012035151045 — gram ramgarh gram Panchyat Ramgarh Kapildhara Cup Nirmad Babulal | Closed | 0 | 0 | 2023-08-16 -
RAISEN / SILWANI / RAMGARH | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1730006072/IF/22012035151052 — gram ramgarh gram Panchyat Ramgarh Kapildhara Cup Nirmad Patiram | Closed | 0 | 0 | 2023-08-16 -
RAISEN / SILWANI / RAMGARH | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Bondry Block - Coastal Shelter Belt-Individuals / Boundary Block Plantation of Coastal Shelter Belt Trees for Individuals | Other Works | 1730006072/IF/22012035151065 — Gram Ramgarh Gram Panchyat RamgarhKhet Talab Nirmad Kary | Closed | 0 | 0 | 2023-08-16 -
RAISEN / SILWANI / RAMGARH | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Biodrainage in Fields-Individuals / Block Plantation of Biodrainage Trees in Fields for Individuals | Plantation | 1730006072/IF/22012035152526 — Gram panchyat ramgarh ke gram simriya kalan me Kallu / Antram ka med bandhan ka nirmad | Closed | 0 | 0 | 2023-08-16 -
RAISEN / SILWANI / RAMGARH | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Block Plantation of Farm Forestry Trees in Fields for Individuals | Plantation | 1730006072/IF/22012035152539 — Gram panchyat ramgarh ke gram simriya kalan me Khet Singh ka kapildhara kup nirmad | Closed | 0 | 0 | 2023-08-16 -
RAISEN / SILWANI / RAMGARH | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Forestry Trees-Fields-Individuals / Block Plantation of Forestry Trees in Fields for Individuals | Plantation | 1730006072/IF/22012035152543 — Gram panchyat ramgarh ke gram simriya kalan me BHagwan singhka med bandhan ka nirmad | Closed | 0 | 0 | 2023-08-16 -
RAISEN / SILWANI / RAMGARH | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Sericulture in fields-Individuals / Block Plantation of Sericulture Trees in fields for Individuals | Plantation | 1730006072/IF/22012035152553 — gram panchyat ramgarh gram simariya Nirpat singh Med vandhan Nirmad | Closed | 0 | 0 | 2023-08-16 -
RAISEN / SILWANI / RAMGARH | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Forestry Trees-Fields-Individuals / Block Plantation of Forestry Trees in Fields for Individuals | Plantation | 1730006072/IF/22012035152556 — Gram panchyat ramgarh ke gram simriya kalan me Abhay ram ka med bandhan ka nirmad | Closed | 0 | 0 | 2023-08-16 -
RAISEN / SILWANI / RAMGARH | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Biodrainage in Fields-Individuals / Block Plantation of Biodrainage Trees in Fields for Individuals | Plantation | 1730006072/IF/22012035152559 — Gram panchyat ramgarh ke gram simriya kalan me Halke / Chhotelal Kapildhara kup nirmad | Closed | 0 | 0 | 2023-08-16 -
RAISEN / SILWANI / RAMGARH | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Sericulture in fields-Individuals / Block Plantation of Sericulture Trees in fields for Individuals | Plantation | 1730006072/IF/22012035152563 — Gram panchyat ramgarh ke gram simriya kalan me Babulal / veera ka med bandhan ka nirmad | Closed | 0 | 0 | 2023-08-16 -
RAISEN / SILWANI / RAMGARH | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Block Plantation of Farm Forestry Trees in Fields for Individuals | Plantation | 1730006072/IF/22012035152564 — Gram panchyat ramgarh ke gram simriya kalan me Jagdish ka med bandhan ka nirmad | Closed | 0 | 0 | 2023-08-16 -
RAISEN / SILWANI / RAMGARH | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Forestry Trees-Fields-Individuals / Block Plantation of Forestry Trees in Fields for Individuals | Plantation | 1730006072/IF/22012035152565 — Gram panchyat ramgarh ke gram simriya kalan me Ramsingh kapildhara kup nirmad | Closed | 0 | 0 | 2023-08-16 -
RAISEN / SILWANI / RAMGARH | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Block Plantation of Farm Forestry Trees in Fields for Individuals | Plantation | 1730006072/IF/22012035152567 — Gram panchyat ramgarh ke gram salaiya kalan me halkeveer kapildhara kup nirmad | Closed | 0 | 0 | 2023-08-16 -
RAISEN / SILWANI / RAMGARH | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Block Plantation of Farm Forestry Trees in Fields for Individuals | Plantation | 1730006072/IF/22012035152569 — Gram panchyat ramgarh ke gram simriya kalan me Hakam Singh ka med bandhan ka nirmad | Closed | 0 | 0 | 2023-08-16 -
RAISEN / SILWANI / RAMGARH | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Block Plantation of Farm Forestry Trees in Fields for Individuals | Plantation | 1730006072/IF/22012035152571 — Gram panchyat ramgarh ke gram Ramgarh Laxmiprasad kapildhara kup nirmad nirmad | Closed | 0 | 0 | 2023-08-16 -
RAISEN / SILWANI / RAMGARH | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Block Plantation of Farm Forestry Trees in Fields for Individuals | Plantation | 1730006072/IF/22012035152572 — Gram panchyat ramgarh ke gram salaiya me BHura ka med bandhan ka nirmad | Closed | 0 | 0 | 2023-08-16 -
RAISEN / SILWANI / RAMGARH | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1730006072/IF/22012035183265 — Khet Talab Prem bai / Narayan Gram Ramgarh Gp Ramgarh | Completed | 357999.63 | 298677 | 2023-12-28 - 2024-10-28
RAISEN / SILWANI / RAMGARH | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1730006072/IF/22012035224607 — Khet Talab Ram singh / Sabbalal Gram Simariya kala Gp Ramgarh | Completed | 300000.32 | 164846 | 2024-03-16 - 2025-06-28
RAISEN / SILWANI / RAMGARH | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1730006072/IF/22012035243355 — खेत तालाब निर्माण कार्य साहबसिंह / अंतराम ग्राम रामगढ | Deleted | 0 | 0 | 2024-06-08 -
RAISEN / SILWANI / RAMGARH | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1730006072/IF/22012035243359 — कपिलधारा कूप निर्माण कार्य बाबूलाल / हल्‍कैया | Deleted | 0 | 0 | 2024-06-08 -
RAISEN / SILWANI / RAMGARH | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1730006072/IF/22012035244222 — पौधारोपण कार्य रणधीर / अंतराम ग्राम रामगढ | Completed | 145050.83 | 43740 | 2024-08-31 - 2025-09-18
RAISEN / SILWANI / RAMGARH | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1730006072/IF/22012035258154 — ग्राम पंचयत रामगढ कपिलधारा कूप निर्माण बाबूलाल /हल्कैया | New | 0 | 0 | 2024-08-16 -
RAISEN / SILWANI / RAMGARH | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1730006072/IF/22012035258159 — ग्राम पंचयत रामगढ कपिलधारा कूप निर्माण विनोद रामलाल सलैया | New | 0 | 0 | 2024-08-16 -
RAISEN / SILWANI / RAMGARH | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1730006072/IF/22012035258163 — ग्राम पंचयात रामगढ कपिलधारा कूप निर्माण हलके सिंह / बलिराम | New | 0 | 0 | 2024-08-16 -
RAISEN / SILWANI / RAMGARH | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1730006072/IF/22012035278506 — Khet talab nirman karya Sevanti bai/Radhelal | Deleted | 0 | 0 | 2024-04-01 -
RAISEN / SILWANI / RAMGARH | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1730006072/IF/22012035278538 — Khet talab nirman karya Sevanti bai / Radhe lal | Completed | 389995.93 | 266830.92 | 2025-01-01 - 2025-06-28
RAISEN / SILWANI / RAMGARH | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1730006072/IF/22012035278936 — Khet talab nirman karya Shivcharan/tantoolal | Completed | 389995.93 | 296478 | 2024-12-25 - 2025-06-28
RAISEN / SILWANI / RAMGARH | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1730006072/IF/22012035337426 — JGSA 2025 Khet Talab Nirman Karya Raghuveer /bhujjilal Simariya Kalan | Physically Completed | 185441.45 | 173405.28 | 2025-04-25 - 2026-04-15
RAISEN / SILWANI / RAMGARH | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1730006072/IF/22012035417372 — JGSA 2025 Dugwel Rechage Structure Kapil Dhara Koop Chotelal/Bhagirath Ramgarh | Completed | 25899.46 | 25547.22 | 2025-05-03 - 2026-02-17
RAISEN / SILWANI / RAMGARH | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1730006072/IF/22012035417442 — JGSA 2025 Dugwel Rechage Structure Kapil Dhara Koop Abadhnarayan/Hariram | Completed | 25899.46 | 25572 | 2025-05-03 - 2026-02-17
RAISEN / SILWANI / RAMGARH | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1730006072/IF/22012035417487 — JGSA 2025 Dugwel Rechage Structure Kapil Dhara Koop Kera Bai /Barelal Ramgarh | Completed | 25899.46 | 25572 | 2025-05-03 - 2026-02-17
RAISEN / SILWANI / RAMGARH | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1730006072/IF/22012035417571 — JGSA 2025 Dugwel Rechage Structure Kapil Dhara Koop Bhuganti Bai /Gokal Ramgarh | Completed | 25899.46 | 25448.1 | 2025-05-03 - 2026-03-13
RAISEN / SILWANI / RAMGARH | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1730006072/IF/22012035417598 — JGSA 2025 Dugwel Rechage Structure Kapil Dhara Koop Babulal/Gangaram ramgarh | Completed | 25899.46 | 25572 | 2025-05-03 - 2026-02-17
RAISEN / SILWANI / RAMGARH | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1730006072/IF/22012035417646 — JGSA 2025 Dugwel Rechage Structure Kapil Dhara Koop Sankarlal/Gangaram Ramgarh | Completed | 25899.46 | 25572 | 2025-05-03 - 2026-02-17
RAISEN / SILWANI / RAMGARH | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1730006072/IF/22012035417682 — JGSA 2025 Dugwel Rechage Structure Kapil Dhara Koop Phool Singh/Bhagirath Ramgarh | Completed | 25899.46 | 25572 | 2025-05-03 - 2026-02-17
RAISEN / SILWANI / RAMGARH | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1730006072/IF/22012035418121 — JGSA 2025 Dugwel Rechage Structure Kapil Dhara Koop Jagdish/Vishram Ramgarh | Completed | 25899.46 | 25572 | 2025-05-03 - 2026-03-13
RAISEN / SILWANI / RAMGARH | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1730006072/IF/22012035418170 — JGSA 2025 Dugwel Rechage Structure Kapil Dhara Koop Laxmi Bai/Jugraj Ramgarh | Completed | 25899.46 | 25572 | 2025-05-03 - 2026-03-13
RAISEN / SILWANI / RAMGARH | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1730006072/IF/22012035418229 — JGSA 2025 Dugwel Rechage Structure Kapil Dhara Koop Bhaiyalal/Jugraj | Deleted | 0 | 0 | 2025-04-26 -
RAISEN / SILWANI / RAMGARH | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1730006072/IF/22012035418261 — JGSA 2025 Dugwel Rechage Structure Kapil Dhara Koop Bhaiyalal/Shivlal Ramgarh | Completed | 25899.46 | 25572 | 2025-05-03 - 2026-03-13
RAISEN / SILWANI / RAMGARH | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1730006072/IF/22012035487439 — JGSA 2025 Khet Talab Nirman Karya Randheer Singh/Antram Ramgarh | Completed | 185441.45 | 173405.4 | 2025-05-10 - 2026-03-31
RAISEN / SILWANI / RAMGARH | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1730006072/IF/22012035487454 — JGSA 2025 Khet Talab Nirman Karya Malti Bai/Tantu Singh | Completed | 185441.45 | 173144.4 | 2025-05-10 - 2026-03-31
RAISEN / SILWANI / RAMGARH | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1730006072/IF/22012035518732 — JGSA 2025 खेत तालाब निर्माण कार्य उमेद / हरिशंकर | Physically Completed | 289847.6 | 277514.16 | 2025-05-20 - 2026-04-15
RAISEN / SILWANI / RAMGARH | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1730006072/IF/22012035566014 — Dugwell Recharge Structure kapil dhara koop rajesh/ mohan singh salaiya | Deleted | 0 | 0 | 2025-04-01 -
RAISEN / SILWANI / RAMGARH | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1730006072/IF/22012035566017 — Dugwell Recharge Structure kapil dhara koop khuman singh/ phool singh salaiya | Deleted | 0 | 0 | 2025-04-01 -
RAISEN / SILWANI / RAMGARH | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1730006072/IF/22012035566304 — JGSA 2025 dugwell recharge structure Kapil dhara koop Rajesh /mohan salaiya | Completed | 25899.46 | 15660 | 2025-06-11 - 2026-05-05
RAISEN / SILWANI / RAMGARH | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1730006072/IF/22012035566308 — JGSA 2025 dugwell recharge structure Kapil dhara koop Khuman singh /phool singh salaiya | Completed | 25899.46 | 15660 | 2025-06-11 - 2026-05-05
RAISEN / SILWANI / RAMGARH | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1730006072/IF/22012035569167 — JGSA 2025 dugwell recharge structure Kapil dhara koop Bhoora/Mangal salaiya | Approved | 0 | 0 | 2025-06-11 -
RAISEN / SILWANI / RAMGARH | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1730006072/IF/22012035569171 — JGSA 2025 dugwell recharge structure Kapil dhara koop Mishree/Mangal salaiya | Approved | 0 | 0 | 2025-04-01 -
RAISEN / SILWANI / RAMGARH | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1730006072/IF/22012035579707 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO.MP105539918 | Completed | 25000 | 23490 | 2025-09-09 - 2026-05-21
RAISEN / SILWANI / RAMGARH | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1730006072/IF/22012035579709 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO.MP105538530 | Completed | 25000 | 23490 | 2025-08-29 - 2026-05-21
RAISEN / SILWANI / RAMGARH | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1730006072/IF/22012035579711 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO.MP105539076 | Completed | 25000 | 21924 | 2025-09-09 - 2026-06-01
RAISEN / SILWANI / RAMGARH | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1730006072/IF/22012035579712 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO.MP113615201 | Completed | 25000 | 12528 | 2025-09-09 - 2026-06-03
RAISEN / SILWANI / RAMGARH | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1730006072/IF/22012035579713 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO.MP105539826 | Completed | 25000 | 8874 | 2025-09-09 - 2026-06-03
RAISEN / SILWANI / RAMGARH | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1730006072/IF/22012035579714 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO.MP105538337 | Completed | 25000 | 9135 | 2025-09-09 - 2026-06-03
RAISEN / SILWANI / RAMGARH | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1730006072/IF/22012035579715 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO.MP114102778 | Completed | 25000 | 23490 | 2025-08-26 - 2026-05-21
RAISEN / SILWANI / RAMGARH | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1730006072/IF/22012035579716 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO.MP113615232 | Completed | 25000 | 12528 | 2025-09-09 - 2026-06-03
RAISEN / SILWANI / RAMGARH | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1730006072/IF/22012035587373 — एक वगिया मॉ के नाम रूपवतीबाई / रणधीर ग्राम रामगढ | New | 0 | 0 | 2025-08-01 -
RAISEN / SILWANI / RAMGARH | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1730006072/IF/22012035608907 — Ek Bagiya Maa Ke Naam 2025 ROOPWATI BAI/RANDHEER 004/383 A | New | 0 | 0 | 2025-08-01 -
RAISEN / SILWANI / RAMGARH | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1730006072/IF/22012035609937 — Ek Bagiya Maa ke Naam 2025 ROOPVATI BAI/ RANDHEER SINGH 3/316 | Ongoing | 127247.55 | 68051 | 2025-09-05 -
RAISEN / SILWANI / RAMGARH | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1730006072/IF/22012035636732 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO.MP105539568 | Physically Completed | 25000 | 8456.4 | 2025-11-28 - 2026-06-22
RAISEN / SILWANI / RAMGARH | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730006072/IF/IAY/4389155 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118546917 | Completed | 18360 | 17103 | 2023-04-17 - 2024-10-28
RAISEN / SILWANI / RAMGARH | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730006072/IF/IAY/4686190 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105537390 | Completed | 23490 | 21717 | 2024-12-14 - 2025-07-18
RAISEN / SILWANI / RAMGARH | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730006072/IF/IAY/4711009 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125529841 | Completed | 23490 | 21357 | 2024-12-14 - 2025-07-18
RAISEN / SILWANI / RAMGARH | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730006072/IF/IAY/5826080 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113615201 | Approved | 23490 | 0 | 2025-02-07 -
RAISEN / SILWANI / RAMGARH | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730006072/IF/IAY/5827135 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105538337 | Approved | 23490 | 0 | 2025-02-07 -
RAISEN / SILWANI / RAMGARH | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730006072/IF/IAY/5827136 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105538530 | Approved | 23490 | 0 | 2025-02-07 -
RAISEN / SILWANI / RAMGARH | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730006072/IF/IAY/5827138 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105539826 | Approved | 23490 | 0 | 2025-02-07 -
RAISEN / SILWANI / RAMGARH | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730006072/IF/IAY/5827592 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105538918 | Physically Completed | 23490 | 0 | 2025-02-07 - 2026-06-07
RAISEN / SILWANI / RAMGARH | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730006072/IF/IAY/5827593 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105539076 | Approved | 23490 | 0 | 2025-02-07 -
RAISEN / SILWANI / RAMGARH | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1730006072/RC/22012034636849 — CC Road | Closed | 0 | 0 | 2023-04-14 -
RAISEN / SILWANI / RAMGARH | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1730006072/RC/22012034673046 — ग्राम पंचयात रामगढ़ के ग्राम रामगढ में सी. सी. रोड निर्माण कार्य | Closed | 0 | 0 | 2023-08-16 -
RAISEN / SILWANI / RAMGARH | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1730006072/RC/22012034677313 — cc road sah nali nirman karya kailash ke ghar se kanchedi ke ghar ki or | Completed | 61000 | 58786 | 2024-02-29 - 2024-11-07
RAISEN / SILWANI / RAMGARH | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1730006072/RC/22012034846604 — सीसी रोड सह नाली निर्माण कार्य आगनवाडी से कुआ की ओर | Approved | 58000 | 0 | 2025-04-01 -
RAISEN / SILWANI / RAMGARH | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1730006072/RC/22012034847281 — सीसी रोड सह नाली निर्माण कार्य रूपसिंह के घर से शास कूप की ओर | Approved | 58000 | 0 | 2025-04-01 -
RAISEN / SILWANI / RAMGARH | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1730006072/RC/22012034847282 — सीसी रोड सह नाली निर्माण कार्य कमलेश के घर से रमेश के घर की ओर | Approved | 58000 | 0 | 2025-04-01 -
RAISEN / SILWANI / RAMGARH | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1730006072/RC/22012034847284 — सीसी रोड सह नाली निर्माण कार्य ब्रजेश के घर से भूरा के घर की ओर | Approved | 45000 | 0 | 2025-04-01 -
RAISEN / SILWANI / RAMGARH | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Community / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1730006072/RS/22012034693866 — Nadep nirman school ke pass gram ramgarh gram panchayat ramgarm | Completed | 64000.32 | 51730 | 2023-09-05 - 2024-01-16
RAISEN / SILWANI / RAMGARH | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Community / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1730006072/RS/22012034693996 — Nadep Nirman Roopsingh ke ghar ke pass Gram Ramgarh Gram Panchyat Ramgarh | Completed | 57000.49 | 51932.11 | 2023-07-26 - 2024-01-16
RAISEN / SILWANI / RAMGARH | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Community / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1730006072/RS/22012034693997 — Nadep Nirman Balkishan ke ghar ke pass Gram Ramgarh Gram Panchyat Ramgarh | Completed | 64000.32 | 49741 | 2023-08-28 - 2024-10-23
RAISEN / SILWANI / RAMGARH | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Community / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1730006072/RS/22012034694000 — Nadep Nirman Bhura ke ghar ke pass Gram Salaiya Gram Panchyat Ramgarh | Closed | 64000.32 | 0 | 2023-04-14 -
RAISEN / SILWANI / RAMGARH | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Community / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1730006072/RS/22012034694001 — Nadep Nirman Brajesh ke ghar ke pass Gram Salaiya Gram Panchyat Ramgarh | Ongoing | 64000.32 | 8619 | 2023-10-26 -
RAISEN / SILWANI / RAMGARH | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Community / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1730006072/RS/22012034694002 — Nadep Nirman kasham ke ghar ke pass Gram Salaiya Gram Panchyat Ramgarh | Ongoing | 64000.32 | 6630 | 2024-03-16 -
RAISEN / SILWANI / RAMGARH | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Community / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1730006072/RS/22012034694004 — Nadep Nirman Sardar ke ghar ke pass Gram Simariya Gram Panchyat Ramgarh | Completed | 64000.32 | 49740.1 | 2023-10-26 - 2025-08-29
RAISEN / SILWANI / RAMGARH | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Community / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1730006072/RS/22012034694005 — Nadep Nirman mandir ke ghar ke pass Gram Simariya Gram Panchyat Ramgarh | Closed | 64000.32 | 0 | 2023-04-14 -
RAISEN / SILWANI / RAMGARH | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Community / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1730006072/RS/22012034694006 — Nadep Nirman mandir ke ghar ke pass Gram Simariya Gram Panchyat Ramgarh | Completed | 64000.32 | 49740.1 | 2023-10-26 - 2024-10-28
RAISEN / SILWANI / RAMGARH | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Community / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1730006072/RS/22012034694010 — Nadep Nirman Govind ke ghar ke pass Gram Simariya Gram Panchyat Ramgarh | Completed | 64000.32 | 49740.1 | 2023-10-16 - 2024-10-28
RAISEN / SILWANI / RAMGARH | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Groups / Construction of Compost Pit for Groups | Construction of NADEP/Vermi Compost Pit | 1730006072/RS/22012035113254 — Gram panchyat ramgarh ke gram salaiya Me Nadep Nirmad Brajesh Ke Ghar Ke Pass | Closed | 0 | 0 | 2023-08-16 -
RAISEN / SILWANI / RAMGARH | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Community / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1730006072/RS/22012035113257 — Gram panchyat ramgarh ke gram Salaiya me Nadev nirmad Kasham Ke Ghar ke pass | Closed | 0 | 0 | 2023-08-16 -
RAISEN / SILWANI / RAMGARH | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1730006072/RS/22012035132239 — नाली निर्माण कार्य धर्मदास के घर से नदी तक | Completed | 100000 | 97431.35 | 2024-10-23 - 2025-01-31
RAISEN / SILWANI / RAMGARH | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Road Line Plantation of Forestry Trees for Comm / Road side line plantation of Forestry Trees for Community | Plantation | 1730006072/WC/22012035067534 — Nali Nirmad | Closed | 0 | 0 | 2023-04-14 -