## Work List
Exported on: 2026-08-24 19:22:07
Filters applied:
Data source: MGNREGA
District: JABALPUR
Block: PATAN
Panchayat: UJRAUD
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
| 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of WBM Roads for Community / Construction of WBM Roads for Community | Construction of Road and Culvert | 1733003023/RC/22012034390345 — TIKARAM KE GHAR SE CHUNNU PATEL KE GHAR TAK SAKRA | Closed | 267500 | 0 | 2016-10-02
| 2019-2020 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1733003067/AV/22012034400090 — CC Road & Naali Nirman 14th vitt 2019-20 | Closed | 0 | 0 | 2019-04-01
| 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1733003067/AV/22012034448539 — सी सी रोड १४ वित्त आतंरिकमार्गशांति धाम से मैंन रोड तक१8-19 | Physically Completed | 23000 | 22350 | 2019-03-08 | 2020-08-08
| 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1733003067/AV/22012034448541 — सी सी रोड १४ वित्त आतंरिकमार्ग मंदिर के सामने से कोमल के घर तक १8-19 | Physically Completed | 64000 | 17246 | 2019-03-08 | 2020-08-08
| 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1733003067/AV/22012034448543 — सी सी रोड १४ वित्त आतंरिकमार्ग मा शा से मंदिर तक १8-19 | Physically Completed | 21500 | 19182 | 2019-03-08 | 2021-07-17
| 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1733003067/AV/22012034448546 — सी सी रोड १४ वित्त आतंरिकमार्ग सोनेलाल के घ से अवस्थी जी के के घर तक १8-19 | Completed | 7000 | 4926 | 2019-03-08 | 2020-06-22
| 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1733003067/AV/22012034448548 — सी सी रोड १४ वित्त आतंरिकमार्ग बिजली के खम्भे से कोमल रजक के घर के घर तक १8-19 | Physically Completed | 11400 | 7566 | 2019-03-08 | 2020-08-08
| 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1733003067/AV/22012034448549 — शांति धाम जीर्णोद्धार एंड शेड निर्माण कार्य ग्राम उजरोंड | Physically Completed | 160000 | 174 | 2019-03-08 | 2021-12-22
| 2020-2021 | C--COMMON INFRASTRUCTURE FOR NRLM COMPLIANT SELF HELP GROUPS / Anganwadi/Other Rural Infrastructure | Constr of agri produce storage building for groups / Construction of Agricultural produce storage Building for Groups | Constr of Food Grain storage | 1733003067/AV/22012034537032 — SHANTI DHAM UJROUND ME BUINNDRIWAL NIRMAN KARYA | Deleted | 94000 | 0 | 2020-04-14
| 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1733003067/AV/22012034537262 — Santidham shamshan ghat ujrond me baundrybal nirmand | Completed | 94800 | 95570 | 2020-09-21 | 2022-02-26
| 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Repr MainT of Cmpnd wall for govt schools / Repair and Maintenance of Compound wall for government run schools for Community | Repair & Maint of Community infrastructure | 1733003067/AV/22012034587027 — Constrution of dining hall at govt. m.s. school Ujrond | Closed | 0 | 0 | 2021-04-01
| 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Repr MainT of Cmpnd wall for govt schools / Repair and Maintenance of Compound wall for government run schools for Community | Repair & Maint of Community infrastructure | 1733003067/AV/22012034587028 — Constrution of dining hall at govt. m.s. school Ujrond | Completed | 18971.24 | 18755 | 2022-02-05 | 2022-12-17
| 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Repr MainT of Cmpnd wall for govt schools / Repair and Maintenance of Compound wall for government run schools for Community | Repair & Maint of Community infrastructure | 1733003067/AV/22012034587030 — Constrution of dining hall at govt. p.s. school bhotiya | Completed | 18971.24 | 15689 | 2022-03-20 | 2022-12-17
| 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Kitchen Shed / Construction of Kitchen shed Building for Community | Constr of Kitchen Shed | 1733003067/AV/22012034591552 — PRATHMIK MADHYMIK SHAALA MAA KI BAGIYA NIRMAN KARYA UJRAUD | Closed | 0 | 0 | 2021-07-14
| 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Kitchen Shed / Construction of Kitchen shed Building for Community | Constr of Kitchen Shed | 1733003067/AV/22012034591553 — MADHYMIK SHAALA MAA KI BAGIYA NIRMAN KARYA BHOTIYA UJRAUD | Closed | 0 | 0 | 2021-07-14
| 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1733003067/AV/22012034617472 — Baundrywall Nirmand Karya Pratahmik Shala Bhontiya | Completed | 143000 | 141642 | 2022-04-11 | 2023-06-09
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Anganwadi/Other Rural Infrastructure | Constr of Poultry Shelter for Community / Construction of Poultry Shelter for Community | Poultry Shelter | 1733003067/AV/22012034622296 — shanthidham unnayan avm shed nirman kary | Closed | 0 | 0 | 2022-04-15
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Anganwadi/Other Rural Infrastructure | Constr of Poultry Shelter for Community / Construction of Poultry Shelter for Community | Poultry Shelter | 1733003067/AV/22012034622297 — shanthidham unnayan avm shed nirman kary | Closed | 0 | 0 | 2022-04-15
| 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1733003067/AV/22012034648014 — MS Atirikt Kacha Me Water Prufing Darwaza Riporting Khdki Palle Flooring Penting Putai Ujrond | Completed | 10000 | 9940 | 2023-10-06 | 2025-02-27
| 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Repair and maintenance of GP building / Repair and Maintenance of Gram Panchayat/Panchayat Bhavan Building for Community | Repair & Maint of Community infrastructure | 1733003067/AV/22012034648245 — P S Shala Ujrond Me khidki Palle Floring Putai | Completed | 9000 | 6900 | 2023-10-06 | 2025-02-27
| 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Repair and maintenance of GP building / Repair and Maintenance of Gram Panchayat/Panchayat Bhavan Building for Community | Repair & Maint of Community infrastructure | 1733003067/AV/22012034648246 — Kichin Shed Me water Prufing Floring Khidki Plaster Putai Penting | Completed | 7000 | 5116 | 2023-10-06 | 2025-02-27
| 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Repair and maintenance of GP building / Repair and Maintenance of Gram Panchayat/Panchayat Bhavan Building for Community | Repair & Maint of Community infrastructure | 1733003067/AV/22012034648247 — M Shala Ujrond Me Khdki Palle Floring Putai Karya | Completed | 10000 | 4360 | 2023-10-06 | 2025-02-27
| 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Repair and maintenance of GP building / Repair and Maintenance of Gram Panchayat/Panchayat Bhavan Building for Community | Repair & Maint of Community infrastructure | 1733003067/AV/22012034649800 — M S School Me khidki Palle Floring Putai | Completed | 10000 | 9980 | 2023-10-19 | 2025-02-27
| 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1733003067/AV/22012034653893 — Shanthidham Unnayan avm shed nirman kary Ujroand | Closed | 217193.48 | 0 | 2024-01-26
| 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1733003067/AV/22012034654043 — Shanthidham Unnayan avm shed nirman kary Jugtaraiya | Closed | 227083.88 | 0 | 2024-01-26
| 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1733003067/AV/22012034654044 — Shanthidham Unnayan avm shed nirman kary Bhotiya | Closed | 245246.06 | 0 | 2024-01-26
| 2025-2026 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1733003067/AV/22012034667880 — Pever Blok Nirmand karya Neelesh Patel Ke ghar Se Imrat Ki or | Ongoing | 50000 | 31304.4 | 2025-12-23
| 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1733003067/DP/22012034408215 — Shantidham ujrond me Plantation 2018.19 | Completed | 342540 | 185804 | 2018-07-14 | 2024-08-16
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1733003067/DP/22012034545221 — Mai ki bagiya nirmaan karya Govt. M. S. Ujround | Completed | 16467.56 | 4026 | 2022-02-05 | 2023-05-09
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation of Forestry-Community / Boundary Line Plantation of Forestry Trees for Community | Plantation | 1733003067/DP/22012034548555 — Mai ki bagiya nirmaan karya Govt. M.S SCHOOL UJROAND | Completed | 16467.56 | 4614 | 2022-02-27 | 2023-05-09
| 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Horticulture -Community / Boundary Line Plantation of Horticulture Trees for Community | Plantation | 1733003067/DP/22012034563162 — Podharopan karya Talab kinare bhotiya | Physically Completed | 408007.29 | 134708.57 | 2022-09-09 | 2026-06-18
| 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1733003067/DP/22012034581341 — Podharopan kary p.s parisar ke baju m | Closed | 0 | 0 | 2023-04-14
| 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation of Forestry-Community / Boundary Line Plantation of Forestry Trees for Community | Plantation | 1733003067/DP/22012034581395 — Podharopan kary P.S. parisar ke baju m bhotiya | Ongoing | 435815.48 | 97152.38 | 2023-08-19
| 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation of Forestry-Community / Boundary Line Plantation of Forestry Trees for Community | Plantation | 1733003067/DP/22012034590908 — Amrat Vatika Talab kinare AvmP.S. school ke sameep Bhotiya | Completed | 55847.4 | 27404.07 | 2023-09-16 | 2026-05-15
| 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Flood Control and Protection | Cross Bund / Construction of Earthen graded Bund for Community | Works for Flood Control and Protection | 1733003067/FP/235 — भौतिया नाला विस्‍तारीकरण कार्य | Completed | 475246 | 84597 | 2012-06-07 | 2014-07-30
| 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Micro Irrigation Works | Renovation of sub-minor Canal for Community / Renovation of sub-minor Canal for Community | Renovation of Canal | 1733003067/IC/22012034387777 — Jungle clearance slipped earth removal of Kantora sub minor RD0.1 to 1.2 | Closed | 0 | 0 | 2020-09-17
| 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1733003067/IF/22012034345581 — सार्वजनिक शांति धाम में वृक्षा रोपण कार्य | Completed | 335000 | 119532 | 2017-06-10 | 2021-09-16
| 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1733003067/IF/22012034346325 — Sarv janik Parisar me - Veraksha ropand karya santi dham Bhontiya | Completed | 335000 | 226192 | 2017-06-08 | 2021-09-15
| 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1733003067/IF/22012034346345 — sarvjanik Veraksha ropand karya saskiya Parisar school ke baju me | Completed | 335000 | 183272 | 2017-06-08 | 2021-09-15
| 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1733003067/IF/22012034350950 — सार्वजानिक वृक्षारोपण कार्य खेल मैदान परिसर में ग्राम भौतिया | Completed | 335000 | 174890 | 2017-06-17 | 2021-09-20
| 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1733003067/IF/22012034350954 — वृक्षारोपण कार्य शांति धाम परिसर में ग्राम उजरोंड | Deleted | 335000 | 0 | 2017-06-16
| 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1733003067/IF/22012034350956 — सार्वजनिक वृक्षा रोपण कार्य खेल मैदान परिसर में ग्राम जुगतरिया | Completed | 335000 | 25600 | 2017-06-17 | 2026-02-24
| 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of stone peripheral bund for indiv / Construction of Stone peripheral/farm/field Bund for Individuals | Construction of Bund | 1733003067/IF/22012034470203 — मेड बधान कार्य लाडली बाई पति नेतराम के खेत पर | Completed | 36000 | 26574 | 2019-03-06 | 2020-10-29
| 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of stone peripheral bund for indiv / Construction of Stone peripheral/farm/field Bund for Individuals | Construction of Bund | 1733003067/IF/22012034470236 — मेड बधान कार्य लेखराम पिता रामदास के खेत पर | Completed | 34000 | 174 | 2019-03-06 | 2020-10-29
| 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of pebble peripheral bund for indiv / Construction of Pebble peripheral/farm/field Bund for Individuals | Construction of Bund | 1733003067/IF/22012034470240 — मेड बधान कार्य जय राम पिता रामदास सिंह के खेत पर | Completed | 26000 | 9570 | 2019-03-06 | 2020-10-29
| 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of pebble peripheral bund for indiv / Construction of Pebble peripheral/farm/field Bund for Individuals | Construction of Bund | 1733003067/IF/22012034470243 — मेड बधान कार्य यशवंत पिता नारायण के खेत पर | Completed | 36000 | 174 | 2019-03-06 | 2020-10-29
| 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of pebble peripheral bund for indiv / Construction of Pebble peripheral/farm/field Bund for Individuals | Construction of Bund | 1733003067/IF/22012034471100 — मेड बधान कार्य फलीराम पिता देव सिंह के खेत पर | Completed | 36000 | 23994 | 2019-03-06 | 2020-10-29
| 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of pebble peripheral bund for indiv / Construction of Pebble peripheral/farm/field Bund for Individuals | Construction of Bund | 1733003067/IF/22012034471103 — मेड बधान कार्य जगदीश पिता रामदास के खेत पर | Completed | 29000 | 11790 | 2019-03-06 | 2020-10-29
| 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of pebble peripheral bund for indiv / Construction of Pebble peripheral/farm/field Bund for Individuals | Construction of Bund | 1733003067/IF/22012034471106 — मेड बधान कार्य सुरेन्द्र पिता दमड़ी के खेत पर | Completed | 36000 | 19174 | 2019-03-06 | 2020-10-29
| 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1733003067/IF/22012034473711 — मेड बधान कार्य बसोरी लाल के खेत पर | Completed | 35000 | 7566 | 2019-03-10 | 2020-10-29
| 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1733003067/IF/22012034534659 — med badhan karya beniprasad /prem lal laghu kishan | Deleted | 0 | 0 | 2020-01-26
| 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1733003067/IF/22012034534660 — med badhan karya shankar lal/sunder lal laghu kishan | Deleted | 0 | 0 | 2020-01-26
| 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of pebble peripheral bund for indiv / Construction of Pebble peripheral/farm/field Bund for Individuals | Construction of Bund | 1733003067/IF/22012034534661 — med badhan karya keshar bai/ rajkumar laghu kishan | Deleted | 0 | 0 | 2020-01-26
| 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1733003067/IF/22012034534662 — med badhan karya khajanchi / prem lal laghu kishan | Deleted | 0 | 0 | 2020-01-26
| 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1733003067/IF/22012034534663 — med badhan karya banshi lal /prem lal laghu kishan | Deleted | 0 | 0 | 2020-01-26
| 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of pebble peripheral bund for indiv / Construction of Pebble peripheral/farm/field Bund for Individuals | Construction of Bund | 1733003067/IF/22012034551269 — med badhan karya shankar lal/sundar lal laghu kishan | Completed | 23592.16 | 15960 | 2020-06-12 | 2020-10-29
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of pebble peripheral bund for indiv / Construction of Pebble peripheral/farm/field Bund for Individuals | Construction of Bund | 1733003067/IF/22012034551271 — med badhan karya banshi lal/premlal laghu kishan | Completed | 27182.31 | 26508 | 2021-05-04 | 2021-06-17
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of pebble peripheral bund for indiv / Construction of Pebble peripheral/farm/field Bund for Individuals | Construction of Bund | 1733003067/IF/22012034551272 — med badhan karya khanjanchi / prem lallal laghu kishan | Completed | 27182.31 | 17016 | 2021-06-03 | 2021-06-19
| 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of pebble peripheral bund for indiv / Construction of Pebble peripheral/farm/field Bund for Individuals | Construction of Bund | 1733003067/IF/22012034551273 — med badhan karya beni prasad /premlal lal laghu kishan | Completed | 28720.89 | 2280 | 2020-06-30 | 2021-07-25
| 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of pebble peripheral bund for indiv / Construction of Pebble peripheral/farm/field Bund for Individuals | Construction of Bund | 1733003067/IF/22012034551275 — med badhan karya keshar bai/rajkumar lal laghu kishan | Completed | 22566.41 | 9500 | 2020-05-20 | 2020-10-29
| 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of pebble peripheral bund for indiv / Construction of Pebble peripheral/farm/field Bund for Individuals | Construction of Bund | 1733003067/IF/22012034557173 — med badhan karyabrajendra /rajaram laghu kishan | Completed | 30259.55 | 7220 | 2020-05-20 | 2020-10-29
| 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of pebble peripheral bund for indiv / Construction of Pebble peripheral/farm/field Bund for Individuals | Construction of Bund | 1733003067/IF/22012034557174 — med badhan karya vinid kumar/chokhelal laghu kishan | Completed | 49748.64 | 19380 | 2020-05-27 | 2020-10-29
| 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of pebble peripheral bund for indiv / Construction of Pebble peripheral/farm/field Bund for Individuals | Construction of Bund | 1733003067/IF/22012034557175 — med badhan karya jageswar/rajaram laghu kishan | Completed | 30259.55 | 14630 | 2020-05-20 | 2020-10-29
| 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of pebble peripheral bund for indiv / Construction of Pebble peripheral/farm/field Bund for Individuals | Construction of Bund | 1733003067/IF/22012034557176 — med badhan karya devi singh/rajaramlaghu kishan | Completed | 30259.55 | 17100 | 2020-05-20 | 2020-10-29
| 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of pebble peripheral bund for indiv / Construction of Pebble peripheral/farm/field Bund for Individuals | Construction of Bund | 1733003067/IF/22012034560185 — med badhan karya sant kumar/veeran laghu kishan | Completed | 21540.67 | 13300 | 2020-05-27 | 2020-10-29
| 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of pebble peripheral bund for indiv / Construction of Pebble peripheral/farm/field Bund for Individuals | Construction of Bund | 1733003067/IF/22012034560186 — med badhan karya chokelal/gokal prasad laghu kishan | Completed | 26669.4 | 6840 | 2020-05-27 | 2020-10-29
| 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of pebble peripheral bund for indiv / Construction of Pebble peripheral/farm/field Bund for Individuals | Construction of Bund | 1733003067/IF/22012034562448 — med badhan karya moti lal /dhanpatl laghu kishan | Closed | 25130.82 | 0 | 2020-04-14
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of pebble peripheral bund for indiv / Construction of Pebble peripheral/farm/field Bund for Individuals | Construction of Bund | 1733003067/IF/22012034562449 — med badhan karya sukhdev / khublal laghu kishan | Completed | 38978.35 | 25460 | 2021-04-27 | 2021-06-22
| 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1733003067/IF/22012034720774 — CTR खेत तालाब वीरेन्द्र तिवारी | Completed | 309874.51 | 125188 | 2021-04-30 | 2025-01-15
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1733003067/IF/22012034733559 — CTR MED BANDHAN KARY JAMMAN PRASAD / GOVIND | Completed | 13458.94 | 17480 | 2021-05-13 | 2021-07-17
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1733003067/IF/22012034733581 — CTR Med Bandhan Kary Mukesh/Omkar | Completed | 19360.16 | 23286 | 2021-05-13 | 2021-06-15
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1733003067/IF/22012034733587 — CTR Med Bandhan Kary Mukesh/Omkar | Closed | 0 | 0 | 2021-04-14
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1733003067/IF/22012034733595 — CTR Med Bandhan Kary Mukesh/Omkar | Closed | 0 | 0 | 2021-04-14
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1733003067/IF/22012034733635 — CTR Med Bandhan Kary Satesh/Omkar | Closed | 0 | 0 | 2021-04-14
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1733003067/IF/22012034733644 — CTR Med Bandhan Kary OmprakashJhariya/Koddu | Closed | 30230.83 | 0 | 2021-04-14
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1733003067/IF/22012034733646 — CTR Med Bandhan Kary OmprakashJhariya/Koddu | Closed | 0 | 0 | 2021-04-14
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1733003067/IF/22012034733647 — CTR Med Bandhan Kary OmprakashJhariya/Koddu | Closed | 0 | 0 | 2021-04-14
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1733003067/IF/22012034733648 — CTR Med Bandhan Kary OmprakashJhariya/Koddu | Closed | 0 | 0 | 2021-04-14
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1733003067/IF/22012034733661 — CTR Med Bandhan Kary Dinesh Patel / Kirshne Kumar | Completed | 32301.43 | 16920 | 2021-05-20 | 2021-06-22
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1733003067/IF/22012034733665 — CTR Med Bandhan Kary Dinesh Patel / Kirshne Kumar | Closed | 0 | 0 | 2021-04-14
| 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003067/IF/9993707614 — indra aawas JAYNTI BASOR / MOHAN | Completed | 84310 | 9858 | 2016-04-06 | 2017-11-17
| 2015-2016 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Compost Pit / Construction of Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1733003067/IF/9993708289 — indra aawas suman basor / deepchand | Completed | 84310 | 14310 | 2016-02-01 | 2017-11-17
| 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1733003067/IF/9993708291 — indra aawas kalpna gond / omkar | Completed | 84310 | 9858 | 2016-03-22 | 2017-11-17
| 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003067/IF/9993708293 — indra aawas sapna kevat / sukhchen | Completed | 84310 | 9858 | 2016-03-22 | 2017-11-17
| 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003067/IF/9993708295 — indra aawas chandwati sen /dhwrka sen | Completed | 84310 | 9848 | 2016-03-22 | 2017-11-17
| 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003067/IF/IAY/235837 — Construction of IAY House -IAY REG. NO. MP1420467 | Completed | 15030 | 15030 | 2017-02-01 | 2017-12-28
| 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003067/IF/IAY/243671 — Construction of IAY House -IAY REG. NO. MP1643453 | Completed | 15030 | 15030 | 2017-01-27 | 2017-12-06
| 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003067/IF/IAY/2530494 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4810444 | Completed | 17100 | 17100 | 2020-06-05 | 2020-09-24
| 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003067/IF/IAY/259941 — Construction of IAY House -IAY REG. NO. MP2364942 | Completed | 15030 | 15030 | 2017-02-01 | 2017-12-08
| 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003067/IF/IAY/261018 — Construction of IAY House -IAY REG. NO. MP2507004 | Completed | 15030 | 15030 | 2017-02-09 | 2018-02-07
| 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003067/IF/IAY/3069053 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4988703 | Completed | 17370 | 17370 | 2021-06-09 | 2021-12-04
| 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003067/IF/IAY/3092078 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4889928 | Completed | 17370 | 17370 | 2021-05-04 | 2022-03-18
| 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003067/IF/IAY/3128871 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5066029 | Completed | 17370 | 17370 | 2021-06-09 | 2022-07-14
| 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003067/IF/IAY/3287721 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP1414671 | Completed | 17370 | 17370 | 2021-12-01 | 2022-09-09
| 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003067/IF/IAY/3288807 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2774573 | Completed | 17370 | 17370 | 2021-11-23 | 2022-09-20
| 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003067/IF/IAY/3288838 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2802081 | Completed | 17370 | 17370 | 2021-12-10 | 2022-09-09
| 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003067/IF/IAY/3288870 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2824492 | Completed | 17370 | 17370 | 2021-11-23 | 2022-07-14
| 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003067/IF/IAY/3290960 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4297078 | Completed | 17370 | 17370 | 2021-12-01 | 2022-09-09
| 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003067/IF/IAY/3291875 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4594579 | Completed | 17370 | 17370 | 2021-12-01 | 2022-09-09
| 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003067/IF/IAY/3459760 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2802083 | Completed | 17370 | 17502 | 2022-01-29 | 2022-09-09
| 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003067/IF/IAY/42969 — Construction of IAY House -IAY REG. NO. MP-33-003-067-003/20935900 | Deleted | 14310 | 0 | 2015-11-07
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003067/IF/IAY/4316924 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106719836 | Completed | 18360 | 18360 | 2022-08-28 | 2022-12-02
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003067/IF/IAY/4338525 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106675346 | Completed | 18360 | 18360 | 2022-10-06 | 2023-02-11
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003067/IF/IAY/4370044 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106719868 | Completed | 18360 | 18360 | 2022-11-04 | 2023-03-30
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003067/IF/IAY/4384048 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106719813 | Completed | 18360 | 18360 | 2022-11-15 | 2023-06-21
| 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003067/IF/IAY/456162 — Construction of IAY House -IAY REG. NO. MP1641203 | Completed | 15030 | 15030 | 2017-02-09 | 2018-02-07
| 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003067/IF/IAY/531045 — Construction of IAY House -IAY REG. NO. MP2824481 | Completed | 15030 | 15030 | 2017-02-09 | 2018-02-07
| 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003067/IF/IAY/532619 — Construction of IAY House -IAY REG. NO. MP2865908 | Completed | 15030 | 15030 | 2017-04-05 | 2017-12-08
| 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003067/IF/IAY/56227 — Construction of IAY House -IAY REG. NO. MP-33-003-067-001/10 | Deleted | 14310 | 0 | 2015-12-14
| 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003067/IF/IAY/56228 — Construction of IAY House -IAY REG. NO. MP-33-003-067-003/20837439 | Deleted | 14310 | 0 | 2015-12-14
| 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003067/IF/IAY/56230 — Construction of IAY House -IAY REG. NO. MP-33-003-067-003/20845210 | Deleted | 14310 | 0 | 2015-12-14
| 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003067/IF/IAY/56231 — Construction of IAY House -IAY REG. NO. MP-33-003-067-003/29425880 | Deleted | 14310 | 0 | 2015-12-14
| 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003067/IF/IAY/564879 — Construction of IAY House -IAY REG. NO. MP3844773 | Completed | 15030 | 15030 | 2017-03-02 | 2017-12-08
| 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003067/IF/IAY/859714 — Construction of IAY House -IAY REG. NO. MP1609943 | Completed | 15480 | 15030 | 2017-08-24 | 2017-12-08
| 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003067/IF/IAY/863237 — Construction of IAY House -IAY REG. NO. MP1651117 | Completed | 15480 | 15030 | 2017-08-24 | 2017-12-08
| 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003067/IF/IAY/863238 — Construction of IAY House -IAY REG. NO. MP1651118 | Completed | 15480 | 15030 | 2017-05-18 | 2017-12-28
| 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003067/IF/IAY/867518 — Construction of IAY House -IAY REG. NO. MP1701199 | Completed | 15480 | 15030 | 2017-08-24 | 2018-02-07
| 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003067/IF/IAY/916189 — Construction of IAY House -IAY REG. NO. MP2364845 | Deleted | 17100 | 0 | 2017-04-09
| 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003067/IF/IAY/926252 — Construction of IAY House -IAY REG. NO. MP2526789 | Completed | 15480 | 15030 | 2017-08-03 | 2018-02-07
| 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003067/IF/IAY/942856 — Construction of IAY House -IAY REG. NO. MP2865608 | Completed | 15480 | 15030 | 2017-08-03 | 2017-12-08
| 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003067/IF/IAY/956002 — Construction of IAY House -IAY REG. NO. MP3197148 | Completed | 15480 | 15030 | 2017-08-24 | 2018-02-07
| 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003067/IF/IAY/960749 — Construction of IAY House -IAY REG. NO. MP3307993 | Completed | 15480 | 15030 | 2017-08-24 | 2017-12-08
| 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003067/IF/IAY/965363 — Construction of IAY House -IAY REG. NO. MP3429160 | Approved | 23490 | 0 | 2017-04-09
| 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003067/IF/IAY/965504 — Construction of IAY House -IAY REG. NO. MP3432823 | Completed | 15480 | 15030 | 2017-08-03 | 2017-12-28
| 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003067/IF/IAY/978490 — Construction of IAY House -IAY REG. NO. MP3820806 | Completed | 15480 | 15030 | 2017-05-04 | 2017-12-08
| 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1733003067/LD/121 — मेढबंधान कार्य श्‍यामा बाई दीक्षित/उजरौड | Deleted | 0 | 0 | 2008-04-01
| 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1733003067/LD/170 — मेढ बंधान श्‍यामाबाई / लक्ष्‍मी प्रसाद | Deleted | 0 | 0 | 2008-04-19
| 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1733003067/LD/22012034240150 — Med Bandhan - Anant ram / ramaprashad | Completed | 2609500000 | 15534 | 2015-12-01 | 2016-07-29
| 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1733003067/LD/22012034240152 — मेढ बधान कार्य रज्‍जू पटेल वल्‍द सुन्‍दरलाल | Completed | 2609500000 | 20169 | 2015-12-08 | 2016-07-29
| 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1733003067/LD/22012034240155 — Med bandhan - Omkar / Arjun singh | Completed | 24464 | 15690 | 2016-05-09 | 2016-07-29
| 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1733003067/LD/22012034240157 — मेढ बधान कार्य सतीश तिवारी वल्‍द दमडी लाल | Completed | 2446400000 | 132 | 2015-12-16 | 2016-09-18
| 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1733003067/LD/22012034240161 — med bandhan - endr raj / beni prashad | Completed | 2609500000 | 6252 | 2015-12-01 | 2016-07-29
| 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1733003067/LD/22012034240168 — Med Bandhan - Dilvashiya bai / lalloo ram | Completed | 2609500000 | 16221 | 2015-12-01 | 2016-07-29
| 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1733003067/LD/22012034240172 — मेढ बधान कार्य हुलकर झारिया वल्‍द छिकोडी | Completed | 2609500000 | 139 | 2015-12-16 | 2016-09-18
| 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1733003067/LD/22012034240174 — Med Bandhan - Purshottam / devi singh | Completed | 2446400000 | 16277 | 2015-12-23 | 2016-07-29
| 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1733003067/LD/22012034240175 — मेढ बधान कार्य रूपसीग वल्‍द मुरारी लाल | Completed | 1630900000 | 4733 | 2015-12-23 | 2016-07-29
| 2015-2016 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1733003067/LD/22012034240421 — Khail maidan Bhoitiya | Completed | 403000 | 33616 | 2016-01-01 | 2020-11-06
| 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1733003067/LD/22012034314064 — शांतिधाम निर्माण भोतिया | Completed | 227000 | 47363.6 | 2017-05-25 | 2021-06-14
| 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1733003067/LD/22012034598968 — Bhoomi vikas kary shanthidham parisar gram Jugtaraiya | Physically Completed | 354610.65 | 292600.07 | 2023-12-11 | 2026-05-29
| 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1733003067/LD/3799400678 — Puhup Singh / Arjun Singh - Ujroud | Deleted | 32000 | 0 | 2013-04-01
| 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1733003067/LD/3799401196 — Ramsing/Murari Lal - Ujaroud | Deleted | 32000 | 0 | 2013-04-01
| 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1733003067/LD/3799401197 — khel maidan samtalikarn - Ujaroud | Deleted | 0 | 0 | 2013-04-01
| 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1733003067/LD/3799401200 — Khel Maidan Samtalikarn - Ujaroud | Deleted | 406000 | 0 | 2013-04-01
| 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1733003067/LD/3799430885 — शांति धाम निर्माण कार्य उजरोड | Completed | 166000 | 61180 | 2014-03-01 | 2016-08-31
| 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1733003067/LD/882 — मेढबधान - उत्‍तम पटैल | Completed | 0 | 17202 | 2011-06-17 | 2011-06-29
| 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1733003067/LD/883 — मेढबधान - जशवीर सिह | Completed | 0 | 9882 | 2011-06-17 | 2011-06-29
| 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1733003067/LD/978 — जुगतरिया शांतिधाम निर्माण कार्य | Completed | 338000 | 265294 | 2012-07-01 | 2016-02-16
| 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play field for Community | Construction of Play field | 1733003067/PG/22012034311892 — खेल मैदान और समतलीकरण जग तरेया | Completed | 154000 | 1050 | 2017-05-25 | 2017-07-07
| 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play field for Community | Construction of Play field | 1733003067/PG/9425891863 — खेल मैदान समतलीकरण उजरोंड | Completed | 105000 | 50987.03 | 2017-01-04 | 2020-11-06
| 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1733003067/RC/10813 — पंचपरमेश्‍वर सी सी रोड एवं नाली निर्माण उजरौड | Completed | 88473 | 18178 | 2012-03-16 | 2014-07-30
| 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1733003067/RC/10909 — 1733003067/RC/10909 | Completed | 120000 | 111482 | 2013-02-14 | 2014-07-30
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1733003067/RC/22012034191534 — Jugtrai awash colny me c.c. road nali nirmand ka | Deleted | 100383 | 0 | 2013-08-15
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1733003067/RC/22012034192972 — जुगतरेया आवास कालोनी में उजरोड़ | Completed | 100000 | 90724 | 2013-12-06 | 2014-05-31
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1733003067/RC/22012034196234 — कालोनी से कोलू की और jugterya | Completed | 85000 | 81543 | 2014-01-01 | 2014-05-31
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1733003067/RC/22012034202355 — C.C. Raod 3rd Phese Nali Nirmand Karya Jagdish ke | Completed | 74000 | 58612 | 2014-02-06 | 2014-05-31
| 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1733003067/RC/22012034226204 — Panch Parmeswar 6th phese tulshi ke ghar se talab | Completed | 82000 | 51958 | 2014-08-02 | 2015-07-30
| 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1733003067/RC/22012034282857 — Satwa CharaN Panchparmenshwar C. C Nirmad Karya | Deleted | 0 | 0 | 2015-04-14
| 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1733003067/RC/22012034282858 — 7th Panchparmenshwar C. C Nirmad Karya | Completed | 44000 | 51468 | 2015-08-23 | 2016-01-06
| 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1733003067/RC/22012034314590 — 14 ba bitt c c road & nali nirmand kirana dukan se kisan ke ghar ki or | Completed | 43000 | 28182 | 2017-08-26 | 2017-12-13
| 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1733003067/RC/22012034314591 — 14 ba vitt c c road & nali nirmand visan patel ke ghar se ramkumar se ghar ki or | Completed | 43000 | 24084 | 2017-04-05 | 2017-11-28
| 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1733003067/RC/22012034331684 — c c road nirmand karya | Closed | 0 | 0 | 2017-01-26
| 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1733003067/RC/22012034352283 — 14 vitt (nerga) - C.C. Road & Nali Nirmad Kary - Hori Dai Se Indra Raj Ke Ghar Tak | Deleted | 0 | 0 | 2016-10-02
| 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1733003067/RC/22012034352287 — 14 vitt (nerga) - C.C. Road & Nali Nirmad - Hori Dai Se Indraraj Ke Ghar Tak | Completed | 60187.5 | 42192 | 2017-09-06 | 2017-12-30
| 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1733003067/RC/22012034368976 — c c road nirmaan | Closed | 0 | 0 | 2017-04-14
| 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1733003067/RC/22012034514768 — CC Road and Nali convergence - Ramkumar ke ghar se pan bai ke ghar ki or 19-20 | Completed | 25000 | 10208 | 2020-01-31 | 2020-11-06
| 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1733003067/RC/22012034561421 — ujrod mainar se bhotiya gao tak | Closed | 0 | 0 | 2020-10-25
| 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Mitti Murram Roads for Community / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1733003067/RC/22012034561703 — Ujrod mainar se Bhotiya gao tak sudoor sadak pahuch marg | Closed | 0 | 0 | 2020-10-25
| 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1733003067/RC/22012034574912 — Ujrond mainar se Bhotiya gao tak Sudoor sadak pahuch marg | Ongoing | 1494740.17 | 836222.97 | 2021-06-20
| 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Mitti Murram Roads for Community / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1733003067/RC/22012034614016 — Approach road Awas calony se shantidham phuch marg jugtariya | Closed | 0 | 0 | 2022-04-01
| 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1733003067/RC/22012034670808 — C C road nirmand pan bai ke ghar se Gopi sahu ke ghar tak | Completed | 52000 | 50089 | 2024-02-17 | 2025-01-21
| 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Interlocking block/tiles Roads for Comm / Construction of Inter-locking cement block/tiles Roads for Community | Constr of Cement Concrete Roads | 1733003067/RC/22012034838759 — pewar block nirman kary mukhye marg se deepak dube k ghasr tak | Completed | 10000 | 9654.28 | 2025-06-11 | 2026-02-25
| 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1733003067/RC/35 — उजरौड से भौतिया पहुच मार्ग | Completed | 400000 | 18788 | 2008-05-20 | 2011-05-18
| 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1733003067/RS/22012034651911 — JAM SOAK PIT NIRMAN KARY WORD NO 13 BHOTIYA HAND PUMP KE PASS | Closed | 2200 | 0 | 2022-04-01
| 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1733003067/RS/22012034651912 — JAM SOAK PIT NIRMAN KARY WORD NO 13 BHOTIYA HAND PUMP KE PASS | Closed | 2200 | 0 | 2022-04-01
| 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1733003067/RS/22012034651915 — JAM SOAK PIT NIRMAN KARY AWAS CALONY UJROAND KE HAND PUMP | Closed | 2200 | 0 | 2022-04-08
| 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1733003067/RS/22012034652906 — JAM SOAK PIT NIRMAN KARY AWAS COLONY JUGTARIYA HAND PUMP KE PASS | Closed | 2200 | 0 | 2022-04-08
| 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1733003067/RS/22012034669203 — SAMUDAYIK SWACHTA PARISAR EKIKRAIT SCHOOL PARISAR ME UJROAND | Completed | 47000 | 45716 | 2022-11-04 | 2024-05-09
| 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1733003067/RS/22012034674782 — SAMUDAYIK NADEEP NIRMAN KARY Ekikrat school ke pass ujroand | Closed | 0 | 0 | 2022-04-01
| 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1733003067/RS/22012034675718 — SAMUDAYIK NADEEP NIRMAN KARY Ekikrat school ke pass ujroand | Completed | 9600 | 8568 | 2022-11-15 | 2023-04-26
| 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1733003067/RS/22012034675721 — SAMUDAYIK NADEEP NIRMAN KARY shanthidham ke pass ujroand | Completed | 9600 | 8568 | 2022-12-07 | 2023-04-26
| 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1733003067/RS/22012034675724 — SAMUDAYIK NADEEP NIRMAN KARY shanthidham ke pass jugtariya | Closed | 9600 | 0 | 2022-11-10
| 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1733003067/RS/22012034675727 — SAMUDAYIK NADEEP NIRMAN KARY Awas caloany jugtariya | Closed | 9600 | 0 | 2022-11-10
| 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1733003067/RS/22012035120659 — R C C nali nirmand karya Pan bai ke ghar se gouri singh ke ghar ki or | Completed | 37000 | 31575 | 2024-12-13 | 2025-05-01
| 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1733003067/RS/22012035128286 — Bhoomigat pipe nali nirman kary lalman ke ghar se ramdas ke ghar tak | New | 0 | 0 | 2024-06-09
| 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1733003067/RS/22012035128287 — Bhoomigat pipe nali nirman kary lalman ke ghar se ramdas ke ghar tak gram bhotiya | Completed | 23000 | 18880 | 2025-01-06 | 2025-07-31
| 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1733003067/RS/22012035136705 — bhumigat payip nali ewam antrik marg m pewar bloc kary vishay k ghar s rajesh k ghar evm dhelan | New | 0 | 0 | 2025-01-26
| 2025-2026 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1733003067/RS/22012035136706 — bhumigat payip nali ewam antrik marg m pewar bloc kary vishay k ghar s rajesh k ghar evm dhelan | Completed | 27000 | 26990.05 | 2025-05-21 | 2025-07-31
| 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Dam / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1733003067/WC/22012034383732 — talab vistarikarn | Closed | 0 | 0 | 2017-04-14
| 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1733003067/WC/22012034496894 — Roof Water harvesting - aganwadi Building 19-20 | Closed | 3000 | 0 | 2019-08-15
| 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1733003067/WC/22012034496899 — Roof Water Harvesting - School Building 19-20 | Closed | 3000 | 0 | 2019-08-15
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1733003067/WC/22012034837244 — WATTER HARVESTING MADHAYAMIK SALA UJROAD | Completed | 3568 | 3088 | 2022-02-13 | 2022-12-26
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1733003067/WC/22012034837253 — WATTER HARVESTING PRATHMIK SALA UJROAD | Completed | 3300 | 3088 | 2022-02-13 | 2022-12-26
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1733003067/WC/22012034837257 — WATTER HARVESTING PRATHMIK SALA BHAWAN BHOTIYA | Completed | 3300 | 3474 | 2022-03-20 | 2022-12-12
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1733003067/WC/22012034907124 — watar harwasting माध्यमिक शाला ujrod | Deleted | 0 | 0 | 2021-08-16
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1733003067/WC/22012034907125 — watar harwasting माध्यमिक शाला ujrod | Deleted | 0 | 0 | 2021-08-16
| 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1733003067/WH/22012034438967 — taalab jernodhar nirman karya gram bhoutiya me 2017-18 | Completed | 228000 | 76858 | 2020-05-06 | 2022-07-14
| 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1733/DP/9926694083 — Khajuri vitran nahar baro 0.00 to 3.90 km Planteti | Completed | 4351000 | 1218076 | 2012-08-25 | 2025-06-13