## Work List
Exported on: 2026-08-24 06:27:17
Filters applied:
Data source: MGNREGA
District: JABALPUR
Block: PATAN
Panchayat: PONIKHURD
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
| 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Fallow Land for Community / Development of Fallow Land for Community | Land Development | 1733003006/LD/22012034583870 — Samtali karan kary Shanti dham k pass gram madwa gram Panchayat Pondi khurd | Closed | 100000 | 0 | 2022-08-15
| 2025-2026 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1733003080/RS/22012035138678 — Kachhi Nali Nirmand karya Gram Madwa Me 100 Meteer | Approved | 0 | 0 | 2025-10-02
| 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1733003082/AV/22012034630789 — construction of shanti dham nirman karya pondikhurd single | Closed | 0 | 0 | 2023-01-26
| 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1733003082/AV/22012034631030 — shantidham nirman karya pondikhurd | Ongoing | 286352.16 | 210017.23 | 2024-06-13
| 2025-2026 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1733003082/AV/22012034666688 — Chabutra Nirmand Karya PS Shala Ke baju Me Gram madwa | Completed | 42000 | 35556.6 | 2025-07-16 | 2026-04-18
| 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1733003082/DP/22012034574515 — Construction of amudayik khet talab nirman karya gram pondikhurd | Closed | 0 | 0 | 2023-01-26
| 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Coastal Block Plantation of Forestry-Community / Along the coast Block Plantation of Forestry Trees for Community | Plantation | 1733003082/DP/22012034591309 — Amrit Watika Auganwadi .Ke Sammep pondikurd | Closed | 55847.4 | 0 | 2023-10-03
| 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Construction of Embankment for community / Construction of Embankment for community | Construction of Embankment | 1733003082/FP/22012034638603 — samudayik pond nriman karya pondikhurd | Closed | 0 | 0 | 2024-01-24
| 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Micro Irrigation Works | Construction of water courses Canal for Community / Construction of water courses for Community | Construction of Canal | 1733003082/IC/22012034883982 — Naveen Talab Nirman Karya Pondikhurd | Closed | 0 | 0 | 2024-01-26
| 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1733003082/IF/22012035066777 — Construction of khet talab dashrath/mojilal barman pondikhurd nirman devi singh ke ghar ke paas | Completed | 179394.25 | 119119 | 2023-06-01 | 2025-02-25
| 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Block Plantation of Farm Forestry Trees in Fields for Individuals | Plantation | 1733003082/IF/22012035128252 — Vrakchharopan karya Hket ki med par abilasha lodhi/mulam singh | Closed | 0 | 0 | 2023-07-10
| 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Stone graded Bund for Individuals / Construction of Stone graded Bund for Individuals | Construction of Bund | 1733003082/IF/22012035135825 — Ganesh / Lakhamni Prasad Barman PMAY | Closed | 19800 | 0 | 2023-04-14
| 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Staggered Trench for individual / Construction of Staggered Trench for individual | Construction of Trench | 1733003082/IF/22012035139155 — Ganesh Barman / Lakhami barman -PMAY | Completed | 19000 | 19890 | 2023-08-22 | 2025-03-24
| 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1733003082/IF/22012035227876 — Niji Khet Talab nirma Karya Channu amehra/Jeewan madwa | Closed | 0 | 0 | 2024-01-26
| 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1733003082/IF/22012035227910 — Niji Khet Talab nirma Karya Rajju Chamar/Hariya Madwa | Closed | 0 | 0 | 2024-01-26
| 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1733003082/IF/22012035227915 — Niji Khet Talab nirma Karya Panji mehra/kamod Mehrar/Hariya Madwa | Closed | 0 | 0 | 2024-01-24
| 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1733003082/IF/22012035227921 — Niji Khet Talab nirma Karya kamla Chamar/Munim Madwa | Closed | 0 | 0 | 2024-01-24
| 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1733003082/IF/22012035227932 — Niji Khet Talab nirma Karya Suwa Chamar/Budhhu Madwa | Closed | 0 | 0 | 2024-01-26
| 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1733003082/IF/22012035227942 — Niji Khet Talab nirma Karya Amit Mehra/ Dbbl Prasad Madwa | Closed | 0 | 0 | 2024-01-26
| 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1733003082/IF/22012035227989 — Niji Khet Talab nirma Karya Charan Gaund / TekSingh Pondikhurd | Closed | 0 | 0 | 2024-01-26
| 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1733003082/IF/22012035228004 — Niji Khet Talab nirma Karya Ramprasad/Noni bai Pondikhurd | Closed | 0 | 0 | 2024-01-26
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Coast Line plntation of Forestry Trees-Individuals / Along the coast Line Plantation of Forestry Trees for Individuals | Plantation | 1733003082/IF/22012035243737 — Vrakchharopan karya panji mehra ke Khet me Madwa | Ongoing | 154954.12 | 98774.48 | 2024-07-19
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Line-coast Plntation-Farm Forstry Trees-Individual / Along the coast Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1733003082/IF/22012035243838 — Vrakchharopan karya Sunwa chamar ke khet me madwa | Ongoing | 151017.41 | 93975.45 | 2024-08-23
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Line-coast Plntation-Farm Forstry Trees-Individual / Along the coast Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1733003082/IF/22012035243859 — Vrakchharopan karya pancham gond pondikhurd | Approved | 0 | 0 | 2024-05-26
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Line-coast Plntation-Farm Forstry Trees-Individual / Along the coast Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1733003082/IF/22012035243860 — Vrakchharopan karya pancham gond pondikhurd | Approved | 0 | 0 | 2024-05-26
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Biodrainage in Fields-Individuals / Block Plantation of Biodrainage Trees in Fields for Individuals | Plantation | 1733003082/IF/22012035248746 — Vrakchharopan karya Sunwa/Budhuwa madwa | Approved | 0 | 0 | 2024-06-25
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Line Plntation(Coast) - horti-trees (Individuals) / Along the coast Line Plantation of Horticulture Trees for Individuals | Plantation | 1733003082/IF/22012035248748 — Vrakchharopan karya pancham gond/Teji pondikhurd | Ongoing | 91141.93 | 41540 | 2024-12-03
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1733003082/IF/22012035360702 — Khet Talab Nirman Karya Uttam Singh/Nirpat Singh ke Khet me 1000cum | Completed | 147621.16 | 102780.89 | 2025-04-23 | 2026-04-02
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1733003082/IF/22012035361040 — Khet Talab Nirman Karya JGSA Charan Singh/Tek Singh Gond ke Khet me 1000cum | New | 0 | 0 | 2025-04-14
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1733003082/IF/22012035374661 — Khet Talab Nirman Kamla bai / munim ke Khet me madwa | Completed | 147621.16 | 96763.9 | 2025-04-22 | 2026-04-01
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1733003082/IF/22012035547950 — JGSA Khet Talab Nirman Karya Bihari Lal / Washudeo Pondikhurd | Closed | 147621.16 | 260.61 | 2025-05-28
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003082/IF/IAY/4369815 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106891469 | Closed | 0 | 0 | 2022-09-29
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003082/IF/IAY/4547590 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106694842 | Completed | 21870 | 21870 | 2024-11-12 | 2025-04-01
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003082/IF/IAY/4660052 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148876265 | Completed | 23490 | 21870 | 2025-02-19 | 2025-05-16
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003082/IF/IAY/4661604 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148942309 | Completed | 23490 | 21870 | 2025-02-19 | 2025-06-03
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003082/IF/IAY/4661725 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148977378 | Completed | 23490 | 21870 | 2025-02-19 | 2025-05-16
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003082/IF/IAY/4661751 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148981884 | Completed | 23490 | 21870 | 2025-02-19 | 2025-05-16
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003082/IF/IAY/4663549 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148991849 | Completed | 23490 | 21870 | 2025-02-19 | 2025-05-16
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003082/IF/IAY/4740671 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106851450 | Completed | 21870 | 21870 | 2024-11-25 | 2026-01-13
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003082/IF/IAY/4881819 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151045770 | Completed | 23490 | 22140 | 2025-02-19 | 2026-01-13
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003082/IF/IAY/5823448 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148926841 | Completed | 23490 | 23490 | 2025-10-23 | 2026-01-13
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003082/IF/IAY/5823484 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106863987 | Completed | 23490 | 23490 | 2026-03-17 | 2026-05-18
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003082/IF/IAY/5823639 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151040415 | Completed | 23490 | 23490 | 2025-10-07 | 2026-01-13
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003082/IF/IAY/5824041 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148948870 | Completed | 23490 | 22968 | 2025-10-07 | 2026-02-20
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003082/IF/IAY/5824406 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148879472 | Completed | 23490 | 23490 | 2025-10-07 | 2026-01-13
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003082/IF/IAY/5826942 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150947583 | Completed | 23490 | 23490 | 2025-10-07 | 2026-01-13
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003082/IF/IAY/5827300 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148684425 | Completed | 23490 | 23490 | 2025-10-07 | 2026-01-13
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003082/IF/IAY/5828157 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106851422 | Completed | 23490 | 23490 | 2025-09-30 | 2026-01-16
| 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003082/IF/IAY/5843676 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151030112 | Ongoing | 23490 | 7830 | 2026-04-03
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003082/IF/IAY/5843707 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151005563 | Completed | 23490 | 22446 | 2025-11-06 | 2026-02-24
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003082/IF/IAY/5843895 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151013511 | Completed | 23490 | 22968 | 2025-11-13 | 2026-02-24
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003082/IF/IAY/5843991 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148965240 | Completed | 23490 | 22446 | 2025-11-06 | 2026-02-24
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003082/IF/IAY/5843992 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148970480 | Completed | 23490 | 23490 | 2025-11-10 | 2026-04-29
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003082/IF/IAY/5843996 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149023946 | Completed | 23490 | 23490 | 2025-10-22 | 2026-01-13
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003082/IF/IAY/5844680 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148959803 | Completed | 23490 | 22968 | 2025-12-03 | 2026-02-20
| 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003082/IF/IAY/5844681 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148989083 | Completed | 23490 | 23490 | 2026-04-03 | 2026-05-29
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003082/IF/IAY/5844683 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148997465 | Completed | 23490 | 23490 | 2025-10-23 | 2026-01-13
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003082/IF/IAY/5844719 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148686830 | Completed | 23490 | 23490 | 2025-10-23 | 2026-01-13
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003082/IF/IAY/5844904 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148903060 | Completed | 23490 | 23490 | 2025-12-11 | 2026-01-27
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003082/IF/IAY/5844928 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150963214 | Completed | 23490 | 23490 | 2025-12-15 | 2026-02-12
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003082/IF/IAY/5844931 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148881178 | Completed | 23490 | 23490 | 2025-10-28 | 2026-02-24
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003082/IF/IAY/5844947 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148680250 | Approved | 23490 | 0 | 2025-03-20
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003082/IF/IAY/5844996 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150968736 | Completed | 23490 | 22707 | 2025-12-15 | 2026-03-11
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003082/IF/IAY/5845001 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148939068 | Completed | 23490 | 22968 | 2025-12-15 | 2026-02-20
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003082/IF/IAY/5845060 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151050802 | Completed | 23490 | 23490 | 2025-11-08 | 2026-02-24
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003082/IF/IAY/5845163 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148956014 | Completed | 23490 | 23490 | 2025-11-08 | 2026-01-13
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003082/IF/IAY/5845220 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148943865 | Completed | 23490 | 23490 | 2025-11-08 | 2026-01-13
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003082/IF/IAY/5845273 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151017602 | Completed | 23490 | 23229 | 2025-11-13 | 2026-01-21
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003082/IF/IAY/5845299 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148883972 | Completed | 23490 | 23490 | 2025-12-03 | 2026-01-13
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003082/IF/IAY/5845334 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148954728 | Completed | 23490 | 23490 | 2025-11-08 | 2026-02-24
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003082/IF/IAY/5845438 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148897646 | Completed | 23490 | 22446 | 2026-02-04 | 2026-03-31
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003082/IF/IAY/5845483 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148906964 | Completed | 23490 | 23490 | 2026-02-04 | 2026-03-31
| 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003082/IF/IAY/5845605 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148915516 | Ongoing | 23490 | 7830 | 2026-04-13
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003082/IF/IAY/5845606 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148923469 | Completed | 23490 | 23490 | 2025-11-10 | 2026-01-13
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003082/IF/IAY/5845607 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148924502 | Completed | 23490 | 23229 | 2025-11-10 | 2026-02-18
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003082/IF/IAY/5845649 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148922166 | Completed | 23490 | 23490 | 2026-02-23 | 2026-03-31
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003082/IF/IAY/5845742 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106851406 | Completed | 23490 | 23490 | 2025-10-28 | 2026-01-21
| 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003082/IF/IAY/5845764 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148932413 | Ongoing | 23490 | 7830 | 2026-04-03
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003082/IF/IAY/5845782 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148688385 | Completed | 23490 | 23490 | 2025-10-28 | 2026-02-24
| 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003082/IF/IAY/5845789 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148911581 | Ongoing | 23490 | 7830 | 2026-04-13
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003082/IF/IAY/5845790 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148917678 | Completed | 23490 | 23490 | 2026-02-04 | 2026-03-31
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003082/IF/IAY/5845876 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148891760 | Completed | 23490 | 22707 | 2025-11-06 | 2026-03-11
| 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003082/IF/IAY/5845877 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148930806 | Ongoing | 23490 | 7830 | 2026-04-03
| 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003082/IF/IAY/5845878 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148934095 | Ongoing | 23490 | 7830 | 2026-04-03
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003082/IF/IAY/5845879 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148678849 | Completed | 23490 | 22968 | 2025-11-10 | 2026-02-18
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003082/IF/IAY/5846107 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148875148 | Completed | 23490 | 22446 | 2025-10-28 | 2026-03-31
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003082/IF/IAY/5846171 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148940539 | Completed | 23490 | 22968 | 2025-12-11 | 2026-02-20
| 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003082/IF/IAY/6006527 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148904683 | Ongoing | 23490 | 15660 | 2026-06-16
| 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003082/IF/IAY/6006528 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148905815 | Ongoing | 23490 | 7830 | 2026-06-01
| 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003082/IF/IAY/6006689 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149000677 | Ongoing | 23490 | 23490 | 2026-06-01
| 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003082/IF/IAY/6008133 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148963525 | Ongoing | 23490 | 15660 | 2026-06-16
| 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003082/IF/IAY/6008881 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148961860 | Ongoing | 23490 | 7830 | 2026-06-01
| 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003082/IF/IAY/6009850 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148901691 | Ongoing | 23490 | 23490 | 2026-06-01
| 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003082/IF/IAY/6151929 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106863954 | Ongoing | 23490 | 7308 | 2026-05-18
| 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003082/IF/IAY/6165711 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106891436 | Ongoing | 23490 | 7830 | 2026-05-11
| 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003082/IF/IAY/6167883 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106851464 | Ongoing | 23490 | 7830 | 2026-05-11
| 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003082/IF/IAY/6213309 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150983495 | Ongoing | 23490 | 23490 | 2026-06-16
| 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003082/IF/IAY/6216506 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148675014 | Ongoing | 23490 | 15660 | 2026-06-16
| 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1733003082/LD/22012034948560 — Samtali karan kary Shanti dham k pass gram madwa gram Panchayat Pondi khurd | Completed | 100000 | 92112.3 | 2025-03-12 | 2026-05-25
| 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Fallow Land for Community / Development of Fallow Land for Community | Land Development | 1733003082/LD/22012034948743 — maidan Samtali Karan Karya Hari Barman ke Ghar Ke Paas | Approved | 0 | 0 | 2024-10-21
| 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1733003082/LD/22012034948835 — Bhumi Vikash Awam Samtalikaran Karya Hari Barman ke Ghar ke Sameep pondikhurd | Completed | 124965.24 | 88490 | 2025-02-09 | 2026-05-25
| 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1733003082/LD/22012034959730 — Sahskiya madhyamink Shala ke maidan me samtalikaran karya | Approved | 0 | 0 | 2025-10-02
| 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1733003082/LD/22012034959731 — Gram pondikhurd me shanti dham ke pass samtalikaran karya | Approved | 0 | 0 | 2025-10-02
| 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1733003082/LD/22012034960854 — Bhumi sudhar samtalikaran govt prathmik shala madwa82/ LD/0854 | Closed | 99720.48 | 4940 | 2026-04-16
| 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1733003082/LD/22012034960855 — Bhumi sudhar samtalikaran Shantidham Parisar me pondikhurd 82/ LD/0855 | Approved | 99007.52 | 0 | 2026-01-02
| 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1733003082/RC/22012034633595 — sudoor sadak Nirman karya PONDIKHURD TIRAHA SE PATHARIYA TOLA tak | Closed | 0 | 0 | 2022-09-01
| 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1733003082/RS/22012034680032 — Construction of community Nadep nirman karya colony me prathmik shala ke paas | Closed | 9600 | 0 | 2022-12-15
| 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1733003082/RS/22012034680051 — Construction of community Nadep nirman karya Kotwar ke Ghar ke paas pondikhurd | Closed | 9600 | 0 | 2022-12-09
| 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1733003082/RS/22012034680054 — Construction of community Nadep nirman karya Radha bai ke Ghar ke paas pondikhurd | Closed | 9600 | 0 | 2022-12-07
| 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of NADEP Compost structure for Groups / Construction of NADEP Compost structure for Groups | Construction of NADEP/Vermi Compost Pit | 1733003082/RS/22012034699957 — सामुदायक नाडेप bindu ke ghar ke pass | Closed | 0 | 0 | 2023-04-14
| 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of NADEP Compost structure for Groups / Construction of NADEP Compost structure for Groups | Construction of NADEP/Vermi Compost Pit | 1733003082/RS/22012034704177 — Samudaik Nadep Main Road Ke pas Heera Bai ke ghar ke pass Gram madwa | Completed | 9600 | 9282 | 2023-10-07 | 2025-02-21
| 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1733003082/RS/22012034704178 — Samudaik Nadep Karya Colony Tola Ke Pass Gram Pondi | Completed | 9600 | 8840 | 2023-10-06 | 2025-02-21
| 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1733003082/RS/22012034704180 — Samudaik Nadep Karya Kotwar Ke ghar ke pass Pondikhurd | Completed | 9600 | 8820 | 2023-10-06 | 2025-02-21
| 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1733003082/RS/22012035116411 — Sochaly Nirmand Karya P S School Pondi Khurd | Completed | 21000 | 18564 | 2023-10-07 | 2025-03-24
| 2025-2026 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1733003082/RS/22012035138679 — Kachhi Nali Nirmand Karya Gram Pondi khurd | Approved | 0 | 0 | 2025-10-02
| 2023-2024 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1733003082/WC/22012035174375 — samudayik khet talab nirman karya | Completed | 458409 | 336312.4 | 2024-03-17 | 2025-03-06
| 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1733003082/WC/22012035213693 — Soak pit Nirman Karya jamun ke ped ke paas chaudhari mohalla madwa | Completed | 2000 | 1944 | 2024-07-10 | 2025-03-06
| 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1733003082/WC/22012035213706 — Soak pit Nirman Prathmik shala ke paas chaudhari mohalla Pondikhurd | Approved | 2000 | 0 | 2024-06-12
| 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1733003082/WC/22012035214016 — soack pit nirman karya prathmik shala gram pondikhurd | Completed | 2000 | 1458 | 2024-07-11 | 2025-03-06
| 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1733003082/WC/22012035218897 — Kachi nalli nirman karya pondikhurd se nadiya ki or pondikhurd | Completed | 44387.28 | 30103.8 | 2024-10-05 | 2025-03-17
| 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1733003082/WC/22012035218902 — Kachi nalli nirman karya gram Vinid ke ghar se gram ke bahar ki or Madwa | Completed | 54855.34 | 44628 | 2024-11-02 | 2025-03-17