JAMUNIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734002088/IF/IAY/5985044 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118344233 | Ongoing | 27000 | 10962 | 2026-05-20
JAMUNIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734002088/IF/IAY/5985775 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120932330 | Ongoing | 27000 | 0 | 2026-02-11
JAMUNIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734002088/IF/IAY/5985843 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125777433 | Ongoing | 27000 | 23229 | 2026-05-02 | 2026-07-12
JAMUNIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734002088/IF/IAY/5986507 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120015515 | Approved | 27000 | 0 | 2026-02-11
JAMUNIYA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1734002088/LD/22012034585541 — Gram panchayat jamuniya khel maidan karye jamuniya | Deleted | 0 | 0 | 2022-08-15
JAMUNIYA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1734002088/LD/22012034585542 — Gram panchayat jamuniya samudayak jal bharav bhumi ki nikashi karye jamuniya | Completed | 62366.72 | 52632 | 2022-12-30 | 2024-02-19
JAMUNIYA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Fallow Land for Community / Development of Fallow Land for Community | Land Development | 1734002088/LD/22012034600081 — Mandir parisar ka samtalikaran karye khumerkheda | Completed | 70326.48 | 60695.12 | 2024-02-10 | 2024-10-18
JAMUNIYA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1734002088/LD/22012034939982 — Samsan ghat mai samtalikaran karye Sukha dhigsara | Deleted | 0 | 0 | 2024-04-01
JAMUNIYA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1734002088/RC/22012034660452 — Cc sadak nirman karye bholenath mandir se tulsiram ki aur | Completed | 60000 | 53780 | 2023-10-07 | 2024-02-19
JAMUNIYA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1734002088/RC/22012034835954 — jamuniya cc sadk nirman karye raju tahkur ke ghar se main roud ki aur sukha dhigsara | Completed | 50000 | 43740 | 2025-02-24 | 2026-02-04
JAMUNIYA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1734002088/RS/22012034700213 — Nali nirman karye niranjan ke makan se talab ki aur | Completed | 16600 | 15912 | 2023-08-08 | 2024-02-24
JAMUNIYA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1734002088/RS/22012035132673 — PVC NALI NIRMAN DHARMESH SHARMA KE MAKAN SE MAIN ROAD | Completed | 17000 | 15795 | 2024-10-29 | 2026-02-04
JAMUNIYA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1734002088/RS/22012035135635 — jamuniya swachta parisar karye jamuniya | Completed | 37000 | 32310 | 2025-02-18 | 2026-05-31
JAMUNIYA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & maint of Community Ponds for Comm / Repair and maintenance of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1734002088/WC/22012035044668 — Jamuniya dag ponds karye khumerkheda | Deleted | 0 | 0 | 2023-01-24
JAMUNIYA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & maint of Community Ponds for Comm / Repair and maintenance of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1734002088/WC/22012035044669 — Jamuniya dag ponds karye khumerkheda | Completed | 459683.26 | 324649 | 2023-08-18 | 2023-09-10
JAMUNIYA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & Maint of Earthen graded Bund for Com / Repair and Maintenance of Earthen graded Bund for Community | Repair & Maint of Bund | 1734002088/WC/22012035132091 — Nala bank stabilization karye main road se talab ki aur | Completed | 212709.35 | 132186 | 2023-10-24 | 2024-09-06
JAMUNIYA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1734002088/WC/22012035132103 — Nala bank stabilization karye talab se tapariya tola ki aur ki aur | Completed | 212709.35 | 156097 | 2023-11-21 | 2024-09-06
JAMUNIYA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & Maint of Gabion Check Dam for Community / Repair and Maintenance of Gabion Check Dam for Community | Repair & Maint of Check Dam/Stop Dam | 1734002088/WC/22012035190913 — Check dam nirman karye nadiya | Deleted | 0 | 0 | 2023-08-16
JAMUNIYA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1734002088/WC/22012035190920 — Nala nirman karye sarkari nal se khel maidan ki aur jamuniya | Completed | 250729.6 | 139725 | 2024-05-30 | 2024-09-24
JAMUNIYA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & Maint of Earthen graded Bund for Com / Repair and Maintenance of Earthen graded Bund for Community | Repair & Maint of Bund | 1734002088/WC/22012035191047 — Talab nirman karye khumerkheda | Deleted | 0 | 0 | 2023-08-16
JAMUNIYA | 2024-2025 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1734002088/WC/22012035191308 — Construction of mini Percolation tank for Community gram ... | Completed | 490864.85 | 314870 | 2024-04-08 | 2024-11-05
JAMUNIYA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1734002088/WC/22012035200388 — Dag ponds karye Sukha dhigsara | Deleted | 0 | 0 | 2024-04-27
JAMUNIYA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1734002088/WC/22012035224241 — RFA GABIAN KARYE TALAB KE PAAS KHUMERKHEDA | Deleted | 0 | 0 | 2024-08-16
JAMUNIYA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1734002088/WC/22012035224244 — RFA GABIAN KARYE tapariya tola KE PAAS KHUMERKHEDA | Deleted | 0 | 0 | 2024-06-16
JAMUNIYA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1734002088/WC/22012035307003 — Amrit Sarovar 2.0 Gram Khumar Khera GP Jamuniya | Approved | 0 | 0 | 2025-04-01
JAMUNIYA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1734002088/WC/22012035307005 — Amrit Sarovar 2.0 Gram Sukha Dhigsara GP Jamuniya | Approved | 0 | 0 | 2025-04-01
JAMUNIYA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1734002088/WC/VB/22012035332079 — jamuniya samudayak bhavan rain water harveshting karye khumerkheda | Approved | 0 | 0 | 2026-06-06
JAMUNIYA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1734002088/WC/VB/22012035332084 — jamuniya sok pit nirman karye khumerkheda | Approved | 0 | 0 | 2026-06-06
HEMRA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1734002/DP/99063 — PLANTATION | Deleted | 0 | 0 | 2010-07-02
BEETALI | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1734002/DP/99139 — खेत कि मेड पर व़क्षरोपण कार्य उमरपानी सुदामा चौधरी | Completed | 165800 | 4770 | 2010-08-13 | 2013-01-25
BEETALI | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1734002/DP/99143 — खेत कि मेड पर व़क्षारोपन उमरपानी मलखनसिंह/श्रीराम अहिर | Completed | 353000 | 5086 | 2010-08-13 | 2013-01-25
BEETALI | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1734002/DP/99144 — तालाब की मेड पर व़क्षारोपन उमरपानी | Completed | 494000 | 31025 | 2010-07-23 | 2013-03-15
BEETALI | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1734002/DP/99185 — खेत की मेड पर व़क्षारोपन उमरपानी मुन्‍नालाल /जमना | Completed | 83600 | 3959 | 2010-07-25 | 2013-01-25
BEETALI | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1734002/DP/99231 — व़क्षारोपन उमरपानी सुरेश /जालम | Completed | 180000 | 10172 | 2010-07-24 | 2013-01-25
BEETALI | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1734002/DP/99232???? — Not Known1 | Completed | 0 | 1342 | 2010-08-16 | 2015-01-25
BEETALI | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1734002/DP/99232कर्य — व़क्षारोपन कार्य लक्ष्‍मी प्रसाद /जालम | Completed | 0 | 776 | 2010-08-13 | 2013-01-25
BEETALI | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1734002/DP/99237 — मेड पर व़क्षारोपन महेश /जालमसिंह उमरपानी | Completed | 212500 | 3566 | 2010-08-13 | 2013-01-25
BEETALI | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1734002/DP/99238 — मेड पर व़क्षारोपन कार्य लक्ष्‍मनसिंह /जालम गाम उमरपानी | Completed | 423500 | 14466 | 2010-08-13 | 2013-01-25
BEETALI | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1734002/DP/99239 — खेत कि मेड पर व़क्षारोपन ग्राम उमरपानी शिवदयाल /गुलाब | Completed | 236000 | 7654 | 2010-08-13 | 2013-01-25
CHHITAPAR | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1734002/DP/99240 — vraksha ropan (54/5) chitapar | Completed | 400000 | 17663 | 2010-08-16 | 2013-01-25
CHHITAPAR | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1734002/DP/99241 — vraksharopan work chitapar se linga marg par (27/1)chitapar | Completed | 491000 | 59838 | 2010-07-23 | 2013-03-15
CHHITAPAR | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1734002/DP/99243 — vraksharopan work kabristan me (53/5)chitapar | Completed | 114400 | 24384 | 2010-08-27 | 2013-01-25
CHHITAPAR | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1734002/DP/99245 — vraksharopan work srita rajesh ke khet pe (28/2)chitapar | Completed | 494000 | 5472 | 2010-08-13 | 2013-01-25
BEETALI | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1734002/DP/99246 — खेत कि मेड पर व़क्षारोपन ग्राम उमरपानी इमरतसिंह/जालम | Completed | 133000 | 6510 | 2010-07-24 | 2013-01-25
BEETALI | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1734002/DP/99247 — खेत कि मेड पर व़क्षारोपन कार्य ग्राम उमरपानी किरन बाई /महंश कोरी | Completed | 140000 | 4840 | 2010-08-13 | 2013-01-25
CHHITAPAR | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1734002/DP/99258 — vraksharopan work rajendra puri ke khet pe (29/3) chitapar | Completed | 494000 | 5672 | 2010-08-13 | 2013-01-25
BEETALI | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1734002/DP/99260 — vraksharopan work ghanshyam dubey ramlal (19/01) Raipani bitli | Completed | 131000 | 8820 | 2010-10-05 | 2013-01-25
BEETALI | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1734002/DP/99262 — vraksharopan work bitli se richa tirahe tk (48 /01 ) bitli | Completed | 491000 | 25541 | 2010-08-30 | 2013-03-15
LINGA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1734002/DP/99265 — vraksharopan work khamghat (55/01) linga | Completed | 491000 | 12700 | 2010-09-01 | 2013-01-25
BEETALI | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1734002/DP/99266 — vraksharopan work talab ki med pr(26/08) umarpani bitli | Completed | 494000 | 5285 | 2010-07-24 | 2013-03-15
BEETALI | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1734002/DP/99267aa — vraksharopan work khet ki med pr (22/04)bitli | Completed | 83600 | 1039 | 2010-07-24 | 2013-03-15
BEETALI | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Land Development / Levelling/shaping of Wasteland Land for Community | Land Development | 1734002/DP/99268 — vraksharopan work imrat singh (25/07) bitli | Completed | 133000 | 3190 | 2010-07-26 | 2013-03-15
HEMRA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1734002/DP/99306 — vrakshropan work (5/4) hemra | Completed | 499000 | 113481 | 2010-07-16 | 2013-03-31
HEMRA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1734002/DP/99307 — vraksharopan work yogesh mishra(17/5)hemra | Completed | 402000 | 22400 | 2010-09-23 | 2013-03-31
HEMRA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1734002/DP/99435 — vraksharopan work (21/09) hemra | Completed | 302000 | 6000 | 2010-11-10 | 2013-03-31
AJANSARA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1734002/DP/99444 — vraksharopan work on govt. land (ts/as-6/1) tekapa | Completed | 499000 | 111319.88 | 2010-08-04 | 2013-03-31
MADESUR | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1734002/DP/99475 — नंन्‍दन फलोउधान कार्य मडेसुर किशोरी गुप्‍ता | Completed | 299000 | 27834 | 2010-08-31 | 2013-03-15
HEMRA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1734002/DP/99476 — vraksharopan work on govt land (ts/as-5/2) bariyabhat HEMRA | Completed | 499000 | 103531.6 | 2010-07-20 | 2013-03-31
HEMRA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1734002/DP/99477 — vraksharopan work (ts/as-23/11) bariyabhat HEMRA | Completed | 499000 | 40950 | 2010-09-06 | 2013-03-31
HEMRA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1734002/DP/99478 — vraksharopan work (ts/as-24/12) bariyabhat HEMRA | Completed | 242000 | 58743.48 | 2010-10-12 | 2013-03-31
HEMRA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1734002/DP/99479 — vraksharopan work lalsahab/raghuvar prasad bramhin | Completed | 182000 | 25904 | 2010-11-01 | 2015-01-25
KHULARI | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1734002/DP/99485 — vraksharopan work on govt land (as/ts-9/1) KHULRI | Completed | 499000 | 79083.26 | 2010-08-12 | 2013-03-31
KHULARI | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1734002/DP/99486 — vraksharopan work on govt land (as/ts-10/11) KHULRI | Completed | 187000 | 13700 | 2010-08-18 | 2013-03-31
KHULARI | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1734002/DP/99492 — vraksharopan work chandrabhan/chotelal as/ts-11/3 KHULRI | Completed | 189000 | 52328 | 2010-08-17 | 2013-03-31
DUGARIYA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1734002/DP/99494 — vraksharopan work TS/AS-14/1 DODAKESLA | Completed | 499000 | 33381 | 2010-09-08 | 2013-03-31
DHADIYA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1734002/DP/99496 — vraksharopan work TS/AS-07/01 budwara DHRIYA | Completed | 199000 | 48331 | 2010-09-05 | 2013-03-31
DHADIYA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1734002/DP/99504 — vraksharopan work jagdish/mulyam (ts/as-12/2) budw | Completed | 123000 | 37564.19 | 2010-11-15 | 2013-03-31
LINGA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1734002/DP/99557 — व़क्षारोपन कार्य लिंगा छीतापार सडक | Completed | 277800 | 8650 | 2010-09-07 | 2013-01-25
SAGORIYA | 2009-2010 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Strengthening of Embankment / Construction of Embankment for community | Strengthening of Embankment | 1734002/FP/10 — वाटर शेड सगौरिया नाला सफाई एवं नाला गहरीकरण कार्य | Completed | 229000 | 35400 | 2010-03-22 | 2013-01-25
HEMRA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1734002/LD/100000hemr — mend bandhan premnarayan | Deleted | 23000 | 0 | 2010-04-01
DHILWAR | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1734002/LD/572 — ढिलवार मेढबंधान कार्य झब्‍बू/झुम्‍मकलाल किरार | Completed | 6100 | 5400 | 2010-05-27 | 2010-05-01
HEMRA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1734002/LD/5801077 — mer bandhan premnarayan 1/1 hemra chawarpatha | Deleted | 34000 | 0 | 2010-05-03
LINGA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1734002/LD/5801096 — med bandhan gayaprasad (09/04) linga | Completed | 61000 | 5600 | 2010-06-09 | 2010-06-15
LINGA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1734002/LD/5801097 — mend bandhan bhogiram (7/02) linga | Completed | 17200 | 3800 | 2010-06-02 | 2010-06-08
LINGA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1734002/LD/5801098 — med bandhan shyam / gjraj(11/5) linga | Completed | 17300 | 6300 | 2010-06-02 | 2010-06-08
SINGOTTA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1734002/LD/5801100 — med bandhan harisingh/kunjilal (18/2) singota | Completed | 12100 | 10000 | 2010-05-01 | 2010-05-15
SINGOTTA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1734002/LD/5801101 — med bandhan buddusingh /ghasiram (21/02) singota | Completed | 25700 | 25300 | 2010-06-05 | 2010-06-17
SINGOTTA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1734002/LD/5801102 — med bandhan yogendra tiwari (17/01) singota | Completed | 15000 | 13400 | 2010-04-23 | 2010-05-03
SINGOTTA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1734002/LD/5801103 — med bandhan viremdra pannlal (05/05) singota | Completed | 61000 | 5000 | 2010-06-11 | 2010-06-17
DIGSARA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1734002/WC/32 — ढिगसरा तालाब विस्‍तारीकरण कार्य | Completed | 382700 | 49556 | 2009-02-09 | 2013-03-31
DUGARIYA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1734002/WC/9993622051 — talab sfaei avam ghrikarn DUGARIYA (TS-AS/16-02) | Deleted | 0 | 0 | 2010-04-01
DUGARIYA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1734002/WC/9993622053 — TALAB GHRIKARN DUGARIYA (AS-TS/16-2) | Deleted | 0 | 0 | 2010-04-01
DUGARIYA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1734002/WC/9993622065 — TALAB GAHRIKARAN DUGARIYA(TS-AS/16/2) | Completed | 219000 | 103164 | 2010-12-25 | 2011-04-26
HEMRA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1734002/WC/9994503 — sok pit ka nirman (37/19) hemra | Completed | 128000 | 10200 | 2010-12-14 | 2010-12-29
ANDIYA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1734002/WC/9994521 — NALAGAHRIKARAN ts/as-8/1 ANDIYA | Completed | 196000 | 7100 | 2010-10-26 | 2015-01-25
CHHITAPAR | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1734002/WC/9994557 — बोरी बंधान कार्य छीतापार | Deleted | 0 | 0 | 2009-07-15
BOHANI | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Wasteland Block Plantation-Horticulture-Community / Wasteland Block Plantation of Horticulture Trees for Community | Plantation | 1734/DP/22012034491310 — नर्सरी स्‍थापना शासकीय संजय निकुंज बोहानी, विकासखण्‍ड चांवरपाठा | Completed | 5034410 | 1736712.49 | 2020-07-22 | 2026-05-29
MARRAVAN | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1734/DP/22012034533979 — बांस वृक्षारोपण कार्य स्थल महुआखेडा ग्राम पंचायत मर्रावन | Physically Completed | 1540935 | 496538.75 | 2021-08-28 | 2026-06-16
RAMPURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1734/DP/22012034533982 — बांस वृक्षारोपण कार्य स्थल रमपुरा ग्राम पंचायत रमपुरा | Physically Completed | 1540935 | 761292.75 | 2021-08-29 | 2026-06-13
RAMPURA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1734/DP/22012034558231 — बांस रोपण वन परिक्षेत्र बरमान कक्ष क्रमांक PF450 ग्राम पंचायत रमपुरा जनपद चांवरपाठा | Ongoing | 4528800 | 1207843.9 | 2022-07-21
HEMRA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1734/DP/99067 — PLANTATION GOVT.LAND 05/02 HEMRA | Deleted | 0 | 0 | 2010-04-15
HEMRA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1734/DP/99069 — Plantation govt.Land 04/01 Hamra | Deleted | 0 | 0 | 2010-06-15
HEMRA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1734/DP/99087 — Vriksharopan 05/02 Hemra | Deleted | 0 | 0 | 2010-06-15
BOHANI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1734/DP/9926693017 — Bhumi vikas karya sanjay Nikunj BOHANI AS/TS-268/4 | Deleted | 499900 | 0 | 2011-04-01
BOHANI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1734/DP/9926693018 — Gov. Plantaion Work Bohani TS/AS-443/4718 | Completed | 1004500 | 99524 | 2012-03-01 | 2015-01-28
BOHANI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1734/DP/9926693022 — शास0भूमि में व़क्षारोपण कार्य संजय निकुंज बोहानी TS 443/AS 4718 | Deleted | 1004500 | 0 | 2011-08-15
MADANPUR | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1734/DP/9926693240 — TASAR PLANTATION KHAIRUWA35 | Completed | 8126200 | 2310259 | 2012-05-01 | 2017-01-14
MADANPUR | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1734/DP/9926693241 — TASAR PLANTATION MADANPUR 16 | Completed | 3649800 | 1760837.3 | 2012-04-23 | 2017-01-14
MADANPUR | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1734/DP/9926693332 — LAND LEVELLING FENCINGAPPROCH ROAD MDANPUR 16 | Completed | 830000 | 1063884.5 | 2012-06-10 | 2015-01-23
MADANPUR | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1734/DP/9926693339 — LAND LAVELLING FENCINGAPPROCH ROAD KHAIRUWA 35 | Completed | 2047000 | 1394104.68 | 2012-06-17 | 2015-01-23
BIJOURA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1734/DP/9926693379 — बिगडे बनो का सुधार कार्य (260/1552) | Completed | 2110184 | 39864 | 2012-04-08 | 2015-01-26
MARRAVAN | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1734/DP/9926693421 — पशु अवरोधक खंती निमार्ण मर्रावन (07/1919) | Completed | 55000 | 47824 | 2012-02-23 | 2015-01-24
MARRAVAN | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1734/DP/9926693422 — पशु अवरोधक खंती निमार्ण (06/1917) | Completed | 44000 | 38430 | 2012-03-09 | 2015-01-25
KHULARI | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1734/DP/9926693697 — Plantation work shri samratsingh ,deewanbahadursingh Rajput khulari | Completed | 100000 | 15732.5 | 2012-08-16 | 2013-01-25
KHULARI | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Land Development / Levelling/shaping of Wasteland Land for Community | Land Development | 1734/DP/9926693705 — plantation work in govt land(75/14) mws khulari | Completed | 122000 | 4000 | 2012-08-18 | 2013-03-31
BIJOURA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Forest Protection / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1734/DP/9926694117 — vigre banu ka shudhar work p-397 (260/1552) | Completed | 510000 | 77130 | 2012-07-07 | 2015-01-26
HEMRA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1734/DP/9926695076 — PLANTATION GRAM BADIYAGHAT | Deleted | 0 | 0 | 2012-04-01
HEMRA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1734/LD/100000 — medbanhan 01/01Hamra | Deleted | 0 | 0 | 2010-04-05
HEMRA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1734/LD/100000a — mend bandhan premnarayan 1/1 hemra | Deleted | 0 | 0 | 2010-04-01
BOHANI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1734/LD/3799381787 — Bhumi vikas karya saskiya sanjaya nikunj BOHANI | Completed | 499000 | 52840 | 2012-01-23 | 2015-01-28
ANDIYA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1734/LD/3799382000 — Mead Bandhan Gajraj /nathulal (63/08) mws andia | Deleted | 25000 | 0 | 2012-04-01
ANDIYA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1734/LD/3799382003 — Mead Bandha 29/07/ mws andia | Completed | 50000 | 19536 | 2012-06-08 | 2013-01-25
AJANSARA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1734/LD/3799382004 — Plantation work shri Harishankar/ Premlal 78/09 mws tekapar (ajansara) | Completed | 123000 | 14784 | 2012-09-24 | 2013-01-25
BEETALI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1734/LD/3799382005 — Mead Bandhan shri Rishiram/jaynarayan 86/08 mws be | Completed | 11000 | 5124 | 2011-06-10 | 2011-06-25
BEETALI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1734/LD/3799382006 — Pralad/sitaram (85/07) mead Bandhan work mws beet | Completed | 61000 | 2684 | 2011-06-10 | 2011-06-28
MADESUR | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1734/LD/3799382011 — mead Bandhan shyam bai/balprasad | Completed | 45000 | 9028 | 2011-06-11 | 2011-06-29
MADESUR | 2011-2012 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1734/LD/3799382012 — Mead Bandhan Shankarsingh/narmada 75/04 mws madesur | Completed | 27500 | 10126 | 2011-06-11 | 2011-06-29
DEORI | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Bitumen Top / Construction of Bitumen Top Roads for Community | Construction of Road and Culvert | 1734/RC/22012034152567 — Deori to Chilka (Upgration) | Completed | 4858000 | 1935970 | 2011-03-25 | 2014-03-29
NAINWARA | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Bitumen Top / Construction of Bitumen Top Roads for Community | Construction of Road and Culvert | 1734/RC/22012034152569 — Tendukheda (Dobhi) to Nainwara (Upgradation) | Completed | 3135000 | 2197848.3 | 2010-12-18 | 2013-12-05
GUNDRAI | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Bitumen Top / Construction of Bitumen Top Roads for Community | Construction of Road and Culvert | 1734/RC/22012034152570 — Mehgunwa to Chouki | Completed | 1306000 | 22082 | 2011-03-08 | 2013-12-05
GUNDRAI | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Bitumen Top / Construction of Bitumen Top Roads for Community | Construction of Road and Culvert | 1734/RC/22012034152572 — Aawariya to Jagannathpur | Completed | 2318000 | 322412.1 | 2011-02-14 | 2013-12-05
BILTHARI | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Bitumen Top / Construction of Bitumen Top Roads for Community | Construction of Road and Culvert | 1734/RC/22012034152573 — Bilthari to Kathai | Completed | 2425000 | 15860 | 2011-01-27 | 2013-12-05
GUNDRAI | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Bitumen Top / Construction of Bitumen Top Roads for Community | Construction of Road and Culvert | 1734/RC/22012034152575 — Gundrai to Khairi | Completed | 3277000 | 1074991.2 | 2011-03-01 | 2013-12-05
KARHAIYA | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Bitumen Top / Construction of Bitumen Top Roads for Community | Construction of Road and Culvert | 1734/RC/22012034152577 — Barha to Jhiri | Completed | 948000 | 657866.2 | 2011-04-04 | 2013-12-05
BOHANI | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1734/RC/22012034154657 — Cause Way Cum Rapta Nirman Sanjay Nikunj Bohani | Completed | 1758300 | 281028 | 2012-06-20 | 2015-01-28
KOUDIYA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1734/RC/22012034154664 — SC Ward marg Puliya Nirman vill Koudiya | Completed | 246400 | 70488 | 2012-04-22 | 2015-01-28
GUNDRAI | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Repair & maint of Gravel Road Roads for Comm / Repair and maintenance of Gravel Road Roads for Community | Repair & maint of Road | 1734/RC/22012034609366 — ग्रेवल मार्ग मरम्‍मत कार्य जीएसबी सडक महगवा से चौक Periodical Regravelling / Periodical Maintenacne | Completed | 385000 | 348089.72 | 2022-05-20 | 2023-10-07
KARHAIYA(KORAI) | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Repair & maint of Gravel Road Roads for Comm / Repair and maintenance of Gravel Road Roads for Community | Repair & maint of Road | 1734/RC/22012034609511 — ग्रेवल मार्ग मरम्‍मत कार्य करहैया सलैया से कोरई Periodical Regravelling / Periodical Maintenacne | Completed | 594000 | 346239 | 2022-05-20 | 2023-10-07
GUNDRAI | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Bitumen Top / Construction of Bitumen Top Roads for Community | Construction of Road and Culvert | 1734/RC/AG/100000 — आंवरिया से गुदरई मार्ग 25/1113/C | Completed | 4244000 | 1518068.7 | 2010-12-13 | 2013-12-05
IMJHIRA | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Bitumen Top / Construction of Bitumen Top Roads for Community | Construction of Road and Culvert | 1734/RC/IM/100000 — तेदूखेडा रोड से उमाहा मार्ग 48/91 | Completed | 1248000 | 325743.2 | 2010-12-08 | 2013-12-05
NAINWARA | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Bitumen Top / Construction of Bitumen Top Roads for Community | Construction of Road and Culvert | 1734/RC/TK/100000 — तेदुखेडा से खैरी खुर्द सडक निर्माण 46/85 | Completed | 2863000 | 1089264.6 | 2010-11-19 | 2013-12-05
SAGORIYA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1734/WC/9993623352 — shokpit kusmi TS/AS-43/01 | Completed | 128000 | 260166.05 | 2011-02-01 | 2013-03-31
DUGARIYA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1734/WC/9993623353 — shikpit dodakesla TS/As-52/05 | Completed | 128000 | 23668 | 2011-04-05 | 2013-01-25
DHADIYA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1734/WC/9993623364 — shokpit budhvara TS/AS-42/04 | Completed | 80000 | 101600 | 2011-01-01 | 2011-07-15
ANDIYA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1734/WC/9993623412 — nala sfaighrikaran TS/AS-05/02 | Completed | 78500 | 43600 | 2010-12-28 | 2013-03-31
ANDIYA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1734/WC/9993623413 — shokpit andiya TS/AS-36/05 | Deleted | 96000 | 0 | 2010-09-22
ANDIYA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Mini Percolation Tank / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1734/WC/9993623414 — sokpit andiya TS/AS-36/05 | Completed | 96000 | 52248 | 2011-04-03 | 2013-01-25
ANDIYA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1734/WC/9993623415 — bori bandhan andiya TS/AS-32/02 | Completed | 72000 | 7700 | 2010-12-15 | 2013-01-25
AJANSARA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1734/WC/9993623736 — Nala sfaei ghrikaran TS/AS-41/03 | Deleted | 500000 | 0 | 2010-04-04
AJANSARA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1734/WC/9993623737 — Nala ghrikaran TS/AS-41/03 | Deleted | 500000 | 0 | 2010-10-14
AJANSARA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1734/WC/9993623754 — Nala sfaei and ghrikaran TS/As-41/03 | Deleted | 500000 | 0 | 2010-10-14
AJANSARA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1734/WC/9993623755 — Nala safei ghrikarna TS/AS-41/03 | Deleted | 500000 | 0 | 2010-10-14
AJANSARA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1734/WC/9993623756 — Nala sfaieghrikaranTS/AS-41/03 | Completed | 500000 | 162938 | 2010-12-03 | 2013-03-31
AJANSARA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1734/WC/9993623757 — Kunda-Kundi ka nirmad TS/AS-40-02 | Completed | 500000 | 8400 | 2010-12-14 | 2010-12-26
SAGORIYA | 2011-2012 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1734/WC/9993625878 — Bori Bandhan work 2/1 mws sagoriya | Completed | 30000 | 10000 | 2011-04-04 | 2011-04-04
ANDIYA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1734/WC/9993628922 — बोरीबंधान अंडिया ( 68/07 ) mwss | Completed | 50000 | 43104 | 2012-09-10 | 2013-03-31
AJANSARA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Stop Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1734/WC/9993629986 — बोरी बंघान टेकापार 81/10 | Completed | 20000 | 9504 | 2012-11-18 | 2013-03-31
BHORJHIR | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | AWC / Construction of Anganwadi Building for Community | Constr of Aganwadi | /AV/5945 — आँगनबाड़ी भवन निर्माण कार्य ग्राम भौंरझिर-2 | Deleted | 0 | 0 | 2016-08-15
RAMPURA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | N.H.R.J व्रक्षरोपण कार्य173434002229/DP/45 — N.H.R.J रम्‍पुरा व़क्षारोपण कार्य | Completed | 155000 | 11455 | 2008-08-03 | 2013-03-31
AJANSARA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | अजसरा से सिहाेरा मेढ् तक सड्क के दो1734002081/DP/1 — अजसरा से सिहाेरा मेढ् तक सड्क के दोनो ओर व़क्षारोपण | Completed | 292000 | 22563 | 2008-04-07 | 2008-01-01
KHAIRI | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | खेरीकला म‍टटी मुरम बजरा कार्य 1734002023/RC/32 — खेरीकला म‍टटी मुरम बजरा कार्य | Completed | 496200 | 44528 | 2008-04-07 | 2008-03-01
GANGAI | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | गंगई नं‍दन फलोधान कार्य लच्‍छू/1734002034/DP/59 — गंगई नं‍दन फलोधान कार्य लच्‍छू | Completed | 155000 | 54593 | 2008-07-03 | 2008-03-01
GANGAI | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | गंगई नं‍दन फलोधान कार्य हनुमत सि‍ह1734002034/DP/58 — गंगई नं‍दन फलोधान कार्य हनुमत सि‍हं | Completed | 155000 | 26078 | 2008-08-09 | 2008-03-01
GANGAI | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | गंगई मेड बधांन कार्य/1734002034/LD/8 — गंगई चन्‍द्रभान/नारायण मेड बधांन कार्य | Deleted | 29822 | 0 | 2008-05-10
GANGAI | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | गंगई मेड बधान कार्य 1734002034/LD/9 — गंगई मेड बधान कार्य | Deleted | 29800 | 2080 | 2008-05-03
GANGAI | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | गंगई मेड बंधान कार्य कैलाश/पुरनसिंग1734002034/WC/5 — गंगई मेडबंधान कार्य कैलाश/पुरनसिंग लोधी | Deleted | 34000 | 10704 | 2008-05-03
GUTORI | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | गुटोरी व़क्षारोपण कार्य 1734002010/DP/61 — गुटोरी व़क्षारोपण कार्य | Deleted | 117000 | 3600 | 2008-08-20
GUTORI | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Forest Protection / Block Plantation of Forestry Trees in Fields for Community | Plantation | गुटौरी N.H 12 सड्क के दानो ओर व़क्1734002010/DP/60 — गुटौरी N.H 12 सड्क के दानो ओर व़क्षारोपण | Deleted | 472000 | 5360 | 2008-08-30
GHAGHROLA KALAN | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | घघरोला कला‍ मटटी मुरम बजरा सड्क1734002047/RC/61 — घघरोला कला‍ मटटी मुरम बजरा सड्क | Completed | 498000 | 391368.93 | 2008-05-31 | 2012-03-07
DHILWAR | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | ढिलवार नर्सरी कार्य रेशम विभाग1734002002/DP/12 — ढिलवार नर्सरी कार्य रेशम विभाग | Completed | 1568000 | 1090121 | 2008-04-29 | 2011-11-19
DEORI | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Flood Control and Protection | Cross Bund / Construction of Earthen graded Bund for Community | Works for Flood Control and Protection | देवरी नाला निर्माण गा्म 1734002009/FP/1 — देवरी नाला निर्माण गा्म के बा‍हर नाला सं एन एच 12 तक | Completed | 106000 | 56172 | 2008-04-01 | 2009-04-11
NAINWARA | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नं‍दन फलोधान कार्य कढोरी इन्‍दर स1734002043/DP/55 — नैनवारा नं‍दन फलोधान कार्य कढोरी इन्‍दर सि‍हं | Deleted | 155000 | 0 | 2008-03-01
GANGAI | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नं‍दन फलोधान कार्य कढोरी इन्‍दर स 1734002043/DP/56 — गंगई नं‍दन फलोधान कार्य राजकुमार /सीताराम | Deleted | 155000 | 2485 | 2008-08-20
RAMPURA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नदंन वन कार्य शम्‍भू ठाकर1734002004/DP/45 — नदंन वन कार्य शम्‍भू ठाकर | Deleted | 155000 | 0 | 2008-08-07
BIKOR | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | नवीन तालाब निर्माण बिकोर1734002038/WC/1 — बिकोर नवीन तालाब निर्माण बिकोर | Deleted | 483000 | 2606 | 2008-04-01
NAINWARA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नैनवारा नं‍दन फलोधान कार्य दयांशकर1734002043/DP/53 — नैनवारा नं‍दन फलोधान कार्य दयांशकर | Completed | 155000 | 20345 | 2008-08-04 | 2013-03-31
NAINWARA | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | नैनवारा नं‍दन फलोधान कार्य सुम‍िय1734002043/DP/54 — नैनवारा नं‍दन फलोधान कार्य सुम‍िया बाई | Deleted | 155000 | 0 | 2008-03-01
BHANSKHEDA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Forest Protection / Block Plantation of Forestry Trees in Fields for Community | Plantation | बासखेड्ा नंदन फलोधान कल्‍लूदास /सुम1734002084/DP/8 — बासखेड्ा नंदन फलोधान कल्‍लूदास /सुम्‍मेर | Completed | 85000 | 5374 | 2008-07-14 | 2008-01-02
BHANSKHEDA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | बासखेड्ा नंदन फलोधान चरनदास/सुम्‍मे1734002084/DP/4 — बासखेड्ा नंदन फलोधान चरनदास/सुम्‍मेर | Deleted | 92000 | 7971 | 2008-07-14
BHANSKHEDA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | बासखेड्ा नंदन फलोधान परश्षोत्‍तम मे1734002084/DP/3 — बासखेड्ा नंदन फलोधान परश्षोत्‍तम मेहरा | Deleted | 495000 | 11610 | 2008-07-07
BHANSKHEDA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | बासखेड्ा नंदन फलोधान हरनारायण /झलकन1734002084/DP/6 — बासखेड्ा नंदन फलोधान हरनारायण /झलकन | Completed | 64000 | 4379 | 2008-07-14 | 2008-01-02
BEETALI | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | बितली व्रक्षारोपण कार्य ग्राम रायपा1734002061/DP/9 — बितली व्रक्षारोपण कार्य ग्राम रायपानी | Deleted | 128600 | 5000 | 2008-08-04
MADESUR | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | मडेसूनन्‍दन फलोधान कार्य नन्‍हेवीर1734002064/DP/33 — मडेसूर नन्‍दन फलोधान कार्य नन्‍हेवीर | Deleted | 0 | 0 | 2008-03-01
MADESUR | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | मडेसूनन्‍दन फलोधान कार्य नन्‍हेवीर1734002064/DP/34 — मडेसूर नन्‍दन फलोधान कार्य नन्‍हेवीर | Completed | 68000 | 6045 | 2008-08-22 | 2008-03-01
SIMARIYA KANLA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | मडेसूर नन्‍दन फलोधान कार्य 1734002033/DP/35 — सिमरियाकला नन्‍दन फलोधान कार्य अशोक/राधेलाल | Completed | 126000 | 16923 | 2008-07-08 | 2008-03-01
MADANPUR | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | मदनपुर ज्ञानी बडेवीर केनिजी खेत नं1734002017/DP/28 — मदनपुर ज्ञानी बडेवीर केनिजी खेतमे नंदन फलो उधान कार्य | Completed | 97000 | 3715 | 2008-08-03 | 2008-03-01
MADANPUR | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | मदनपुर नदंन फलोधान गोविंद/मुंशीलाल1734002017/DP/25 — मदनपुर नदंन फलोधान गोविंद/मुंशी लाल | Completed | 47000 | 21797 | 2008-08-01 | 2013-12-06
MADANPUR | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | मदनपुर नदंन फलोधानपूरनलाल/धन्‍नूलल1734002017/DP/25 — मदनपुर नदंन फलोधान पूरनलाल/धन्‍नूलाल | Deleted | 0 | 0 | 2007-10-25
MADANPUR | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | मदनपुर नदंन फलोधानपूरनलाल/धन्‍नूलल1734002017/DP/26 — मदनपुर नदंन फलोधान पूरनलाल/धन्‍नूलाल | Completed | 155600 | 9105 | 2008-08-01 | 2007-10-25
SINGOTTA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | मदनपुर व़क्षारोपण खेरूआ से 1734002017/DP/27 — सिगोटा तालाब निर्माण्‍ा कार्य | Completed | 483000 | 114746 | 2008-04-07 | 2011-06-13
MADANPUR | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | मदनपूर नदंन फलोधान कार्य सुल्‍तान 1734002017/DP/42 — मदनपूर नदंन फलोधान कार्य सुल्‍तान | Deleted | 155000 | 0 | 2008-07-29
MANKAPUR | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | मनकापुर मेड् बधान प्रकाश /देबी सिंह1734002036/LD/4 — मनकापुर मेड् बधान प्रकाश /देबी सिंह | Deleted | 10560 | 0 | 2008-04-28
MARRAVAN | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | मर्रावन मिटटी मुरम बजरा सडक 1734002001/RC/42 — मर्रावन मिटटी मुरम बजरा सडक निर्माण कार्य | Completed | 499200 | 130561 | 2008-04-01 | 2013-03-31
MEHGUWAN (GUNVE) | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | महगंवा गुनवे मेड बंधान करनसिंह/तोडल1734002053/LD/6 — महगंवा गुनवे मेड बंधान करनसिंह/तोडल मेहरा | Completed | 36000 | 26042 | 2008-06-13 | 2008-01-02
MEHGUWAN (GUNVE) | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | महगंवा गुनवे मेड्बंधान हेमराज/रधुवर1734002053/LD/5 — महगंवा गुनवे मेड्बंधान हेमराज/रधुवर | Deleted | 30300 | 0 | 2008-06-13
MEHGUNVA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | म‍िहगवां1734002028/DP/43 — म‍िहगवां व्रक्षारोपण कार्य | Completed | 155000 | 19291 | 2008-08-22 | 2013-03-31
RAMPURA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | रम्‍मपुरा नंदन वन राजू /कढ्ोरी 1734002004/DP/7 — रम्‍मपुरा नंदन वन राजू /कढ्ोरी | Completed | 63000 | 4190 | 2008-08-10 | 2014-03-19
LOLARI | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | लोलरी मिटटी मुरम बजरा सड्क तालाब स1734002025/RC/37 — लोलरी मिटटी मुरम बजरा सड्क तालाब से सुपले के घ्‍र | Deleted | 491000 | 1500 | 2008-04-02
LOLARI | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | लोलरी व्रक्षारोपण कार्य1734002025/DP/44 — लोलरी व्रक्षारोपण कार्य | Deleted | 155000 | 6500 | 2008-08-18