MANDLA / GHUGHRI / SUREHLI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1735007/WC/1345 — Ket talab karya telahndeh Mudda singh / Ghuha | Completed | 0 | 20880 | 2012-06-15 - 2016-09-13
MANDLA / GHUGHRI / KUSMI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1735007/WC/1346 — Stop dem kary Kushmi CARD Bahra nala | Completed | 0 | 262154 | 2012-04-21 - 2015-06-30
MANDLA / GHUGHRI / SUREHLI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Mini Percolation tank / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1735007/WC/1381 — cpt MAHADEV /GALIRAM surehli (card) | Completed | 0 | 6344 | 2012-03-18 - 2012-03-24
MANDLA / GHUGHRI / CHHATARPUR | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1735007/WC/1387 — khata taliaba /nana shaing / dhanuan/ card / garam chatapur | Completed | 0 | 0 | 2008-03-22 - 2009-02-22
MANDLA / GHUGHRI / JUNWANI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Micro Irrigation Works | Lining of minor Canal for Community / Lining of minor Canal for Community | Lining of Canal | 1735007/WC/22012034547841 — Junwani Jalashay Nahar Lining Karya | Completed | 7682000 | 7377544.82 | 2020-05-17 - 2026-02-04
MANDLA / GHUGHRI / TIKARIYA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1735007/WC/461 — मरघट नाला गली प्‍लग मागा | Completed | 24000 | 16951 | 2008-02-25 - 2010-08-28
MANDLA / GHUGHRI / SINGHANPURI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1735007/WC/463 — खेततालाब निर्माण कार्य दवलसिंह/गज्‍जू | Completed | 12931 | 12931 | 2008-09-22 - 2010-03-11
MANDLA / GHUGHRI / PARASWAH | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1735007/WC/638 — उमरनाला स्‍टोरेज निर्माण कठईडीह परसवाह | Completed | 2893000 | 4247711.8 | 2009-05-20 - 2010-12-25
MANDLA / GHUGHRI / BHAINSAWAHI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1735007/WC/641 — नरबदा नाला स्‍टोरेज भैसवाही 6/10 | Completed | 5390330 | 461560 | 2010-05-02 - 2016-09-13
MANDLA / GHUGHRI / DULADAR | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1735007/WC/642 — स्‍टापडेम निर्माण कार्य स्‍टोरेज दुलादर 5/10 | Completed | 0 | 0 | 2009-10-28 - 2016-04-05
MANDLA / GHUGHRI / DULADAR | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1735007/WC/643 — स्‍टापडेम निर्माण कार्य स्‍टोरेज दुलादर 5/10 | Completed | 359963 | 4887496.61 | 2010-01-26 - 2016-08-12
MANDLA / GHUGHRI / BHAINSAWAHI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1735007/WC/648 — रायजला स्‍टोरेज भैसवाही | Completed | 4974000 | 8012041.2 | 2010-02-12 - 2016-09-13
MANDLA / GHUGHRI / GAJRAJ | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1735007/WC/649 — गजराज स्‍टोरेज जल संसाधन निवास | Completed | 4890000 | 6551238 | 2010-01-30 - 2016-08-28
MANDLA / GHUGHRI / BILGAON | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1735007/WC/650 — बिसांधर स्‍टोरेड जल संसाधन वि भाग | Completed | 4993000 | 5665825.5 | 2010-01-02 - 2016-08-14
MANDLA / GHUGHRI / GHOREGHAT | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1735007/WC/651 — घारेघाट स्‍टोरेज जल संसाधन वि भाग | Completed | 4974000 | 4984976 | 2009-12-21 - 2016-08-13
MANDLA / GHUGHRI / EMLITOLA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1735007/WC/652 — इमली टोला स्‍टोरेल जल संसाधन वि भाग | Completed | 4170000 | 5184928 | 2009-12-12 - 2016-08-14
MANDLA / GHUGHRI / BANIYA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1735007/WC/735 — बनिया स्‍टापडेम 4/10 | Completed | 351000 | 317950 | 2010-02-21 - 2015-06-30
MANDLA / GHUGHRI / BARWANI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1735007/WC/736 — जमुनाही स्‍टाप डेम 8/10 बरवानी | Completed | 4956000 | 109800 | 2010-05-09 - 2016-08-13
MANDLA / GHUGHRI / DONGAR MANDLA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1735007/WC/737 — आर एम एस स्‍टाप डेम डोगर मंडला | Completed | 2134000 | 547494 | 2009-12-02 - 2016-04-05
MANDLA / GHUGHRI / SINGHANPURI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1735007/WC/760 pft — चेकडेम अधन नाला बधान निमार्ण कार्य पी एफ टी वि भाग पददीकोन्‍हा | Completed | 0 | 0 | 2007-07-17 - 2010-03-11
MANDLA / GHUGHRI / SINGHANPURI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1735007/WC/760pft — चेकडेम अधन नाला बधान निमार्ण कार्य पी एफ टी वि भाग पददीकोन्‍हा | Completed | 0 | 0 | 2007-07-17 - 2010-03-11
MANDLA / GHUGHRI / SINGHANPURI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1735007/WC/761 pft — चेकडेम अधन नाला बधान निमार्ण कार्य पी एफ टी वि भाग पददीकोन्‍हा | Completed | 15000 | 0 | 2008-02-06 - 2010-03-11
MANDLA / GHUGHRI / SINGHANPURI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1735007/WC/762 pft — सी पी डब्‍लू निमार्ण कार्य पी एफ टी वि भाग पददीकोन्‍हा | Completed | 178000 | 0 | 2008-02-06 - 2010-03-11
MANDLA / GHUGHRI / KISLI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1735007/WC/775 — कून निर्माण कार्य सैन्‍दवारा रामप्रसाद/मोतीलाल किसली | Completed | 54200 | 103345 | 2010-05-12 - 2010-03-11
MANDLA / GHUGHRI / DUNDADEHI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1735007/WC/785 — कूप निर्माण कार्य बीरबलदास/प्रेमलाल डूण्‍डादेई | Completed | 106180 | 70095 | 2009-04-11 - 2012-02-15
MANDLA / GHUGHRI / DUNDADEHI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1735007/WC/786 — कूप निर्माण कार्य सुकलाल/ प्रेमसिंह डूण्‍डादेई | Completed | 91249 | 82235 | 2009-04-01 - 2010-03-11
MANDLA / GHUGHRI / DUNDADEHI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1735007/WC/787 — कूप निर्माण कार्य पतंनू/कारेलाल डूण्‍डादेई | Completed | 109900 | 130033 | 2009-11-09 - 2010-03-11
MANDLA / GHUGHRI / DUNDADEHI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1735007/WC/791 — ग्रेबियन निमार्ण कार्य डुडादेही | Completed | 15835 | 42145 | 2010-03-13 - 2010-03-11
MANDLA / GHUGHRI / DUNDADEHI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1735007/WC/792 — ग्रेबियन निमार्ण कार्य सिगराम /धानू डुडादेही | Completed | 16335 | 12090 | 2010-03-20 - 2010-03-11
MANDLA / GHUGHRI / DUNDADEHI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1735007/WC/793 — ग्रेबियन निमार्ण कार्य कुमार डुडादेही | Completed | 15890 | 51020 | 2010-05-20 - 2010-03-11
MANDLA / GHUGHRI / KHODAKHUDRA N | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1735007/WC/794 — ग्रेबियन निमार्ण कार्य महली | Completed | 13460 | 58060 | 2010-03-12 - 2010-03-11
MANDLA / GHUGHRI / CHHATARPUR | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Mini Percolation tank / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1735007/WC/893 — nala bandhan | Completed | 93000 | 100743 | 2011-01-27 - 2011-08-25
MANDLA / GHUGHRI / CHHATARPUR | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1735007/WC/898 — स्‍टाप डेम निमार्ण कार्य छतरपुर | Completed | 11880 | 244668 | 2011-01-30 - 2011-08-24
MANDLA / GHUGHRI / TIKARIYA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1735007/WC/906 — स्‍टाप डेम निमार्ण कार्य ग्राम टिकरिया | Completed | 12500 | 248078 | 2011-01-22 - 2011-08-19
MANDLA / GHUGHRI / CHHATARPUR | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1735007/WC/984 — koop nirman karya GENDABAI/ BUDHSIH chhatarour | Completed | 0 | 123295 | 2011-04-02 - 2011-08-24
MANDLA / GHUGHRI / MANAGA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1735007/WC/985 — koop nirman MALSA \ AKLU gwara | Completed | 0 | 126950 | 2011-04-01 - 2011-08-11
MANDLA / GHUGHRI / DONGAR MANDLA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1735007/WC/986 — koop nirman PREMLAL \ CHAMRA katangi | Completed | 0 | 131954 | 2011-04-05 - 2011-09-30
MANDLA / GHUGHRI / CHHATARPUR | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1735007/WC/987 — koop nirman BHOLA \ GULJAR | Completed | 0 | 118732 | 2011-05-09 - 2011-08-24
MANDLA / GHUGHRI / MANAGA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1735007/WC/988 — STOP DEM G.L. TIKARIYA | Completed | 0 | 286701.4 | 2011-01-12 - 2011-08-19
MANDLA / GHUGHRI / TIKARIYA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1735007/WC/989 — KOOP NIRMAN NANKOBAI \ THANSING TIKARIYA | Completed | 0 | 131964 | 2011-04-03 - 2011-08-19
MANDLA / GHUGHRI / CHHATARPUR | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1735007/WC/990 — KOOP NIRMAN KOSALYA \ JHADUDAS KANDRA | Completed | 0 | 112515 | 2011-04-02 - 2011-07-29
MANDLA / GHUGHRI / KHAMARIYA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Gully Plug / Construction of Earthen Gully Plugs for Community | Boulder Check/Gully Plug | 1735007/WC/991 — gully plug/baratu/samva/kaknu/khamhariya | Completed | 0 | 14616 | 2011-12-01 - 2012-02-02
MANDLA / GHUGHRI / GAJRAJ | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1735007/WC/992 — STOP DEM NIRMAN GOVT.LND PIPARDON | Completed | 0 | 252373.4 | 2011-03-29 - 2011-10-15
MANDLA / GHUGHRI / GAJRAJ | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1735007/WC/993 — koop nirman karya AMRIT \ MANWAR pipardon | Completed | 0 | 115283 | 2011-05-21 - 2011-10-15
MANDLA / GHUGHRI / GAJRAJ | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1735007/WC/994 — nala bandhan SUKHRU \ BALKU pipardon | Completed | 0 | 92818 | 2011-05-22 - 2011-09-01
MANDLA / GHUGHRI / MANAGA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1735007/WC/995 — NALA BANDHAN SUDDHU \ MULWA MANGA | Completed | 0 | 46238 | 2011-05-26 - 2011-08-25
MANDLA / GHUGHRI / KHAMARIYA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Gully Plug / Construction of Earthen Gully Plugs for Community | Boulder Check/Gully Plug | 1735007/WC/996 — GALI PLAG GOVT. LAND | Completed | 0 | 137696 | 2011-11-08 - 2011-12-27
MANDLA / GHUGHRI / CHHATARPUR | D--RURAL INFRASTUCTURE / Renovation of traditional water bodies | Strengthening of Embankment / Construction of Embankment for community | Renovation of traditional water bodies | 1735007/WH/1 — KOOP MARAMMAT GOVT.LND KANDRA | Completed | 0 | 16946 | 2011-06-15 - 2011-07-29
MANDLA / GHUGHRI / CHHATARPUR | D--RURAL INFRASTUCTURE / Renovation of traditional water bodies | Strengthening of Embankment / Construction of Embankment for community | Renovation of traditional water bodies | 1735007/WH/2 — KOOP MARAMMAT SIVLAL \ NANDU KANDRA | Completed | 0 | 11175 | 2011-07-05 - 2011-04-11
MANDLA / GHUGHRI / GAJRAJ | D--RURAL INFRASTUCTURE / Renovation of traditional water bodies | Strengthening of Embankment / Construction of Embankment for community | Renovation of traditional water bodies | 1735007/WH/3 — KOOP MARAMMAT JIYA LAL \ NAVALSIGH | Completed | 0 | 8976 | 2011-04-01 - 2011-05-07
MANDLA / GHUGHRI / MANAGA | D--RURAL INFRASTUCTURE / Renovation of traditional water bodies | Strengthening of Embankment / Construction of Embankment for community | Renovation of traditional water bodies | 1735007/WH/4 — KOOP MARAMMAT GOVT. LND. MANGA | Completed | 4850 | 4850 | 2011-04-28 - 2011-04-25
MANDLA / GHUGHRI / CHHATARPUR | D--RURAL INFRASTUCTURE / Renovation of traditional water bodies | Strengthening of Embankment / Construction of Embankment for community | Renovation of traditional water bodies | 1735007/WH/5 — KOOP MARAMMAT PRTAP \ INDAR CHHATARPUR | Completed | 0 | 10925 | 2011-04-05 - 2011-04-11
MANDLA / GHUGHRI / GAJRAJ | D--RURAL INFRASTUCTURE / Renovation of traditional water bodies | Strengthening of Embankment / Construction of Embankment for community | Renovation of traditional water bodies | 1735007/WH/6 — KOOP MARAMMAT GOVT. LND PIPARDON | Completed | 0 | 16961 | 2011-04-03 - 2011-05-18
MANDLA / GHUGHRI / GAJRAJ | D--RURAL INFRASTUCTURE / Renovation of traditional water bodies | Strengthening of Embankment / Construction of Embankment for community | Renovation of traditional water bodies | 1735007/WH/7 — KOOP MARAMMAT MUNIYA \ KALIRAM PIPARDON | Completed | 0 | 17000 | 2011-06-02 - 2011-09-01
MANDLA / GHUGHRI / GHUGARI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1735007/घुघरी/IF-1 — कपिलधारा कुप निर्माण कार्य सुदामा/रामजी | Completed | 12000 | 94179 | 2008-04-06 - 2008-07-29
MANDLA / GHUGHRI / NAHARBELI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1735007/नाहरवेलीWC/22 — कूप निर्माण मिहीलाल बीरन | Completed | 13200 | 63545 | 2008-02-23 - 2010-03-22
MANDLA / GHUGHRI / DONGAR MANDLA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1735/LD/3799381507 — CPT/CPW | Completed | 200000 | 46911 | 2011-09-21 - 2015-06-30
MANDLA / GHUGHRI / DHENKO | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1735/LD/3799381508 — CPT/CPW | Completed | 216000 | 37151 | 2011-10-03 - 2011-11-25
MANDLA / GHUGHRI / KUNTIDADARGAON | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1735/LD/3799381509 — CPT/CPW | Completed | 298000 | 70457 | 2011-10-15 - 2016-08-13
MANDLA / GHUGHRI / CHURIYA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1735/LD/3799381510 — CPT/CPW | Completed | 225000 | 51425 | 2011-10-17 - 2016-08-13
MANDLA / GHUGHRI / SINGHANPURI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1735/LD/3799381511 — CPT/CPW | Completed | 306000 | 4455 | 2011-11-21 - 2016-08-12
MANDLA / GHUGHRI / NAHARBELI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1735/LD/3799381512 — CPT/CPW | Completed | 308000 | 74971 | 2011-09-16 - 2016-08-13
MANDLA / GHUGHRI / TABALPANI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1735/LD/3799381513 — CPT/CPW | Completed | 305000 | 57525 | 2011-09-20 - 2016-08-13
MANDLA / GHUGHRI / PARASWAH | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1735/LD/3799381514 — CPT/CPW | Completed | 202000 | 44837 | 2011-09-19 - 2016-08-13
MANDLA / GHUGHRI / SALWAH | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1735/LD/3799381515 — CPT/CPW | Completed | 199000 | 37761 | 2011-10-09 - 2016-08-12
MANDLA / GHUGHRI / GHUGARI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1735/LD/3799381521 — CPT/CPW | Completed | 309000 | 64174 | 2011-09-19 - 2016-08-13
MANDLA / GHUGHRI / BAMAHANI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1735/LD/3799381939 — Tusser Plantation | Completed | 2106000 | 626319 | 2012-05-09 - 2016-08-12
MANDLA / GHUGHRI / DHENKO | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1735/RC/22012034584207 — Gravel Road Nirman Chitrahi se Bodhatola | Completed | 2319000 | 1822309 | 2021-10-14 - 2025-11-28
MANDLA / GHUGHRI / KUNTIDADARGAON | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1735/RC/22012034584336 — Gravel Road Nirman Chhapartola se Kewlari Tola Kunti Dadargaon tak | Completed | 2427000 | 1677929.09 | 2021-10-22 - 2026-01-24
MANDLA / GHUGHRI / BHAINSAWAHI | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1735/RC/22012034607717 — Gravel Road Nirman Work Bhainsvahi to Pipraha tola tak | Completed | 5534000 | 3093398.17 | 2022-04-04 - 2025-12-22
MANDLA / GHUGHRI / KHAJRI | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1735/RC/22012034608062 — Gravel Road Nirman Mukhya Marg To Anganwadi Bhavan Chandali Tola | Completed | 2794000 | 2417735.88 | 2022-04-13 - 2024-11-17
MANDLA / GHUGHRI / JUNWANI | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1735/RC/22012034612102 — GRAVEL ROAD NIRMAN JAISINGH KE GHAR SE HARILAL KE GHAR TAK | Completed | 3534000 | 2648927.45 | 2022-04-26 - 2024-11-17
MANDLA / GHUGHRI / SAHJAR | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Land Development / Levelling/shaping of Wasteland Land for Community | Land Development | सहजर1735007014/DP/-03 — पटपर घाट कमकोनाला में अस्‍थाई बोरीबांध | Completed | 4930 | 1955 | 2008-04-20 - 2009-04-12
MANDLA / GHUGHRI / SAHJAR | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Land Development / Levelling/shaping of Wasteland Land for Community | Land Development | सहजर1735007014/DP/-04 — अस्‍थाई बोरी बांध आमाघाट बरनाला | Completed | 4930 | 6375 | 2008-04-20 - 2009-04-12
MANDLA / GHUGHRI / SAHJAR | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Flood Control and Protection | Desilting / Renovation of Community Water Harvesting Ponds for Community | Deepening / Desilting of Flood Channels | सहजर1735007014/FP/-05 — अस्‍थाई बोरी बांध घुघरा घाट बरनाला | Completed | 4845 | 5440 | 2008-04-23 - 2010-04-12
MANDLA / GHUGHRI / SAHJAR | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Flood Control and Protection | Desilting / Renovation of Community Water Harvesting Ponds for Community | Deepening / Desilting of Flood Channels | सहजर1735007014/FP/-06 — अस्‍थाई बोरी बांध पसघाट से बरनाला | Completed | 4930 | 5780 | 2008-04-20 - 2010-04-12
MANDLA / GHUGHRI / SAHJAR | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Flood Control and Protection | Desilting / Renovation of Community Water Harvesting Ponds for Community | Deepening / Desilting of Flood Channels | सहजर1735007014/FP/-10 — अस्‍थाई बोरी बांध कोसूम घाटनाला | Completed | 4930 | 5780 | 2008-04-20 - 2010-04-12
MANDLA / GHUGHRI / SAHJAR | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Flood Control and Protection | Desilting / Renovation of Community Water Harvesting Ponds for Community | Deepening / Desilting of Flood Channels | सहजर1735007014/FP/-11 — अस्‍थाई बोरी बांध सेम्‍हर घाट नाला | Completed | 4930 | 4930 | 2008-04-20 - 2010-04-12
MANDLA / GHUGHRI / SAHJAR | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Flood Control and Protection | Desilting / Renovation of Community Water Harvesting Ponds for Community | Deepening / Desilting of Flood Channels | सहजर1735007014/FP/-12 — अस्‍थाई बोरी बांध घाट नाला | Completed | 4930 | 5865 | 2008-04-20 - 2010-04-12
MANDLA / GHUGHRI / SAHJAR | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Flood Control and Protection | Desilting / Renovation of Community Water Harvesting Ponds for Community | Deepening / Desilting of Flood Channels | सहजर1735007014/FP/-13 — अस्‍थाई बोरी बांध पीपरघाट पीपरनाला | Completed | 4845 | 4505 | 2008-04-20 - 2010-04-12