MANDLA | 2014-2015 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Forest Protection / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1736006/DP/9993628085 — cpw/cpt comp 705 part 1 | Deleted | 499503 | 0 | 2014-04-10
MARAI | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Rural Drinking Water | DUGWELLS / Construction of Irrigation Open Well for Community | Construction of Well | 1736006/DW/22012034293967 — water hole ( pond bund) mandai saori range | Deleted | 0 | 0 | 2017-01-01
UMRETH | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Wastelands Block Plantation-Farm Forestry -Comm / Wasteland Block Plantation of Farm Forestry Trees for Community | Plantation | 1736006/LD/22012034518615 — BAMBOO PLANTATION | Completed | 8013000 | 2637186.76 | 2020-07-01 | 2025-05-21
UMRETH | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1736006/LD/22012034518618 — C T | Completed | 49000 | 48130 | 2020-06-24 | 2021-01-12
BELGAON | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Stop Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1736006/OP/9425881093 — वाटर होल निर्माण कार्य कक्ष क्रमांक पी678 | Completed | 52000 | 50812 | 2011-04-04 | 2011-05-15
SABLADHANA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Stop Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1736006/OP/9425881094 — वाटर होल निर्माण कार्य कक्ष क्रं0 695 सावंलाढाना | Completed | 52000 | 36000 | 2011-04-04 | 2012-11-10
SABLADHANA | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Bitumen Top / Construction of Bitumen Top Roads for Community | Construction of Road and Culvert | 1736006/RC/22012034227092 — Vanmarg unnyan work | Deleted | 499838 | 0 | 2014-04-10
URDHAN | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | WBM / Construction of WBM Roads for Community | Construction of Road and Culvert | 1736006/RC/22012034227097 — Vanmarg Unnyan work | Deleted | 500000 | 0 | 2014-04-10
URDHAN | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | WBM / Construction of WBM Roads for Community | Construction of Road and Culvert | 1736006/RC/22012034227098 — Vanmarg Unnyan work | Deleted | 500000 | 0 | 2014-04-10
BAGBARDIYA | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | WBM / Construction of WBM Roads for Community | Construction of Road and Culvert | 1736006/RC/22012034227099 — Vanmarg Unnyan work | Deleted | 500000 | 0 | 2014-04-05
CHARGAON | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Metal Second coat / Construction of WBM Roads for Community | Construction of Road and Culvert | 1736006/RC/9443 — ग्रेवल मार्ग निर्माण चारगांव से तिनसई | Deleted | 2975000 | 0 | 2010-04-01
CHARGAON | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Metal Second coat / Construction of WBM Roads for Community | Construction of Road and Culvert | 1736006/RC/9444 — ग्रेवल मार्ग निर्माण टी 07 से झांकी | Deleted | 3034000 | 0 | 2010-04-01
BHUSADEHI | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & Maint of Gabion Check Dam for Community / Repair and Maintenance of Gabion Check Dam for Community | Repair & Maint of Check Dam/Stop Dam | 1736006/WC/22012034448695 — STOP DAM ME GATEAGANA | Deleted | 891000 | 0 | 2018-08-14
UMRETH | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1736006/WC/22012034562838 — CHECK DEM | Ongoing | 152000 | 19570 | 2020-11-04
UMRETH | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & Maint of Gabion Check Dam for Community / Repair and Maintenance of Gabion Check Dam for Community | Repair & Maint of Check Dam/Stop Dam | 1736006/WC/22012034562844 — TALAB GEHRIKARAN | Closed | 493000 | 0 | 2020-05-02
PARSOLI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1736006/WC/22012035062012 — बोल्डर चेक डेम जग्गनाथ पवार के खेत दस पास पारसोली | Closed | 0 | 0 | 2023-04-14
PARSOLI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1736006/WC/22012035062014 — खेत तलब निर्माण कार्य हीराचंद के खेत में पारसोली | Closed | 0 | 0 | 2023-04-14
PATPADA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1736006/WC/22012035062031 — छिपीवडा तिराहा से हिरपवाडा रोड तक १ की .मी. | Closed | 0 | 0 | 2023-04-14
TAL PIPARIYA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone boulder Gully Plugs for Comm / Construction of Stone boulder Gully Plugs for Community | Boulder Check/Gully Plug | 1736006/WC/22012035062040 — पटरा नाला गली प्लग करला खुर्द | Closed | 0 | 0 | 2023-04-14
TAL PIPARIYA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Coast Line Plntation-Coastal Shelter Belt-Comm / Along the coast Line Plantation of Coastal Shelter Belt Trees for Community | Plantation | 1736006/WC/22012035062058 — नाला सफाई कार्य तालपिपरिया | Closed | 194596.18 | 0 | 2023-04-14
SINDRAI GURAIYATHAR | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1736006/WC/9993622138 — Construction of CheckDam Sindrai | Completed | 354000 | 180519.2 | 2010-05-20 | 2010-10-30
KHAJARI ANTU | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1736006/WC/9993622140 — चेक डेम निर्माण खजरी अन्‍तु लाल चन्‍द के खेत के पास | Completed | 0 | 251703.28 | 2010-03-10 | 2010-01-27
GAJANDOH | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1736006/WC/9993622143 — चेक डेम निर्माण बादरनीर नाला | Completed | 363000 | 293024.12 | 2010-02-02 | 2011-07-12
KHAJARI ANTU | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1736006/WC/9993622144 — चेक डेम निर्माण खजरीअन्‍तु लालचन्‍द के खेत के पास | Completed | 376000 | 289499.58 | 2010-03-01 | 2011-06-14
PAIJANWADA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1736006/WC/9993622145 — चेक डेम निर्माण हर्राहेडा पेजनवाडा | Completed | 352000 | 263470 | 2010-07-08 | 2012-02-15
KOHKA | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1736006/WC/9993622147 — चेक डेम निर्माण पेडो नाला कोहका | Deleted | 360000 | 0 | 2009-06-01
GAJANDOH | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1736006/WC/9993622148 — चेक डेम निर्माण घोघरानाला चांदामेठा | Completed | 357000 | 262282.59 | 2010-02-02 | 2011-06-17
MOTHAR | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1736006/WC/9993622149 — चेक डेम निर्माण मोठार | Completed | 365000 | 350753 | 2010-07-08 | 2013-06-25
KHAJARI ANTU | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1736006/WC/9993622150 — चेक डेम निर्माण खजरीअंतु जीवन के खेत के पास | Completed | 375000 | 198818 | 2011-09-22 | 2013-12-16
PAGARA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1736006/WC/9993622151 — चेक डेम निर्माण गोधन नाला | Completed | 323000 | 144136 | 2010-07-08 | 2011-05-27
PAGARA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1736006/WC/9993622153 — चेक डेम निर्माण छपरानाला | Completed | 350000 | 251434 | 2010-07-08 | 2016-03-17
SINDRAI GURAIYATHAR | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1736006/WC/9993622154 — चेक डेम निर्माण कार्य गोधननाला क्रं 05 | Completed | 345000 | 245602 | 2011-05-26 | 2011-06-07
SINDRAI GURAIYATHAR | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1736006/WC/9993622156 — चेक डेम निर्माण रामप्रसाद के खेत के पास क्रं 1 सिन्‍दरई गुरैयाथार | Completed | 346000 | 241710 | 2011-07-07 | 2012-01-25
MAYAWADI | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1736006/WC/9993622157 — चेक डेम निर्माण जेठीनाला मायावाडी | Completed | 342000 | 192248 | 2011-01-11 | 2011-07-10
MANDLA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1736006/WC/9993622158 — चेक डेम निर्माण कार्य घोडाघाट | Completed | 344000 | 197500 | 2010-12-30 | 2011-04-20
GAJANDOH | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1736006/WC/9993622159 — चेक डेम निर्माण कार्य बिजोरी पथरई नदी | Completed | 360000 | 136214.24 | 2010-06-29 | 2011-05-14
SINDRAI GURAIYATHAR | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1736006/WC/9993622160 — चेक डेम निर्माण कार्य सुंदर जगननाला नं 1 | Completed | 317000 | 190555 | 2010-06-16 | 2012-12-12
SINDRAI GURAIYATHAR | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1736006/WC/9993622161 — चेक डेम निर्माण सिंदरईगुरैयाथार | Completed | 368000 | 105000 | 2011-07-07 | 2009-06-01
GAJANDOH | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1736006/WC/9993622163 — चेक डेम निर्माण गुरूप्रसाद के खेत के पास गाजनडोह | Completed | 371000 | 334083.87 | 2010-03-02 | 2011-10-29
SINDRAI GURAIYATHAR | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1736006/WC/9993622211 — चेक डेम निर्माण कार्य गोधननाला क्रं 7 | Completed | 317000 | 289026 | 2011-07-07 | 2011-11-26
SINDRAI GURAIYATHAR | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1736006/WC/9993622212 — चेक डेम निर्माण कार्य जोबनाला क्रं 2 | Completed | 332000 | 471118 | 2011-05-05 | 2012-12-12
SINDRAI GURAIYATHAR | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1736006/WC/9993622213 — चेक डेम निर्माण जगननाला क्रं 3 | Completed | 369000 | 215084 | 2011-06-30 | 2012-12-12
SINDRAI GURAIYATHAR | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1736006/WC/9993622214 — चेक डेम निर्माण रामप्रसाद के खेत के पास | Completed | 357000 | 358052 | 2011-04-07 | 2011-10-17
SAHPANI | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1736006/WC/9993622215 — चेक डेम निर्माण सहपानी | Completed | 346000 | 132380 | 2010-12-20 | 2011-11-25
SINDRAI GURAIYATHAR | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1736006/WC/9993622216 — चेक डेम निर्माण क्रं 03 | Completed | 366000 | 84956 | 2011-05-05 | 2012-12-12
SINDRAI GURAIYATHAR | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1736006/WC/9993622217 — चेक डेम निर्माण जोबनाला क्रं 03 | Completed | 342000 | 487000 | 2011-07-07 | 2012-12-12
AMBADA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Mini Percolation Tank / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1736006/WC/9993622879 — nistari/percoletaion tank ambara hinglaj 2 | Deleted | 4998121 | 0 | 2010-10-02
AMBADA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Sub Surface Dam / Construction of Underground Dykes for Community | Underground Dyke for Ground Water Recharge | 1736006/WC/9993622888 — nistari/percolation tank ambara | Completed | 5850000 | 5739779 | 2011-05-19 | 2014-03-16
KHIRSADOH | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Staggered Trench / Construction of Staggered Trench for Community | Construction of Trench | 1736006/WC/9993640274 — Stayguard Trench Near Bypass Khirsadoh | Deleted | 409000 | 0 | 2012-04-14
KHIRSADOH | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Staggered Trench / Construction of Staggered Trench for Community | Construction of Trench | 1736006/WC/9993641004 — Stay Guard Plot No.16/2 Khirsadoh | Deleted | 49000 | 0 | 2012-01-26
KHIRSADOH | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1736006/WC/9993642184 — Check Dam School ke pas Khirsadoh | Deleted | 215000 | 0 | 2012-02-05
LIKHAVADI | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1736006/WC/9993642185 — Checj Dam Devri Dhana Khirsadoh | Deleted | 215000 | 0 | 2012-10-02
KHAMARA JHETHU | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1736006/WC/9993642187 — Check Dam Khamra Jethu | Deleted | 215000 | 0 | 2011-10-02
HARRAI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Staggered Trench / Construction of Staggered Trench for Community | Construction of Trench | 1736006/WC/9993642188 — Stay Guard Trench Harrai | Deleted | 495000 | 0 | 2011-10-02
MAYAWADI | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1736/DP/22012034489500 — Bamboo plantation mayawadi comp no P 716 area 30 ha | Completed | 3548540 | 1079398.69 | 2020-06-23 | 2025-05-27
ITAWA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Constr of Stone boulder Gully Plugs for Comm / Construction of Stone boulder Gully Plugs for Community | Boulder Check/Gully Plug | 1736/DP/22012034541451 — Loos Bolder Structutre | Closed | 35200 | 0 | 2021-04-02
SETHIA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1736/DP/22012034555056 — Bamboo plantation comp no P 711A setiya 15 ha | Ongoing | 2229600 | 593442.63 | 2022-05-25
KARIDOGARI | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Micro Irrigation Works | Construction of Canal, Distributary and Minor / Construction of distributary Canal for Community | Construction of Canal | 1736/IC/9993637479 — Karidongri Canal Work | Deleted | 99000 | 0 | 2015-11-18
PHUTERA | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Micro Irrigation Works | Construction of Canal, Distributary and Minor / Construction of distributary Canal for Community | Construction of Canal | 1736/IC/9993637480 — Phutera Canal Work | Deleted | 84000 | 0 | 2015-11-18
PAGARA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Fallow Land for Community / Development of Fallow Land for Community | Land Development | 1736/LD/22012034954525 — Bamboo plantation mainawadi comp no P 712 area 15 ha parasia range | Ongoing | 2000000 | 168256.12 | 2025-05-24
BAGBARDIYA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Stop Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1736/OP/9425881100 — वाटर होल निर्माण कार्य हिर्रीपठार कक्ष क्रं0 703ए | Completed | 52000 | 35000 | 2011-04-01 | 2011-04-30
CHARGAON | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Bitumen Top / Construction of Bitumen Top Roads for Community | Construction of Road and Culvert | 1736/RC/22012034152342 — construction of grawal road Chargaon to tinsai | Completed | 2975000 | 1019128.4 | 2010-12-01 | 2014-06-25
CHARGAON | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Bitumen Top / Construction of Bitumen Top Roads for Community | Construction of Road and Culvert | 1736/RC/22012034152344 — construction of grawal road T07 to Jhanki | Completed | 2236000 | 803604.2 | 2010-12-29 | 2014-06-25
JAMUNIA JETHU | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Bitumen Top / Construction of Bitumen Top Roads for Community | Construction of Road and Culvert | 1736/RC/22012034152460 — construction of grawal road jamuniya jethu to bich | Completed | 2258000 | 665423.65 | 2010-10-05 | 2014-06-25
JAMUNIA JETHU | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Bitumen Top / Construction of Bitumen Top Roads for Community | Construction of Road and Culvert | 1736/RC/22012034152461 — construction of grawal road jamuniya jethu to path | Completed | 2192000 | 78768 | 2011-05-03 | 2012-12-10
DAMUA RAIYAT | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Bitumen Top / Construction of Bitumen Top Roads for Community | Construction of Road and Culvert | 1736/RC/22012034152462 — construction of grawal road damuamal to damuaryat | Completed | 2580000 | 748020.3 | 2011-09-23 | 2014-06-25
APTARA | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1736/RC/22012034152463 — construction of grawal road aptara madimal to domri | Deleted | 1885000 | 0 | 2010-07-27
MADAYIMAL | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Bitumen Top / Construction of Bitumen Top Roads for Community | Construction of Road and Culvert | 1736/RC/22012034152464 — construction of grawal road Maidaimal to Maidairai | Completed | 1915000 | 653821.4 | 2012-08-08 | 2015-04-03
TIGAYI | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1736/RC/22012034152466 — construction of grawal road Tighra to hirnakhdi | Completed | 4422000 | 1169873 | 2010-12-10 | 2014-06-25
KHAJARI ANTU | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Bitumen Top / Construction of Bitumen Top Roads for Community | Construction of Road and Culvert | 1736/RC/22012034152467 — construction of grawal road Kajri antu kkhariya to | Completed | 639000 | 249804 | 2010-12-02 | 2013-09-11
KHAJARI ANTU | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Bitumen Top / Construction of Bitumen Top Roads for Community | Construction of Road and Culvert | 1736/RC/22012034152468 — construction of grawal road Kjriantu to khkhariya | Completed | 3400000 | 2444951 | 2010-12-09 | 2013-12-12
NEEMKUHI | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Bitumen Top / Construction of Bitumen Top Roads for Community | Construction of Road and Culvert | 1736/RC/22012034152469 — construction of grawal road Umreth mordongri to do | Completed | 785000 | 378380.8 | 2011-01-30 | 2014-04-12
CHANDAMETA KALA | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Bitumen Top / Construction of Bitumen Top Roads for Community | Construction of Road and Culvert | 1736/RC/22012034152470 — construction of grawal road Chandametakala to chad | Completed | 1196000 | 656221.4 | 2011-11-24 | 2014-06-25
PATHA | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Bitumen Top / Construction of Bitumen Top Roads for Community | Construction of Road and Culvert | 1736/RC/22012034152471 — construction of grawal road Guba to patha | Completed | 1805000 | 1161977.6 | 2010-11-08 | 2014-06-25
JAMUNIA JETHU | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Repair & maint of Gravel Road Roads for Comm / Repair and maintenance of Gravel Road Roads for Community | Repair & maint of Road | 1736/RC/22012034609040 — Periodical Regravelling of CMGSY ROAD Jamuniyajethu to Bichhiyaghati | Deleted | 0 | 0 | 2021-10-04
JAMUNIA JETHU | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1736/RC/22012034609043 — Periodical Regravelling of CMGSY ROAD Jamuniyajethu to Bichhiyaghati | Deleted | 0 | 0 | 2021-10-04
JAMUNIA JETHU | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736/RC/22012034609059 — riodical RegravellinPeg of CMGSY ROAD Jamuniyajethu to Bichhiyaghati | Completed | 267000 | 218700.4 | 2022-03-09 | 2023-08-17
MARAI | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1736/RC/22012034609063 — Periodical Regravelling of CMGSY ROAD Mothar Shivpuri Road to Jaitharidhana | Completed | 584000 | 220022.84 | 2022-03-10 | 2023-08-17
GHOGHRI RAIYATWADI | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736/RC/22012034609066 — Periodical Regravelling of CMGSY ROAD Ghoghari to Shivpuri | Completed | 235000 | 207881.32 | 2022-03-10 | 2023-08-17
NONA PATHAR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736/RC/22012034609074 — Periodical Regravelling of CMGSY ROAD Tursi to Pathakhuri | Completed | 796000 | 350464.59 | 2022-03-09 | 2024-10-24
MANDLA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736/RC/22012034666939 — Sudur Sadak with Puliya Mandli se Mandla Two Km | Closed | 0 | 0 | 2023-08-15
MANDLA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1736/RC/22012034666942 — Sudur Sadak with Puliya Mandli se Mandla Two Km | Ongoing | 5256000 | 2436064.74 | 2023-12-31
SEMARTAAL | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736/RC/22012034666953 — Sudur Sadak with Puliya School Dhana SE main road Damua DolaGhat 1.70 Km | Ongoing | 6874000 | 3486083.65 | 2024-01-02
SEMARTAAL | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1736/RC/22012034666954 — Sudur Sadak with Puliya School Dhana SE main road Damua DolaGhat 1.70 Km | Closed | 0 | 0 | 2023-08-15
LOHARIBANDRI | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736/RC/22012034667005 — Sudur Sadak Seh Puliya Nirman Karya Duddi Se buddi 2.10KM Gram Loharibandri | Ongoing | 6553000 | 2947368.27 | 2024-01-09
LIKHAVADI | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736/RC/22012034672923 — Sudoor Sadak with Puliya Likhawadi Main Road to Kolhukheda L 2Km Gram Likhawadi | Ongoing | 5377000 | 1429621.18 | 2024-03-09
DAMUA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1736/RC/22012034680453 — Sudoor Sadak with Puliya Damua to Sarekhadhana L 1.30Km Gram Danua | Ongoing | 3888000 | 1879204.9 | 2024-06-18
BHUSADEHI | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & Maint of Gabion Check Dam for Community / Repair and Maintenance of Gabion Check Dam for Community | Repair & Maint of Check Dam/Stop Dam | 1736/WC/22012034448700 — STOP DAM ME GATE LAGANA GRAM PURA | Completed | 891000 | 890231.16 | 2019-01-04 | 2019-06-25
HARRAI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1736/WC/22012035143415 — Slab culvert with Stop Dam gram harrai | Ongoing | 4846000 | 4203339.85 | 2024-01-03
DAMUA RAIYAT | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1736/WC/22012035143490 — Nistari Talab Nirman Katel Nala Gram Gorpani | Ongoing | 3529000 | 1262150.18 | 2024-01-31
MARAI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1736/WC/22012035143506 — Nistari Talab Nirman Karya Junapani Nala Nazarlal Dhurve K Khet K pass Jaitharii | Ongoing | 5438000 | 4006062.89 | 2024-01-04
KARIDOGARI | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Feeder Channel / Construction of Feeder Canal for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1736/WC/9993627396 — KARI DONGARI JALASHAY KI NAHARO KA MARMMAT SUDHA | Completed | 1672000 | 679770.28 | 2012-10-28 | 2017-09-20
TAL PIPARIYA | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1736/WC/9993649576 — Check Dam 8 no. | Completed | 4989000 | 2027319.32 | 2014-03-05 | 2015-06-15
APTARA | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1736/WC/9993649578 — Check Dam 8 No. | Completed | 4975000 | 2789137.2 | 2014-03-05 | 2015-06-30
SIRGORI KHURD | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Repair & Maint of Earthen Check Dam for Community / Repair and Maintenance of Earthen Check Dam for Community | Repair & Maint of Check Dam/Stop Dam | 1736/WH/22012034332864 — stop dam gate & renovation work sirgorikhurd | Closed | 139000 | 0 | 2016-04-14
BHUSADEHI | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1736/WH/22012034332866 — Stop dam gate karya pura gram panchayat mushadehi | Deleted | 0 | 0 | 2017-04-14
BELGAON | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1736/WH/22012034332867 — stop dam me gate lagana & repering karya kolabarra belgao | Deleted | 0 | 0 | 2017-04-14
KHAIRICHETU | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1736/WH/22012034332868 — Stop dam me gate lagan & renovation chhitri jp kherichetu | Deleted | 0 | 0 | 2017-04-14
BIJORI GUMAI | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1736/WH/22012034332869 — Stop dam gate & renovation bijorigumai | Deleted | 0 | 0 | 2017-04-14
SATNUR | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1736/WH/22012034332870 — Stop dam gate & renovation satnor | Deleted | 0 | 0 | 2017-04-14
SAHPANI | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1736/WH/22012034332871 — Stop dam gate & renovation sahpani | Deleted | 0 | 0 | 2017-04-14
BHUSADEHI | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1736/WH/22012034389500 — Stop dame me get lagana Pura | Suspended | 891000 | 0 | 2019-03-20
BHUSADEHI | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1736/WH/22012034389628 — STOP DAM ME GATE LAGANA | Deleted | 0 | 0 | 2018-04-14
BHUSADEHI | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1736/WH/22012034389629 — STOP DAM ME GATE LAGANA | Suspended | 891000 | 0 | 2019-03-20
BIJORI GUMAI | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1736/WH/22012034389630 — stop dam me gate me gate lagana,jirnodhar- Bijori gumai | Completed | 217000 | 196667.4 | 2019-01-05 | 2020-08-12
KHAIRICHETU | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1736/WH/22012034389631 — stop dam me gate me gate lagana,jirnodhar- kheri chaitu | Deleted | 356000 | 0 | 2019-03-07