## Work List
Exported on: 2026-08-22 01:35:40
Filters applied:
Data source: MGNREGA
District: CHHINDWARA
Block: MOHKHED
Panchayat: JHIRYA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
| 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | AWC / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1736007073/AV/22012034354405 — santigham me shed nirman sirkuhi | Completed | 180000 | 170486.52 | 2017-07-25 | 2017-08-05
| 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1736007073/AV/22012034392642 — boulder boundari wall nirman p/s school sirkuhi | Closed | 0 | 0 | 2018-08-16
| 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1736007073/AV/22012034584482 — डायनिंग हॉल निर्माण मा. शाला झिरिया | Closed | 0 | 0 | 2021-04-15
| 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1736007073/AV/22012034584483 — डायनिंग हॉल निर्माण मा. शाला झिरिया | Closed | 0 | 0 | 2021-04-15
| 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1736007073/AV/22012034584486 — डायनिंग हॉल निर्माण मा. शाला झिरिया | Closed | 0 | 0 | 2021-04-15
| 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1736007073/AV/22012034632576 — BOUNDRIBAL NIRMAN KARY MS PARISAR | Completed | 32400 | 31460 | 2023-08-01 | 2024-02-05
| 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1736007073/AV/22012034643255 — Baundribal Nirman gram panchyat bhavan parisar | Completed | 42000 | 41940 | 2023-10-06 | 2024-03-21
| 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1736007073/DP/22012034234351 — Plantation - डोबरी टेकड़ी झिरिया, ग्रा.पं झिरिया | Completed | 1499000 | 600619 | 2016-08-09 | 2021-05-29
| 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Farm Forestry-Community / Boundary Line Plantation of Farm Forestry Trees for Community | Plantation | 1736007073/DP/22012034427351 — Plantation Road Line- Bichhua Road to Uamriya Road | Completed | 342000 | 114431 | 2018-08-28 | 2023-10-12
| 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation of Forestry-Community / Boundary Line Plantation of Forestry Trees for Community | Plantation | 1736007073/DP/22012034427353 — Plantation - Santidham Parisar Kundalikhur Part-II | Completed | 342000 | 119069 | 2018-10-03 | 2023-06-24
| 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation of Forestry-Community / Boundary Line Plantation of Forestry Trees for Community | Plantation | 1736007073/DP/22012034482409 — PLANTESAN ROAD SIAD KARY JIRIYA | Completed | 373989.79 | 116560 | 2019-10-18 | 2023-09-04
| 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1736007073/DP/22012034490479 — Contour Trench Nirman Talab Pahadi Jhiriya | Completed | 970125.2 | 712435 | 2020-07-07 | 2023-02-01
| 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1736007073/DP/22012034490482 — Contour Trench Nirman Sarkari Kuaa ke pass Pahadi, Kundalikhurd | Completed | 970125.2 | 715915 | 2020-07-07 | 2023-02-11
| 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1736007073/DP/22012034490753 — Plantation Block Shaskiy Kuye ke pass Pahadi, Kundalikhurd | Completed | 677985.75 | 430169.65 | 2020-07-22 | 2026-02-04
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1736007073/DP/22012034530210 — Contour Trench Nirman Bandhi vali Pahadi Jhiriya | Completed | 1204069.43 | 775808 | 2021-07-06 | 2023-02-23
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1736007073/DP/22012034530222 — Plantation Block Bandhi vali Pahadi Jhiriya | Completed | 685575.78 | 267780.13 | 2021-07-07 | 2026-04-29
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1736007073/DP/22012034530233 — Contour Trench Nirman Chekdem vali Pahadi Sirkuhi | Completed | 603712.69 | 527674 | 2021-11-30 | 2023-02-01
| 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1736007073/DP/22012034556369 — Contour Trench Nirman Shamshan ghat bali pahadi kundali khurd | Completed | 637967.11 | 547751.44 | 2022-08-03 | 2024-10-01
| 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1736007073/DP/22012034556374 — Plantation Block Mahuaa pahadi ke pass, Kundalikhurd) | Completed | 713191.92 | 269336.12 | 2022-08-09 | 2026-05-29
| 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1736007073/DP/22012034575031 — CONTUR TRENCH NIRMAN VAHAV PATEL KE KHET KE PASS PAHADI JHIRIYA | Closed | 0 | 0 | 2023-01-27
| 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation of Forestry-Community / Boundary Line Plantation of Forestry Trees for Community | Plantation | 1736007073/DP/22012034604424 — वसुधा वंदन चेकडेम के पास झिरिया | Completed | 55847.4 | 24751 | 2023-09-01 | 2026-04-24
| 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Coastal Block Plantation of Forestry-Community / Along the coast Block Plantation of Forestry Trees for Community | Plantation | 1736007073/DP/22012034619802 — BLOCK PLANTATION MAHUAA BALI PAHADI JHIRIYA | Deleted | 0 | 0 | 2024-06-08
| 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1736007073/DP/22012034621136 — BLOCK PLANTATION MAHUAA BALI PAHADI JHIRIYA | Ongoing | 829925.21 | 200190.13 | 2024-07-09
| 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1736007073/DP/45646 — बांसरोपण कार्य सिरकुही | Completed | 396000 | 104526 | 2008-01-01 | 2011-03-31
| 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1736007073/DP/झिरया/ 043 — शाला भवन परिसर झिरिया मे व्रक्षारोपण कार्य | Completed | 109000 | 104656 | 2007-08-07 | 2012-12-22
| 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1736007073/DP/झिरिया/ 0044 — पुरानी कब्रस्‍तान झिरिया मे व्रक्षारोपण कार्य | Completed | 109000 | 122122 | 2007-08-07 | 2012-12-25
| 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1736007073/DP/झिरिया /0045 — नवीन कब्रस्‍तान झिरिया मे व्रक्षारोपण कार्य | Completed | 83600 | 181883 | 2007-08-08 | 2012-12-20
| 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1736007073/DP/झिरिया/046 — शमशानघाट मे व्रक्षारोपण कार्य | Completed | 100000 | 115205 | 2007-08-16 | 2012-12-20
| 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1736007073/DP/झिरिया 048 — शमशान घाट सिरकुही मे व्रक्षारोपण कार्य | Completed | 109000 | 99337 | 2007-08-07 | 2012-10-20
| 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1736007073/DP/झिरिया/54/657 — वझारोपण कार्य सिरकुही | Completed | 48000 | 223174 | 2007-06-29 | 2012-11-12
| 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1736007073/DP/झिरीया 01 — शाला भवन परीसर सिरकुही मे व्रक्षा रोपण | Completed | 97000 | 99581 | 2007-08-07 | 2016-07-19
| 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Poultry Shelter / Construction of Poultry Livestock_Shelter for Individuals | Poultry Shelter | 1736007073/IF/1000043738 — मुर्गी शेडा सहसराम/टीकाराम | Completed | 54000 | 52160 | 2013-10-04 | 2016-06-20
| 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1736007073/IF/1000043741 — मवेशी शेड पार्वती/इठोबा | Completed | 85000 | 83760.5 | 2013-10-04 | 2016-06-27
| 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1736007073/IF/22012034316450 — kapildhara kup sah talab nirman rayvati / jivan | Completed | 230000 | 229608 | 2017-01-31 | 2018-08-21
| 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1736007073/IF/22012034319315 — kapildhara kup shivcharan ramteke | Deleted | 0 | 0 | 2017-01-26
| 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1736007073/IF/22012034325368 — कपिलधारा सह तालाब निर्माण सीताराम/ सेवक (FRA ) | Completed | 230000 | 229489 | 2017-03-07 | 2018-08-21
| 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1736007073/IF/22012034332128 — Kapildhara with Farm pond - Ramsawarup/Sukhlal | Completed | 230000 | 229766 | 2017-04-11 | 2018-09-21
| 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1736007073/IF/22012034344044 — Plantation BP -Maidan ke pass plantation Jhiriya | Completed | 535000 | 122110 | 2017-05-23 | 2021-02-05
| 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1736007073/IF/22012034347961 — Plantation RSP वृक्षारोपन सडक के दोनो साइड पी ड्ब्ल्यु डी रोड से खेल मैदान तक झिरिया | Completed | 335000 | 87097 | 2017-06-27 | 2021-02-07
| 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1736007073/IF/22012034347962 — Plantation BP -वृक्षारोपन शांतीधाम कुंडालिखुर्द | Completed | 535000 | 110710 | 2017-06-06 | 2021-02-05
| 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1736007073/IF/22012034347963 — Plantation RSP- वृक्षारोपन बिछुआ मुख्य मार्ग से सिरकुही तक | Completed | 335000 | 70116 | 2017-06-06 | 2021-02-05
| 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1736007073/IF/22012034347964 — Plantation RSP - वृक्षारोपन कुंडाली से मुख्यमार्ग | Completed | 335000 | 61914 | 2017-06-27 | 2021-02-05
| 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1736007073/IF/22012034368944 — Plantation PCP- Plantation at Shantidham Sirkhuhi | Completed | 335000 | 79162 | 2017-08-01 | 2021-02-05
| 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1736007073/IF/22012034385555 — kapildhara | Deleted | 0 | 0 | 2017-10-02
| 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1736007073/IF/22012034385556 — kapildhara | Closed | 0 | 0 | 2017-10-02
| 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1736007073/IF/22012034385557 — plantation | Closed | 0 | 0 | 2017-10-02
| 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of stone peripheral bund for indiv / Construction of Stone peripheral/farm/field Bund for Individuals | Construction of Bund | 1736007073/IF/22012034451265 — Med Bandhan (Bolder) Ramswroop / Sukhlal , Jhiriya | Completed | 149000 | 129428 | 2019-01-29 | 2019-07-18
| 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of stone peripheral bund for indiv / Construction of Stone peripheral/farm/field Bund for Individuals | Construction of Bund | 1736007073/IF/22012034451274 — Med Bandhan (Bolder) Ramji / Dayaram, Jhirya | Completed | 132000 | 128160 | 2019-01-29 | 2019-08-19
| 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1736007073/IF/22012034457109 — Kapildhara Kup Nirman - | Closed | 0 | 0 | 2018-10-02
| 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of stone peripheral bund for indiv / Construction of Stone peripheral/farm/field Bund for Individuals | Construction of Bund | 1736007073/IF/22012034466165 — Med Bandhan (Boldar) Champalal / Ramdayal, Jhirya | Completed | 170000 | 164986 | 2019-03-05 | 2020-06-10
| 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of stone peripheral bund for indiv / Construction of Stone peripheral/farm/field Bund for Individuals | Construction of Bund | 1736007073/IF/22012034466202 — Med Bandhan (Boldar) Fakira / Munna, Jhirya | Completed | 170000 | 164842 | 2019-03-05 | 2020-08-16
| 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1736007073/IF/22012034475484 — Kapildhara Kup Sumru S/o Gendlal Yadao Sirkuhi | Completed | 210000 | 209982 | 2019-05-29 | 2020-08-05
| 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1736007073/IF/22012034475489 — Kapildhara Kup Champalal S/o Ramdayal Sirkuhi | Deleted | 0 | 0 | 2018-12-28
| 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of stone peripheral bund for indiv / Construction of Stone peripheral/farm/field Bund for Individuals | Construction of Bund | 1736007073/IF/22012034495530 — Med (Bolder) Kishor / Sukhlal | Closed | 0 | 0 | 2019-04-14
| 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of stone peripheral bund for indiv / Construction of Stone peripheral/farm/field Bund for Individuals | Construction of Bund | 1736007073/IF/22012034501973 — Meb Bandhan (Bolder) KISHOR / SUKHLAL PARTETI | Completed | 124875.44 | 101441 | 2020-02-11 | 2020-06-10
| 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of stone peripheral bund for indiv / Construction of Stone peripheral/farm/field Bund for Individuals | Construction of Bund | 1736007073/IF/22012034501975 — Meb Bandhan (Bolder) RAYWATI / JEEVAN | Completed | 124875.44 | 100586 | 2020-02-11 | 2020-06-10
| 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of stone peripheral bund for indiv / Construction of Stone peripheral/farm/field Bund for Individuals | Construction of Bund | 1736007073/IF/22012034501976 — Meb Bandhan (Bolder) BHURAO / DAYARAM | Completed | 103381.56 | 84438 | 2020-02-11 | 2020-06-10
| 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Stone boulder Gully Plugs for Individual / Construction of Stone boulder Gully Plugs for Individuals | Boulder Check/Gully Plug | 1736007073/IF/22012034558313 — MED BANDHAN BOLDER SAMPAT/LAXMAN | Completed | 68627.94 | 55290 | 2020-06-09 | 2021-01-20
| 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Stone boulder Gully Plugs for Individual / Construction of Stone boulder Gully Plugs for Individuals | Boulder Check/Gully Plug | 1736007073/IF/22012034558319 — MED BANDHAN BOIDER BEDU/KHUSHRYA | Completed | 133998.46 | 108110 | 2020-06-09 | 2021-01-22
| 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Stone boulder Gully Plugs for Individual / Construction of Stone boulder Gully Plugs for Individuals | Boulder Check/Gully Plug | 1736007073/IF/22012034577078 — MED BANDHAN BOLDER SEVARAM/BALIRAM | Completed | 199955.75 | 160717 | 2020-07-07 | 2021-06-24
| 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1736007073/IF/22012034579454 — Neno Archid Falodhyan Imla / Sahasram Pawar Jhiriya | Completed | 58300 | 35753 | 2020-07-14 | 2023-02-10
| 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Boundary Line Plantation of Horticulture Trees for Individuals | Plantation | 1736007073/IF/22012034579460 — Neno Archid Falodhyan Kaikai / Hijju Pawar Jhiriya | Completed | 58300 | 29517 | 2020-07-14 | 2023-02-10
| 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Boundary Line Plantation of Horticulture Trees for Individuals | Plantation | 1736007073/IF/22012034579466 — Neno Archid Falodhyan Chhampa/sumaru yadava Sirkuhi | Completed | 58300 | 25073 | 2020-07-14 | 2023-02-10
| 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Boundary Line Plantation of Horticulture Trees for Individuals | Plantation | 1736007073/IF/22012034579469 — Neno Archid Falodhyan Hira / Champalal | Completed | 58300 | 36223 | 2020-07-14 | 2023-02-22
| 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Boundary Line Plantation of Horticulture Trees for Individuals | Plantation | 1736007073/IF/22012034579474 — Neno Archid Falodhyan Raywati / Jivanlal Sirkuhi | Completed | 58300 | 39085 | 2020-07-14 | 2023-02-11
| 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Boundary Line Plantation of Horticulture Trees for Individuals | Plantation | 1736007073/IF/22012034579480 — Neno Archid Falodhyan Sunita Bhaurav Kundali Khurd | Completed | 58300 | 32626 | 2020-07-07 | 2023-02-11
| 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Boundary Line Plantation of Horticulture Trees for Individuals | Plantation | 1736007073/IF/22012034579490 — Neno Archid Falodhyan Ranjana kishor sirkuhi | Completed | 58300 | 18583 | 2020-07-14 | 2023-02-23
| 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Boundary Line Plantation of Horticulture Trees for Individuals | Plantation | 1736007073/IF/22012034579497 — Neno Archid Falodhyan dujiya/fakira | Completed | 58300 | 41311 | 2020-07-14 | 2022-11-05
| 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Boundary Line Plantation of Horticulture Trees for Individuals | Plantation | 1736007073/IF/22012034579501 — Neno Archid Falodhyan suhga baliram | Completed | 58300 | 27463 | 2020-07-14 | 2022-12-10
| 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Boundary Line Plantation of Horticulture Trees for Individuals | Plantation | 1736007073/IF/22012034580049 — Neno Archid Falodhyan rekha / raju sahu | Completed | 58300 | 39157 | 2020-07-14 | 2023-02-22
| 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Boundary Line Plantation of Horticulture Trees for Individuals | Plantation | 1736007073/IF/22012034596513 — Neno Archid Falodhyan SEVANTI/SHIVCHARAN KUNDALI | Completed | 58300 | 30858 | 2020-08-18 | 2023-02-11
| 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Boundary Line Plantation of Horticulture Trees for Individuals | Plantation | 1736007073/IF/22012034596519 — Neno Archid Falodhyan Sahavati/bhaddu yadav jhiriya | Completed | 58300 | 21438 | 2020-08-18 | 2023-06-01
| 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Boundary Line Plantation of Horticulture Trees for Individuals | Plantation | 1736007073/IF/22012034596520 — Neno Archid Falodhyan sukhvati/sahadev jhiriya | Completed | 58300 | 18937 | 2020-08-18 | 2022-12-10
| 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Boundary Line Plantation of Horticulture Trees for Individuals | Plantation | 1736007073/IF/22012034596522 — Neno Archid Falodhyan Gaora/endarsing jhiriya | Completed | 58300 | 26235 | 2020-08-25 | 2022-12-10
| 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Boundary Line Plantation of Horticulture Trees for Individuals | Plantation | 1736007073/IF/22012034596523 — Neno Archid Falodhyan RAYA/SYAMU KUNDALI | Completed | 58300 | 22627 | 2020-08-18 | 2022-12-10
| 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Piggery Shelter for Individuals / Construction of Piggery Shelter for Individuals | Piggery Shelter | 1736007073/IF/22012034618476 — मवेशी शेड निर्माण बली यादव /टुन्नू यादव झिरिया | Completed | 101804.91 | 95478.73 | 2020-10-20 | 2021-06-24
| 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Poultry Shelter for Individuals / Construction of Poultry Livestock_Shelter for Individuals | Poultry Shelter | 1736007073/IF/22012034618487 — मवेशी शेड निर्माण बली यादव /टुन्नू यादव झिरिया | Closed | 0 | 0 | 2020-08-15
| 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1736007073/IF/22012034618503 — मवेशी शेड निर्माण अजाबराव /भैयालाल कुंडली खुर्द | Completed | 101804.91 | 97011.4 | 2020-10-08 | 2021-12-01
| 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1736007073/IF/22012034618508 — मवेशी शेड निर्माण रामवती यादव /मटरू यादव झिरिया | Completed | 101804.91 | 95668.73 | 2020-10-08 | 2021-06-27
| 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1736007073/IF/22012034660642 — Med Bhandhan (Bolder):- Med Bhandhan (Bolder) Nirman Karya Jagdish/Bipttu Parteti Sirkuhi Jhiriya | Completed | 203754.75 | 165980 | 2021-05-04 | 2021-06-24
| 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Bondry Block - Coastal Shelter Belt-Individuals / Boundary Block Plantation of Coastal Shelter Belt Trees for Individuals | Other Works | 1736007073/IF/22012034734818 — MED BANDHAN BOLDER PANDARI /ITHOBA PAWAR JHIRIYA | Closed | 0 | 0 | 2021-01-27
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Stone boulder Gully Plugs for Individual / Construction of Stone boulder Gully Plugs for Individuals | Boulder Check/Gully Plug | 1736007073/IF/22012034734895 — MED BANDHAN BOLDER PANDARI /ITHOBA PAWAR JHIRIYA | Completed | 203754.75 | 164822 | 2021-05-11 | 2021-06-24
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Stone boulder Gully Plugs for Individual / Construction of Stone boulder Gully Plugs for Individuals | Boulder Check/Gully Plug | 1736007073/IF/22012034748592 — MED BANDHAN BOLDER SUMRU/GENDLAL YADAV SIRKUHI | Completed | 136538.29 | 108557 | 2021-05-18 | 2022-07-25
| 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Vermi Compost structure for Individual / Construction of Vermi Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1736007073/IF/22012034857386 — VERMI COMPOST RAMJI/DYARAM KUNDALI | Closed | 22556.97 | 0 | 2021-08-18
| 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Vermi Compost structure for Individual / Construction of Vermi Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1736007073/IF/22012034857410 — VERMI COMPOST SHIVRAN/SAUVA KUNDALI khurd | Completed | 22824.7 | 14908 | 2021-10-08 | 2023-06-26
| 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Compost Pit for Individual / Construction of Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1736007073/IF/22012034857412 — NADEP NIRMAN ASHOK/TULASHIRAM KUNDALI KHURD | Completed | 20104.16 | 13484 | 2021-11-16 | 2023-06-26
| 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Vermi Compost structure for Individual / Construction of Vermi Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1736007073/IF/22012034861726 — VERMI COMPOST RADHESYAM/MAROTI KUNDALI KUNDALI | Closed | 22016.71 | 0 | 2021-08-18
| 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Compost Pit for Individual / Construction of Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1736007073/IF/22012034861728 — VERMI COMPOST KOUTIKA/MAROTI KUNDALI | Closed | 22619.46 | 0 | 2021-08-18
| 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Vermi Compost structure for Individual / Construction of Vermi Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1736007073/IF/22012034887664 — Varmi Compost nirman shiv charan/sauva kundali | Completed | 24107.01 | 15188 | 2021-12-11 | 2023-06-26
| 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Vermi Compost structure for Individual / Construction of Vermi Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1736007073/IF/22012034887667 — Varmi compost nirman syamu/dalshing kundali | Completed | 24107.01 | 15205 | 2021-12-11 | 2023-06-26
| 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1736007073/IF/22012034939932 — MED BANDHAN BOLDAR ENDARLAL /DENDLAL YADAV | Closed | 0 | 0 | 2022-01-25
| 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1736007073/IF/22012035114792 — KAPIL KUP NIRMAN CHAMPALAL SAHU | Deleted | 0 | 0 | 2023-04-14
| 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1736007073/IF/22012035122973 — KAPIL KUP NIRMAN HANSRAJ SAHU | Closed | 0 | 0 | 2023-04-14
| 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1736007073/IF/22012035122999 — KAPIL KUP NIRMAN CHAMPALAL SAHU | Deleted | 0 | 0 | 2023-04-14
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Boundary Line Plantation of Horticulture Trees for Individuals | Plantation | 1736007073/IF/22012035145606 — Neno Archid Falodhyan sitaram/sevak | Ongoing | 65100 | 23094 | 2024-07-30
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Boundary Line Plantation of Horticulture Trees for Individuals | Plantation | 1736007073/IF/22012035146942 — Neno Archid Falodhyan rajju/laxman | Completed | 65100 | 28665 | 2024-08-27 | 2026-06-03
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Boundary Line Plantation of Horticulture Trees for Individuals | Plantation | 1736007073/IF/22012035146949 — Neno Archid Falodhyan Bharat/kisan | Completed | 65100 | 23724 | 2024-09-03 | 2026-05-18
| 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Boundary Line Plantation of Horticulture Trees for Individuals | Plantation | 1736007073/IF/22012035149812 — Neno Archid Falodhyan Fulvan/Mannu dhurve | Closed | 65100 | 0 | 2023-07-20
| 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation of Forstry Trees for Individual / Boundary Line Plantation of Forestry Trees for Individuals | Plantation | 1736007073/IF/22012035149820 — Neno Archid Falodhyan Fulvan/Mannu dhurve | Deleted | 0 | 0 | 2023-07-20
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1736007073/IF/22012035486417 — KHET TALAB NIRMAN HARIRAM SAHU GULAB SAHU SIRKUHI | Physically Completed | 55865.38 | 27683.04 | 2025-05-09 | 2026-05-20
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1736007073/IF/22012035522615 — Kapil dhara kup nirman kary Champalal Sahu/ Ramdayal sahu sirkuhi | New | 0 | 0 | 2025-04-14
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1736007073/IF/22012035522680 — Kapil dhara kup nirman kary Champalal Sahu/ Ramdayal sahu sirkuhi | Approved | 322434.5 | 0 | 2025-04-14
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Line-coast Plntation-Farm Forstry Trees-Individual / Along the coast Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1736007073/IF/22012035619193 — EK BAGIYA MAA KE NAAM JAMBATI /HARIRAM SAHU | New | 0 | 0 | 2025-08-19
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1736007073/IF/22012035619255 — EK BAGIYA MAA KE NAAM JAMBATI /HARIRAM SAHU | Ongoing | 266577.25 | 88207.16 | 2025-09-14
| 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1736007073/IF/9926704375 — Boulder Med Bandhan Phulvan/ Mannu | Completed | 108000 | 90580 | 2014-02-21 | 2015-02-16
| 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Peripheral Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1736007073/IF/9993692926 — Boulder Med Bandhan- Suhaga Baliram | Completed | 108000 | 85884 | 2015-12-08 | 2016-05-22
| 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Peripheral Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1736007073/IF/9993705387 — बोल्डर मेड बांधन-नत्थू बलीराम | Completed | 285000 | 184618 | 2016-01-19 | 2017-01-15
| 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007073/IF/IAY/1161500 — Construction of IAY House -IAY REG. NO. MP3703649 | Completed | 16340 | 15480 | 2017-08-15 | 2017-12-15
| 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007073/IF/IAY/2095498 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4044140 | Completed | 16720 | 16480 | 2019-08-20 | 2020-07-30
| 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007073/IF/IAY/2112166 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4368395 | Completed | 16720 | 16194 | 2019-08-27 | 2020-07-31
| 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007073/IF/IAY/2142418 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5081351 | Completed | 16720 | 17462 | 2019-08-06 | 2020-07-18
| 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007073/IF/IAY/2153436 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5345973 | Completed | 16720 | 17202 | 2019-07-30 | 2020-07-18
| 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007073/IF/IAY/2153929 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5361007 | Completed | 16720 | 16276 | 2019-07-30 | 2020-06-17
| 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007073/IF/IAY/2204954 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4316679 | Completed | 16720 | 17000 | 2019-09-10 | 2020-06-10
| 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007073/IF/IAY/2205817 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5303347 | Completed | 16720 | 16452 | 2019-07-30 | 2020-06-17
| 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007073/IF/IAY/2404035 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4510628 | Completed | 18050 | 16910 | 2020-06-02 | 2021-01-07
| 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007073/IF/IAY/2434068 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5344468 | Completed | 18050 | 17860 | 2020-05-26 | 2021-01-07
| 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007073/IF/IAY/2536205 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4937162 | Completed | 18050 | 18050 | 2020-06-02 | 2020-10-20
| 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007073/IF/IAY/2677135 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5305908 | Completed | 18050 | 16984 | 2021-04-27 | 2021-12-27
| 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007073/IF/IAY/2687967 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5358252 | Completed | 18050 | 17370 | 2021-04-01 | 2021-12-27
| 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007073/IF/IAY/2693172 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5423401 | Completed | 18050 | 15826 | 2021-04-01 | 2022-04-28
| 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007073/IF/IAY/2693173 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5423413 | Completed | 18050 | 17370 | 2021-04-01 | 2022-05-24
| 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007073/IF/IAY/2835430 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3038969 | Completed | 18050 | 18142 | 2021-04-06 | 2021-12-15
| 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007073/IF/IAY/2857906 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3455728 | Completed | 18050 | 18335 | 2021-04-29 | 2021-12-09
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007073/IF/IAY/3768698 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123804414 | Completed | 19380 | 19236 | 2022-07-05 | 2023-06-10
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007073/IF/IAY/3856753 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126828762 | Completed | 19380 | 19216 | 2022-09-20 | 2022-11-28
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007073/IF/IAY/3857410 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126026372 | Completed | 19380 | 19104 | 2022-11-22 | 2023-06-22
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007073/IF/IAY/4201198 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126655633 | Completed | 19380 | 18312 | 2022-10-11 | 2023-06-22
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007073/IF/IAY/4207220 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149521800 | Completed | 19380 | 19060 | 2022-08-17 | 2023-01-27
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007073/IF/IAY/4628219 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127279508 | Completed | 24795 | 22968 | 2024-11-19 | 2026-01-30
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007073/IF/IAY/4654950 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145383462 | Completed | 24795 | 23085 | 2024-10-29 | 2026-01-30
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007073/IF/IAY/4660608 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148258529 | Ongoing | 24795 | 5346 | 2025-05-05
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007073/IF/IAY/5292933 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147644458 | Completed | 24795 | 21870 | 2025-04-22 | 2026-01-26
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007073/IF/IAY/5293740 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146927446 | Completed | 24795 | 23175 | 2025-04-22 | 2026-02-12
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007073/IF/IAY/5311432 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146948195 | Completed | 24795 | 23085 | 2025-04-29 | 2026-01-26
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007073/IF/IAY/5321185 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149524402 | Completed | 24795 | 21627 | 2025-04-29 | 2026-01-26
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007073/IF/IAY/5322019 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142753540 | Completed | 24795 | 21870 | 2025-04-22 | 2026-01-26
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007073/IF/IAY/5337973 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126813383 | Completed | 24795 | 21870 | 2025-04-22 | 2026-01-26
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007073/IF/IAY/5343090 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142753597 | Completed | 24795 | 19926 | 2025-04-22 | 2026-01-26
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007073/IF/IAY/5387815 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149521765 | Completed | 24795 | 21870 | 2025-04-29 | 2026-01-26
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007073/IF/IAY/5393872 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142753633 | Completed | 24795 | 21870 | 2025-04-22 | 2026-01-26
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007073/IF/IAY/5393873 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142755815 | Completed | 24795 | 23319 | 2025-05-15 | 2026-02-12
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007073/IF/IAY/5395306 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126623938 | Completed | 24795 | 23139 | 2025-06-17 | 2026-01-26
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007073/IF/IAY/5399195 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127278647 | Completed | 24795 | 22374 | 2025-04-29 | 2026-02-28
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007073/IF/IAY/5411457 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126628735 | Completed | 24795 | 23175 | 2025-05-15 | 2026-01-26
| 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007073/IF/IAY/543671 — Construction of IAY House -IAY REG. NO. MP3173668 | Completed | 15865 | 15290 | 2017-03-24 | 2017-12-15
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007073/IF/IAY/5497003 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127878707 | Completed | 24795 | 22599 | 2025-05-06 | 2026-01-26
| 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007073/IF/IAY/549845 — Construction of IAY House -IAY REG. NO. MP3358761 | Completed | 15865 | 15250 | 2017-05-02 | 2018-02-15
| 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007073/IF/IAY/549847 — Construction of IAY House -IAY REG. NO. MP3358784 | Completed | 15865 | 15250 | 2017-05-02 | 2018-02-15
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007073/IF/IAY/5501604 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120230000 | Completed | 24795 | 23085 | 2025-05-20 | 2026-01-26
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007073/IF/IAY/5832571 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143008559 | Completed | 24795 | 23814 | 2025-10-07 | 2026-02-21
| 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007073/IF/IAY/602241 — Construction of IAY House -IAY REG. NO. MP1334865 | Completed | 15865 | 15457 | 2017-03-24 | 2017-12-15
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007073/IF/IAY/6088449 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126627006 | Approved | 24795 | 0 | 2026-01-28
| 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007073/IF/IAY/622099 — Construction of IAY House -IAY REG. NO. MP3159756 | Completed | 15865 | 15270 | 2017-03-24 | 2018-01-27
| 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1736007073/LD/1156 — मेढ बंधान कार्य नरेश/शामू | Completed | 40000 | 10128 | 2011-05-31 | 2012-03-21
| 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1736007073/LD/1157 — मेढ बंधान कार्य अंतरबती/चतरू | Completed | 40000 | 73276 | 2011-05-20 | 2012-06-12
| 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1736007073/LD/1158 — मेढ बंधान कार्य ओमवती/विपतलाल | Completed | 40000 | 34542 | 2011-06-07 | 2012-03-04
| 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1736007073/LD/1589 — झिरिया से फल्‍लीवाला नाला तक निर्माण कार्य | Completed | 100000 | 84663.8 | 2012-05-15 | 2012-07-01
| 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Land Leveling / Levelling/shaping of Wasteland Land for Community | Land Development | 1736007073/LD/22012034293508 — SHANTIDHHAM NIRMAN SHIRKHUI JHIRIYA | Completed | 180000 | 57105 | 2016-11-29 | 2017-06-28
| 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Land Leveling / Levelling/shaping of Wasteland Land for Community | Land Development | 1736007073/LD/22012034294489 — shantidham nirman jhiiriya | Completed | 180000 | 179803.7 | 2016-12-06 | 2017-06-30
| 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play field for Community | Construction of Play field | 1736007073/LD/22012034299981 — Khel Maidan Dobari Jhiriya | Completed | 353000 | 352179.07 | 2017-01-31 | 2018-10-17
| 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1736007073/LD/22012034301612 — kundali khurd talab sevak ke khat ke pass | Closed | 0 | 0 | 2017-01-26
| 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Land Leveling / Levelling/shaping of Wasteland Land for Community | Land Development | 1736007073/LD/22012034309928 — Shantidham Nirman Kundalikhurd | Completed | 180000 | 169406.17 | 2017-05-23 | 2017-07-05
| 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Land Leveling / Levelling/shaping of Wasteland Land for Community | Land Development | 1736007073/LD/22012034314336 — खेल मैदान कुंडली खुर्द | Closed | 0 | 0 | 2017-04-14
| 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1736007073/LD/3799395341 — झिरिया बोल्‍डर मेड बंधान सिताराम/सेवकराम साहू | Completed | 78000 | 76282 | 2013-06-18 | 2014-01-08
| 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1736007073/LD/3799395343 — सिरकुही मेढ बंधान तुकडू/उददे | Completed | 40000 | 40566 | 2013-07-01 | 2014-01-08
| 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1736007073/LD/979 — झिरिया मेंढ बन्‍धान कार्य केसरी/तुलसी | Completed | 0 | 25452 | 2010-05-05 | 2011-01-24
| 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1736007073/LD/980 — झिरिया मेंढ बन्‍धान कार्य अशोक/तुलसीराम | Completed | 0 | 25360 | 2010-05-05 | 2011-01-23
| 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1736007073/LD/981 — झिरिया मेंढ बन्‍धान कार्य श्‍यामू/दालसिंग | Completed | 0 | 22895 | 2010-05-05 | 2011-01-10
| 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1736007073/LD/982 — झिरिया मेंढ बन्‍धान कार्य लखन/धनलाल | Completed | 0 | 23663 | 2010-05-05 | 2011-01-17
| 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play field for Community | Construction of Play field | 1736007073/PG/22012034312052 — Play Ground Kundalikhurd | Completed | 186600 | 181156.9 | 2017-05-23 | 2018-12-06
| 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play field for Community | Construction of Play field | 1736007073/PG/22012034312613 — PLAY GROUND SIRKUHI | Completed | 186600 | 144171 | 2017-09-05 | 2019-07-03
| 2007-2008 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1736007073/RC//19/4/1161 — द्वितीय श्रेणी सडक निर्माण शमसान घाट झिरीया | Completed | 48000 | 35756 | 2008-02-19 | 2009-12-22
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736007073/RC/22012034174558 — सी सी रोड खेमचंद के घर से राजू साहू की घर की ओर | Completed | 63000 | 64034.5 | 2013-07-16 | 2013-09-22
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736007073/RC/22012034177353 — सी सी रोड इरफ़ान के घर से चन्‍द्रभान के घर की ओर | Completed | 89500 | 72417 | 2013-08-04 | 2013-09-15
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1736007073/RC/22012034180122 — SECOND CLASS ROAD BICHHUA MAIN ROAD TO BAGDEO JHEEL | Completed | 500000 | 410625.41 | 2013-09-03 | 2015-01-15
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1736007073/RC/22012034188623 — द्वितीय श्रेणी सडक निर्माण सिरकुही से बडी मोरड की | Completed | 498000 | 477927.75 | 2013-10-04 | 2015-01-15
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736007073/RC/22012034188634 — सी सी रोड‍ निर्माण प्‍यारे पटेल के घर से चिरकुट बा | Completed | 89600 | 87322.05 | 2013-10-04 | 2015-01-15
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Village Drain / Construction of Open / Covered Grey Water/Storm Drain for Community | Construction of Road and Culvert | 1736007073/RC/22012034188637 — नाली निर्माण कार्य सुकमन के घर से हनुमान मंदिर चबू | Completed | 70800 | 63987 | 2013-10-04 | 2014-03-26
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Village Drain / Construction of Open / Covered Grey Water/Storm Drain for Community | Construction of Road and Culvert | 1736007073/RC/22012034188640 — नाली निर्माण कार्य रमेश पवार के घर से महेश पवार के | Completed | 25600 | 21266.74 | 2013-10-04 | 2014-03-26
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1736007073/RC/22012034201025 — IInd Class Road Bichhua Main Road to towards Dhobr | Completed | 306300 | 275652.26 | 2014-01-28 | 2015-01-15
| 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1736007073/RC/22012034207932 — sudhur graam sadak ganesh prasahd shau ke khet se mohan partaty ke khet tak | Completed | 1065000 | 1032090.82 | 2014-04-22 | 2018-11-22
| 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1736007073/RC/22012034291862 — Sudur Sadak Sitaram sahu to fulwan dhurve ke khet tak | Completed | 382000 | 372865.8 | 2015-12-08 | 2018-12-06
| 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736007073/RC/22012034295872 — C.C Road from Raju house to School | Completed | 16000 | 16380 | 2016-01-11 | 2016-01-28
| 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1736007073/RC/22012034302801 — Khet Sadak Yonja - | Deleted | 0 | 0 | 2015-10-30
| 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1736007073/RC/22012034326009 — surdur sadak gram sirkoiy | Closed | 0 | 0 | 2016-01-26
| 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1736007073/RC/22012034326010 — sudur sadak kudali khurd | Closed | 0 | 0 | 2016-01-26
| 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1736007073/RC/22012034372650 — sudur road | Closed | 0 | 0 | 2017-10-02
| 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736007073/RC/22012034396140 — Puliya Nirman Sirkuhi to Umariya Road, Hanumant Nala | Completed | 450000 | 449869 | 2018-10-25 | 2019-01-07
| 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736007073/RC/22012034536186 — C C Road Nirman Shaskiy Kup se Kichan shed tak Jhiriya | Completed | 38200 | 38190 | 2020-09-08 | 2020-11-30
| 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736007073/RC/22012034548313 — Puliya Nirman Jamunghonda Nale Me Jhiriya | Completed | 1160877.36 | 1154463.13 | 2020-11-17 | 2021-06-17
| 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736007073/RC/22012034550056 — C C Road Nirman Shivram ke makan se chhiddu ke makan tak | Completed | 112860 | 112670 | 2020-11-27 | 2021-03-03
| 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736007073/RC/22012034651738 — सी सी रोड निर्माण कार्य दाजीबा पवार के मकान से मज्जिद तक झिरिया | Completed | 27000 | 26764 | 2023-10-06 | 2024-02-15
| 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1736007073/RC/8918 — झि‍रिया/ रोड निमार्ण कार्य पी डब्‍लू डी मार्ग से जमुनिय माधो द्वितीय श्रंणी संडक निमार्ण भाग 2 | Completed | 127600 | 178764 | 2008-05-11 | 2009-12-31
| 2007-2008 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1736007073/RC/8951 — सड़क निर्माण कार्य झिरिया बस स्‍टाप से उमरिया रोड तक भाग 1 | Deleted | 0 | 0 | 2008-01-26
| 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1736007073/RC/8952 — सडक निमाण कार्य झिरिया बस स्‍टाप से उमरिया भाग 1 | Completed | 197600 | 557158 | 2009-01-01 | 2011-01-23
| 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1736007073/RC/8953 — सडक निर्माण कार्य झिरिया बसस्‍टाप से उमरिया रोड तक भाग 2 | Completed | 147600 | 489570.5 | 2009-02-24 | 2011-01-30
| 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1736007073/RC/8994 — सिरकुही से टोला द्वितीय श्रेणी सडकनिर्माण कार्य | Completed | 197600 | 729483 | 2009-02-15 | 2011-01-28
| 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1736007073/RC/9111 — सडक निर्माण कार्य कुण्‍डाली खुर्द से किरारी ढाना-1 | Completed | 492000 | 627564.2 | 2010-12-20 | 2011-10-10
| 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1736007073/RC/9169 — झिरिया जामुनगोदा से बिछुआ मार्ग तक | Completed | 492000 | 487765.4 | 2011-05-31 | 2012-05-30
| 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1736007073/RC/9199 — रोड निर्माण कार्य सिरकुही से तालाब तक | Completed | 597000 | 468323 | 2011-11-06 | 2013-03-31
| 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1736007073/RC/9200 — झिरिया तालाब टोला से बिछुआ मुख्‍य मार्ग | Completed | 499000 | 503175.6 | 2011-11-05 | 2013-03-31
| 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1736007073/RC/9201 — बिछुआ मुख्‍य मार्ग से ढोबरीनाला रोड | Completed | 497000 | 503147.27 | 2011-11-04 | 2012-06-16
| 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1736007073/RC/9202 — झिरिया जामुनगोदा से बिछुआ मुख्‍य मार्ग भाग 2 | Completed | 332000 | 322269.3 | 2011-11-05 | 2012-05-30
| 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1736007073/RC/9203 — कुण्‍डाली खुर्द से किरारीढाना भाग 2 | Completed | 357000 | 263311 | 2011-11-15 | 2013-03-31
| 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736007073/RC/9240 — cc रोड निर्माण कार्य समी खान के घर से शासकिय हेडपम | Completed | 185000 | 121827.2 | 2012-07-10 | 2013-08-25
| 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1736007073/RC/9293 — द्वितीय श्रेणी सडक निर्माण कार्य झिरिया तालाब टोला से बिछुआ मुख्‍य मार्ग भाग 2 | Completed | 499000 | 298794 | 2013-02-05 | 2013-03-31
| 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1736007073/RC/9294 — द्वि. श्रे. स. निर्माण कार्य मुख्‍य मार्ग से अ | Completed | 499000 | 494971.92 | 2013-01-15 | 2015-02-26
| 2007-2008 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1736007073/RC/झिरिया 20/20 — p.w.d.रोड से जमुनिया माधोक‍ि सीमा तक | Completed | 496000 | 195187 | 2007-12-25 | 2009-12-30
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1736007073/RS/22012034190932 — निर्मल भारत अभियान ( माधवराव / घुडिया ) | Completed | 4400 | 4385.5 | 2014-01-28 | 2015-01-15
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1736007073/RS/22012034199332 — Nirmal Bhart Abhiyan - Parvti/ Ethoba Pawar | Completed | 4400 | 4385.5 | 2014-01-29 | 2015-01-15
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1736007073/RS/22012034202462 — Nirmal Bhart Abhiyan -DASRU/PREMLAL TANDEKAR | Completed | 4400 | 4385.5 | 2014-02-11 | 2015-01-15
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1736007073/RS/22012034207744 — NIRMAL BHART ABHIYAN MAHADEV/SIRI PANAR | Completed | 4400 | 4385.5 | 2014-03-04 | 2015-01-15
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1736007073/RS/22012034209872 — निर्मल भारत अभियान सुकमन/चैतराम | Completed | 4400 | 4385.5 | 2014-03-04 | 2015-01-15
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1736007073/RS/22012034209897 — निर्मल भारत अभियान गामाजी/हरीराम पवार | Completed | 4400 | 4385.5 | 2014-03-04 | 2015-01-15
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1736007073/RS/22012034209900 — निर्मल भारत अभियान सरीफ खान /शहीदखान | Completed | 4400 | 4385.5 | 2014-03-04 | 2015-01-15
| 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1736007073/RS/22012034209912 — निर्मल भारत अभियान सकील /सहीदखान | Deleted | 0 | 0 | 2012-04-14
| 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1736007073/RS/22012034215808 — ि‍नर्मल भारत अ ि‍भयान सकील/सहीदखां | Completed | 4400 | 4385.5 | 2014-03-11 | 2015-01-15
| 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1736007073/RS/22012034248824 — Nirmal Bhart Abhiyan Jhiria Part 1 10 Beneficial | Completed | 44000 | 41937.79 | 2014-07-08 | 2015-01-15
| 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1736007073/RS/22012034248832 — Nirmal Bharat Abhiyan Sirkuhi (12 Beneficial) Par | Completed | 52800 | 53444 | 2014-07-08 | 2015-01-11
| 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Repair & maint of Open/Covered Grey_Water for Comm / Repair and maintenance of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1736007073/RS/22012035116369 — C C Nali Nirman Kalua ke makan se kanhaiya ke makan tak | Completed | 54000 | 53309.06 | 2024-03-19 | 2025-05-14
| 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Repair & maint of Open/Covered Grey_Water for Comm / Repair and maintenance of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1736007073/RS/22012035116438 — C C Nali Nirman dinesh pawar ke makan se bajerao ke makan tak | Closed | 28000 | 0 | 2023-10-05
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1736007073/WC/22012034821549 — CTR-SOKFIT NIRMAN SYAMU KE MAKAN KE PASS HEDPAMP KUNDALI KHURD | Completed | 27458.99 | 9866.3 | 2021-10-08 | 2024-08-12
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1736007073/WC/22012034821553 — CTR-SOKFIT NIRMAN SHIVRAM KE MAKAN KE PASS HEDPAMP KUNDALI KHURD | Closed | 0 | 0 | 2021-08-18
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1736007073/WC/22012034824369 — CTR-SOKFIT NIRMAN VISNIYA KE MAKAN PASS HEDPAMP KUNDALI KHURD | Closed | 0 | 0 | 2021-08-18
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1736007073/WC/22012034905019 — NALA SUDURIKARAN KARYA JHIRIYA | Closed | 0 | 0 | 2022-01-25
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Boundary Line Plantation-Farm Forestry-Community / Boundary Line Plantation of Farm Forestry Trees for Community | Plantation | 1736007073/WC/22012034923903 — माँ की बगिया माध्यमिक स्कुल सिरकुही | Closed | 0 | 0 | 2022-03-03
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Boundary Line Plantation-Shelter Belt Trees (Comm) / Boundary Line Plantation of Shelter Belt Trees for Community | Plantation | 1736007073/WC/22012034923906 — माँ की बगिया माध्यमिक स्कुल सिरकुही | Closed | 0 | 0 | 2022-03-03
| 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Boundary Line Plantation-Shelter Belt Trees (Comm) / Boundary Line Plantation of Shelter Belt Trees for Community | Plantation | 1736007073/WC/22012034923907 — माँ की बगिया माध्यमिक स्कुल सिरकुही | Closed | 0 | 0 | 2022-03-03
| 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1736007073/WC/22012034979392 — NALA SUDURIKARAN KARYA JHIRIYA puliya se pawar ke khet tak | Closed | 0 | 0 | 2022-04-14
| 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Boundary Line Plantation of Forestry-Community / Boundary Line Plantation of Forestry Trees for Community | Plantation | 1736007073/WC/22012034987960 — माँ की बगिया माध्यमिक स्कुल सिरकुही | Closed | 8871.96 | 0 | 2022-04-14
| 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Boundary Line Plantation of Forestry-Community / Boundary Line Plantation of Forestry Trees for Community | Plantation | 1736007073/WC/22012034987961 — माँ की बगिया माध्यमिक स्कुल झिरिया | Closed | 8871.96 | 0 | 2022-04-14
| 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1736007073/WC/22012035058490 — Contour Trench Nirman Vahab patel kekhet ke pass | Completed | 520212.05 | 450288.48 | 2023-08-22 | 2026-04-15
| 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Brushwood Check Dam for Community / Construction of Brushwood Check Dam for Community | Construction of Check Dam/Stop Dam | 1736007073/WC/22012035071533 — BOULDER CHECK DAMS PAWAR KE KETKE PASS JHIRYA | Closed | 0 | 0 | 2023-04-14
| 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Brushwood Check Dam for Community / Construction of Brushwood Check Dam for Community | Construction of Check Dam/Stop Dam | 1736007073/WC/22012035071545 — BOULDER CHECK DAMS MAHUVA KE PED PASS JHIRYA | Closed | 0 | 0 | 2023-04-14
| 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Brushwood Check Dam for Community / Construction of Brushwood Check Dam for Community | Construction of Check Dam/Stop Dam | 1736007073/WC/22012035071546 — BOULDER CHECK DAMS MAHUVA KE PED PASS JHIRYA | Closed | 0 | 0 | 2023-04-14
| 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Brushwood Check Dam for Community / Construction of Brushwood Check Dam for Community | Construction of Check Dam/Stop Dam | 1736007073/WC/22012035071550 — BOULDER CHECK DAMS CHHIND KE PED PASS JHIRYA | Closed | 0 | 0 | 2023-04-14
| 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Brushwood Check Dam for Community / Construction of Brushwood Check Dam for Community | Construction of Check Dam/Stop Dam | 1736007073/WC/22012035071556 — BOULDER CHECK DAMS JAMUN GONDHA NALA ME PASS JHIRYA | Closed | 0 | 0 | 2023-04-14
| 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1736007073/WC/22012035166136 — कन्टूरट्रेंच निर्माण कार्य | New | 0 | 0 | 2023-10-02
| 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1736007073/WC/22012035272420 — Dugwell Recharge Naljal kup Sirkuhi | Physically Completed | 25899.46 | 24940.18 | 2025-04-24 | 2026-02-13
| 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1736007073/WC/22012035272480 — Dugwell Recharge Sarvjanik kup Kundali Khurd | Physically Completed | 25899.46 | 24926.77 | 2025-04-24 | 2026-02-13
| 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1736007073/WC/22012035288598 — Dug well Recharge Fit Naljal kup Gram Jhiriya | Physically Completed | 25899.46 | 24880.88 | 2025-05-01 | 2026-02-13
| 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1736007073/WC/22012035288741 — Dugwell Recharge Fit Sarvjanik kup Sirkuhi | Physically Completed | 25899.46 | 24902.55 | 2025-05-01 | 2026-02-13
| 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1736007073/WC/22012035307326 — Contour Trench Nirman Semar bali pahadi Kundali Kurd | Completed | 199838.92 | 174115.66 | 2025-06-03 | 2026-05-20
| 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1736007073/WC/22012035309349 — Contour Trench Nirman Ganesh sahu ke khet ke niche bali Pahadi me gram Sirkuhi | Completed | 199838.92 | 169789.11 | 2025-06-03 | 2026-05-22
| 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1736007073/WC/7967 — कपिल धारा कूप निर्माण तूकडू/उद़े सिरकुही | Completed | 111000 | 88770 | 2008-01-06 | 2008-10-23
| 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1736007073/WC/7969 — कपिलधारा कूप निर्माण अशोक/तुलसीराम | Completed | 111000 | 5634 | 2008-01-05 | 2007-01-01
| 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1736007073/WC/8239 — झिरिया निस्‍तारी तालाब गहरीकरण | Completed | 0 | 106719 | 2010-04-02 | 2011-02-05
| 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Stone Bund / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1736007073/WC/8288 — निर्मल नीर कूप निर्माण कार्य | Completed | 280000 | 250990.5 | 2011-03-04 | 2013-03-31
| 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Stone Bund / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1736007073/WC/8289 — निर्मल नीर कूप निर्माण कार्य झिरिया | Completed | 280000 | 251477 | 2011-03-04 | 2013-03-31
| 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Stone Bund / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1736007073/WC/8460 — कपिल धारा कुप निर्माण राजु/सुखपाल | Completed | 237000 | 199882.74 | 2012-02-14 | 2013-04-02
| 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Stone Bund / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1736007073/WC/9993638215 — Gully Plug Talab Pahadi | Completed | 173600 | 1022 | 2013-10-04 | 2014-08-16
| 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1736007073/WC/mnnu /jillu/19/4/1160 — kup niman kary mnnu /jillu | Completed | 111000 | 146170.6 | 2007-12-30 | 2009-03-07
| 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1736007073/WC/झिरीया /12/46 — कूप निर्माण कार्य सुकमन/बैशाकू | Completed | 111000 | 98192 | 2007-12-28 | 2008-10-23
| 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation of Fisheries Ponds for Community / Renovation of Fisheries Ponds for Community | Repair & maint of Pond/ Tank | 1736007073/WH/19962197 — तालाब जीर्णोद्धार/मरम्मत निर्माण कार्य ग्राम झिरिया | Completed | 345000 | 340785.1 | 2017-05-30 | 2019-07-03
| 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1736007073/WH/19962205 — तालाब जीर्णोद्धार/मरम्मत निर्माण कार्य ग्राम सिरकुही गोसाई देव तालाब | Completed | 346000 | 344356.46 | 2017-05-30 | 2020-05-25
| 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Excavation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1736007073/WH/अशोक/ तूलसीराम/19/4/1159 — कूप निर्माण कार्य अशोक/ तूलसीराम | Completed | 111000 | 128215.8 | 2007-12-22 | 2009-03-07
| 2007-2008 | D--RURAL INFRASTUCTURE / Renovation of traditional water bodies | Strengthening of Embankment / Construction of Embankment for community | Renovation of traditional water bodies | 1736007073/WH/झ‍िरिया//1158 — कुप निर्माण कार्य | Completed | 111000 | 165200 | 2007-12-22 | 2009-03-07
| 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Excavation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1736007073/WH/मन्‍नू/जिल्‍लू/19/4/1160 — कूप निमााकूप निर्माण कार्य मन्‍नू/जिल्‍लू | Deleted | 0 | 0 | 2015-04-15
| 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736/RC/22012034609122 — Periodical Regraveling Of CMGSY Road From T-06 to Kundali Khurd | Completed | 239000 | 199313.21 | 2022-03-16 | 2023-02-13
| 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Dam / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1736/WC/22012034386148 — NISTARI WATER TANK SIRKOHI | Completed | 4291000 | 2873997.59 | 2018-02-09 | 2019-12-23