## Work List
Exported on: 2026-09-11 12:18:20
Filters applied:
Data source: VBGRAMG
District: BALAGHAT
Block: LALBARRA
Panchayat: MOHGAON DH
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1738003033/IC/22012034891911 — kup nirman kary mokchdham surjatola me | New | 0 | 0 | 2025-04-01
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1738003033/IF/22012035303054 — kapil dhara kup nirman kary Sunita /Nandkishor mohgaon dh | Ongoing | 251024.34 | 0 | 2025-03-28
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1738003033/IF/22012035315509 — Khet talab nirman kary Arun/Pancham Mohgaon Dha | Approved | 0 | 0 | 2025-01-21
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1738003033/IF/22012035315519 — Khet talab nirman kary Samula/Punaram Mohgaon Dha | Approved | 0 | 0 | 2025-01-21
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1738003033/IF/22012035485287 — khet talab nirman kary Dinesh/Dharam Khongatola | Approved | 138138.91 | 0 | 2025-04-01
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1738003033/IF/22012035485466 — kapil dhara kup nirman kary Dinesh/Ruplal khongatola | Approved | 0 | 0 | 2025-04-01
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1738003033/IF/22012035515201 — Khet Talab Nirman Kary Rekha/Naresh Mohgaon | Approved | 137007.34 | 0 | 2025-04-15
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1738003033/IF/22012035527670 — khet talab nirman kary Hemchand/Ramsingh surjatola | Approved | 137029.97 | 0 | 2025-04-01
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1738003033/IF/22012035527682 — khet talab nirman kary Laxman/Mahipal surjatola | Approved | 136962.34 | 0 | 2025-04-01
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1738003033/IF/22012035528732 — khet talab nirman kary Taranbai/Tiwarilal surjatola | Approved | 137200.2 | 0 | 2025-04-01
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1738003033/IF/22012035539194 — khet talab nirman kary Tinkesh/Satanand Mohgaon dh | Approved | 137490.51 | 0 | 2025-04-01
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1738003033/IF/22012035543235 — kapil dhara kup nirman kary Kewalsingh/Dashrath Surjatola | Approved | 0 | 0 | 2025-04-01
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1738003033/IF/22012035543775 — khet talab nirman kary Durgabai/Asharam Khongatola | Approved | 137490.51 | 0 | 2025-04-01
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1738003033/IF/22012035548629 — kapil dhara kup nirman kary Dinesh/Ruplal khongatola | Approved | 0 | 0 | 2025-04-01
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1738003033/IF/22012035548645 — kapil dhara kup nirman kary Balram/parasram mohgaon dh | Approved | 0 | 0 | 2025-04-01
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1738003033/IF/22012035577655 — khet talab nirman kary Sunil/Dasharam surjatola | Approved | 0 | 0 | 2025-04-01
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1738003033/IF/22012035588635 — Ek bagiya maa ke naam Amrita MP38 003 033 001/1090A | Ongoing | 195356.09 | 0 | 2025-09-05
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1738003033/IF/22012035588701 — Ek bagiya maa ke naam KIRAN MP 38 003 033 001/1006B | Ongoing | 206759.57 | 0 | 2025-08-30
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1738003033/IF/22012035617018 — Ek bagiya maa ke naam Sarita Nagpure Mohgaon Dha | Approved | 0 | 0 | 2025-08-15
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1738003033/IF/22012035619741 — Ek Bagiya Maa Ke naam Skhwanti suraj Nagpure | Approved | 162502.27 | 0 | 2025-08-15
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1738003033/IF/22012035625699 — Ek Bagiya Maa Ke naam Anjani Dashriya | Ongoing | 162502.27 | 0 | 2025-10-14
| 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1738003033/IF/22012035625706 — Ek Bagiya Maa Ke naam Hemeshwari Dashariye | Ongoing | 162503.12 | 0 | 2026-08-09
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1738003033/IF/22012035625707 — Ek Bagiya Maa Ke naam Hemeshwari Dashariye | Ongoing | 162502.27 | 0 | 2025-10-17
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1738003033/IF/22012035625710 — Ek Bagiya Maa Ke naam Lilavati | Approved | 0 | 0 | 2025-08-15
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1738003033/IF/22012035625711 — Ek Bagiya Maa Ke naam Rangita Damahe | Approved | 162503.12 | 0 | 2025-08-15
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1738003033/IF/22012035639476 — Ek Bagiya Maa Ke naam Pushplata | Ongoing | 162503.12 | 0 | 2025-11-21
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1738003033/IF/22012035639482 — Ek Bagiya Maa Ke naam Geeta | New | 0 | 0 | 2025-08-15
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1738003033/IF/22012035639483 — Ek Bagiya Maa Ke naam Geeta | Ongoing | 162503.12 | 0 | 2025-11-21
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1738003033/IF/22012035650924 — Ek Bagiya Maa Ke naam Pushplata mohgaon dha | Approved | 162503.12 | 0 | 2025-08-15
| 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738003033/IF/IAY/1142776 — Construction of IAY House -IAY REG. NO. MP-38-003-033-001/23703 | Approved | 28500 | 0 | 2015-10-06
| 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738003033/IF/IAY/2656046 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2665129 | Approved | 28500 | 0 | 2020-10-21
| 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738003033/IF/IAY/3210354 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2725499 | Physically Completed | 24795 | 4500 | 2023-05-23 | 2026-08-09
| 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738003033/IF/IAY/3320614 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5589976 | Approved | 28500 | 0 | 2021-11-03
| 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738003033/IF/IAY/3426872 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5157599 | Approved | 28500 | 0 | 2021-12-02
| 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738003033/IF/IAY/3518624 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3695755 | Approved | 28500 | 0 | 2022-01-03
| 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738003033/IF/IAY/3521625 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3881048 | Approved | 28500 | 0 | 2022-01-03
| 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738003033/IF/IAY/3545014 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4756904 | Approved | 28500 | 0 | 2022-01-04
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738003033/IF/IAY/3639709 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2995475 | Ongoing | 28500 | 0 | 2022-08-31
| 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738003033/IF/IAY/4386608 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3177392 | Approved | 28500 | 0 | 2022-11-25
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738003033/IF/IAY/5088290 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129315391 | Ongoing | 28500 | 0 | 2025-03-24
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738003033/IF/IAY/5475573 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP137748922 | Approved | 28500 | 0 | 2025-03-25
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738003033/IF/IAY/5479770 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP133944039 | Approved | 28500 | 0 | 2025-04-08
| 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738003033/IF/IAY/5638950 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128534483 | Ongoing | 28500 | 22500 | 2026-07-27
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738003033/IF/IAY/5639329 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129636711 | Approved | 28500 | 0 | 2025-04-11
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738003033/IF/IAY/5644238 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132869063 | Approved | 28500 | 0 | 2025-05-07
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738003033/IF/IAY/5686682 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP135563379 | Approved | 28500 | 0 | 2024-09-25
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738003033/IF/IAY/5709508 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP137292581 | Approved | 28500 | 0 | 2025-01-25
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738003033/IF/IAY/5709636 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP135563472 | Approved | 28500 | 0 | 2025-05-16
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738003033/IF/IAY/5938232 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126933957 | Approved | 28500 | 0 | 2026-02-11
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738003033/IF/IAY/5943126 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125667368 | Approved | 28500 | 0 | 2026-02-11
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738003033/IF/IAY/6153163 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125663352 | Approved | 28500 | 0 | 2025-03-08
| 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738003033/IF/IAY/62896 — Construction of IAY House -IAY REG. NO. MP-38-003-033-001/6814 | Approved | 28500 | 0 | 2015-10-05
| 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1738003033/RC/22012034676191 — Sudur sadak nirman kary surjatola | New | 0 | 0 | 2024-01-26
| 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1738003033/RC/22012034819179 — cc road nirman kary ward no 6 mohgaon dh | Approved | 0 | 0 | 2024-06-08
| 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1738003033/RC/22012034840922 — Men Road Ramprasad Dashariye ke ghar se Mastram Durgaji Basene ke khet Tak Khongatola Mohgaon dh | Ongoing | 1599603.74 | 0 | 2025-03-31
| 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1738003033/RC/22012034845010 — c c road nirman kary ward no 20 raju biranwar ke ghar se buddi tikra tak | Approved | 46000 | 0 | 2025-04-01
| 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1738003033/RC/22012034845011 — c c road nirman kary ward no 13 sajan ke ghar se sosayti tak | Approved | 46000 | 0 | 2025-04-01
| 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1738003033/RS/22012034693133 — dayaram ke ghar ke pass sokpit nirman kary ward no.20 surjatola | Ongoing | 57828.6 | 0 | 2023-06-25
| 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1738003033/WC/22012035299821 — recharge pit nirman kary ward no 20 dharamchand dashriye ke ghar ke pass surjatola | Approved | 23977.32 | 0 | 2025-04-01
| 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1738003033/WC/22012035306534 — Naveen Talab Nirman Kary Khongatola | Ongoing | 1743311.85 | 0 | 2025-05-23
| 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1738003033/WC/22012035309368 — Parculation Tank nirman kary surjatola mohgaon | Approved | 199957.71 | 0 | 2025-04-01
| 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1738003033/WC/22012035326529 — Sanjay Nikunj Udyan me Naveen Talab Nirman kary Mohgaon dh | Approved | 0 | 0 | 2025-12-08
| 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1738/RC/22012034851482 — GRAM SURJA TOLA ME RAJU BIRNVAR KE MAKAN SE DAYARAM KE GHAR TAK CC ROAD NIRMAN KARYA | Approved | 148000 | 0 | 2025-04-14
| 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1738/RC/22012034851486 — WARD NO 04 SANTOSH NAGPURE KE GHAR SE DURGA JEE KE BASENE KE KHET KI OR GRAVEL SADAK NIRMAN KARYA | Ongoing | 411000 | 0 | 2025-12-27