## Work List
Exported on: 2026-09-07 06:29:18
Filters applied:
Data source: VBGRAMG
District: BALAGHAT
Block: PARASWADA
Panchayat: GUDMA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1738008050/IF/22012035309409 — khet Talab Sarasvati bai / tijulal | New | 0 | 0 | 2025-01-30
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1738008050/IF/22012035495282 — Khet talab Saraswati bai/Tijulal Gudma | New | 0 | 0 | 2025-04-01
| 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1738008050/IF/22012035661222 — Khet talab Sohanlal/Sunhar Gudma | Ongoing | 199971.39 | 0 | 2026-02-17
| 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738008050/IF/IAY/1088168 — Construction of IAY House -IAY REG. NO. MP2907992 | Approved | 28500 | 0 | 2017-05-10
| 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738008050/IF/IAY/2533887 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4888864 | Ongoing | 28500 | 0 | 2020-05-25
| 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738008050/IF/IAY/3475532 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5098585 | Ongoing | 28500 | 0 | 2022-03-07
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738008050/IF/IAY/4563569 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115812204 | Approved | 28500 | 0 | 2024-09-10
| 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738008050/IF/IAY/4908891 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115812414 | Ongoing | 28500 | 0 | 2025-03-27
| 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738008050/IF/IAY/638133 — Construction of IAY House -IAY REG. NO. MP1424463 | Approved | 28500 | 0 | 2017-02-13
| 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1738008050/RC/22012034835872 — Construction of cc road from main road chinditola to puliya | New | 0 | 0 | 2024-08-01
| 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1738008050/RC/22012034835873 — Construction of cc road from main road chinditola to puliya | Ongoing | 48000 | 0 | 2025-02-17
| 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1738008050/RC/22012034835874 — Construction of Rcc drain w no 18 19 Gudma | Ongoing | 141000 | 3915 | 2025-03-12
| 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1738008050/RC/22012034846817 — Test cc road 2025 | Approved | 45000 | 0 | 2025-05-15
| 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1738008050/RS/22012035123194 — Construction of pcc drain from house of umesh to house of Salik ram | New | 0 | 0 | 2024-01-24
| 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1738008050/WC/22012035141871 — Construction of Stop dam on Gudma nala GP Gudma | Ongoing | 2401999.46 | 0 | 2023-10-08
| 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter-Borewell recharge for Comm / Construction of Sand filter for borewell recharge for Community | Well Recharge | 1738008050/WC/22012035309055 — JGSA Dugwell recharge near shamshanghat Gudma | Approved | 0 | 0 | 2025-04-14
| 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1738008050/WC/22012035318513 — test talab 2025 | Approved | 45000 | 0 | 2025-05-15
| 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1738008050/WC/22012035318518 — test nirmanl neer 2025 | Approved | 45000 | 0 | 2025-05-15