## Work List
Exported on: 2026-10-21 06:42:52
Filters applied:
Data source: VBGRAMG
District: MORENA
Block: All
Panchayat: MALBASAI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
AMBAH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Fisheries | Construction of Fisheries Ponds for Community / Construction of Fishery Pond for Community | Construction of Tank | 1701001008/FR/22012034322702 — Talav nirman kary hori bai ke dande par | Ongoing | 1463773.9 | 0 | 2025-07-06
AMBAH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Fisheries | Construction of Fisheries Ponds for Community / Construction of Fishery Pond for Community | Construction of Tank | 1701001008/FR/22012034322710 — Talav nirman kary kola ki nariya ke pass | Ongoing | 1496330.6 | 0 | 2025-02-22
AMBAH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1701001008/IF/22012034859130 — Bad Rahat Awash nirmad vijendra / munasi kisroli | Ongoing | 17370 | 0 | 2026-01-01
AMBAH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1701001008/IF/22012034859147 — Bad Rahat Aawash nirmad shrilal/ munsi kisroli | Ongoing | 17370 | 0 | 2026-01-01
AMBAH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1701001008/IF/22012035491272 — khet talab rameswar ke khet mai kisroli | Approved | 147621.16 | 0 | 2025-04-14
AMBAH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1701001008/IF/22012035491319 — khet talab ranchor singh ke khet mai kisroli | Approved | 147621.16 | 0 | 2025-04-14
AMBAH | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1701001008/RC/22012034838677 — cc kharanja nirmad kartarsingh ke makan se mohan singh ke gar tak dhaniram pura | Approved | 55800 | 0 | 2024-04-14
AMBAH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1701001008/WC/22012035323228 — Talab nirman kary hanuman mandir ke bagal me | Approved | 0 | 0 | 2025-10-02
AMBAH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1701001008/WC/22012035323279 — Talab Nirman Kary Katebna ke Dhagre ke pass | Approved | 0 | 0 | 2025-10-02
AMBAH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1701001008/WC/22012035323280 — Talab Nirman Kary neele khai ke pass | Approved | 0 | 0 | 2025-10-02
AMBAH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1701001008/WC/22012035323281 — Talab Nirman Kary Parimal Ke Kua ke Pass | Approved | 0 | 0 | 2025-10-02
AMBAH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1701001008/WC/22012035323282 — Talab Nirman Kary Mkheda Ke Dhagre Ke Pass | Approved | 0 | 0 | 2025-10-02
AMBAH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1701001008/WC/22012035323283 — Talab Nirman Kary Bhori Ki Naiya Ke Pass | Approved | 0 | 0 | 2025-10-02
AMBAH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1701001008/WC/22012035323284 — Talab Nirman Kary Jharna khar ke Piche | Approved | 0 | 0 | 2025-10-02
AMBAH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1701001008/WC/22012035323285 — Talab Nirman Kary Khere Ki Khadiya Ke Pass | Approved | 0 | 0 | 2025-10-02
AMBAH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1701001008/WC/22012035323287 — Talab Nirman Kary Unche Dande Ke Pass | Approved | 0 | 0 | 2025-10-02
AMBAH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1701001008/WC/22012035323288 — Talab Nirman Kary Jasrath Ki Naiya Ke Pass | Approved | 0 | 0 | 2025-10-02
AMBAH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1701001008/WC/22012035327755 — Talab Nirman Kary Udayveer ke khet ke pass | Ongoing | 1486703.85 | 0 | 2026-02-18
AMBAH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1701001008/WC/22012035327757 — Talab Nirman Kary komal ke khet ke pass | Ongoing | 1488330.06 | 0 | 2026-02-18