## Work List
Exported on: 2026-10-23 23:56:38
Filters applied:
Data source: MGNREGA + VBGRAMG
District: MORENA
Block: All
Panchayat: RAMPURGUNJ
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
MORENA | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1701003005/AV/22012034659318 — शांतिधाम निर्माण कार्य जगराम के पुरा के पास, रामपुरगंज | Approved | 229312.16 | 0 | 2024-06-08
MORENA | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1701003005/AV/22012034659529 — शांतिधाम निर्माण कार्य देवीसिंह का पुरा, रामपुरगंज | Deleted | 0 | 0 | 2024-06-08
MORENA | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play field for Community | Construction of Play field | 1701003005/AV/22012034661524 — खेल मैदान निर्माण कार्य सिद्ध बाबा मंदिर के पास | Deleted | 0 | 0 | 2024-06-08
MORENA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701003005/DP/01 — व़क्षारोपण भरोषी के कुंआ से मीरपुर रोड तक | Completed | 490000 | 1548 | 2008-08-14 | 2008-04-14
MORENA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701003005/DP/02 — व़क्षारोपण देवीसिंह के पुरा से रामपुर रोड तक | Completed | 466250 | 7492.65 | 2008-08-14 | 2008-04-14
MORENA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701003005/DP/03 — व़क्षारोपण मनफूल के पुरा से रामजी लाल के पुरा तक | Completed | 466250 | 5815 | 2008-08-28 | 2008-04-14
MORENA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701003005/DP/04 — व़क्षारोपण देवीसिंह के पुरा से मीरपुर रोड तिराहे तक | Completed | 466250 | 2082 | 2008-08-21 | 2008-04-14
MORENA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701003005/DP/05 — रतनज्‍योति व़क्षारोपण सिद्व बाबा स्‍थान | Completed | 35500 | 6772 | 2008-08-28 | 2008-10-26
MORENA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701003005/DP/06 — बांस पौध रोपण सिद्व देव स्‍थान राखन सिंह का पुरा | Completed | 20000 | 2405 | 2008-08-28 | 2008-10-26
MORENA | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Forest Protection / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701003005/DP/132 — व़क्षारोपड कार्य ग्‍यासीराम का पुरा से गदुआ कापुरा तक | Completed | 0 | 3592 | 2009-09-09 | 2008-04-01
MORENA | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701003005/DP/22012034328737 — वृक्षारोपण कार्य | Deleted | 0 | 0 | 2017-10-02
MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Drought Proofing | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1701003005/DP/22012034526649 — प्रवलित सीमेन्ट कंक्रीट नाली निर्माण बालाजी मंदिर से जगराम के पुरा की ओर | Completed | 44400 | 44390 | 2021-06-17 | 2021-10-21
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Lining of water courses Canal for Community / Lining of water courses Canal for Community | Lining of Canal | 1701003005/DP/22012034539352 — प्रवलित सीमेंट कोंक्रीट नाला निर्माण राखन सिंह के पुरा से सिद्ध बाबा की और ग्राम पंचायत रामपुर गंज | Deleted | 58650 | 0 | 2021-08-13
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Shelter Belt Trees (Comm) / Boundary Line Plantation of Shelter Belt Trees for Community | Plantation | 1701003005/DP/22012034579367 — वृक्षारोपण कार्य -अमृत सरोवर तालाब के पास शिवदेव का पुरा रामपुरगंज | Closed | 427106.07 | 0 | 2023-04-14
MORENA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701003005/DP/277 — निर्मल वाटिका निर्माण कार्य | Completed | 0 | 31935 | 2010-09-04 | 2014-09-14
MORENA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Land Development / Levelling/shaping of Wasteland Land for Community | Land Development | 1701003005/DP/292 — शाती धाम | Completed | 366000 | 229701 | 2011-03-18 | 2014-01-07
MORENA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701003005/DP/293 — शाती धाम देवी सिह का पुरा | Completed | 0 | 2684 | 2011-03-17 | 2011-03-25
MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of intrmediate and Link Water Drain-Comm / Construction of intermediate and Link Storm Water Drain for Community | Works for Flood Control and Protection | 1701003005/FP/22012034627159 — सीमेंट कोंक्रीट नाला निर्माण राखन सिंह के पूरा से सिद्ध बाबा की और ग्राम पंचायत रामपुर गंज | Deleted | 58650 | 0 | 2021-08-13
MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701003005/FP/22012034627160 — सीमेंट कंक्रीट नाला निर्माण राखन के पुरा से सिद्ध बाबा की और ग्राम राखन का पुरा | Completed | 58650 | 57707 | 2021-11-02 | 2021-12-24
MORENA | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood or Diversion Channel for Community | Works for Flood Control and Protection | 1701003005/FP/22012034629630 — पत्थर नाला निर्माण कार्य -पुराना गाव रामपुर गंज | Ongoing | 1484608.82 | 857038.71 | 2022-10-31
MORENA | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood or Diversion Channel for Community | Works for Flood Control and Protection | 1701003005/FP/22012034630988 — पत्थर नाला निर्माण कार्य -रामपुर से नदी की और रामपुरगंज | Ongoing | 1338455.94 | 175696.25 | 2022-12-26
MORENA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Fisheries | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1701003005/FR/22012034322719 — तालाब निर्माण कार्य तोर वालो के पुरा के पास | Deleted | 0 | 0 | 2024-10-02
MORENA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Fisheries | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1701003005/FR/22012034322720 — तालाब निर्माण कार्य हरी सिंह के खेत के पास | Deleted | 0 | 0 | 2024-10-02
MORENA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Fisheries | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1701003005/FR/22012034322721 — तालाब निर्माण कार्य नदी के पास | Deleted | 0 | 0 | 2024-10-02
MORENA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Fisheries | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1701003005/FR/22012034323347 — तालाब निर्माण कार्य दीवान सिंह गुर्जर के खेत के पास तिघरा का पुरा | Deleted | 0 | 0 | 2024-10-02
MORENA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Fisheries | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1701003005/FR/22012034323348 — तालाब निर्माण कार्य सुल्तान सिंह गुर्जर के खेत के पास तिघरा का पुरा | Deleted | 0 | 0 | 2024-10-02
MORENA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Fisheries | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1701003005/FR/22012034323349 — तालाब निर्माण कार्य मुंशी सिंह कुशवाह के खेत के पास तिघरा का पुरा | Deleted | 0 | 0 | 2024-10-02
MORENA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Fisheries | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1701003005/FR/22012034323350 — तालाब निर्माण कार्य अशोक सिंह गुर्जर के खेत के पास तिघरा का पुरा | Deleted | 0 | 0 | 2024-10-02
MORENA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Fisheries | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1701003005/FR/22012034323351 — तालाब निर्माण कार्य कमलेश गुर्जर के खेत के पास तिघरा का पुरा | Deleted | 0 | 0 | 2024-10-02
MORENA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Fisheries | Construction of Fisheries Ponds for Community / Construction of Fishery Pond for Community | Construction of Tank | 1701003005/FR/22012034325107 — तालाब निर्माण कार्य मुंशी के खेत के पास | New | 0 | 0 | 2025-04-14
MORENA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Fisheries | Construction of Fisheries Ponds for Community / Construction of Fishery Pond for Community | Construction of Tank | 1701003005/FR/22012034325108 — तालाब निर्माण कार्य अशोक के खेत के पास | New | 0 | 0 | 2025-04-14
MORENA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Fisheries | Construction of Fisheries Ponds for Community / Construction of Fishery Pond for Community | Construction of Tank | 1701003005/FR/22012034325109 — तालाब निर्माण कार्य प्रताप के खेत के पास | New | 0 | 0 | 2025-04-14
MORENA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Fisheries | Construction of Fisheries Ponds for Community / Construction of Fishery Pond for Community | Construction of Tank | 1701003005/FR/22012034325110 — तालाब निर्माण कार्य दीमान खेत के पास | New | 0 | 0 | 2025-04-14
MORENA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Fisheries | Construction of Fisheries Ponds for Community / Construction of Fishery Pond for Community | Construction of Tank | 1701003005/FR/22012034325111 — तालाब निर्माण कार्य कमलेश गुर्जर खेत के पास | New | 0 | 0 | 2025-04-14
MORENA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Fisheries | Construction of Fisheries Ponds for Community / Construction of Fishery Pond for Community | Construction of Tank | 1701003005/FR/22012034325128 — Talab nirmaan karya sultan gurjar ke khet ke pass | New | 0 | 0 | 2025-04-14
MORENA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Fisheries | Construction of Fisheries Ponds for Community / Construction of Fishery Pond for Community | Construction of Tank | 1701003005/FR/22012034325129 — Talab nirmaan karya hari singh ke khet ke pass | New | 0 | 0 | 2025-04-14
MORENA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Fisheries | Construction of Fisheries Ponds for Community / Construction of Fishery Pond for Community | Construction of Tank | 1701003005/FR/22012034325130 — Talab nirmaan karya tor walo ke pura ke pass | New | 0 | 0 | 2025-04-14
MORENA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Fisheries | Construction of Fisheries Ponds for Community / Construction of Fishery Pond for Community | Construction of Tank | 1701003005/FR/22012034325131 — Talab nirmaan karya nadi ke pass | New | 0 | 0 | 2025-04-14
MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701003005/IF/22012034346623 — सामुदायिक ब़क्षारोपण कार्य-सिद्ध स्थान राखन का पूरा रामपुरगंज | Completed | 335000 | 84794 | 2017-07-03 | 2020-12-18
MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1701003005/IF/22012034816306 — नाडेप बनवारी शर्मा/धर्मनारायन शर्मा के घर के पास सामले सिंह क पुरा{slwm} | Closed | 18552.12 | 0 | 2021-04-26
MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1701003005/IF/22012034816310 — नाडेप रामवरन /श्रीचंद के घर के पास सामले सिंह क पुरा{slwm} | Closed | 18552.12 | 0 | 2021-04-26
MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1701003005/IF/22012034816311 — नाडेप दिलीप/रामबरन के घर के पास सामले सिंह क पुरा{slwm} | Closed | 18552.12 | 0 | 2021-04-26
MORENA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1701003005/IF/22012035452868 — Khet Talab Nirmaan Karya Baijnath Singh S/O Badan Singh | Ongoing | 147621.16 | 261 | 2025-05-08
MORENA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1701003005/IF/22012035452898 — Khet Talab Nirmaan Karya Narendra Sharma S/O Radheshyam | Ongoing | 147621.16 | 261 | 2025-05-08
MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1701003005/IF/22012035453026 — Dugwell Recharg Nirmaan karya Nitin Rathore | Approved | 25899.46 | 0 | 2025-04-14
MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1701003005/IF/22012035453066 — Dugwell Recharg Nirmaan karya Munshi Rathor | Approved | 25899.46 | 0 | 2025-04-14
MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1701003005/IF/22012035453092 — Dugwell Recharg Nirmaan karya Rabina Sharma | Approved | 25899.46 | 0 | 2025-04-14
MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1701003005/IF/22012035453106 — Dugwell Recharg Nirmaan karya Raghubanshi | Ongoing | 25899.46 | 261 | 2025-05-08
MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1701003005/IF/22012035497378 — Dugwell Richarge Pit Nirmaan Karya Hariom Ke Yaha | Closed | 25899.46 | 0 | 2025-05-13
MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1701003005/IF/22012035497394 — Dugwell Richarge Pit Nirmaan Karya Aman Ke Yaha | Closed | 25899.46 | 0 | 2025-05-13
MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1701003005/IF/22012035497400 — Dugwell Richarge Pit Nirmaan Karya Ramesh Ke Yaha | Closed | 25899.46 | 0 | 2025-05-13
MORENA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1701003005/IF/22012035512971 — khet talav nirman kary veerendra ke khet me gram panchayat rampurganj | Approved | 147621.16 | 0 | 2025-04-14
MORENA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1701003005/IF/22012035649239 — Ek Bagiya Ma Ke Naam GIRIJA 163686535 | Ongoing | 283818.64 | 51366 | 2025-12-14
MORENA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1701003005/IF/22012035649240 — Ek Bagiya Ma Ke Naam MEENA 35214950 | Ongoing | 283818.64 | 1566 | 2025-12-14
MORENA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1701003005/IF/22012035649241 — Ek Bagiya Ma Ke Naam RAMA 161973959 | Ongoing | 283818.64 | 51066 | 2025-12-14
MORENA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1701003005/IF/22012035649243 — Ek Bagiya Ma Ke Naam SHASHI 35215185 | Ongoing | 283818.64 | 1566 | 2025-12-14
MORENA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1701003005/IF/22012035649244 — Ek Bagiya Ma Ke Naam GUDDI 161863977 | Ongoing | 283818.64 | 51066 | 2025-12-15
MORENA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1701003005/IF/22012035654636 — Ek Bagiya Ma Ke Naam RABOODI/MATAPRASHAD SHARMA 35214097 | Ongoing | 283818.64 | 0 | 2026-01-11
MORENA | 2011-2012 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1701003005/IF/261 — मेढ वन्‍धान निमार्ण कार्य पंचमसिह पुञ फेरू | Completed | 0 | 16714 | 2011-10-02 | 2011-10-23
MORENA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003005/IF/9926714080 — पशु शेड निर्माण सुरेश शर्मा /धर्मनारायण शर्मा | Deleted | 86000 | 0 | 2014-01-26
MORENA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003005/IF/9926714112 — पशु शेड प्रदीप/रामोतार | Deleted | 0 | 0 | 2014-01-26
MORENA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003005/IF/9993725120 — pashu set nirman shumati sharma/dwarika prsad sharma devi singh ka pura | Deleted | 0 | 0 | 2016-01-26
MORENA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003005/IF/9993725518 — पशु शेड -सभाराम शर्मा/द्वारिकाप्रसाद शर्मा ग्राम देवी सिंह का पूरा | Deleted | 0 | 0 | 2016-01-26
MORENA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003005/IF/9993727998 — पशु शेट निर्माण -राधेशयाम /गोविंदा ग्राम तिघरा का पूरा | Deleted | 0 | 0 | 2016-01-26
MORENA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003005/IF/IAY/199196 — Construction of IAY House -IAY REG. NO. MP-01-003-005-001/23 | Completed | 15030 | 12024 | 2017-01-09 | 2017-06-02
MORENA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003005/IF/IAY/48841 — Construction of IAY House -IAY REG. NO. MP-01-003-005-001/17 | Completed | 14310 | 9972 | 2016-01-18 | 2017-08-02
MORENA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701003005/LD/1118 — मेड वन्‍धान कार्य पहलवान सिह पुञ बदन सिह | Completed | 0 | 16000 | 2010-07-06 | 2010-07-22
MORENA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701003005/LD/1145 — मेड वन्‍धान कार्य हरी सिह पुञ मुकन्‍दी | Completed | 0 | 15600 | 2010-08-09 | 2010-10-20
MORENA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701003005/LD/1146 — मेड वन्‍धान कार्यकेदार पुञ भूपद | Completed | 0 | 7500 | 2010-08-09 | 2010-10-27
MORENA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701003005/LD/1147 — मेड वन्‍धान कार्य सुमेर सिह पुञ हाकिम | Completed | 0 | 15000 | 2010-08-09 | 2010-08-22
MORENA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701003005/LD/1224 — मैडवन्‍धान कार्य राजवीर रामओतार | Completed | 0 | 11700 | 2010-09-22 | 2010-10-27
MORENA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701003005/LD/1225 — मैडवन्‍धान कार्य प्रदीप पुञ रामअवतार | Completed | 0 | 13500 | 2010-09-11 | 2010-10-27
MORENA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701003005/LD/1428 — खेलमेदान रामपुरगंज | Completed | 433700 | 62362 | 2012-02-01 | 2015-10-30
MORENA | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701003005/RC/01 — मिटटी मुरम रोड निर्माण ग्‍यासी राम का पुरा से गड़आ | Completed | 148000 | 99876 | 2008-11-09 | 2009-07-27
MORENA | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003005/RC/1109 — सी सी खरंजा नाली सहित बदना के घर से खेलमैदान एवं श | Completed | 228000 | 216745.09 | 2012-03-09 | 2014-01-07
MORENA | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701003005/RC/17 — मिटटीमुरम निर्माण देवीसिंह का पुरा से मनफूल का पुरा तक | Completed | 148000 | 23159.96 | 2008-12-26 | 2013-12-20
MORENA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003005/RC/22012034182384 — सी सी खरंजा एवं नाली निर्माण कार्य - रमेश के घर से बलबीर के घर की ओर | Completed | 23741 | 13870 | 2014-01-07 | 2014-02-02
MORENA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003005/RC/22012034182387 — सी सी खरंजा एवं नाली निर्माण कार्य - रामभजन से राम | Completed | 103707 | 102476 | 2013-09-18 | 2014-01-07
MORENA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701003005/RC/22012034187329 — पत्थर खरंजा निर्माण कार्य -माता का मन्दिर ग्राम ति | Completed | 497000 | 201135 | 2014-02-27 | 2015-09-30
MORENA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701003005/RC/22012034203118 — पत्‍थर खरंजा निर्माण कार्य - रामवरन के घर से हरिओम | Completed | 307000 | 187225 | 2014-02-27 | 2015-09-30
MORENA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701003005/RC/22012034209670 — पत्थर खरंजा निर्माण - पंडित रामेश्वर दयाल के घर से | Deleted | 498000 | 0 | 2014-03-05
MORENA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701003005/RC/22012034212258 — मिट्टी बजरी रोड | Deleted | 1335490 | 0 | 2014-01-26
MORENA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003005/RC/22012034229505 — सी. सी. खरंजा एंव नाली निर्माण कार्य दर्शन के मकान | Deleted | 41511 | 0 | 2014-03-04
MORENA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003005/RC/22012034229507 — सी. सी. खरंजा एंव नाली निर्माण कार्य - मेनरोड से प | Deleted | 36180 | 0 | 2014-01-26
MORENA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003005/RC/22012034294293 — सी. सी. खरंजा एंव नाली निर्माण कार्य - पूरन सिंह के घर कमल सिंह के घर की और ग्राम राखन सिंह का पूरा | Completed | 115203 | 114893 | 2016-01-25 | 2017-08-22
MORENA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701003005/RC/22012034294432 — पत्थर खरंजा निर्माण-तिघार के पूरा से गैंदालाल के घर नत्थी के घर तक | Completed | 192000 | 92061 | 2016-01-04 | 2017-09-10
MORENA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701003005/RC/22012034307677 — पत्थर खरंजा निर्माण कार्य माता के मंदिर से राजवीर के घर तक | Deleted | 0 | 0 | 2016-01-26
MORENA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003005/RC/22012034307683 — सी सी खरंजा निर्माण केदार के द्वार से भगवती गुर्जर के घर तक | Deleted | 0 | 0 | 2016-01-26
MORENA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701003005/RC/22012034307687 — पत्थर खरंजा निर्माण दुर्जन सिंह के पूरा से मुगाराम का पूरा तक | Deleted | 0 | 0 | 2016-01-26
MORENA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701003005/RC/22012034308878 — मिट्टीबजरी रोड-समुदायक भवन जगराम के पूरा से गडुआ के पूरा तक | Deleted | 0 | 0 | 2016-01-26
MORENA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701003005/RC/22012034308883 — पत्थर खरंजा निर्माण -राजाराम गुर्जर के यहाँ से रामप्रकाश के घर तक | Deleted | 0 | 0 | 2016-01-26
MORENA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701003005/RC/22012034308888 — मिटटी बजरी रोड -रखन सिंह के पूरा से राजवीर के खेत तक | Deleted | 0 | 0 | 2016-01-26
MORENA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701003005/RC/22012034308893 — पत्थर खरंजा निर्माण -मेघ सिंह केघर से राजाराम के घर तक | Deleted | 0 | 0 | 2016-01-26
MORENA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701003005/RC/22012034320638 — सुदूर ग्राम संपर्क सड्क - पीएमजीएसबाई रोड् से सामले का पुरा रामपुरगंज | Completed | 824000 | 568304.39 | 2017-02-06 | 2018-09-30
MORENA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003005/RC/22012034327462 — सी सी खरंजा एवं नाली निर्माण कार्य - केदार के घर से भगवती गुर्जर के घर तक तिघरा का पुरा रामपुरगंज | Completed | 86625 | 81936 | 2017-02-20 | 2017-08-11
MORENA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003005/RC/22012034327466 — सी सी खरंजा एवं नाली निर्माण - रामखिलाड़ी के घर से लक्ष्मन शर्मा तक एवं मेघ सिंह घर तक तिघरापुरा | Completed | 79425 | 78438 | 2017-03-20 | 2017-07-21
MORENA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701003005/RC/22012034339295 — सुदूर ग्राम संपर्क सड्क निर्माण पुलिया सहित- रामपुर से राखन का पुरा तक भाग 1 | Completed | 1153000 | 636845.56 | 2017-06-14 | 2023-07-06
MORENA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701003005/RC/22012034339296 — सुदूर ग्राम संपर्क सडक निर्माण पुलिया सहित- रामपुर से राखन के पुरा भाग 2 | Completed | 1153000 | 467024.07 | 2017-10-24 | 2023-07-06
MORENA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003005/RC/22012034340363 — सी सी खरंजा एवं नाली निर्माण कार्य - गढ़ुआ का पुरा रामदीन के घर से | Completed | 60000 | 59168 | 2017-07-31 | 2018-04-04
MORENA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003005/RC/22012034349136 — सी सी खरंजा एवं नाली निर्माण - दुर्जन का पुरा एवं मूंगाराम का पुरा रामपुरगंज | Completed | 144000 | 143964 | 2017-09-18 | 2018-04-04
MORENA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003005/RC/22012034368700 — सी सी खरंजा निर्माण - जगराम का पुरा रामपुरगंज | Completed | 95700 | 95460 | 2018-01-02 | 2018-04-23
MORENA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003005/RC/22012034397032 — सी सी खरंजा नाली निर्माण - मैनरोड् से छोटेलाल कुशवाह के घर एवं रवि के घर की ओर राखन का पुरा | Completed | 119700 | 113796 | 2018-12-19 | 2019-12-03
MORENA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003005/RC/22012034439650 — सी सी खरंजा एवं नाली निर्माण - लज्‍जाराम का पुरा, रामपुरगंज | Completed | 97650 | 73610 | 2019-02-18 | 2019-05-08
MORENA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003005/RC/22012034439658 — सी सी खंरजा एवं नाली निर्माण - हरपाल का घर एवं नत्‍थ्‍ी कुशवाह के घर रामपुरगंज | Completed | 62250 | 51636 | 2019-02-18 | 2019-05-08
MORENA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003005/RC/22012034471262 — सीमेन्ट कॉक्रीट खरंजा प्रधानमंत्री रोड से द्वारिका प्रसाद शर्मा के घर तक देवी सिंह का पूरा रामपुरगंज | Completed | 57375 | 58960 | 2019-08-06 | 2019-10-10
MORENA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003005/RC/22012034471265 — सीमेन्ट कॉक्रीट खरंजा निर्माण मुकदी का पूरा रामपुरगंज | Completed | 114750 | 95920 | 2019-08-06 | 2019-10-05
MORENA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003005/RC/22012034524714 — सी.सी. खरंजा नाली सहित तोर वाला पुरा | Completed | 137587 | 135280 | 2020-06-08 | 2020-08-19
MORENA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Mitti Murram Roads for Community / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701003005/RC/22012034526493 — नबीन सुदूर सड़क रामपुर मेन रोड से छोटेलाल का पूरा तक | Completed | 828460.53 | 786266.19 | 2020-07-06 | 2020-11-09
MORENA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Mitti Murram Roads for Community / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701003005/RC/22012034537556 — नवीन सुदूर सड़क -दुर्जन सिंह का पूरा मार्ग ग्राम पंचायत रामपुरगंज | Completed | 1491228.96 | 1087561.43 | 2020-09-19 | 2024-03-04
MORENA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003005/RC/22012034554927 — सी .सी .खरन्जा निर्माण कार्य नाली सहित सामले सिंह का पुरा | Deleted | 166500 | 0 | 2020-11-20
MORENA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003005/RC/22012034555009 — सी सी खरंजा एबं नाली निर्माण सामले सिंह का पूरा | Completed | 106650 | 105830 | 2020-12-30 | 2021-03-19
MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003005/RC/22012034569370 — सीमेन्ट कंक्रीट खरंजा नाली सहित गेंदालाल का पुरा रामपुरगंज | Completed | 52200 | 49215 | 2021-06-17 | 2021-11-02
MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003005/RC/22012034569375 — प्रवलित सीमेन्ट कंक्रीट नाली निर्माण बालाजी मंदिर से जयराम के पुरा की ओर | Deleted | 44400 | 0 | 2021-04-14
MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003005/RC/22012034569376 — सीमेन्ट कंक्रीट सडक नाली सहित गोसपुर वालों का पुरा | Completed | 27900 | 27792 | 2021-06-17 | 2021-09-10
MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003005/RC/22012034587386 — सीमेंट काक्रीट सड़क निर्माण -माता मंदिर से जगराम का पूरा ग्राम पंचायत रामपुर गंज | Completed | 73050 | 72954 | 2021-10-18 | 2021-11-26
MORENA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel / Mitti Murram Road for Community | Construction of Road and Culvert | 1701003005/RC/22012034649389 — सुदुर/खेत सडक निर्माण कार्य रामपुर डंबर रोड से सती माता मंदिर होते हुए पलपुरा रोड तक रामपुरगंज | Ongoing | 2462936.27 | 1875318.02 | 2023-10-07
MORENA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003005/RC/22012034672799 — सी सी रोड निर्माण कार्य नेतराम वाली गली देवी सिंह का पुरा | Completed | 38400 | 37128 | 2024-01-24 | 2024-11-04
MORENA | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Metal First coat / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701003005/RC/24 — मिटटी बजरी मुरम सडक निर्माण पलपुरा रोड से शिवदेव का पुरा तक | Completed | 345000 | 81275 | 2008-12-26 | 2015-08-22
MORENA | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003005/RC/25 — सी सी खरंजा निर्माण कार्य रामपुर गंज | Deleted | 148000 | 30750 | 2009-01-07
MORENA | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Metal Second coat / Construction of WBM Roads for Community | Construction of Road and Culvert | 1701003005/RC/308 — पत्‍थर खरजा निर्माण रामपुरा | Completed | 0 | 78957 | 2009-08-18 | 2009-12-19
MORENA | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Metal First coat / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701003005/RC/34 — सी सी खरंजा निर्माण कार्य मुकंदी का पुरा | Completed | 148000 | 104150 | 2009-01-07 | 2009-05-14
MORENA | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701003005/RC/36 — सीमेन्‍ट कांकीट खंरजा निर्माण मोनी बबा से रमेश | Completed | 495000 | 76468 | 2009-02-18 | 2016-02-05
MORENA | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Metal First coat / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701003005/RC/464 — पत्‍थर खरजा निर्माण | Completed | 0 | 104255 | 2010-03-11 | 2010-05-03
MORENA | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701003005/RC/67 — सोख्‍ता गडडा सोकफिट मुकन्‍दी का पुरा | Completed | 394000 | 10894 | 2009-02-23 | 2009-05-29
MORENA | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003005/RC/7 — मिम़टी बजरी मुरम सडक निमार्ण | Completed | 394000 | 192252 | 2009-02-07 | 2010-05-17
MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex for Community | Community Sanitary Complex | 1701003005/RS/22012034601475 — कचरा भंडारगृह केंद्र सेग्रीगेसन शेड रामपुर गंज (SLWM) | Ongoing | 628297.23 | 46380 | 2021-11-08
MORENA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1701003005/RS/22012034680081 — सामुदायिक स्वच्छता परिसर सिद्ध स्थान रामपुरगंज | Completed | 69000 | 66026 | 2023-06-20 | 2026-01-05
MORENA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Dam / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003005/WC/22012034386286 — नवीन तालाब निर्माण कार्य - पुराना गांव, रामपुरगंज | Completed | 805000 | 609367.56 | 2018-04-02 | 2020-08-20
MORENA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003005/WC/22012034432312 — नवीन तालाब निर्माण कार्य - | Deleted | 0 | 0 | 2019-01-26
MORENA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701003005/WC/22012034555292 — नवीन तालाब निर्माण कार्य-राखन का पुरा रामपुरगंज | Completed | 796626.22 | 382577 | 2020-06-29 | 2023-07-18
MORENA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1701003005/WC/22012034616247 — सोख़्ता गड्डा सामुदायिक भवन जगराम का पूरा रामपुरगंज (एस.एल.डब्ल्यू.एम.) | Completed | 18200.38 | 17350.47 | 2021-02-22 | 2023-12-13
MORENA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1701003005/WC/22012034616260 — सोख़्ता गड्डा ओमप्रकाश के घर के पास तिघरा का पूरा रामपुरगंज {SLWM} | Deleted | 0 | 0 | 2021-01-21
MORENA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1701003005/WC/22012034616518 — सोख्ता गड्ढा भूकन के घर के पास राखन का पूरा रामपुरगंज {S L W M } | Completed | 18200.38 | 17269.5 | 2021-02-22 | 2022-07-18
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1701003005/WC/22012034618164 — सोख्ता गड्ढा पंकज शर्मा के घर के पास सामले सिंह का पूरा{S L W M } | Completed | 18200.38 | 17219 | 2021-04-03 | 2022-02-15
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1701003005/WC/22012034618165 — सोख्ता गड्ढा रामबरन राठौर के घर के पास सामले सिंह का पूरा{S L W M } | Completed | 18200.38 | 17218 | 2021-04-03 | 2022-02-06
MORENA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1701003005/WC/22012034620008 — सोख्ता गड्डा रतीराम के घर के पास लज्जाराम का पूरा रामपुरगंज {SLWM} | Closed | 18382.8 | 0 | 2021-01-21
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003005/WC/22012034663485 — चेक डेम सिद्ध स्थान के पास रामपुरगंज(1) | Deleted | 0 | 0 | 2021-04-10
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003005/WC/22012034663513 — चेक डेम राम नरेश के खेत के पास (२) | Deleted | 0 | 0 | 2021-04-10
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003005/WC/22012034663527 — चेक डेम बैजनाथ के खेत के पास रामपुरगंज(३) | Deleted | 0 | 0 | 2021-04-10
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003005/WC/22012034663532 — चेक डेम शिव देव का पूरा रामपुर गंज (4) | Deleted | 0 | 0 | 2021-04-10
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701003005/WC/22012034663540 — तालाव निर्माण कार्य रामपुर गंज | Deleted | 0 | 0 | 2021-04-10
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701003005/WC/22012034663568 — निस्तारी तालाव तिघरा का पूरा रामपुर गंज | Deleted | 0 | 0 | 2021-04-10
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003005/WC/22012034663804 — चेक डेम नदी के किनारे रामपुर गंज | Deleted | 0 | 0 | 2021-04-10
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003005/WC/22012034665818 — nws check dam shidh sthan ke pass raampur ganj | Completed | 1495811.45 | 1457662 | 2021-06-05 | 2021-12-23
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003005/WC/22012034665826 — nws check dam bejnath ke khet ke pass raampur ganj | Completed | 1496827.41 | 1460142 | 2021-06-07 | 2021-12-23
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003005/WC/22012034665833 — nws check dam raam naresh ke khet ke pass | Completed | 1495850.43 | 1459454 | 2021-06-07 | 2021-12-23
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003005/WC/22012034665856 — nws chech dam naadi ke kinare raamour ganj | Completed | 1498333.11 | 1460813 | 2021-06-07 | 2021-12-23
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003005/WC/22012034665865 — nws talab nirman kary raampur ganj | Completed | 1499246.9 | 1424918 | 2022-03-15 | 2023-07-01
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen Gully Plugs for Community / Construction of Earthen Gully Plugs for Community | Boulder Check/Gully Plug | 1701003005/WC/22012034665871 — nws gully plug raampur ganj | Completed | 1497662.16 | 1183002 | 2021-11-01 | 2024-01-11
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1701003005/WC/22012034779273 — सोखता गड्डा भारत शर्मा /केशव शर्मा के घर के पास सामले सिंह क पुरा(slwm) | Closed | 18443.75 | 0 | 2021-04-26
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1701003005/WC/22012034779275 — सोखता गड्डा कम्लेश शर्मा/जगदीश के घर के पास सामले सिंह क पुरा(slwm) | Closed | 18443.75 | 0 | 2021-04-26
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1701003005/WC/22012034779277 — सोखता गड्डा नितिन/रामप्रकाश के घर के पास सामले सिंह क पुरा(slwm) | Closed | 18443.75 | 0 | 2021-04-26
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1701003005/WC/22012034779278 — सोखता गड्डा शिव सिह /बाबूलाल के घर के पास सामले सिंह क पुरा(slwm) | Closed | 18443.75 | 0 | 2021-04-26
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1701003005/WC/22012034779279 — सोखता गड्डा सुमतिचंद /द्वारिका प्रसाद शर्मा के घर के पास सामले सिंह क पुरा(slwm) | Closed | 18443.75 | 0 | 2021-04-26
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1701003005/WC/22012034782996 — सोखता गड्डा शाशकीय स्कूल के पास मनफूल का पुरा | Closed | 18443.75 | 0 | 2021-05-20
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003005/WC/22012034802265 — ctr check dam nirman pamai bala | Completed | 1498661.8 | 1458606 | 2021-11-01 | 2023-04-01
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003005/WC/22012034802268 — ctr check dam nirman sathan ke pass | Completed | 1499990.8 | 1460240 | 2021-11-01 | 2022-07-23
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003005/WC/22012034802270 — ctr check dam nirman chukradud bala | Completed | 1496003.8 | 1455020 | 2021-11-01 | 2022-08-23
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003005/WC/22012034802275 — ctr check dam nirman bagira bala | Completed | 1497848.81 | 1459414 | 2021-11-01 | 2022-12-21
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003005/WC/22012034802281 — ctr check dam nirman goha bala | Closed | 1496371.31 | 0 | 2021-07-14
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003005/WC/22012034802284 — ctr check dam nirman mayaraam ke khet ke pass | Closed | 1497958.32 | 0 | 2021-07-14
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen Gully Plugs for Community / Construction of Earthen Gully Plugs for Community | Boulder Check/Gully Plug | 1701003005/WC/22012034802289 — ctr/nws gully plug rampurgaanj | Closed | 1499327.13 | 0 | 2021-07-14
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003005/WC/22012034802292 — ctr/nws gully plug rampurgaanj | Closed | 998556.44 | 0 | 2021-07-14
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003005/WC/22012034802304 — ctr/nws talab nirman bakil ke khet ke pass rampurgaanj | Closed | 1498930.28 | 0 | 2021-07-14
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003005/WC/22012034802307 — ctr/nws talab nirman kary khar me rampurgaanj | Closed | 1494674.52 | 0 | 2021-07-14
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003005/WC/22012034802314 — ctr/nws talab nirman kary khar me aage rampurgaanj | Closed | 1499152.57 | 0 | 2021-07-14
MORENA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1701003005/WC/22012034913563 — TALAB NIRMAN KARY SIDH STHAN KE PAS RAMPURGANJ | Ongoing | 492502.36 | 329664 | 2022-04-25
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Pebble peripheral Bund for Community / Construction of Pebble peripheral/farm/field Bund for Community | Construction of Bund | 1701003005/WC/22012034913564 — TALAB NIRMAN KARY POORAN SARPANCH KE KHET KE PAS RAMPURGANJ | Deleted | 0 | 0 | 2022-01-24
MORENA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1701003005/WC/22012034967376 — nws talab nirman kary behad me rampurganj | Completed | 1485184.93 | 992620 | 2022-05-20 | 2024-03-13
MORENA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Stone graded Bund for Community / Construction of Stone graded Bund for Community | Construction of Bund | 1701003005/WC/22012034967378 — nws talab nirman kary jagram ke purake pas rampurganj | Completed | 1492467.44 | 1130968 | 2022-05-20 | 2024-03-13
MORENA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen Gully Plugs for Community / Construction of Earthen Gully Plug for Community | Boulder Check/Gully Plug | 1701003005/WC/22012034967380 — nws gally plug rampurganj | Ongoing | 859891.85 | 2448 | 2022-05-20
MORENA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen Gully Plugs for Community / Construction of Earthen Gully Plugs for Community | Boulder Check/Gully Plug | 1701003005/WC/22012034967381 — nws gally pulg rampurganj | Deleted | 0 | 0 | 2022-04-14
MORENA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1701003005/WC/22012034983983 — तालाब निर्माण कार्य सुल्तान के खेत के और पास रामपुरगंज | Deleted | 0 | 0 | 2022-04-14
MORENA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1701003005/WC/22012034983984 — तालाब निर्माण कार्य सुल्तान के खेत के और पास रामपुरगंज | Deleted | 0 | 0 | 2022-04-14
MORENA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701003005/WC/22012034994354 — तालाब निर्माण कार्य -पीपर के खेत के पास रामपुर गंज | Deleted | 0 | 0 | 2022-08-16
MORENA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701003005/WC/22012034994356 — तालाब निर्माण कार्य -फूल सिंह के खेत के पास रामपुर गंज | Deleted | 0 | 0 | 2022-08-16
MORENA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701003005/WC/22012034994357 — तालाब निर्माण कार्य -शिव देव का पुरा रामपुर गंज | Deleted | 0 | 0 | 2022-08-16
MORENA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701003005/WC/22012034995551 — तालाब निर्माण कार्य -रवि के खेत के पास रामपुर गंज | Deleted | 0 | 0 | 2022-08-16
MORENA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1701003005/WC/22012035003379 — Amrit Sarovar nirman kary -shivdev ka pura gram panchayat rampurganj | Ongoing | 1995082.31 | 1727960.88 | 2022-12-19
MORENA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701003005/WC/22012035007575 — amrat sarovar talav nirman kary shivdev ke pura ke pass | Deleted | 0 | 0 | 2022-08-16
MORENA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701003005/WC/22012035007833 — nws talav nirman kary bamool ke pass behad me | Ongoing | 1482479.79 | 662235 | 2022-11-21
MORENA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701003005/WC/22012035007836 — nws talav nirman kary sidh sthan ke pass rakhan ka pura | Ongoing | 1483687.86 | 600100 | 2022-11-21
MORENA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701003005/WC/22012035051872 — talav nirman kary piper ke khet ke pass | Deleted | 0 | 0 | 2023-03-01
MORENA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701003005/WC/22012035051873 — talav nirman kary fool singh kushwaah ke khet ke pass | Deleted | 0 | 0 | 2023-03-01
MORENA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701003005/WC/22012035051874 — talav nirman kary mukandi ka pura | Deleted | 0 | 0 | 2023-03-01
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003005/WC/22012035092156 — रपटा निर्माण कार्य दुर्जन सिंह के पुरा के पास। | Deleted | 0 | 0 | 2023-04-14
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003005/WC/22012035092158 — रपटा निर्माण कार्य सिद्ध बाबा की रोड पर। | Ongoing | 1489230.12 | 677859.52 | 2023-08-14
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003005/WC/22012035092159 — रपटा निर्माण कार्य कुशवाह पुरा के पास। | Ongoing | 1496582.94 | 1234618.09 | 2023-08-14
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003005/WC/22012035129651 — रपटा निर्माण कार्य सती माता मंदिर के पास | Deleted | 1480742.36 | 0 | 2023-08-16
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003005/WC/22012035129656 — रपटा निर्माण कार्य राकेश कुशवाह पुरा के पास | Ongoing | 1466125.38 | 956613.03 | 2024-03-15
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003005/WC/22012035129659 — नवीन तालाब निर्माण कार्य रवि कुशवाह के खेत के पास राखन का पुरा | Closed | 1427718.55 | 0 | 2023-08-16
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003005/WC/22012035129663 — नवीन तालाब निर्माण कार्य पूरन सिंह के खेत के पास राखन का पुरा | Closed | 1461631.18 | 0 | 2023-08-16
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone boulder Gully Plugs for Comm / Construction of Stone boulder Gully Plugs for Community | Boulder Check/Gully Plug | 1701003005/WC/22012035162067 — रपटा निर्माण कार्य पारूआ के घर के पास | Deleted | 0 | 0 | 2023-10-02
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone boulder Gully Plugs for Comm / Construction of Stone boulder Gully Plugs for Community | Boulder Check/Gully Plug | 1701003005/WC/22012035162099 — रपटा निर्माण कार्य सिद्ध बाबा मंदिर के पास | Deleted | 0 | 0 | 2023-10-02
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1701003005/WC/22012035162109 — रपटा निर्माण कार्य सती माता मंदिर के पास | Deleted | 0 | 0 | 2023-10-02
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701003005/WC/22012035178760 — रपटा निमार्ण कार्य देवेन्द्र के बोरवेल के पास | Physically Completed | 1480742.36 | 1364784.03 | 2024-03-15 | 2026-05-27
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701003005/WC/22012035178761 — रपटा निमार्ण कार्य सोबा बाबा वाले रोड पर | Ongoing | 1480742.36 | 1417962.12 | 2024-03-15
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701003005/WC/22012035178764 — रपटा निमार्ण कार्य कुशवाह पुरा के पास | Deleted | 0 | 0 | 2024-01-24
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Pebble peripheral Bund for Community / Construction of Pebble peripheral/farm/field Bund for Community | Construction of Bund | 1701003005/WC/22012035198106 — रपटा निर्माण कार्य माता मंदिर के पास | Deleted | 0 | 0 | 2024-01-24
MORENA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701003005/WC/22012035228812 — नवीन तालाब निर्माण कार्य सिद्ध बाबा मंदिर एवं सुल्तान के खेत के पास | Deleted | 0 | 0 | 2024-10-02
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1701003005/WH/22012034453888 — तालाब मरम्मत कार्य ग्राम तिघरा का पुरा ग्राम पंचायत रामपुरगंज | Deleted | 0 | 0 | 2021-10-21
MORENA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1701003005/WH/22012034920073 — तालाब मरमम्त कार्य तिघरा का पुरा | Completed | 44945 | 35496 | 2022-05-09 | 2022-05-28
MORENA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701/RC/22012034188556 — मिटटी बजरी सड्क डब्‍लू बीएम रोड से लाखन का पुरा एवं तिगरा का पुरा | Deleted | 1731997 | 0 | 2013-10-05