## Work List
Exported on: 2026-09-14 00:01:41
Filters applied:
Data source: MGNREGA + VBGRAMG
District: MORENA
Block: All
Panchayat: GOSPUR
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
MORENA | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1701003014/AV/22012034659259 — शांतिधाम निर्माण कार्य हंसराज का पुरा, गोसपुर | New | 0 | 0 | 2024-06-08
MORENA | 2015-2016 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construct building for federation of women SHG / Construction of SHG/Federation Building for Groups | Construction of building/workshed for SHG | 1701003014/AV/5032 — आंगनबाड़ी बाड़ी भवन | Deleted | 0 | 0 | 2016-01-26
MORENA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701003014/DP/01 — व़क्षारोपण शासकीय वि0 गोसपुरा | Completed | 450000 | 4290 | 2008-07-16 | 2008-06-30
MORENA | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701003014/DP/158 — व्रश्रा रोपण कार्य गोसपुर | Completed | 0 | 14914 | 2009-09-12 | 2009-07-20
MORENA | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1701003014/DP/22012034236953 — शांतिधाम निर्माण कार्य गौसपुर | Completed | 180000 | 178510.92 | 2016-12-28 | 2017-12-11
MORENA | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701003014/DP/22012034328711 — वृक्षारोपण कार्य | Deleted | 0 | 0 | 2017-10-02
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Gov blding premises-Block Plantation-Horticulture / Block Plantation of Horticulture Trees in Government building premises for Community | Plantation | 1701003014/DP/22012034542991 — माँ की बगिया शा. प्रा. वि. गौसपुर | Completed | 21445.35 | 10036 | 2022-01-20 | 2022-05-20
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Gov blding premises-Block Plantation-Horticulture / Block Plantation of Horticulture Trees in Government building premises for Community | Plantation | 1701003014/DP/22012034542993 — माँ की बगिया शा मा वि गौसपुर | Completed | 13445.35 | 6948 | 2022-01-20 | 2022-05-20
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1701003014/DP/22012034544449 — ma ki bagiya ps shala dhanu ka pura gospur | Closed | 20945.35 | 0 | 2021-04-14
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1701003014/DP/22012034599775 — वृक्षारोपण कार्य ग्राम पंचायत गौसपुर, मेरी माटी मेरा देश | Closed | 0 | 0 | 2023-04-14
MORENA | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701003014/FP/22012034638718 — कच्चा पक्का नाला निर्माण कार्य रामज्ञान के घर से रामसहाय बघेल के घर तक हंसराज का पुरा | Closed | 0 | 0 | 2024-01-24
MORENA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Fisheries | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1701003014/FR/22012034322904 — Talab nirman kary laal khaar ke pass | Ongoing | 1461240.19 | 1311231.02 | 2025-02-24
MORENA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Fisheries | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1701003014/FR/22012034322905 — Talab nirman kary dunda khaar ke pass | Ongoing | 1445763.77 | 1226851.44 | 2025-02-24
MORENA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Fisheries | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1701003014/FR/22012034322906 — Talab nirman kary piluaa ke ped ke pass | Ongoing | 1416310.47 | 948436 | 2025-02-24
MORENA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Fisheries | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1701003014/FR/22012034322907 — Talab nirman kary jhaadi ke pass | Approved | 1465243.96 | 0 | 2024-10-02
MORENA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Fisheries | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1701003014/FR/22012034322908 — Talab nirman kary peepal ke ped ke pass | Ongoing | 1415579.86 | 972496.4 | 2025-02-24
MORENA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Fisheries | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1701003014/FR/22012034322909 — Talab nirman kary aam khaar ke pass | Ongoing | 1445763.77 | 2430 | 2025-02-24
MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701003014/IF/22012034347027 — सार्वजनिक परिसर मे व्रक्षारोपण कार्य ग्राम गोसपुर | Completed | 335000 | 14624 | 2017-06-29 | 2020-08-18
MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701003014/IF/22012034369382 — सार्वजनिक परिसर मे व्रक्षारोपण कार्य हरनारायन के पुरा की ओर | Closed | 335000 | 0 | 2017-04-14
MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Berkeley Compost Pit for Individual / Construction of Berkeley Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1701003014/IF/22012034731660 — nadap nirman gokul singh | Completed | 18374.27 | 16024 | 2021-06-03 | 2021-10-18
MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Berkeley Compost Pit for Individual / Construction of Berkeley Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1701003014/IF/22012034731690 — nadap nirman bhupendra singh slwm | Completed | 18374.27 | 16024 | 2021-06-03 | 2021-10-18
MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Berkeley Compost Pit for Individual / Construction of Berkeley Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1701003014/IF/22012034731701 — nadap nirman slwm raju | Closed | 18374.27 | 0 | 2021-04-14
MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Berkeley Compost Pit for Individual / Construction of Berkeley Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1701003014/IF/22012034731703 — nadap nirman slwm raju | Deleted | 0 | 0 | 2021-04-14
MORENA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1701003014/IF/22012035452758 — khet talab nirmaan karya Bhagirath Ke Khet me | Ongoing | 147621.16 | 101602.2 | 2025-05-10
MORENA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1701003014/IF/22012035452816 — khet talab nirmaan karya Uttam Singh ke Khet Me | Ongoing | 147621.16 | 27144 | 2025-05-04
MORENA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003014/IF/9993725784 — पशु सेड निर्माण कार्य महाराज /द्वारिका | Deleted | 0 | 0 | 2016-01-26
MORENA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003014/IF/9993725789 — पशु सेड निर्माण कार्य भूपेंद्र /द्वारिका | Deleted | 0 | 0 | 2016-01-26
MORENA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003014/IF/9993725791 — पशुस्रेड निर्माण कार्य रमेश /सियाराम | Deleted | 0 | 0 | 2016-01-26
MORENA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003014/IF/9993725793 — पशुस्रेड निर्माण कार्य रमेश /अंगद सिंह | Deleted | 0 | 0 | 2016-01-26
MORENA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003014/IF/9993725794 — पशुस्रेड निर्माण कार्यअजमेर सिंह /रामेश्वर | Deleted | 0 | 0 | 2016-01-26
MORENA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003014/IF/9993725795 — पशुस्रेड निर्माण कार्यनिवास /लक्षमण | Deleted | 0 | 0 | 2016-01-26
MORENA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003014/IF/IAY/1919113 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5262655 | Completed | 15660 | 15660 | 2018-09-22 | 2019-01-14
MORENA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003014/IF/IAY/312068 — Construction of IAY House -IAY REG. NO. MP1052278 | Completed | 15030 | 14844 | 2017-02-16 | 2017-09-08
MORENA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003014/IF/IAY/312459 — Construction of IAY House -IAY REG. NO. MP1053287 | Completed | 15030 | 14844 | 2017-02-16 | 2017-11-02
MORENA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003014/IF/IAY/318492 — Construction of IAY House -IAY REG. NO. MP1066226 | Completed | 15030 | 14934 | 2017-03-21 | 2017-11-02
MORENA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003014/IF/IAY/319700 — Construction of IAY House -IAY REG. NO. MP1068931 | Completed | 15030 | 14869 | 2017-02-16 | 2017-11-27
MORENA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003014/IF/IAY/424092 — Construction of IAY House -IAY REG. NO. MP1354265 | Completed | 15030 | 14934 | 2017-02-16 | 2017-11-02
MORENA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003014/IF/IAY/42742 — Construction of IAY House -IAY REG. NO. MP-01-003-014-001/21 | Completed | 14310 | 11082 | 2016-09-19 | 2017-09-08
MORENA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003014/IF/IAY/463493 — Construction of IAY House -IAY REG. NO. MP1743122 | Completed | 15030 | 14934 | 2017-03-21 | 2017-09-23
MORENA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003014/IF/IAY/465870 — Construction of IAY House -IAY REG. NO. MP1769608 | Completed | 15030 | 14934 | 2017-03-21 | 2017-09-23
MORENA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003014/IF/IAY/48890 — Construction of IAY House -IAY REG. NO. MP-01-003-014-001/120 | Completed | 14310 | 12401 | 2016-09-19 | 2018-06-16
MORENA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003014/IF/IAY/48891 — Construction of IAY House -IAY REG. NO. MP-01-003-014-001/16 | Approved | 27000 | 0 | 2015-08-19
MORENA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003014/IF/IAY/541725 — Construction of IAY House -IAY REG. NO. MP3115662 | Completed | 15030 | 14844 | 2017-02-16 | 2017-09-08
MORENA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003014/IF/IAY/541900 — Construction of IAY House -IAY REG. NO. MP3120786 | Completed | 15030 | 14844 | 2017-02-17 | 2017-09-08
MORENA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003014/IF/IAY/542001 — Construction of IAY House -IAY REG. NO. MP3123221 | Completed | 15030 | 14697 | 2017-02-16 | 2017-11-22
MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003014/IF/IAY/688541 — Construction of IAY House -IAY REG. NO. MP1071783 | Completed | 15030 | 14964 | 2017-04-27 | 2017-09-23
MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003014/IF/IAY/688543 — Construction of IAY House -IAY REG. NO. MP1071851 | Completed | 15030 | 14964 | 2017-04-27 | 2017-09-23
MORENA | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701003014/RC/01 — सी सी खरंजा निर्माण कार्य गासोपुरा | Completed | 458000 | 132194 | 2009-02-26 | 2009-08-03
MORENA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003014/RC/22012034188314 — सी सी खरंजा बरेठा मोह्ल्ला से फेरन सिह के मकान तक् | Deleted | 0 | 0 | 2013-01-15
MORENA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003014/RC/22012034188323 — सी सी खरंजा निर्माण कार्य बरेठा मोहल्ला से फेरन सिह के मकान तक | Deleted | 148000 | 0 | 2013-04-15
MORENA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003014/RC/22012034188327 — सी सी रोड निर्माण कार्य भोगीराम के दरबाजे से देबीराम के घर तक् | Deleted | 148000 | 0 | 2012-04-15
MORENA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701003014/RC/22012034293829 — पत्‍थर खरंजा निर्माण कार्य पी एम विध्‍यालय से रघुनाथ के घर की और | Completed | 125000 | 8268 | 2016-01-14 | 2016-10-03
MORENA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701003014/RC/22012034307778 — मिट्टी बजरी रोड कार्य कोल्ड बाले से मरघट की और | Deleted | 0 | 0 | 2016-01-26
MORENA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701003014/RC/22012034307780 — मिट्टी बजरी रोड मरघट से ग्राहे के पूरा की और | Deleted | 0 | 0 | 2016-01-26
MORENA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701003014/RC/22012034307817 — पत्थर खरंजा निर्माण कार्य पंचायत भवन से नरेश के घर की और | Deleted | 0 | 0 | 2016-01-26
MORENA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701003014/RC/22012034307818 — पत्थर खरंजा निर्माण कार्य सिद्ध बाबा मंदिर से चरण की ओर | Deleted | 0 | 0 | 2016-01-26
MORENA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003014/RC/22012034324563 — सी सी खरंजा एवं नाली निर्माण रामदीन के घर से परसराम के घर की और छत्‍ते का पुरा | Completed | 668750 | 100200 | 2017-02-22 | 2017-03-21
MORENA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003014/RC/22012034330099 — सीसी रोड चंटोली के घर से मातादीन के घर की और धांधू का पूरा | Completed | 80250 | 80115 | 2017-03-10 | 2017-04-07
MORENA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003014/RC/22012034333694 — सी सी खरंजा एबं नाली निर्माण कार्य पवन के मकान से हरिओम के मकान तक कटारे का पुरा गोसपुर | Completed | 32100 | 23908 | 2017-04-01 | 2017-04-07
MORENA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003014/RC/22012034337077 — सी सी खर्ंजा निर्माण कार्य रतन सिह का पुरा भगवान सिह लाखन सिह शिवसिह के घर तक | Completed | 65587 | 65532 | 2017-06-29 | 2017-09-23
MORENA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701003014/RC/22012034337981 — सुदुर ग्राम संपक खेत सडक - मिटटी बजरी रोड निर्माण -कोलू बाई pmgsy सड़क से हरिनारायण का पूरा गोसपुर | Completed | 1440000 | 1253806.48 | 2017-06-05 | 2019-04-08
MORENA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003014/RC/22012034342317 — सी सी खरंजा ऐब नाली निर्माण कार्य बघेले का पुरा गोसपुर | Completed | 96187 | 95976 | 2017-08-16 | 2017-09-08
MORENA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003014/RC/22012034347640 — सी सी खरंजा एंव नाली निर्माण कार्य कटारे के मकान से पंचायत भवन तक ग्राम गोसपुर | Completed | 80250000000 | 119712 | 2017-08-01 | 2017-09-08
MORENA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003014/RC/22012034360164 — सी सी खरंजा निर्माण कार्य प्राथमिक विद्यालय से रघुनाथ के घर की और गोसपुर | Completed | 4012500000 | 40076 | 2017-09-21 | 2017-09-29
MORENA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003014/RC/22012034360167 — सी सी खरंजा अवं नाली निर्माण कार्य कल्लू के घर से अजमेर के द्वार तक | Completed | 4012500000 | 40076 | 2017-09-28 | 2017-10-10
MORENA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003014/RC/22012034362352 — सी सी खरंजा एवं नाली निर्माण कार्य जरदान बघेल के घर से रघुनाथ के घर की और | Completed | 4012500000 | 40076 | 2017-09-30 | 2017-11-02
MORENA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003014/RC/22012034362353 — सी सी खरंजा एवं नाली निर्माण कार्य अजमेर के द्वार से राजेंद्र के द्वार की और | Completed | 4012500000 | 40076 | 2017-09-30 | 2017-11-02
MORENA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003014/RC/22012034395841 — सी.सी. खरंजा एवं नाली निर्माण कार्य - कल्ला की दुकान से रामस्वरूप के घर की ओर, गोसपुर | Completed | 84750 | 84738 | 2018-10-04 | 2018-11-15
MORENA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003014/RC/22012034395847 — सी.सी. खरंजा एवं नाली निर्माण कार्य - रामसिंह के घर से चरन के घर की ओर, गोसपुर | Completed | 84750 | 84738 | 2018-10-04 | 2018-12-03
MORENA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003014/RC/22012034396480 — सी सी खरंजा एवं नाली निर्माण कार्य रामवीर के मकान से मैन रोड की ओर गोसपुर् | Closed | 33900 | 0 | 2018-08-15
MORENA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003014/RC/22012034436525 — सी.सी. खरंजा एवं नाली निर्माण कार्य - विश्वम्बर कुशवाह के घर से भागीरथ कुशवाह के घर की ओर गौसपुर। | Completed | 42375 | 41760 | 2019-02-04 | 2019-05-15
MORENA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003014/RC/22012034442630 — सी.सी. खरंजा एवं नाली निर्माण कार्य - दामोदर कुशवाह के घर से चैकीदार के घर की ओर। | Completed | 148312 | 148248 | 2019-02-12 | 2019-04-08
MORENA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003014/RC/22012034469372 — सी.सी.खरंजा एवं नाली निर्माण कार्य - महीपाल के घर से हाकिम के घर की ओर | Completed | 21187 | 21296 | 2019-08-02 | 2019-09-17
MORENA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003014/RC/22012034469583 — सी.सी. खरंजा एवं नाली निर्माण कार्य - महेन्द्र सिंह के घर से धनिया परमार के घर तक गोसपुर। | Completed | 84750 | 85184 | 2019-08-02 | 2019-10-09
MORENA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003014/RC/22012034469585 — सी.सी. खरंजा एवं नाली निर्माण कार्य - ताल की पार हरिशंकर कटारे के घर तक गोसपुर | Completed | 42375 | 42064 | 2019-08-02 | 2019-10-10
MORENA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003014/RC/22012034478262 — सी.सी. खरंजा एवं नाली निर्माण कार्य - मैन रोड से सरपंच के घर की ओर धाधू का पुरा, गोसपुर | Completed | 95343 | 89232 | 2019-09-28 | 2019-11-10
MORENA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003014/RC/22012034481591 — सी.सी. खरंजा एवं नाली निर्माण कार्य - मैन रोड से रतनसिंह के घर की ओर धाधू का पुरा, गौसपुर | Completed | 76275 | 76032 | 2019-10-19 | 2019-11-28
MORENA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003014/RC/22012034508819 — सी.सी. खरंजा एवं नाली निर्माण कार्य - नत्थी के घर से विजय सिंह के घर की ओर छत्ते का पुरा, गौसपुर | Completed | 127125 | 127110 | 2020-06-09 | 2020-08-05
MORENA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Mitti Murram Roads for Community / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701003014/RC/22012034523572 — सुदूर ग्राम सम्पर्क सड़क निर्माण कार्य - चिंतामनी के पुरा से प्रा. विधlलय, छत्तेका पुरा, गोसपुर | Completed | 1325536.85 | 959975.37 | 2020-09-23 | 2021-03-22
MORENA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003014/RC/22012034528958 — सी.सी. खरंजा नाली संिहत रमेश रोशन मातादीन मंगल फूलंिसह का पुरा सुखलाल का पुरा गोसपुर | Completed | 84750 | 84740 | 2020-07-14 | 2020-08-18
MORENA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003014/RC/22012034534441 — सी. सी. खरंजा एवं नाली निर्माण कार्य पचौरी का पुरा गोशपुर | Completed | 84750 | 84740 | 2020-08-23 | 2020-10-07
MORENA | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701003014/RC/381 — पत्‍थर खरंजा गोसपुर | Completed | 257000 | 142836 | 2009-08-17 | 2016-01-22
MORENA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1701003014/RS/22012034513687 — सामुदायिक नाडेप कावेन्द्र के घर के समीप | Deleted | 0 | 0 | 2021-03-08
MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Community / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1701003014/RS/22012034526610 — कचरा भण्डार केंद्र (सेग्रीगेशन शेड ) गोसपुर | Ongoing | 628297.23 | 1158 | 2021-11-09
MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1701003014/RS/22012034580062 — samudayak sochalay | Deleted | 0 | 0 | 2021-04-14
MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1701003014/RS/22012034580067 — सामुदायिक स्वच्छता परिसर गोशपुर | Completed | 43000 | 42846 | 2021-11-09 | 2022-02-21
MORENA | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Mini Percolation tank / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1701003014/WC/22012034378079 — तालाब मरम्‍मत नर्सरी तालाब् निर्माण कार्य गोसपुर | Completed | 181000 | 169248 | 2018-01-02 | 2018-02-23
MORENA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003014/WC/22012034432255 — नवीन तालाब निर्माण कार्य - | Deleted | 0 | 0 | 2019-01-26
MORENA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1701003014/WC/22012034608532 — नवीन तालाब निर्माण कार्य ग्राहे के पुरा के पास गोशपुर | Deleted | 0 | 0 | 2020-11-20
MORENA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1701003014/WC/22012034608533 — नवीन तालाब निर्माण कार्य ठाड़े खार हंसराज के पुरा के पास गोशपुर | Deleted | 0 | 0 | 2020-11-20
MORENA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1701003014/WC/22012034608534 — नवीन तालाब निर्माण कार्य रामऔतार के खार के पास गोशपुर | Deleted | 0 | 0 | 2020-11-20
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003014/WC/22012034612551 — naveen talab nirman giraye ka pura ke pass | Completed | 1481065.33 | 1419083 | 2021-06-28 | 2022-05-11
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003014/WC/22012034612554 — naveen talab bhagirath ke khar ke pass | Completed | 1484674.95 | 1425880.28 | 2021-04-01 | 2021-09-12
MORENA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003014/WC/22012034612555 — naveen talab dande khar ke pass hanshraj ka pura | Completed | 1484270.33 | 1418435 | 2021-03-18 | 2021-12-23
MORENA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003014/WC/22012034612556 — naveen talab ode nale ke pas | Completed | 1487660.2 | 1425508 | 2021-03-18 | 2021-12-23
MORENA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003014/WC/22012034612557 — naveen talab bade naria ke pass | Completed | 1492274.63 | 1437786.4 | 2021-03-18 | 2021-09-12
MORENA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003014/WC/22012034612558 — naveen stop dam munni ke khar ke pass | Completed | 1492847.81 | 1465894 | 2021-03-24 | 2021-08-26
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003014/WC/22012034612559 — naveen stop dam marghati ke pas | Completed | 1471403.93 | 1456038 | 2021-04-30 | 2021-06-23
MORENA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003014/WC/22012034612560 — naveen stop dam bade khar ke pass | Completed | 1489797.3 | 1457996 | 2021-03-24 | 2021-08-26
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003014/WC/22012034612561 — naveen stop dam rant bhawar ke pass | Completed | 1488675.83 | 1453932 | 2021-04-01 | 2021-08-26
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003014/WC/22012034612562 — naveen stop dam aam khar ke pass | Completed | 1483068.36 | 1452774 | 2021-04-15 | 2021-08-26
MORENA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1701003014/WC/22012034616622 — सोकपिट निर्माण कार्य रमेश के घर के पास (एस.एल.डब्ल्यू.एम.) | Completed | 18200.38 | 17337 | 2021-03-10 | 2021-09-25
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1701003014/WC/22012034616624 — सोकपिट निर्माण कार्य विशुनलाल के घर के पास (एस.एल.डब्ल्यू.एम.) | Completed | 18200.38 | 17412 | 2021-05-18 | 2021-09-13
MORENA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1701003014/WC/22012034637235 — सोकपिट निर्माण कार्य रतनसिंघ का पुरा slwm | Closed | 18382.8 | 0 | 2021-03-08
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1701003014/WC/22012034637241 — सोकपिट निर्माण कार्य पचौरी का पुरा slwm | Completed | 18382.8 | 17219 | 2021-06-03 | 2021-09-25
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1701003014/WC/22012034637247 — सोकपिट निर्माण कार्य मुंसी का पुरा का पुरा slwm | Completed | 18382.8 | 17412 | 2021-05-18 | 2021-09-25
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1701003014/WC/22012034644189 — सोकपिट निर्माण धर्मवीर के यह पचौरी का पुरा | Completed | 18382.8 | 17412 | 2021-05-18 | 2021-09-13
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701003014/WC/22012034684346 — sokhata gadda gospur slwm | Completed | 91911.85 | 84938.94 | 2021-06-03 | 2021-09-13
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701003014/WC/22012034752519 — soktagadda nirman SLWM | Closed | 91911.85 | 0 | 2021-04-24
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003014/WC/22012034793240 — ctr/nws check dam gadi khar ke pass | Completed | 1496003.8 | 1461744 | 2021-11-06 | 2023-04-01
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003014/WC/22012034793241 — ctr/nws check dam ratnagad bale khar ke pass | Completed | 1495717.52 | 1458764 | 2021-11-06 | 2023-03-17
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003014/WC/22012034793243 — ctr/nws check dam bhalla khar ke pass | Completed | 1495190.81 | 1462016 | 2021-11-06 | 2023-04-01
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003014/WC/22012034793249 — ctr/nws check dam bade khar ke pass | Completed | 1497452.65 | 1466129 | 2021-11-06 | 2022-07-23
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003014/WC/22012034793252 — ctr/nws talab nirman badha khar ke pass | Completed | 1494674.52 | 1432125 | 2021-10-19 | 2022-07-23
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003014/WC/22012034793255 — ctr/nws talab nirman sand bali ke pass | Completed | 1496658.21 | 1431828 | 2021-10-04 | 2022-05-11
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003014/WC/22012034793261 — ctr/nws talab nirman gad nalle ke pass | Completed | 1498651.71 | 1420386 | 2021-10-19 | 2022-05-11
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen Gully Plugs for Community / Construction of Earthen Gully Plugs for Community | Boulder Check/Gully Plug | 1701003014/WC/22012034835682 — ctr/nws earthan bund behad me gospur | Completed | 1496213.58 | 1297780 | 2021-10-19 | 2022-11-09
MORENA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen Gully Plugs for Community / Construction of Earthen Gully Plugs for Community | Boulder Check/Gully Plug | 1701003014/WC/22012034835684 — ctr/nws earthan bund khar me gospur | Completed | 1494466.68 | 1209148 | 2022-04-01 | 2022-12-22
MORENA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003014/WC/22012034940059 — nws chek dam nirman kary khadar me | Closed | 0 | 0 | 2022-04-07
MORENA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003014/WC/22012034940075 — nws chek dam nirman kary atta bali gati ke pass | Closed | 0 | 0 | 2022-04-07
MORENA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003014/WC/22012034940092 — nws talab nirman kary khirki ke nare ke pass | Completed | 1475522.1 | 1405088 | 2022-04-30 | 2022-09-24
MORENA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003014/WC/22012034940104 — nws talab nirman kary khoi ke nare ke pass | Completed | 1496692.87 | 1428403.52 | 2022-04-30 | 2024-01-05
MORENA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003014/WC/22012034940116 — nws talab nirman kary uche dande par | Completed | 1492792.95 | 1432536.99 | 2022-04-30 | 2023-07-01
MORENA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003014/WC/22012034940123 — nws talab nirman kary pali khar ke pass | Completed | 1498800.07 | 1418742 | 2022-04-30 | 2022-09-24
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003014/WC/22012034940135 — nws earthan bund purane peepal ke pass | Completed | 915663.1 | 856878 | 2023-07-19 | 2026-01-17
MORENA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003014/WC/22012034940142 — nws earthan bund chote dande khar ke pass | Closed | 871077.36 | 0 | 2022-04-07
MORENA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003014/WC/22012034944211 — Amrat sarovar talab nirman kary ratan singh ke pura ke pass | Completed | 1987167.01 | 1881076 | 2022-04-23 | 2022-09-24
MORENA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003014/WC/22012034944217 — Amrat sarovar talab nirman kary chote dade khar ke pass | Completed | 1985825.18 | 1877928 | 2022-04-30 | 2022-09-24
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1701003014/WC/22012035001072 — nws talab nirman kary dhoiya ke pass hanshraj ka pura gospur | Completed | 1487300.28 | 1411798 | 2023-09-08 | 2024-09-10
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701003014/WC/22012035001074 — nws talab nirman kary nichlo bandha hanshraj ka pura | Completed | 1489290.52 | 1397311.72 | 2023-09-08 | 2024-10-14
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701003014/WC/22012035018179 — Amrat sarovar talab nirman kary sadak ke pass gospur | Physically Completed | 2029081.78 | 1719942.32 | 2023-05-12 | 2026-06-12
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003014/WC/22012035101468 — रपटा निर्माण कार्य गौसपुर मुख्य मार्ग से हरनारायण के पुरा तक | Closed | 0 | 0 | 2023-08-16
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003014/WC/22012035101469 — रपटा निर्माण कार्य सुदूर सड़क पर गौसपुर | Closed | 0 | 0 | 2023-08-16
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003014/WC/22012035101474 — रपटा निर्माण कार्य गोपीयापुरा मुख्य मार्ग से भूमियां बाबा मन्दिर तक गोसपुर | Completed | 1484608.84 | 1381613.52 | 2024-02-09 | 2024-12-20
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1701003014/WC/22012035105484 — AH talab nirman kary dandi khaar ke pass | Closed | 0 | 0 | 2023-08-16
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1701003014/WC/22012035105485 — AH talab nirman kary neem waale khaar ke pass | Closed | 0 | 0 | 2023-08-16
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003014/WC/22012035151651 — nws anicut nirman kary choti nariya ke pass | Completed | 1463369.3 | 1421183 | 2024-01-21 | 2024-10-14
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003014/WC/22012035151654 — nws anicut nirman kary behad ke pass | Completed | 1459846.39 | 1429096 | 2024-01-21 | 2026-04-15
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701003014/WC/22012035152730 — nws talab nirman kary higothiyai ke pass | Ongoing | 1432702.62 | 1371222.92 | 2024-03-11
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701003014/WC/22012035152732 — nws earthan bund nirman kary marghati ke pass | Ongoing | 774890.66 | 546155 | 2024-01-22
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701003014/WC/22012035152734 — nws earthan bund nirman kary chakor khaar ke pass | Ongoing | 802641.38 | 573283 | 2024-01-22
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701003014/WC/22012035152839 — nws lbs nirman kary neebai ke pass | Ongoing | 765105.21 | 725069.81 | 2024-02-06
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701003014/WC/22012035152840 — nws lbs nirman kary aamkhaar ke pass | Ongoing | 795815.04 | 521311.8 | 2024-02-06
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003014/WC/22012035170725 — nws anicut nirman kary jhaar ke pass | Completed | 1461935.29 | 1391380 | 2024-02-24 | 2024-10-09
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003014/WC/22012035170728 — Nws anicut nirman kary babool ke ped ke pass | Completed | 1467393.73 | 1427358 | 2024-02-25 | 2024-10-09
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701003014/WC/22012035170730 — Nws talab nirman kary neeb bali nari ke pass | Completed | 1435477.38 | 1328239 | 2024-02-25 | 2024-10-29
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701003014/WC/22012035170733 — Nws Earthen bund nirman kary khaar ke pass | Ongoing | 788945.18 | 651541 | 2024-02-25
MORENA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701003014/WC/22012035212985 — nws talab nirman karya kumra bali naiya ke pass | Deleted | 0 | 0 | 2024-06-16
MORENA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701003014/WC/22012035212986 — nws talab nirman karya kumra bali naiya ke pass | Ongoing | 1473173.76 | 1411574.5 | 2024-09-03
MORENA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701003014/WC/22012035212989 — nws talab nirman karya dane baba ki nariya ke pass | Ongoing | 1467258.18 | 1391477.18 | 2024-09-03
MORENA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701003014/WC/22012035212990 — nws talab nirman karya ker bale khar ke pass | Physically Completed | 1491967.6 | 1377463.74 | 2024-09-03 | 2026-05-23
MORENA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701003014/WC/22012035212991 — nws earthan bund nirman karya karila bale khar ke pass | Approved | 871354.83 | 0 | 2024-06-16
MORENA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701003014/WC/22012035212995 — nws earthan bund nirman karya chokata bale khar ke pass | Approved | 888425.63 | 0 | 2024-04-16
MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701003014/WC/22012035317675 — Talab nirmaan karya tahseeldar ke khet ke pass | Approved | 0 | 0 | 2025-04-14
MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701003014/WC/22012035317676 — Talab nirmaan karya Ped ke pass | Approved | 0 | 0 | 2025-04-14
MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701003014/WC/22012035317677 — Talab nirmaan karya Tilghana naria ke pass | Approved | 0 | 0 | 2025-04-14
MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701003014/WC/22012035317678 — Talab nirmaan karya kareel ke pass | Approved | 0 | 0 | 2025-04-14
MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701003014/WC/22012035317685 — Talab nirmaan karya Fakira wale khaar me | Approved | 0 | 0 | 2025-04-14
MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701003014/WC/22012035317687 — Talab nirmaan karya Dante wale naria me | Approved | 0 | 0 | 2025-04-14
MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701003014/WC/22012035317711 — Talab nirmaan karya Bade khar ke paas | Approved | 0 | 0 | 2025-04-14
MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701003014/WC/22012035317712 — Talab nirmaan karya Pilee mati me | Approved | 0 | 0 | 2025-04-14
MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701003014/WC/22012035317713 — Talab nirmaan karya Retua ke pass | Approved | 0 | 0 | 2025-04-14
MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701003014/WC/22012035317714 — Talab nirmaan karya Rutiya wale khaar ke pass | Approved | 0 | 0 | 2025-04-14
MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701003014/WC/22012035317715 — Talab nirmaan karya Gusai wale khaar me | Approved | 0 | 0 | 2025-04-14
MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701003014/WC/22012035317716 — Talab nirmaan karya Karu khar ke pass | Approved | 0 | 0 | 2025-04-14
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1701003014/WH/22012034454334 — तालाब जीर्णोद्धार गौरी शंकर चोकीदार के पास गौसपुर | Deleted | 0 | 0 | 2021-10-02
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1701003014/WH/22012034454336 — तालाब जीर्णोद्धार गौसपुर | Deleted | 0 | 0 | 2021-10-02
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1701003014/WH/22012034920048 — तालाब जीर्णोद्धार गोरीशंकर चौकीदार के पास | Completed | 62000 | 56518 | 2022-03-23 | 2022-05-10
MORENA | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701003/RC/552 — बारह मासी सडक निर्माण् कार्य ए वी रोड से होला का पुरा | Completed | 0 | 888680.3 | 2010-06-02 | 2012-03-30
MORENA | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701/RC/36 — मिटटी ग्रेवल रोड गोसपुर से धान्‍धू का पुरा | Completed | 0 | 279899 | 2010-12-14 | 2011-08-05