## Work List
Exported on: 2026-10-06 20:56:59
Filters applied:
Data source: MGNREGA + VBGRAMG
District: MORENA
Block: All
Panchayat: GADORA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
MORENA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Anganwadi/Other Rural Infrastructure | Construction of Cattle Shelter for Community / Construction of Cattle Shelter for Community | Cattle Shed | 1701003015/AV/22012034512167 — गोशाला निर्माण कार्य गडोरा | Completed | 3784582.21 | 3717778.06 | 2020-09-21 | 2022-09-25
MORENA | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1701003015/AV/22012034535746 — शान्तिधाम निर्माण कार्य गडोरा | Completed | 194312.08 | 146174.04 | 2020-09-21 | 2020-12-09
MORENA | 2015-2016 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Building for Gram Panchayats / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1701003015/AV/5146 — आंगनबाड़ी निर्माण कार्य गडोरा | Deleted | 0 | 0 | 2016-01-26
MORENA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1701003015/DP/01 — व़क्षारोपण सिद्वबाबा आश्रम सडक किनारे | Completed | 430500 | 4710 | 2008-08-19 | 2008-04-14
MORENA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1701003015/DP/2 — व़क्षारोपण सिद्वबाबा आश्रम सडक किनारे | Deleted | 430500 | 0 | 2008-08-19
MORENA | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Land development / Levelling/shaping of Wasteland Land for Community | Land Development | 1701003015/DP/22012034229842 — शांती धाम निर्माण कार्य गडोरा | Deleted | 0 | 0 | 2016-01-26
MORENA | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Land development / Levelling/shaping of Wasteland Land for Community | Land Development | 1701003015/DP/22012034230025 — स्कूल बॉउंड्री बाल निर्माण कार्य नदउापुरा | Closed | 0 | 0 | 2016-01-26
MORENA | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701003015/DP/22012034232010 — सामुदायिक ब़क्षारोपण गडोरा | Completed | 318000 | 112079.75 | 2016-07-11 | 2018-12-04
MORENA | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1701003015/DP/22012034233689 — शांतिधाम निर्माण - गड़ौरा | Completed | 515000 | 353222.57 | 2016-09-19 | 2018-05-25
MORENA | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701003015/DP/22012034328707 — वृक्षारोपण कार्य | Closed | 0 | 0 | 2017-10-02
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Canal Line Plantation-Horticulture - Community / Canal Line Plantation of Horticulture Trees for Community | Plantation | 1701003015/DP/22012034530057 — सामुदायिक बृक्षारोपण कार्य गोशाला में | Completed | 394489.84 | 194170.3 | 2021-11-08 | 2024-12-10
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Gov blding premises-Block Plantation-Horticulture / Block Plantation of Horticulture Trees in Government building premises for Community | Plantation | 1701003015/DP/22012034542986 — माँ की बगिया हथियार सिंह का पुरा गडोरा | Completed | 22445.35 | 6948 | 2022-01-20 | 2022-06-30
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1701003015/DP/22012034544439 — Ma ki bagiya ps shala gadora | Closed | 0 | 0 | 2021-04-01
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Agro Forestry Block Plantation for Community | Plantation | 1701003015/DP/22012034599603 — वृक्षारोपण कार्य झरना मंदिर के पास गडौरा मेरी माटी मेरा देश | Ongoing | 55847.4 | 43854.3 | 2023-09-11
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Medicinal Plantation in Community land / Block Plantation of Medicinal Trees in fields for Community | Plantation | 1701003015/DP/22012034614622 — सामुदायिक पोषण वाटिका झरना सरकार गडौरा | Ongoing | 427106.07 | 242437.15 | 2024-03-08
MORENA | 2018-2019 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701003015/FP/22012034362917 — पत्थर नाला निर्माण कार्य सी सी खरंजा से पुलिया झरना सरकार गडोरा | Completed | 1282000 | 1119479.51 | 2019-03-08 | 2020-08-26
MORENA | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701003015/FP/22012034629572 — नाला निर्माण कार्य नहर से लक्खा बाबा के घर से मैन रोड की ओर | Completed | 868212.07 | 812864.6 | 2022-10-24 | 2023-09-11
MORENA | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701003015/FP/22012034634290 — पत्थर नाला निर्माण कार्य महादेव मंदिर से नदी की ओर गडौरा। | Completed | 1487132.47 | 1292470.7 | 2023-08-07 | 2024-08-22
MORENA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Fisheries | Construction of Fisheries Ponds for Community / Construction of Fishery Pond for Community | Construction of Tank | 1701003015/FR/22012034322866 — Talav Nirmaan Karya Sathane Wali Nariya Me | Ongoing | 1468172.06 | 992773.72 | 2025-01-13
MORENA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Fisheries | Construction of Fisheries Ponds for Community / Construction of Fishery Pond for Community | Construction of Tank | 1701003015/FR/22012034325058 — Talav Nirmaan Karya bade agola wali nariya me | New | 0 | 0 | 2025-04-14
MORENA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Fisheries | Construction of Fisheries Ponds for Community / Construction of Fishery Pond for Community | Construction of Tank | 1701003015/FR/22012034325059 — Talav Nirmaan Karya chondai wali nariya me | New | 0 | 0 | 2025-04-14
MORENA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Fisheries | Construction of Fisheries Ponds for Community / Construction of Fishery Pond for Community | Construction of Tank | 1701003015/FR/22012034325060 — Talav Nirmaan Karya cheeka mati wali nariya me | New | 0 | 0 | 2025-04-14
MORENA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Fisheries | Construction of Fisheries Ponds for Community / Construction of Fishery Pond for Community | Construction of Tank | 1701003015/FR/22012034325061 — Talav Nirmaan Karya ditini wali nariya me | New | 0 | 0 | 2025-04-14
MORENA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Fisheries | Construction of Fisheries Ponds for Community / Construction of Fishery Pond for Community | Construction of Tank | 1701003015/FR/22012034325062 — Talav Nirmaan Karya bade bharika wali nariya me | New | 0 | 0 | 2025-04-14
MORENA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Fisheries | Construction of Fisheries Ponds for Community / Construction of Fishery Pond for Community | Construction of Tank | 1701003015/FR/22012034325063 — Talav Nirmaan Karya mehtab ki nai tor ke pass | New | 0 | 0 | 2025-04-14
MORENA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003015/IF/1000064418 — पशुशैड निर्माण - मनोज /रामवरन | Completed | 80000 | 1752 | 2014-03-01 | 2016-11-16
MORENA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003015/IF/1000064420 — पशुशैड निर्माण कार्य- सुरेन्‍द्र /आशाराम | Completed | 80000 | 48824 | 2014-03-01 | 2016-11-16
MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701003015/IF/22012034347469 — सार्वजनिक परिसर मे व्रक्षारोपण कार्य ग्राम गडोरा से झरना सरकार मंदिर मार्ग पर | Completed | 335000 | 123558 | 2017-06-15 | 2020-12-12
MORENA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Agro Forestry Block Plantation for Individual | Plantation | 1701003015/IF/22012035247329 — वृक्षारोपण निजी खेत मे फलोद्यान कार्य शैलेन्द्र सिंह गुर्जर पुत्र श्री सरनाम सिंह | Approved | 0 | 0 | 2024-06-08
MORENA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Agro Forestry Block Plantation for Individual | Plantation | 1701003015/IF/22012035247330 — वृक्षारोपण निजी खेत मे फलोद्यान कार्य बृजेन्द्र सिंह पुत्र श्री सरनाम सिंह | Approved | 0 | 0 | 2024-06-08
MORENA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1701003015/IF/22012035482546 — Khet talab nirmaan karya Kamlesh S/O Natthi Singh | Completed | 147621.16 | 75429 | 2025-05-21 | 2025-10-08
MORENA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1701003015/IF/22012035482601 — Khet talab nirmaan karya Rajveer Singh S/O Prem Singh | Completed | 147621.16 | 103356 | 2025-05-10 | 2025-08-12
MORENA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1701003015/IF/22012035482609 — Khet talab nirmaan karya Ramjilal S/O Natthi Singh | Completed | 147621.16 | 104922.18 | 2025-05-13 | 2025-10-15
MORENA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1701003015/IF/22012035482625 — Khet talab nirmaan karya Ramvilas S/O Radha Kishan | Completed | 147621.16 | 108315 | 2025-05-10 | 2025-10-06
MORENA | 2011-2012 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1701003015/IF/267 — मेड वन्‍धान जरजोधन / दधिराम | Completed | 0 | 16958 | 2011-11-04 | 2011-11-17
MORENA | 2011-2012 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1701003015/IF/268 — मेड वन्‍धान ओतार / सूरतराम | Completed | 0 | 10126 | 2011-11-12 | 2011-12-05
MORENA | 2011-2012 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1701003015/IF/270 — मेड वन्‍धान रनवीर / हरीकि‍शुन | Completed | 0 | 12688 | 2011-11-19 | 2011-11-24
MORENA | 2011-2012 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1701003015/IF/271 — मेढ वन्‍धान राजेन्‍द्व /आशाराम | Completed | 0 | 8418 | 2011-11-29 | 2011-12-05
MORENA | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1701003015/IF/426 — मेढवंधान कार्य | Completed | 0 | 18480 | 2012-08-30 | 2012-09-05
MORENA | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1701003015/IF/427 — मेढवंधान कार्य | Completed | 0 | 21516 | 2012-09-06 | 2012-09-12
MORENA | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1701003015/IF/428 — मेढवंधान कार्य | Completed | 0 | 15576 | 2012-09-13 | 2012-09-19
MORENA | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1701003015/IF/447 — मेढवंधान कार्य | Completed | 0 | 24288 | 2012-09-27 | 2012-10-03
MORENA | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1701003015/IF/448 — मेढवंधान कार्य | Completed | 0 | 15972 | 2012-09-20 | 2012-09-26
MORENA | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1701003015/IF/458 — मेढवंधान | Completed | 0 | 25476 | 2012-10-04 | 2012-10-10
MORENA | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1701003015/IF/481 — मेढवंधान कार्य | Completed | 0 | 13728 | 2012-10-11 | 2012-10-17
MORENA | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1701003015/IF/511 — मेढवंधान कार्य | Completed | 0 | 33792 | 2012-10-18 | 2012-10-31
MORENA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003015/IF/9926705826 — पशुशैड निर्माण कार्य रविन्‍द्र/दीप सिंह | Completed | 80000 | 68839 | 2014-03-01 | 2016-11-16
MORENA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003015/IF/9926712926 — पशुशैड निर्माण कार्य - रामखिलाडी/ज्‍वाला प्रसाद | Completed | 86000 | 71762 | 2014-03-05 | 2016-11-16
MORENA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003015/IF/9926712929 — पशुशैड निर्माण कार्य - गंगाराम/आशाराम | Completed | 80000 | 31678 | 2014-03-05 | 2016-12-07
MORENA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003015/IF/9926713335 — पशु शेड निर्माड कार्य रामकेश /गोकुल सिंह | Completed | 80000 | 72728 | 2014-03-05 | 2016-11-16
MORENA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003015/IF/9926713344 — पशु शेड निर्माण केशव /कम्पोटर | Completed | 86000 | 876 | 2014-03-05 | 2016-11-16
MORENA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003015/IF/9926713351 — पशु शेड निर्माण कार्य बिजेंद्र /बिशाल सिह | Completed | 86000 | 68170 | 2014-03-05 | 2014-08-29
MORENA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003015/IF/9993725998 — पशु शेड निर्माण कार्य पूरन सिंह | Deleted | 0 | 0 | 2016-01-26
MORENA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003015/IF/9993726018 — पशु शेड निर्माण कार्य गीताराम | Deleted | 0 | 0 | 2016-01-26
MORENA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003015/IF/9993728090 — पशु शेड निर्माण कार्य गमवीर सिंह | Deleted | 0 | 0 | 2016-01-26
MORENA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003015/IF/9993728092 — पशु शेड निर्माण कार्य अमरीश सिंह राजेंद्र | Deleted | 0 | 0 | 2016-01-26
MORENA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003015/IF/9993728097 — पशु शेड निर्माण कार्य महेश सिंह सुजान सिंह | Deleted | 0 | 0 | 2016-01-26
MORENA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003015/IF/9993728100 — पशु शेड निर्माण कार्य रामजीत सिंह औतारसिंह | Deleted | 0 | 0 | 2016-01-26
MORENA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1701003015/IF/IAY/119159 — Construction of IAY House -IAY REG. NO. MP-01-003-015-001/20 | Approved | 27000 | 0 | 2016-01-14
MORENA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003015/IF/IAY/205477 — Construction of IAY House -IAY REG. NO. MP-01-003-015-001/33 | Completed | 15030 | 14028 | 2016-12-12 | 2018-02-05
MORENA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003015/IF/IAY/491059 — Construction of IAY House -IAY REG. NO. MP2142467 | Completed | 15030 | 15300 | 2017-01-30 | 2018-02-02
MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003015/IF/IAY/735309 — Construction of IAY House -IAY REG. NO. MP2114523 | Completed | 15030 | 15420 | 2017-04-10 | 2018-02-05
MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003015/IF/IAY/735330 — Construction of IAY House -IAY REG. NO. MP2114864 | Completed | 15030 | 15420 | 2017-04-10 | 2018-02-05
MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003015/IF/IAY/735349 — Construction of IAY House -IAY REG. NO. MP2115275 | Completed | 15030 | 15420 | 2017-04-10 | 2018-02-05
MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003015/IF/IAY/735687 — Construction of IAY House -IAY REG. NO. MP2123273 | Completed | 15030 | 15420 | 2017-04-10 | 2018-02-05
MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003015/IF/IAY/736612 — Construction of IAY House -IAY REG. NO. MP2143470 | Completed | 15030 | 15420 | 2017-04-10 | 2018-02-05
MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003015/IF/IAY/736617 — Construction of IAY House -IAY REG. NO. MP2143529 | Completed | 15030 | 15480 | 2017-04-10 | 2018-02-05
MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003015/IF/IAY/738408 — Construction of IAY House -IAY REG. NO. MP2182199 | Completed | 15030 | 15480 | 2017-04-10 | 2018-02-05
MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003015/IF/IAY/738411 — Construction of IAY House -IAY REG. NO. MP2182434 | Completed | 15030 | 15480 | 2017-04-10 | 2018-02-02
MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003015/IF/IAY/756329 — Construction of IAY House -IAY REG. NO. MP2789587 | Completed | 15030 | 15480 | 2017-04-18 | 2018-02-02
MORENA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1701003015/IF/IAY/772508 — Construction of IAY House -IAY REG. NO. MP3548532 | Approved | 27000 | 0 | 2017-03-19
MORENA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1701003015/IF/IAY/772899 — Construction of IAY House -IAY REG. NO. MP3568103 | Approved | 27000 | 0 | 2017-03-19
MORENA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1701003015/IF/IAY/774808 — Construction of IAY House -IAY REG. NO. MP3661496 | Approved | 27000 | 0 | 2017-03-19
MORENA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003015/IF/IAY/794463 — Construction of IAY House -IAY REG. NO. MP2123264 | Deleted | 15480 | 0 | 2018-06-29
MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003015/IF/IAY/794797 — Construction of IAY House -IAY REG. NO. MP2148630 | Completed | 15480 | 15480 | 2017-05-08 | 2018-02-02
MORENA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701003015/LD/1138 — मेड वन्‍धान कार्य राजेन्‍द मोहर सिह | Deleted | 0 | 0 | 2010-07-24
MORENA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701003015/LD/1139 — मेड वन्‍धान कार्य रनवीर पुञ हरिकशिन पुञ | Completed | 0 | 12000 | 2010-07-24 | 2010-07-30
MORENA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701003015/LD/1140 — मेड वन्‍धान कार्य नवल सिह पुञ महाराज | Completed | 0 | 7600 | 2010-08-08 | 2010-08-14
MORENA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701003015/LD/1141 — मेड वन्‍धान कार्य निहाल पुञ सोनेराम | Completed | 0 | 4300 | 2010-07-31 | 2010-08-06
MORENA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701003015/LD/1142 — मेड वन्‍धान कार्य वीरवल पूञ शंकर सिह | Completed | 0 | 6900 | 2010-08-08 | 2010-08-14
MORENA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701003015/LD/1143 — मेड वन्‍धान कार्य गजाधर पुञ मूगाराम | Deleted | 0 | 0 | 2010-07-31
MORENA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701003015/LD/1216 — मैडवन्‍धान कार्य सगुना पुञ छिदृदाराम | Completed | 0 | 14200 | 2010-08-16 | 2010-08-22
MORENA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701003015/LD/1217 — मैडवन्‍धान कार्य आशाराम पुञ पूरन | Completed | 0 | 5600 | 2010-08-16 | 2010-08-22
MORENA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701003015/LD/1218 — मैडवन्‍धान कार्य मुकेश पुञ गम्‍भीर | Completed | 0 | 15500 | 2010-08-26 | 2010-09-01
MORENA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701003015/LD/1219 — मैडवन्‍धान कार्य फदृदी पुञ रामस्‍वरूप | Completed | 0 | 7900 | 2010-08-26 | 2010-04-01
MORENA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701003015/LD/1229 — मैडवन्‍धान कार्य रामहेत पुञ लखपति | Completed | 0 | 13700 | 2010-09-09 | 2010-04-01
MORENA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701003015/LD/1230 — मैडवन्‍धान कार्य नत्‍थी पुञ श्‍यामा | Completed | 0 | 8500 | 2010-09-22 | 2010-09-27
MORENA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701003015/LD/1231 — मैडवन्‍धान कार्य गुलावो पुञ खूवचन्‍द्र | Completed | 0 | 7200 | 2010-09-09 | 2010-09-09
MORENA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701003015/LD/1232 — मैडवन्‍धान कार्य रामवेरी पुञ सरनाम | Completed | 0 | 8500 | 2010-09-02 | 2010-09-21
MORENA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701003015/LD/1233 — मैडवन्‍धान कार्य कदमसिंह पुञ गयाशीराम | Completed | 0 | 6100 | 2010-09-16 | 2010-09-16
MORENA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701003015/LD/1234 — मैडवन्‍धान कार्य भेदराम पुञ मोहकसिंह | Completed | 0 | 9700 | 2010-09-02 | 2010-09-02
MORENA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701003015/LD/1235 — मैडवन्‍धान कार्य पंछी पुञ कल्‍यान | Completed | 0 | 3900 | 2010-09-02 | 2010-09-02
MORENA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701003015/LD/1236 — मैढ बंधान कार्य बाबू / लोकमन | Completed | 0 | 6300 | 2010-09-22 | 2010-09-22
MORENA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701003015/LD/1237 — मैढ बंधान कार्य बैताल / मूगाराम | Completed | 0 | 7100 | 2010-09-22 | 2010-04-01
MORENA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701003015/LD/1238 — मैढ बंधान कार्य केदार अतर सिंह / भरत सिंह | Completed | 0 | 8000 | 2010-09-28 | 2010-09-28
MORENA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Dev of Silvipasture Grassslands for Community / Development of Silvipasture Grassslands for Community | Grass Land Development | 1701003015/LD/22012034538411 — चारागाह विकास कार्य ग्राम पंचायत गडोरा | Completed | 792213.45 | 538376.87 | 2021-03-09 | 2024-12-10
MORENA | 2012-2013 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1701003015/LD/3799388010 — मेढ बन्धान वीरेन्द्र/हेतसिंह् | Deleted | 0 | 0 | 2013-01-26
MORENA | 2017-2018 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1701003015/PG/22012034365431 — खेलमैदान निर्माण कार्य - गडौरा | Completed | 353000 | 2076 | 2017-10-30 | 2018-10-25
MORENA | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Metal Second coat / Construction of WBM Roads for Community | Construction of Road and Culvert | 1701003015/RC/1071 — सी सी खरंजा गडोरा | Completed | 0 | 113189 | 2012-02-22 | 2012-04-01
MORENA | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701003015/RC/22 — सीमेन्‍ट फ्रान्‍फीट खरंजा | Completed | 492000 | 10829 | 2009-05-21 | 2009-06-03
MORENA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003015/RC/22012034159568 — सी सी खरंजा पंचपरमेश्‍वर गणोरा | Completed | 35400 | 34977 | 2013-02-22 | 2013-04-26
MORENA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003015/RC/22012034161080 — पंच परमेश्‍वर सी सी खरंजा एवं नाजी निर्माण कार्य गडोरा | Deleted | 0 | 0 | 2013-01-26
MORENA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003015/RC/22012034161085 — पंचपरमेश्‍वर सी सी खरंजा एवं नाली निर्माण कार्य रा | Completed | 39038 | 38506 | 2013-03-20 | 2014-01-28
MORENA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003015/RC/22012034162751 — सी सी खरजा नाली निर्माण पंचपरमेश्वर बच्चू के घर से | Completed | 80013 | 72920 | 2013-10-04 | 2014-03-01
MORENA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003015/RC/22012034162756 — सी सी खरंजा नाली निर्माण पंचपरमेश्वर बच्चू के मकान से मंडले के मकान तक | Deleted | 0 | 0 | 2013-01-26
MORENA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701003015/RC/22012034209597 — खेत सड्क - मिटटी बजरी रोड निर्माण नदुआपुरा से खार | Completed | 1476000 | 36858 | 2014-03-04 | 2016-09-19
MORENA | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003015/RC/22012034223911 — सी सी खरंजा एवं नाली निर्माण कार्य - रामवीर के मका | Completed | 124260 | 108690 | 2014-08-01 | 2014-08-16
MORENA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003015/RC/22012034296609 — सी. सी. खरंजा एंव नाली निर्माण कार्य - झिरना मंदिर गडौरा | Completed | 55000 | 52752 | 2016-01-18 | 2016-06-16
MORENA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701003015/RC/22012034298229 — पत्थर खरंजा ऐब नाली निर्माण कार्य घ्हिरना मंदिर से गड़ोरा | Deleted | 961000 | 0 | 2015-08-15
MORENA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003015/RC/22012034307895 — सी सी खरंजा निर्माण कार्य सुरेन्द्र के घर से रामखिलाडी के घर तक | Deleted | 0 | 0 | 2016-01-26
MORENA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701003015/RC/22012034307897 — पत्थर खरजा निर्माण कार्य गडोरा | Deleted | 0 | 0 | 2016-01-26
MORENA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003015/RC/22012034325283 — सी सी खरंजा निर्माण कार्य - हरिजन बस्‍ती में परिमाल सिंह के घर से फददी के घर तक गडोरा | Completed | 36000 | 30316 | 2017-02-06 | 2017-12-05
MORENA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003015/RC/22012034325285 — सी सी खरंजा निर्माण - दामोदर के घर से लाल सिंह के घर तक गडोरा | Completed | 54000 | 53836 | 2017-04-10 | 2017-12-05
MORENA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003015/RC/22012034325287 — सी सी खरंजा निर्माण कार्य - सुल्‍तान सिंह के घर से रामखिलाडी के घर गडोरा | Completed | 36000 | 35776 | 2017-08-07 | 2018-01-05
MORENA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Mitti Murram Roads for Community / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701003015/RC/22012034325289 — सुदूर ग्राम संपर्क सड्क - नन्‍दूआपुरा से सिल्‍लेबाई तक गडोरा | Completed | 1498000 | 1387800.72 | 2017-02-06 | 2020-08-26
MORENA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003015/RC/22012034353406 — सी सी खरंजा निर्माण - कुआ से महादेव मंदिर तक गडोरा | Completed | 80250 | 71724 | 2017-10-09 | 2018-04-04
MORENA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003015/RC/22012034353407 — सी सी खरंजा निर्माण - कदम सिंह के घर से अशोक के घर तक | Completed | 36150 | 35432 | 2017-10-09 | 2018-04-04
MORENA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003015/RC/22012034365080 — सी सी खरंजा निर्माण - मुख्‍य सडक से गीताराम के घर तक | Completed | 36150 | 35432 | 2017-10-30 | 2018-04-04
MORENA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003015/RC/22012034365081 — सी सी खरंजा निर्माण - रमेश के घर से पंजाब सिंह के घर तक | Completed | 36150 | 36292 | 2017-10-30 | 2018-04-04
MORENA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003015/RC/22012034385230 — सी सी खरंजा एवं नाली निर्माण - नदुआ पुरा में माता मंदिर से स्‍कूल तक गडोरा | Deleted | 36000 | 0 | 2017-01-26
MORENA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003015/RC/22012034385232 — सी सी खरंजा एवं नाली निर्माण - लवकुश के घर से हवेली तक गडोरा | Deleted | 54000 | 0 | 2017-01-26
MORENA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003015/RC/22012034386680 — सी सी खरंजा एवं नाली निर्माण - नदुआ पुरा से माता मंदिर से स्कूल तक | Completed | 36000 | 36018 | 2018-04-23 | 2018-11-19
MORENA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003015/RC/22012034386681 — सी सी खरंजा एवं नाली निर्माण - लवकुश के घर से हवेली तक गड़ोरा | Physically Completed | 54000 | 53832 | 2019-03-08 | 2020-12-09
MORENA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003015/RC/22012034449141 — सी.सी. खरंजा एवं नाली निर्माण कार्य - मुख्य रोड से जगदीश बापू के घर तक | Completed | 59850 | 59816 | 2019-03-07 | 2019-08-30
MORENA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003015/RC/22012034449146 — सी.सी. खरंजा एवं नाली निर्माण कार्य - मुख्य मार्ग से रामू के घर तक | Completed | 35910 | 35704 | 2019-03-07 | 2019-08-30
MORENA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003015/RC/22012034449151 — सी.सी. खरंजा एवं नाली निर्माण कार्य - केदार सिंह के घर से कुए तक | Completed | 71820 | 71256 | 2019-03-07 | 2019-11-28
MORENA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003015/RC/22012034502693 — सी.सी. खरंजा एवं नाली निर्माण कार्य - मुख्य मार्ग से सिरमौर के पुरा तक। | Completed | 63840 | 63536 | 2019-12-02 | 2020-01-01
MORENA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701003015/RC/22012034524207 — एप्रोच रोड निर्माण कार्य गडोरा से शासकीय माध्यमिक विद्यालय तक | Completed | 1497116.76 | 992631.54 | 2020-08-03 | 2022-04-30
MORENA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701003015/RC/22012034526602 — सुदूर ग्राम संपर्क /खेत सड़क गडोरा से लटीला बाबा होते हुए नदुआपुरा तक रोड | Completed | 7950336.83 | 5879546.32 | 2020-07-20 | 2023-10-04
MORENA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003015/RC/22012034540355 — सी. सी. खरंजा निर्माण कार्य मुख्या सड़क से लाखाराम के पूरा तक | Closed | 41692 | 0 | 2020-04-14
MORENA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003015/RC/22012034540542 — सी.सी. खरंजा निर्माण कार्य मुख्य सड़क से लाखाराम के पूरा तक | Closed | 0 | 0 | 2020-04-14
MORENA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003015/RC/22012034540547 — सी.सी. खरंजा निर्माण कार्य मुख्य सड़क से देवसिंघ के घर तक | Completed | 19890 | 14820 | 2021-02-23 | 2022-05-31
MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003015/RC/22012034540548 — सी.सी. खरंजा निर्माण कार्य मुख्य सड़क से सुरेंद्र सिंह के घर तक | Completed | 19125 | 19107 | 2021-04-03 | 2021-08-10
MORENA | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701003015/RC/569 — मिट्रटी वजरी रोड निर्माण कार्य गडोरा से झिरना तक | Completed | 0 | 323383.95 | 2010-10-06 | 2010-10-06
MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1701003015/RS/22012034607705 — सामुदायिक स्वछता परिसर ग्राम पंचायत गडोरा | Completed | 43000 | 42846 | 2021-11-15 | 2022-02-22
MORENA | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Stone Bund / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701003015/WC/22012034297055 — रिंगबंड निर्माण बीहड़ में ग्राम गरौड़ा | Completed | 115319 | 107701.66 | 2016-06-27 | 2016-09-23
MORENA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701003015/WC/22012034392011 — नवीन तालाब निर्माण काार्य - गडौरा | Completed | 695000 | 686558.03 | 2019-03-08 | 2020-08-20
MORENA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003015/WC/22012034432251 — नवीन तालाब निर्माण कार्य - | Closed | 0 | 0 | 2019-01-26
MORENA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003015/WC/22012034529867 — तालाब निर्माण कार्य गडौरा | Closed | 0 | 0 | 2020-01-26
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1701003015/WC/22012034558986 — तालाब निर्माण कार्य गडोरा | Completed | 1445991.62 | 1346766 | 2021-04-01 | 2023-07-11
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003015/WC/22012034658491 — nws check dam nirman kary sadhane per | Completed | 1499034.41 | 1471082.08 | 2021-05-06 | 2022-03-30
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003015/WC/22012034658500 — nws check dam nirman kary khirak per | Completed | 1497001.93 | 1457292 | 2021-05-06 | 2022-08-17
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003015/WC/22012034658507 — nws check dam nirman baisal me | Completed | 1493718.41 | 1440360 | 2021-05-06 | 2022-10-16
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003015/WC/22012034658515 — nws check dam nirman kary khilla per | Completed | 1499698.91 | 1456758 | 2021-05-06 | 2022-07-11
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003015/WC/22012034658526 — nws check dam nirman kary badi kherihai me | Completed | 1494216.78 | 1432047 | 2021-05-06 | 2022-12-28
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003015/WC/22012034658541 — nws check dam nirman kary foola ke khet ke pass | Completed | 1499211.91 | 1479420 | 2021-05-06 | 2022-02-02
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003015/WC/22012034658562 — nws check dam nirman kolhubai | Completed | 1499859.39 | 1432198 | 2021-05-06 | 2021-11-09
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003015/WC/22012034658577 — nws talab nirman piperbai me | Completed | 1499444.7 | 1436107.15 | 2021-05-06 | 2023-09-29
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003015/WC/22012034658584 — nws talab nirman shakhai me | Closed | 0 | 0 | 2021-04-14
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003015/WC/22012034658585 — nws talab nirman shakhai me | Completed | 1497304.64 | 1398330 | 2021-05-06 | 2024-01-05
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003015/WC/22012034658594 — nws talab nirman jatbai me | Completed | 1495413.31 | 1391214.36 | 2021-05-06 | 2022-11-19
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003015/WC/22012034658600 — nws talab nirman choti kherihai me | Completed | 1498862.23 | 1428352.67 | 2021-05-06 | 2024-09-06
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003015/WC/22012034658606 — nws talab nirman datili me | Completed | 1499400.31 | 1429151 | 2021-09-25 | 2023-07-24
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003015/WC/22012034814544 — ctr/nws check dam nirman ramtla me | Completed | 1494498.38 | 1457997 | 2021-11-08 | 2023-04-26
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003015/WC/22012034860701 — ctr/nws talab nirman gadora khere per | Completed | 1495881.75 | 1422611 | 2021-12-03 | 2024-01-05
MORENA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003015/WC/22012034860704 — ctr/nws talab nirman gangabai me | Completed | 1496985.34 | 1420690 | 2022-04-08 | 2022-11-19
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003015/WC/22012034860709 — ctr/nws check dam nirman kary behad me gadora | Completed | 1499674.01 | 1395658 | 2021-11-08 | 2023-04-26
MORENA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003015/WC/22012034860712 — ctr/nws gully plug taal me | Completed | 1495218.4 | 1381212 | 2022-06-05 | 2024-09-06
MORENA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003015/WC/22012034956501 — Amrat sarovar talab nirman kary daba ki thari | Closed | 0 | 0 | 2022-04-20
MORENA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701003015/WC/22012035000478 — nws talab nirman karya tot bali nariya me | Completed | 1478229.62 | 1409527.58 | 2022-10-14 | 2023-07-24
MORENA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701003015/WC/22012035000479 — nws talab nirman karya hori bai nariya me | Completed | 1494695.98 | 1435261.27 | 2022-10-14 | 2023-12-11
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701003015/WC/22012035000481 — nws talab nirman karya taal bali nariya me | Completed | 1464680.91 | 1415177.76 | 2023-05-22 | 2024-08-14
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701003015/WC/22012035000483 — nws talab nirman karya jhor bali nariya me | Completed | 1426866.54 | 1382006 | 2023-05-22 | 2024-06-28
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701003015/WC/22012035000484 — nws talab nirman kary bhodri bali nariya me | Completed | 1451066.69 | 1404655 | 2023-06-12 | 2023-12-06
MORENA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701003015/WC/22012035000762 — nws talab nirman karya ghata bali nariya me | Completed | 1488661.3 | 1422514.92 | 2022-10-14 | 2023-12-22
MORENA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701003015/WC/22012035000763 — nws talab nirman karysheri bari naria me | Completed | 1488898.45 | 1422148.95 | 2022-10-14 | 2023-10-18
MORENA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701003015/WC/22012035000764 — nws talab nirman kary sadhor me | Completed | 1482413.37 | 1420430.36 | 2022-10-14 | 2023-10-18
MORENA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701003015/WC/22012035019033 — nws earthan dam chokar bali naria | Completed | 1472901.68 | 1421861.08 | 2022-12-19 | 2024-01-25
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1701003015/WC/22012035056699 — anicut nirman kary sidh baba ke peeche kosawai nariya ke pass | Completed | 1464000.58 | 1429446 | 2023-06-19 | 2023-10-04
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701003015/WC/22012035056700 — anicut nirman kary laal singh ke khet ke pass | Completed | 1468565.98 | 1439829 | 2024-01-20 | 2025-04-29
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003015/WC/22012035056701 — anicut nirman kary nadua ka pura road ke pass | Completed | 1483765.68 | 1456491 | 2024-01-20 | 2024-06-25
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701003015/WC/22012035073638 — AH talab nirman kary katewari waali nariya me | Completed | 2238895.62 | 2138684 | 2023-08-01 | 2024-11-06
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701003015/WC/22012035073639 — AH talab nirman kary sanbaai nariya me | Completed | 1898898.49 | 1828376.96 | 2023-07-17 | 2024-10-10
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003015/WC/22012035112841 — रपटा निर्माण कार्य झरना सरकार वाली रोड पर घटिया के नीचे | Completed | 1491792.51 | 1412747.16 | 2023-10-04 | 2024-08-14
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1701003015/WC/22012035140648 — Earthan bund nirman kary jhor ki nariya me | Completed | 1173904.15 | 1122742 | 2023-10-09 | 2025-10-06
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1701003015/WC/22012035140657 — earthan bund nirman kary bagiya wali nariya ke pass | Completed | 1164773.35 | 1108923 | 2023-10-09 | 2024-10-09
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003015/WC/22012035148494 — रपटा निर्माण कार्य मझगेल वाली नरिया पर नदूआ पूरा रोड पर | Completed | 1483608.84 | 1279955.8 | 2024-01-20 | 2025-01-15
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003015/WC/22012035148497 — रपटा निर्माण कार्य नदूआ पूरा रोड पर ताल वाली नरिया के पास | Completed | 1461609.52 | 1328411.3 | 2024-01-29 | 2024-12-10
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003015/WC/22012035149508 — nws anicut nirman kary badi nariya khaar ke pass | Closed | 0 | 0 | 2023-10-02
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003015/WC/22012035149510 — nws anicut nirman kary jhirna bali nariya me | Closed | 0 | 0 | 2023-10-02
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701003015/WC/22012035149512 — nws talab nirman kary kakora bali nariya me | Completed | 1429762.4 | 1376918 | 2024-02-05 | 2025-06-11
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701003015/WC/22012035149514 — nws talab nirman kary bhupe ke khet ke pass | Completed | 1470835.92 | 1417013 | 2024-02-05 | 2024-10-10
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701003015/WC/22012035149781 — nws talab nirman kary mistri ki tor ke pass | Completed | 1451766.63 | 1375904 | 2024-02-12 | 2026-01-06
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701003015/WC/22012035149782 — Nws earthan bund hori bai nariya ke bagal bali nariya me | Closed | 0 | 0 | 2023-10-02
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003015/WC/22012035172634 — nws anicut nirman kary jhirna bali nariya me | Completed | 1461935.29 | 1437673 | 2024-02-23 | 2024-11-18
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003015/WC/22012035172637 — nws anicut nirman kary badi nariya khaar ke pass | Completed | 1470963.93 | 1439102 | 2024-02-23 | 2025-03-06
MORENA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701003015/WC/22012035172671 — Nws talab nirman kary bhatiyai naria me | Completed | 1421281.33 | 1384553 | 2024-07-03 | 2026-03-09
MORENA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003015/WC/22012035205961 — nws check dam nirman karya nai tor k pass | Approved | 0 | 0 | 2024-06-12
MORENA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003015/WC/22012035205973 — nws check dam nirman karya parosatum ki pabai ke pass | Approved | 0 | 0 | 2024-06-12
MORENA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003015/WC/22012035205980 — nws check dam nirman karya nadi ke behad me | Approved | 0 | 0 | 2024-06-12
MORENA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003015/WC/22012035205983 — nws check dam nirman karya badi kasbai ke pass | Approved | 0 | 0 | 2024-06-12
MORENA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701003015/WC/22012035220082 — Nws parculation tank nirman kary ramhet ki tor ke pass | Physically Completed | 1465124.57 | 1404890.95 | 2024-10-07 | 2026-05-20
MORENA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701003015/WC/22012035220083 — Nws parculation tank nirman kary sahjanbai naria ke pass | Physically Completed | 1478802.75 | 1431317.44 | 2024-10-07 | 2026-05-20
MORENA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701003015/WC/22012035220085 — Nws parculation tank nirman kary nadi ke behad me | Physically Completed | 1469600.15 | 1406660.25 | 2024-12-03 | 2026-05-20
MORENA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701003015/WC/22012035220086 — Nws parculation tank nirman kary tor ke pass | Physically Completed | 928795.04 | 900132.14 | 2025-02-24 | 2026-05-20
MORENA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701003015/WC/22012035220087 — Nws parculation tank nirman kary behad me ramprakash nai ke khet ke pass | Physically Completed | 1478761.03 | 1400931.44 | 2024-09-23 | 2026-05-20
MORENA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003015/WC/9993630728 — तालाब निर्माण कार्य | Deleted | 0 | 0 | 2013-01-26
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1701003015/WH/22012034452133 — तालाब जीर्णोद्धार पुराना ताल गडोरा | Closed | 0 | 0 | 2021-10-02
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1701003015/WH/22012034452135 — तालाब जीर्णोद्धार नई रोड के पास गडोरा | Closed | 0 | 0 | 2021-10-02
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1701003015/WH/22012034452182 — तालाब जीर्णोद्धार रामतला गडोरा | Closed | 0 | 0 | 2021-10-02
MORENA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1701003015/WH/22012034920042 — तालाब जीर्णोद्धारकार्य नई टोर के पास | Completed | 147066 | 137088 | 2022-06-12 | 2022-08-24