## Work List
Exported on: 2026-10-12 15:01:08
Filters applied:
Data source: MGNREGA
District: MORENA
Block: All
Panchayat: ARDAUNI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1701003075/AV/22012034566421 — shanti dham teen sed nirman | Completed | 195934.71 | 194985.13 | 2021-06-24 | 2023-07-20
MORENA | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1701003075/AV/22012034566422 — khel medan nirman kaary ardauni | Ongoing | 217629.22 | 189147.79 | 2022-09-10
MORENA | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701003075/DP/164 — वुक्षा रोपण निर्माण अरदौनी रोण | Completed | 0 | 3321 | 2009-10-08 | 2009-04-01
MORENA | 2015-2016 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1701003075/DP/22012034228165 — शांती-धाम निर्माण कार्य उदियापुरा | Completed | 577000 | 391314.01 | 2015-12-15 | 2018-08-28
MORENA | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701003075/DP/22012034242836 — पौधा रोपन कार्य अरदौनी | Deleted | 0 | 0 | 2017-05-24
MORENA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1701003075/DP/22012034432471 — सार्वजनिक वृक्षारोपण कार्य - अरदौनी | Closed | 342000 | 0 | 2018-04-14
MORENA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1701003075/DP/22012034432472 — सार्वजनिक वृक्षारोपण कार्य - सार्वजनिक परिसर अरदौनी | Closed | 342000 | 0 | 2018-04-14
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701003075/DP/22012034599953 — ब्रक्षारोपन कार्य सिद्ध मंदिर डांग पर | Closed | 55847.4 | 0 | 2023-08-05
MORENA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Wasteland Block Plantation-Horticulture-Community / Wasteland Block Plantation of Horticulture Trees for Community | Plantation | 1701003075/DP/22012034619407 — ब्रक्षारोपन कार्य बाग मंदिर अर्दौनि | Ongoing | 453563.17 | 2430 | 2024-08-29
MORENA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701003075/DP/265 — निर्मल वाटिका | Completed | 0 | 12658.3 | 2010-09-07 | 2010-09-12
MORENA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701003075/DP/269 — निर्मल वाटिका मिटटी | Completed | 0 | 17848.2 | 2010-08-31 | 2010-09-05
MORENA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1701003075/DP/396 — व्रक्षारोपण शान्तिधाम | Completed | 0 | 6336 | 2012-09-05 | 2012-10-27
MORENA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Land Development / Levelling/shaping of Wasteland Land for Community | Land Development | 1701003075/DP/992668861 — शान्ति‍धाम अरदोनी | Completed | 424000 | 229727.45 | 2011-11-30 | 2014-06-14
MORENA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1701003075/DP/9926688681 — शाती धाम निर्माण कार्य | Completed | 424000 | 105853 | 2010-12-05 | 2014-06-14
MORENA | 2015-2016 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Drainage in Water Logged Areas / Drainage of Community Waterlogged Land | Works for Flood Control and Protection | 1701003075/FP/22012034203951 — नाला निर्माण कार्य बाग़ मंदिर से पुलिया तक | Deleted | 0 | 0 | 2016-01-26
MORENA | 2019-2020 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701003075/FP/22012034364327 — नाला निर्माण कार्य - बासुदेव गुर्जर के घर से बच्चू के कुआ की ओर | Completed | 1490688.67 | 1170712.95 | 2020-03-01 | 2021-10-20
MORENA | 2020-2021 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701003075/FP/22012034623993 — kaccha nala nirman kaary krapaa ram ke pura kee or se bajrang mandir kee or | Deleted | 0 | 0 | 2021-01-21
MORENA | 2020-2021 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701003075/FP/22012034623994 — kaccha nala nirman kaary krapaa ram ke pura kee or se bajrang mandir kee or | Deleted | 0 | 0 | 2021-01-21
MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701003075/FP/22012034624741 — पक्का नाला निर्माण कार्य कृपाराम के पुराकी ओर से बजरंगकी मंदिर की ओर | Ongoing | 999474.18 | 709937.24 | 2021-07-09
MORENA | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of drain for coastal protection for Comm. / Construction of Storm Water drain for coastal protection for Community | Works for Flood Control and Protection | 1701003075/FP/22012034630515 — nala nirmaan kaary baag mandir se hakim ke pura kee or | Ongoing | 985570.95 | 908675.92 | 2023-01-03
MORENA | 2013-2014 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Drainage in Water Logged Areas / Drainage of Community Waterlogged Land | Works for Flood Control and Protection | 1701003075/FP/9977522428 — नाला निर्माण कार्य कृपाराम कि ओर से उद्दात के घर क | Completed | 455863 | 364770.63 | 2014-02-27 | 2016-09-19
MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701003075/IF/22012034345852 — पौधा रोपण कार्य अरदौनी रामहेत | Completed | 335000 | 19838 | 2017-07-27 | 2019-11-28
MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701003075/IF/22012034368181 — ब्रक्षारोपड कार्य मुकेश/ केशव | Completed | 335000 | 15476 | 2017-06-30 | 2019-12-30
MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701003075/IF/22012034368309 — पोधारोपड कार्य गजेन्द्र /रामखातियर के पूरा के सामने | Completed | 335000 | 151224 | 2017-07-27 | 2021-03-29
MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701003075/IF/22012034368780 — ब्रक्षारोपड कार्य रामनिवास /रामवरन सिंह | Completed | 335000 | 25508 | 2017-06-30 | 2019-12-28
MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Berkeley Compost Pit for Individual / Construction of Berkeley Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1701003075/IF/22012034724416 — नाडेप निर्माण कार्य देशराज /धनीराम | Completed | 18374.27 | 18324.5 | 2021-06-04 | 2022-01-01
MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Berkeley Compost Pit for Individual / Construction of Berkeley Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1701003075/IF/22012034724426 — नाडेप निर्माण कार्य रामहेत / धीर | Completed | 18374.27 | 18324.5 | 2021-06-04 | 2022-01-11
MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Berkeley Compost Pit for Individual / Construction of Berkeley Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1701003075/IF/22012034724440 — नाडेप निर्माण कार्य दलबीर/धनीराम | Completed | 18374.27 | 18324.5 | 2021-06-04 | 2022-01-11
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1701003075/IF/22012034724473 — नाडेप निर्माण कार्य देशराज /धनीराम | Deleted | 0 | 0 | 2021-04-14
MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1701003075/IF/22012034790675 — नाडेप निर्माण कार्य - मुन्नी -रामनरेश | Closed | 18552.12 | 0 | 2021-04-14
MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1701003075/IF/22012034790678 — नाडेप निर्माण कार्य -खेमराज- श्याम सुन्दर | Closed | 18552.12 | 0 | 2021-04-14
MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1701003075/IF/22012034790684 — नाडेप निर्माण कार्य - हरिओम /श्यामसुन्दर | Closed | 18552.12 | 0 | 2021-04-14
MORENA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Boundary Line Plantation of Horticulture Trees for Individuals | Plantation | 1701003075/IF/22012034813797 — निजी खेत में फलोद्यान(ब्रक्षरोपन) कार्य दलवीर /धनीराम | Ongoing | 144199.83 | 25358 | 2021-10-11
MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Compost Pit for Individual / Construction of Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1701003075/IF/22012034853694 — नाडेप निर्माण कार्य gajendra /ramkhatiyar udiyapura | Completed | 18552.12 | 18324.5 | 2021-10-14 | 2022-01-11
MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1701003075/IF/22012034853699 — nadep nirmaan kaary ramveer /jamunaprasad udiyapura | Completed | 18552.12 | 18324.5 | 2021-10-14 | 2022-01-11
MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1701003075/IF/22012034853701 — nadep nirmaan kaary siddar /ramdharudiyapura | Completed | 18552.12 | 18324.5 | 2021-09-25 | 2022-01-11
MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1701003075/IF/22012034857739 — नाडेप निर्माण कार्य -गुमान /लायक़ उदियापुरा | Completed | 18552.12 | 18324.5 | 2021-09-25 | 2022-01-11
MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1701003075/IF/22012034862543 — नाडेप निर्माण कार्य manoj / gajendra उदियापुरा | Completed | 18552.12 | 18324.5 | 2021-10-11 | 2022-01-11
MORENA | 2022-2023 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1701003075/IF/22012034975914 — लीच पिट निर्माण कार्य बासुदेव पंडित के घर पर | Deleted | 0 | 0 | 2022-04-24
MORENA | 2022-2023 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1701003075/IF/22012034975919 — shok pit nirman kary jitendra javar singh | Deleted | 0 | 0 | 2022-04-24
MORENA | 2022-2023 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1701003075/IF/22012034975943 — लीच पिट निर्माण कार्य विनोद गोड. | Deleted | 0 | 0 | 2022-04-24
MORENA | 2024-2025 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1701003075/IF/22012035298240 — नाडेप निर्माण कार्य जशरथ सिन्ह के पुरा पर | Approved | 0 | 0 | 2025-01-24
MORENA | 2024-2025 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1701003075/IF/22012035298428 — nadep nirmaan kaary afisar ke pura par | Approved | 0 | 0 | 2025-01-24
MORENA | 2024-2025 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1701003075/IF/22012035298430 — nadep nirman kaary ramu/beerbhan ke pura par | Approved | 0 | 0 | 2025-01-24
MORENA | 2024-2025 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1701003075/IF/22012035298431 — nadep nirman kaary jogendra salikram ke pura par | Approved | 0 | 0 | 2025-01-24
MORENA | 2024-2025 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1701003075/IF/22012035298435 — nadep nirman kaary trilok vijay singh ke pura par | Approved | 0 | 0 | 2025-01-24
MORENA | 2024-2025 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1701003075/IF/22012035298439 — nadep nirman kaary bhagirath haluk singh ke pura par | Approved | 0 | 0 | 2025-01-24
MORENA | 2024-2025 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1701003075/IF/22012035298440 — nadep nirman kaary mukesh keshv ke pura par | Approved | 0 | 0 | 2025-01-24
MORENA | 2024-2025 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1701003075/IF/22012035298869 — nadep nirman kaary bharat ramcharan ke pura par | Approved | 0 | 0 | 2025-01-24
MORENA | 2024-2025 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1701003075/IF/22012035298871 — nadep nirman kary raghunath mahendra ke ghar ke pas | Approved | 0 | 0 | 2025-01-24
MORENA | 2024-2025 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1701003075/IF/22012035298877 — nadep nirman kary ramswaroop shreekrishan ke pura par | Approved | 0 | 0 | 2025-01-24
MORENA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1701003075/IF/22012035502814 — ket talab nirman kaary raghunath/chandan singh ke khet par | Approved | 0 | 0 | 2025-04-14
MORENA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003075/IF/9926713221 — पशु से निर्माण- मेहरबान/ज़ालिम | Completed | 86000 | 81386 | 2014-03-05 | 2014-05-31
MORENA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003075/IF/9926713242 — पशु सेड-माणिक/रजा राम | Completed | 80000 | 40422 | 2014-03-05 | 2016-05-20
MORENA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003075/IF/9926713258 — पशुसेड़ निर्माण -सुरेन्द्र /मुंशी | Completed | 86000 | 60904.95 | 2014-03-05 | 2016-05-20
MORENA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003075/IF/9926713277 — पशुसेड़ -रणजीत/रजा राम | Completed | 80000 | 45198 | 2014-03-05 | 2016-05-20
MORENA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003075/IF/9926713332 — पशु शेड- ऊदल सिंह/मेघ सिंह | Completed | 86000 | 17634 | 2014-03-05 | 2014-06-22
MORENA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003075/IF/9926713350 — पशुसेड़-पारथ/ज़ालिम | Completed | 86000 | 31944 | 2014-03-05 | 2016-05-20
MORENA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003075/IF/9993691225 — पशु-शेड निर्माण कार्य -रामहेत पुत्र धीर सिंह | Deleted | 122000 | 0 | 2015-12-02
MORENA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003075/IF/9993691945 — पशु शेड निर्माण रामहेत /धीर सिंह | Completed | 97000 | 95050.63 | 2015-12-04 | 2016-05-20
MORENA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003075/IF/9993692902 — पशु शेड- भूरा बाबा s/o हलुक सिंह | Completed | 97000 | 22578 | 2015-12-05 | 2016-05-20
MORENA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003075/IF/9993722331 — पशु सेड निर्माण कार्य केलाश /रामदयाल | Deleted | 0 | 0 | 2016-01-26
MORENA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003075/IF/9993722333 — पशु सेड निर्माण कार्य बासुदेव /धीर सिंह | Deleted | 0 | 0 | 2016-01-26
MORENA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003075/IF/9993722335 — पशु सेड निर्माण कार्य सुरेश /बंशी | Deleted | 0 | 0 | 2016-01-26
MORENA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003075/IF/9993722337 — पशु सेड निर्माण कार्य इंद्र / रामनरेश | Deleted | 0 | 0 | 2016-01-26
MORENA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003075/IF/9993726037 — पशुस्रेड निर्माण कार्य बहादुर /दीबान सिंह | Deleted | 0 | 0 | 2016-01-26
MORENA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003075/IF/9993726038 — पशुस्रेड निर्माण कार्य जय राम /राजेंद्र सिंह | Deleted | 0 | 0 | 2016-01-26
MORENA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003075/IF/IAY/203477 — Construction of IAY House -IAY REG. NO. MP-01-003-075-001/30 | Approved | 23490 | 0 | 2015-08-28
MORENA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003075/IF/IAY/238331 — Construction of IAY House -IAY REG. NO. MP1475925 | Completed | 15030 | 14662 | 2017-01-28 | 2017-10-22
MORENA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003075/IF/IAY/4326070 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126536612 | Completed | 18360 | 18275 | 2022-09-27 | 2023-08-18
MORENA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003075/IF/IAY/541926 — Construction of IAY House -IAY REG. NO. MP3121617 | Completed | 15030 | 14944 | 2017-02-01 | 2018-03-25
MORENA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003075/IF/IAY/614115 — Construction of IAY House -IAY REG. NO. MP1806632 | Completed | 15030 | 14747 | 2017-02-16 | 2018-01-30
MORENA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701003075/LD/22012034950125 — ston peripheral kaaru kartar singh ke khet se ramdular ke khet kii or | Approved | 0 | 0 | 2025-01-24
MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701003075/LD/22012034957665 — peripheral ston bond manin road se shiv mandir ki or | Approved | 954416.92 | 0 | 2025-08-15
MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701003075/LD/22012034957667 — peripheral ston bond shiv mandir se tal kii or | Approved | 0 | 0 | 2025-08-15
MORENA | 2013-2014 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1701003075/LD/3799433728 — med bandhan-maniram/shankar | Deleted | 24675 | 0 | 2013-08-15
MORENA | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701003075/RC/02 — पत्‍थर खंरजा निर्माण कार्य रोड से स्‍कूल | Completed | 495000 | 232255.57 | 2009-02-05 | 2011-09-19
MORENA | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Metal Second coat / Construction of WBM Roads for Community | Construction of Road and Culvert | 1701003075/RC/1050 — सी.सी.खरंजा न‍िर्माण अरदोनी | Completed | 0 | 72587.08 | 2011-12-14 | 2011-12-27
MORENA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003075/RC/1165 — सी सी खरंजा ़ | Completed | 0 | 63901 | 2012-05-01 | 2012-05-14
MORENA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003075/RC/1210 — सी सी रोड मुख्‍य मार्ग से असपताल | Completed | 101042 | 93481.2 | 2012-10-21 | 2013-01-25
MORENA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cross Drainage / Construction of Culvert / cross drainage structues for Community | Culvert | 1701003075/RC/22012034156824 — सी सी खंरजा रोड बैजनाथ के घर से रामेश्‍वर पंडित के घर तक | Completed | 35000 | 3731.91 | 2013-01-27 | 2015-09-17
MORENA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003075/RC/22012034163128 — सी सी खराज एव नाली निर्माण काय | Completed | 64017 | 28364.83 | 2013-02-06 | 2013-06-11
MORENA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003075/RC/22012034172816 — सी सी खरंजा एवं नाली निर्माण कार्य मुन्‍नी के घर स | Completed | 81306 | 81136.63 | 2013-07-02 | 2013-10-21
MORENA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003075/RC/22012034187308 — सी.सी खरंजान निर्माण सरकारी स्क़ुळ् सॆ मेन रोड की प | Completed | 100818 | 60444 | 2014-02-11 | 2016-03-12
MORENA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701003075/RC/22012034207905 — पत्थर खरंजा नहर से नृपत के पूरा तक | Deleted | 118000 | 0 | 2014-01-26
MORENA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701003075/RC/22012034208166 — पत्थर खरंजा निर्माड नवाव सिंह के घर से बूढ़ा के घर | Completed | 354500 | 266824.62 | 2014-02-26 | 2016-09-20
MORENA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701003075/RC/22012034208334 — पत्थर खरंजा निर्माण मेन रोड से राम बरन के पूरा तक | Completed | 107000 | 57473.6 | 2014-02-26 | 2016-09-20
MORENA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701003075/RC/22012034208348 — पत्थर खरंजा निर्माण मेन रोड सेचौदरी के पूरा तक | Completed | 118000 | 79160.55 | 2014-02-26 | 2016-09-20
MORENA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701003075/RC/22012034287399 — पत्थर खरंजा -पुलिया से सुन्दे केघर तक एवं लांगरी मोहल्ला | Completed | 231000 | 126856.1 | 2015-10-29 | 2016-09-20
MORENA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701003075/RC/22012034296884 — पत्‍थर खरंजा निर्माण - मैनरोड से हलुके सिंह का पुरा, दिलीप सिंह का पुरा, रामीवर सिंह का पुरा | Completed | 188000 | 20352 | 2016-01-19 | 2017-09-10
MORENA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701003075/RC/22012034305778 — पत्थर खरंजा निर्माण कार्य मैंन रोड से शांती धाम तक उदियापुरा | Deleted | 0 | 0 | 2016-01-26
MORENA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701003075/RC/22012034307917 — मिट्टी बजरी रोड कार्य मेनरोड से हीरा मन मंदिर तक | Deleted | 0 | 0 | 2016-01-26
MORENA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701003075/RC/22012034308063 — पत्थर खरजा निर्माण कार्यमैन रोड से विजय सिंह का पुरा | Deleted | 0 | 0 | 2016-01-26
MORENA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003075/RC/22012034326044 — सी सी खरंजा एवं नाली निर्माण कार्य - राजाराम पंडित के घर से मुरारी के घर तक अरदौनी | Completed | 86568 | 66600 | 2017-03-16 | 2018-05-07
MORENA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003075/RC/22012034336697 — सी सी खर्ंजा निर्माण कार्य बलवीर के घर से रामजांनकी मन्दिर तक | Completed | 86000 | 73272 | 2017-08-14 | 2018-04-04
MORENA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003075/RC/22012034386665 — सीसी रोड निर्माण कार्य मातादीन के घर से पंडित मोहल्ले तक | Completed | 70650 | 70644 | 2018-04-07 | 2019-01-15
MORENA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003075/RC/22012034434095 — सीसी रोड निर्माण नाली निर्माण कार्य - आदिराम के घर से बापू के घर तक | Completed | 84750 | 72060 | 2019-01-12 | 2019-07-14
MORENA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003075/RC/22012034469362 — सी.सी. खरंजा एवं नाली निर्माण कार्य - मैन रोड से सुरेन्द्र के घर तक, ग्राम उदियापुरा | Completed | 114750 | 113620 | 2020-01-29 | 2020-08-28
MORENA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003075/RC/22012034478194 — सी.सी. खंरजा एवं नाली निर्माण कार्य - ठाकुर जी मंदिर से शांतिधाम तक | Closed | 122175 | 0 | 2019-08-15
MORENA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003075/RC/22012034526327 — सी.सी. खरंजा नाली संहित रोड से सुरेश बाल्मीक के घर तक | Closed | 12960 | 0 | 2019-10-02
MORENA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003075/RC/22012034526329 — सी.सी. खरंजा निर्माण हीरामन मंिदर से जण्डेल के घर होते हुए छावई मोहल्ला की ओर उदियापुरा | Completed | 95625 | 96330 | 2020-08-07 | 2020-09-30
MORENA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003075/RC/22012034534888 — सीं.सी. खरंजा मैनरोड से रामाख्तयार के घर तक | Completed | 12960 | 11400 | 2021-02-01 | 2021-02-11
MORENA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003075/RC/22012034534889 — सी.सी. खरंजा रामजानकी मंदिर खरंजा से जयवीर के घर तक | Closed | 21675 | 0 | 2019-10-02
MORENA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003075/RC/22012034535139 — सीं.सी. खरंजा निर्माण ठाकुर जी मंदिर से शांतिधाम तक अरदौनी | Completed | 114750 | 75620 | 2020-08-27 | 2020-10-15
MORENA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003075/RC/22012034538164 — सी.सी. रोड रघुवीर के घर से पूरन के घर तक | Closed | 57375 | 0 | 2019-10-02
MORENA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003075/RC/22012034538165 — सी.सी. रोड नाली सहित मैन रोड से हलुका सिंह का पुरा दिलीप सिंह का पुरा रामवीर सिंह का पुरा अरदोनी | Closed | 57375 | 0 | 2019-10-02
MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003075/RC/22012034574057 — cc road krapaaram mastar kee or se gar singh ke kuaa kee or | Deleted | 0 | 0 | 2021-04-14
MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003075/RC/22012034593392 — सी .सी.रोड निर्माण कार्य कृपाराम ,घनश्याममास्टर के घर से ठाकुर मंदिर की और गरसिंघ कुआ तक | Completed | 90000 | 89938 | 2021-11-25 | 2022-02-04
MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003075/RC/22012034600423 — cc road nirmaan kary ramsevak sharma ke ghar se hariopm sharma ke ghar tak | Completed | 45000 | 44969 | 2021-11-30 | 2022-03-04
MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003075/RC/22012034600425 — cc road nirmaan kary ganeshram ke goda se baghel mohalla tak | Completed | 45000 | 44969 | 2022-01-19 | 2022-02-22
MORENA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701003075/RC/22012034670982 — सुदूर /खेत सड्क निर्माण -मैंनरोड से सिद्ध बाबा स्थान तक | Ongoing | 2490952.03 | 2290842.01 | 2024-03-13
MORENA | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Metal First coat / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701003075/RC/386 — पत्‍थर खरजां चामड माता मन्द्रिर अरदौनी | Completed | 0 | 41652 | 2009-08-15 | 2009-04-01
MORENA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701003075/RS/22012034402286 — शोचालय निर्माण कार्य सिद्दार | Closed | 12000 | 0 | 2018-03-07
MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1701003075/RS/22012034624333 — सामुदायिक स्वछता परिसर निर्माण कार्य अरदौनी | Completed | 43000 | 42876 | 2021-11-30 | 2022-09-14
MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1701003075/WC/22012034380225 — TALAB GARIKAAN | Deleted | 0 | 0 | 2017-10-02
MORENA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003075/WC/22012034432225 — नवीन तालाब निर्माण कार्य - | Deleted | 0 | 0 | 2019-01-26
MORENA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Grps / Construction of Sand filter for openwell recharge for Groups | Well Recharge | 1701003075/WC/22012034558637 — सार्वजनिक पेयजल कूप निर्माण कार्य रेतवाले हनुमान मंदिर के पास अर्दोनी | Deleted | 0 | 0 | 2020-05-16
MORENA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1701003075/WC/22012034560790 — सार्वजनिक कुंआ निर्माण कार्य बजरंग मंदिर अर्दौनी | Completed | 454166.23 | 313510.3 | 2020-06-29 | 2024-10-03
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1701003075/WC/22012034635185 — shokhta gadda | Completed | 18382.8 | 14261.99 | 2021-04-12 | 2023-07-14
MORENA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1701003075/WC/22012034767661 — shokhta gadda nrapat kaa puraa hedpamp ke pas | Completed | 18443.75 | 15705.22 | 2022-09-10 | 2025-08-30
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1701003075/WC/22012034767664 — shokhta gadda ramsevak ke ghar ke samne hedpamp par | Closed | 18443.75 | 0 | 2021-04-14
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1701003075/WC/22012034767677 — shokhta gadda jagdeesh pandit ke samne hedpamp par | Closed | 0 | 0 | 2021-04-14
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1701003075/WC/22012034767698 — शोखता गद्दा निर्माण कार्य मणि कुआ पर | Closed | 18443.75 | 0 | 2021-04-14
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1701003075/WC/22012034775999 — roof water harwesting panchayat bhavan ardauni | Closed | 0 | 0 | 2021-04-14
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1701003075/WC/22012034776027 — शोखता गड्ड सार्वजानिक हेडपंप पर डोयले के पुरा के पीछे | Completed | 18443.75 | 15525.99 | 2021-11-26 | 2023-07-14
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1701003075/WC/22012034776029 — शोखता गड्डा निर्माण खारे कुआं पर | Closed | 0 | 0 | 2021-04-14
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1701003075/WC/22012034776032 — शोखता गड्डा सार्वजानिक हेडपंप पंचायत भवन के सामनेके | Closed | 0 | 0 | 2021-04-14
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701003075/WC/22012034796725 — shokhta gadda ofisar ke puraa par hedpamp ke pas | Completed | 18443.75 | 15525.99 | 2021-09-25 | 2023-07-14
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1701003075/WC/22012034796728 — shokhta gadda ramjilaal ke pura par ke pas | Completed | 18443.75 | 15573.22 | 2021-09-25 | 2026-03-31
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1701003075/WC/22012034796731 — shokhta gadda visambar doyala ke puraa par hedpamp ke pas | Completed | 18443.75 | 16388.99 | 2021-09-25 | 2023-07-14
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1701003075/WC/22012034796735 — shokhta gadda haluk singh ke puraa par hedpamp ke pas | Completed | 18443.75 | 15525.99 | 2021-11-26 | 2023-07-14
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1701003075/WC/22012034796743 — shokhta gaddamehrvan ke pura par hedpamp ke pas | Completed | 18443.75 | 15525.99 | 2021-11-26 | 2023-07-14
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1701003075/WC/22012034882109 — shokhta gadda udiyapura | Closed | 0 | 0 | 2021-10-02
MORENA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701003075/WC/22012034936233 — नवीन तालाब निर्माण कार्य उदियापुरा | Closed | 0 | 0 | 2022-04-06
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1701003075/WC/22012035009074 — shokhta gadaa Panchayat bhavan ke paas | Completed | 21112.66 | 18130.22 | 2023-07-24 | 2025-08-30
MORENA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701003075/WC/22012035022605 — earthan dam khori khora khar ke pass | Deleted | 1482448.08 | 0 | 2022-08-16
MORENA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701003075/WC/22012035022608 — earthan dam remja bali pohi | Deleted | 1474406.82 | 0 | 2022-08-16
MORENA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701003075/WC/22012035022610 — earthan dam jhirna ke pass | Deleted | 1483638.38 | 0 | 2022-08-16
MORENA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701003075/WC/22012035022616 — earthan dam shidh baba ke mandir ke pass | Deleted | 1464233.57 | 0 | 2022-08-16
MORENA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701003075/WC/22012035022620 — earthan dam chola bale khar ke pass | Deleted | 1494407.09 | 0 | 2022-08-16
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003075/WC/22012035022847 — CTR/NWS अर्थन डेम खोटी -खोरा पर | Ongoing | 1442310.51 | 592837 | 2023-10-09
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003075/WC/22012035022849 — CTR/NWS अर्थन डेम रेमजा बाली पोही | Completed | 1467655.6 | 1403776 | 2023-07-04 | 2024-06-27
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003075/WC/22012035022852 — CTR/NWS अर्थन डेम घिरना के पास | Completed | 1458084.85 | 1357065 | 2023-05-03 | 2024-05-13
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003075/WC/22012035022854 — CTR/NWS अर्थन डेम सिद्ध बाबा मंदिर के पास | Completed | 1436475.61 | 1372819 | 2023-07-21 | 2024-05-08
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003075/WC/22012035022857 — CTR/NWS अर्थन डेम छोले वाला खार | Ongoing | 1428404.97 | 787687 | 2023-10-09
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003075/WC/22012035063142 — earthan dem siddh babake mandir ke upar | Deleted | 0 | 0 | 2023-04-14
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003075/WC/22012035069425 — नवीन तालाब निर्माण कार्य सिद्ध बाबा के मंदिर के ऊपर | Ongoing | 1477526.46 | 1352306.74 | 2023-05-26
MORENA | 2023-2024 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1701003075/WC/22012035098147 — रपटा निर्माण कार्य बल्लू के खेत के पास | Ongoing | 1452638.5 | 1359459.78 | 2023-08-30
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003075/WC/22012035098152 — एनीकट निर्माण कार्य सिद्ध पोही मे | Closed | 0 | 0 | 2023-06-05
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1701003075/WC/22012035173649 — Nws bolder anicut nirman kary jhrna kea paas ardauni | Closed | 0 | 0 | 2024-01-24
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003075/WC/22012035173650 — Nws bolder anicut nirman kary dang par ardauni | Closed | 0 | 0 | 2024-01-24
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003075/WC/22012035173728 — Nws anicut nirman kary dang par ardauni | Closed | 0 | 0 | 2024-02-18
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003075/WC/22012035173729 — Nws anicut nirman kary jhrna kea paas ardauni | Closed | 0 | 0 | 2024-02-18
MORENA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003075/WC/22012035210465 — chack dam nirman kaary jharnaa je neeche | Approved | 0 | 0 | 2024-06-08
MORENA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003075/WC/22012035210473 — chack dam nirman kaary udiyapura | Approved | 0 | 0 | 2024-06-08
MORENA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003075/WC/22012035210495 — chack dam nirman kaary ardauni | Approved | 0 | 0 | 2024-06-08
MORENA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003075/WC/22012035210505 — chack dam nirman kaary bade khar me | Approved | 0 | 0 | 2024-06-08
MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1701003075/WC/22012035301293 — Gugwell recharge nirmankaary openwell school ke paas | Ongoing | 25899.46 | 15138 | 2025-05-12
MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1701003075/WC/22012035302037 — Dugwell nirman kaary baag mandir ke pas | Approved | 25899.46 | 0 | 2025-04-14
MORENA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003075/WC/24 — उदियापुरा तालाब का रख रखाव कार्य | Completed | 11000 | 0 | 2008-09-12 | 2008-03-01
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1701003075/WH/22012034451982 — बड़ा तालाब मरम्मत कार्य उदियापुरा | Closed | 0 | 0 | 2021-10-30
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1701003075/WH/22012034453869 — तालाब मरम्मत कार्य अरदौनी | Closed | 0 | 0 | 2021-10-30
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1701003075/WH/22012034453879 — छोटा तालाब मरम्मत कार्य अरदौनी | Closed | 0 | 0 | 2021-10-16
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1701003075/WH/22012034453881 — छोटा तालाब मरम्मत कार्य उदियापुरा | Closed | 0 | 0 | 2021-10-16
MORENA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Excavation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1701003/WH/175 — एती तालाव का रखरखा कार्य | Completed | 0 | 1190 | 2008-10-03 | 2015-09-17