## Work List
Exported on: 2026-10-12 11:41:21
Filters applied:
Data source: MGNREGA
District: MORENA
Block: All
Panchayat: PADHAWALI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
MORENA | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play field for Community | Construction of Play field | 1701003080/AV/22012034510026 — खेल मैदान कार्य मुकेश राजोरिया के यहां पड़ोखरा शासकीय भूमि | Completed | 215276.77 | 191376.28 | 2020-07-06 | 2023-07-03
MORENA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Anganwadi/Other Rural Infrastructure | Construction of Cattle Shelter for Community / Construction of Cattle Shelter for Community | Cattle Shed | 1701003080/AV/22012034512850 — गोशाला निर्माण कार्य पडावली | Closed | 3784582.21 | 0 | 2020-04-01
MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Food grain storage / Construction of Food grain Storage Building for Community | Constr of Food Grain storage | 1701003080/AV/22012034563375 — प्राथमिक कृषि साख सहकारी संस्था मर्यादित चबूतरा निर्माण कार्य पड़ावली | Completed | 461422.25 | 391717.99 | 2021-04-03 | 2021-10-19
MORENA | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701003080/DP/208 — वक्षा रोपढ कार्य प्राथमिक शाला रोड पुलिया तक | Completed | 0 | 3458 | 2009-09-14 | 2008-04-01
MORENA | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701003080/DP/209 — वक्षा रोपड कार्य मिडिल स्‍कूल से पा्यमरी तक पढावली | Completed | 0 | 637 | 2009-09-21 | 2008-04-01
MORENA | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701003080/DP/22012034328727 — वृक्षारोपण कार्य | Closed | 0 | 0 | 2017-10-02
MORENA | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Land development / Levelling/shaping of Wasteland Land for Community | Land Development | 1701003080/DP/22012034329253 — SHANTI DHAM NIRMAN KARY PUR GRAM PANCHAYAT PADAWALI | Closed | 24500000000 | 0 | 2017-10-02
MORENA | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Land development / Levelling/shaping of Wasteland Land for Community | Land Development | 1701003080/DP/22012034329254 — SHANTI DHAM NIRMAN KARY HANSHRAJ KA PURA GRAM PANCHAYAT PADAWALI | Closed | 24500000000 | 0 | 2017-10-02
MORENA | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Land development / Levelling/shaping of Wasteland Land for Community | Land Development | 1701003080/DP/22012034329255 — SHANTI DAM NIRMAN KARY HUBBALAL KA PURA | Closed | 245000 | 0 | 2017-10-02
MORENA | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Land development / Levelling/shaping of Wasteland Land for Community | Land Development | 1701003080/DP/22012034329256 — SHANTI DHAM HARIJAN BASTI GRAM PANCHAYAT PADAWALI | Closed | 245000 | 0 | 2017-10-02
MORENA | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Land development / Levelling/shaping of Wasteland Land for Community | Land Development | 1701003080/DP/22012034329257 — SHANTI DHAM NIRMAN KARY GOLE MOHALLA GRAM PANCHAYT PADAWALI | Closed | 245000 | 0 | 2017-10-02
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1701003080/DP/22012034543346 — ma ki bagiya ms padhawali | Completed | 20481.24 | 8436 | 2022-02-20 | 2023-01-25
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1701003080/DP/22012034543347 — ma ki bagiya ms padhawali | Closed | 0 | 0 | 2021-12-02
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1701003080/DP/22012034543351 — ma ki bagiya ps hubbalal ka pura | Completed | 17471.6 | 7212 | 2022-02-20 | 2023-01-25
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1701003080/DP/22012034543356 — ma ki bagiya ps hansraj ka pura | Completed | 19445.35 | 7278 | 2022-02-20 | 2023-01-25
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1701003080/DP/22012034543357 — ma ki bagiya ps hansraj ka pura | Closed | 0 | 0 | 2021-12-02
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Coastal Block Plantation - Farm Forestry-Community / Along the coast Block Plantation of Farm Forestry Trees for Community | Plantation | 1701003080/DP/22012034546858 — maa ki bagiya nirman kary govt.midd.school padhawali | Closed | 0 | 0 | 2021-10-02
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Coastal Line Plantation-Horticulture-Community / Along the coast Line Plantation of Horticulture Trees for Community | Plantation | 1701003080/DP/22012034546859 — maa ki bagiya nirman kary govt.pra.school hubblal ka pura | Closed | 0 | 0 | 2021-10-02
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003080/DP/22012034546861 — maa ki bagiya nirman kary govt.pra.school hansraj ka pura | Closed | 0 | 0 | 2021-10-02
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation of Forestry-Community / Boundary Line Plantation of Forestry Trees for Community | Plantation | 1701003080/DP/22012034603742 — brachha ropan kary niramary mandi parishar me padhawali | Closed | 0 | 0 | 2023-04-14
MORENA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Land Development / Levelling/shaping of Wasteland Land for Community | Land Development | 1701003080/DP/309 — निर्मल वाटिका निर्माण कार्य पठावली | Completed | 0 | 64820 | 2010-08-21 | 2014-09-13
MORENA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1701003080/DP/351 — खेल मैदान पढावली | Completed | 224000 | 180837.5 | 2011-11-15 | 2014-02-15
MORENA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Land Development / Levelling/shaping of Wasteland Land for Community | Land Development | 1701003080/DP/352 — शान्‍ती धाम पढावली | Completed | 557000 | 141575.64 | 2011-10-18 | 2016-04-15
MORENA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1701003080/DP/390 — व्रक्षारोपढ समसान घाट | Deleted | 0 | 0 | 2012-04-14
MORENA | 2018-2019 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701003080/FP/22012034362464 — पत्थर नाला निर्माण कार्य - नहर से तालाब की ओर अजीतपुरा | Closed | 1481000 | 0 | 2019-02-10
MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Construction of Embankment for community / Construction of Embankment for community | Construction of Embankment | 1701003080/FP/22012034624269 — patthar nala nirman kary panchayat bhavan se men road ki or | Closed | 0 | 0 | 2021-04-02
MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Construction of Embankment for community / Construction of Embankment for community | Construction of Embankment | 1701003080/FP/22012034624270 — patthar nala nirman kary jhoda baba mandir se road ki or | Closed | 0 | 0 | 2021-04-02
MORENA | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Construction of Embankment for community / Construction of Embankment for community | Construction of Embankment | 1701003080/FP/22012034629137 — Patthar nala nirman kary school se pura tak | Closed | 992737.37 | 0 | 2022-04-14
MORENA | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Renovation of Flood/ Diversion Channel for Comm / Renovation of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701003080/FP/22012034629138 — Patthar nala nirman kary pura se road tak | Completed | 987958.31 | 936536.28 | 2023-10-07 | 2024-10-14
MORENA | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Construction of Embankment for community / Construction of Embankment for community | Construction of Embankment | 1701003080/FP/22012034629139 — Patthar nala nirman kary pura se khadan ki or | Completed | 996928.36 | 943309.32 | 2022-11-29 | 2024-10-26
MORENA | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701003080/FP/22012034639364 — SUDUR SAMPARK ROAD PADHAVALI ROAD HIRALAL KE KHET TAK | New | 0 | 0 | 2024-01-24
MORENA | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701003080/FP/22012034639366 — SUDUR SAMPARK ROAD JAVARI KE KHET SE JAGMOHAN KE KHET TAK | New | 0 | 0 | 2024-01-24
MORENA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Fisheries | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1701003080/FR/22012034324773 — Talab Nirman Karya Bade khair ke pass | Ongoing | 1485950.51 | 876940.07 | 2025-05-23
MORENA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Fisheries | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1701003080/FR/22012034324775 — Talab Nirman Karya Bhopa Bale me | Ongoing | 1483704.01 | 1074799.14 | 2025-05-23
MORENA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Fisheries | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1701003080/FR/22012034324776 — Talab Nirman Karya Baba Bale me | Ongoing | 1483680.6 | 1087172.23 | 2025-05-23
MORENA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Fisheries | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1701003080/FR/22012034324777 — Talab Nirman Karya Hardoi me | Ongoing | 1474862.21 | 962266.77 | 2025-05-23
MORENA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Fisheries | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1701003080/FR/22012034324778 — Talab Niman Karya Bade teele bale me | Ongoing | 1493370.25 | 900443.47 | 2025-05-23
MORENA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Fisheries | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1701003080/FR/22012034324780 — Talab Niman Karya Chote Khar me | Ongoing | 1478992.65 | 1270575.17 | 2025-05-23
MORENA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Fisheries | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1701003080/FR/22012034324781 — Talab Nirman Karya Bohare Bale me | Ongoing | 1489681.95 | 1425917.13 | 2025-05-23
MORENA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Fisheries | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1701003080/FR/22012034324782 — Talab Nirman Karya Muneem Bale me | Ongoing | 1477275.67 | 794389.38 | 2025-05-23
MORENA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Fisheries | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1701003080/FR/22012034324783 — Talab Nirman Karya purane Khar me | Ongoing | 1473814.53 | 1100486.61 | 2025-05-23
MORENA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Fisheries | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1701003080/FR/22012034324784 — Talab Nirman Karya Dandhi bale me | Ongoing | 1471717.11 | 875968.41 | 2025-05-23
MORENA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Fisheries | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1701003080/FR/22012034325162 — Talab nirman karya gadi ke pass | New | 0 | 0 | 2025-04-02
MORENA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003080/IF/1000060983 — पशु शैड निर्माड - हरिशंकर शर्मा / रामदयाल | Deleted | 0 | 0 | 2013-12-15
MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701003080/IF/22012034345188 — सार्वजनिक परिसर मे व्रक्षारोपण कार्य ग्राम हंसराज पुरा | Completed | 335000 | 33174 | 2017-07-11 | 2020-12-18
MORENA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701003080/IF/22012034661957 — निजी खेत मैं फलोद्यान जगदीश /मथुराप्रसाद ग्राम पड़ावली | Ongoing | 142446.41 | 11580 | 2021-06-21
MORENA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701003080/IF/22012034661958 — निजी खेत मैं फलोद्यान मुन्नालाल /रामनारायण ग्राम पड़ावली | Ongoing | 142446.41 | 105024.56 | 2021-06-14
MORENA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701003080/IF/22012034661959 — निजी खेत मैं फलोद्यान रामप्रकाश/रामरतन ग्राम पड़ावली | Completed | 142446.41 | 51270 | 2021-06-14 | 2025-03-13
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Boulder Check Dam for Individuals / Construction of Boulder Check Dam for Individuals | Construction of Check Dam/Stop Dam | 1701003080/IF/22012034730336 — nadep taka nirman kary rameshwar/bulakhiram | Completed | 18374.27 | 1930 | 2021-06-10 | 2023-07-08
MORENA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Coastal Shelter Belt-line plntation - Individual / Line Plantation of Coastal Shelter Belt Trees for Individuals | Plantation | 1701003080/IF/22012034730349 — nadep taka nirman kary suresh/ murtiram | Closed | 18374.27 | 0 | 2021-04-14
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen Check Dam for Individuals / Construction of Earthen Anicut Check Dam for Individuals | Construction of Check Dam/Stop Dam | 1701003080/IF/22012034730357 — nadep taka nirman kary suresh/ murtiram | Closed | 18374.27 | 0 | 2021-04-14
MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Berkeley Compost Pit for Individual / Construction of Berkeley Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1701003080/IF/22012034730371 — nadep taka nirman kary manoj / laikram | Closed | 18374.27 | 0 | 2021-04-14
MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Berkeley Compost Pit for Individual / Construction of Berkeley Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1701003080/IF/22012034730380 — nadep taka nirman kary mangu/ ramcharan | Closed | 18374.27 | 0 | 2021-04-14
MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Berkeley Compost Pit for Individual / Construction of Berkeley Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1701003080/IF/22012034730385 — nadep taka nirman kary mukesh rajoriya | Closed | 18374.27 | 0 | 2021-04-14
MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Berkeley Compost Pit for Individual / Construction of Berkeley Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1701003080/IF/22012034730391 — nadep taka nirman kary ramprakash kushwah | Closed | 18374.27 | 0 | 2021-04-14
MORENA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1701003080/IF/22012035433163 — khet talab nirmaan karya Rajendra Prasad Sharma Ke khet me | Deleted | 0 | 0 | 2025-04-14
MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1701003080/IF/22012035499524 — Dugwell Richarge Pit Nirmaan Karya Panjab ke kua ke pass | Approved | 25899.46 | 0 | 2025-04-14
MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1701003080/IF/22012035499531 — Dugwell Richarge Pit Nirmaan Karya Kartar ke kua ke pass | Approved | 25899.46 | 0 | 2025-04-14
MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1701003080/IF/22012035499535 — Dugwell Richarge Pit Nirmaan Karya Ranveer ke kua ke pass | Approved | 25899.46 | 0 | 2025-04-14
MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1701003080/IF/22012035499541 — Dugwell Richarge Pit Nirmaan Karya Radheshyam ke kua ke pass | Approved | 25899.46 | 0 | 2025-04-14
MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1701003080/IF/22012035499552 — Dugwell Richarge Pit Nirmaan Karya Shiv charan ke kua ke pass | Approved | 25899.46 | 0 | 2025-04-14
MORENA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003080/IF/IAY/119187 — Construction of IAY House -IAY REG. NO. MP-01-003-080-001/20 | Approved | 23490 | 0 | 2016-01-14
MORENA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003080/IF/IAY/119189 — Construction of IAY House -IAY REG. NO. MP-01-003-080-001/95 | Approved | 23490 | 0 | 2016-01-14
MORENA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003080/IF/IAY/204261 — Construction of IAY House -IAY REG. NO. MP-01-003-080-001/174S | Approved | 23490 | 0 | 2015-08-19
MORENA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003080/IF/IAY/205478 — Construction of IAY House -IAY REG. NO. MP-01-003-080-001/61 | Approved | 23490 | 0 | 2015-08-19
MORENA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003080/IF/IAY/4206027 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150144086 | Completed | 18360 | 18360 | 2022-08-01 | 2023-07-08
MORENA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003080/IF/IAY/42769 — Construction of IAY House -IAY REG. NO. MP-01-003-080-001/105 | Approved | 23490 | 0 | 2015-09-07
MORENA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003080/IF/IAY/42770 — Construction of IAY House -IAY REG. NO. MP-01-003-080-001/117 | Approved | 23490 | 0 | 2015-09-07
MORENA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003080/IF/IAY/42772 — Construction of IAY House -IAY REG. NO. MP-01-003-080-001/118 | Approved | 23490 | 0 | 2015-09-07
MORENA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003080/IF/IAY/42773 — Construction of IAY House -IAY REG. NO. MP-01-003-080-001/129 | Completed | 14310 | 13026 | 2016-11-25 | 2017-11-20
MORENA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003080/IF/IAY/42774 — Construction of IAY House -IAY REG. NO. MP-01-003-080-001/150 | Approved | 23490 | 0 | 2015-09-07
MORENA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003080/IF/IAY/42775 — Construction of IAY House -IAY REG. NO. MP-01-003-080-001/174 | Approved | 23490 | 0 | 2015-09-07
MORENA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003080/IF/IAY/42776 — Construction of IAY House -IAY REG. NO. MP-01-003-080-001/176 | Approved | 23490 | 0 | 2015-09-07
MORENA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003080/IF/IAY/42778 — Construction of IAY House -IAY REG. NO. MP-01-003-080-001/124 | Approved | 23490 | 0 | 2015-09-07
MORENA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003080/IF/IAY/42779 — Construction of IAY House -IAY REG. NO. MP-01-003-080-001/33 | Approved | 23490 | 0 | 2015-09-07
MORENA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003080/IF/IAY/42780 — Construction of IAY House -IAY REG. NO. MP-01-003-080-001/55 | Approved | 23490 | 0 | 2015-09-07
MORENA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003080/IF/IAY/42781 — Construction of IAY House -IAY REG. NO. MP-01-003-080-001/171 | Approved | 23490 | 0 | 2015-09-07
MORENA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003080/IF/IAY/42782 — Construction of IAY House -IAY REG. NO. MP-01-003-080-001/64 | Approved | 23490 | 0 | 2015-09-07
MORENA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003080/IF/IAY/42784 — Construction of IAY House -IAY REG. NO. MP-01-003-080-001/87 | Approved | 23490 | 0 | 2015-09-07
MORENA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003080/IF/IAY/42785 — Construction of IAY House -IAY REG. NO. MP-01-003-080-001/189 | Approved | 23490 | 0 | 2015-09-07
MORENA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003080/IF/IAY/48812 — Construction of IAY House -IAY REG. NO. MP-01-003-080-001/120 | Approved | 23490 | 0 | 2015-09-07
MORENA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003080/IF/IAY/48832 — Construction of IAY House -IAY REG. NO. MP-01-003-080-001/125 | Approved | 23490 | 0 | 2015-11-09
MORENA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003080/IF/IAY/48833 — Construction of IAY House -IAY REG. NO. MP-01-003-080-001/59 | Approved | 23490 | 0 | 2015-11-09
MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003080/IF/IAY/568236 — Construction of IAY House -IAY REG. NO. MP3983926 | Completed | 15030 | 8352 | 2017-04-27 | 2018-10-29
MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003080/IF/IAY/568432 — Construction of IAY House -IAY REG. NO. MP3995250 | Completed | 15030 | 11484 | 2017-04-27 | 2018-08-25
MORENA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003080/IF/IAY/67188 — Construction of IAY House -IAY REG. NO. MP-01-003-080-001/17 | Approved | 23490 | 0 | 2015-09-07
MORENA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003080/IF/IAY/67189 — Construction of IAY House -IAY REG. NO. MP-01-003-080-001/29 | Approved | 23490 | 0 | 2015-09-07
MORENA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Construction of Stone graded Bund for Community / Construction of Stone graded Bund for Community | Construction of Bund | 1701003080/LD/22012034544441 — चबूतरा निर्माण कार्य सहकारी संस्था हुब्ब्लाल का पुरा पढवली | Closed | 0 | 0 | 2020-11-23
MORENA | 2017-2018 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1701003080/PG/22012034366231 — KHEL MAIDINA NIRMAN KARY HANSRAJ KA PURA PADWALI | Closed | 35300000000 | 0 | 2017-10-02
MORENA | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701003080/RC/01 — सी सी खंरजा निर्माण काय पिडावली | Completed | 54500 | 22106 | 2009-05-31 | 2008-01-26
MORENA | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701003080/RC/02 — पत्‍थर खंरजा निर्माण्‍रा कार्य पठावली | Completed | 495000 | 8645 | 2009-02-27 | 2011-08-10
MORENA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003080/RC/22012034157957 — पंच परमेष्‍वर सी सी खरंजा | Completed | 83396 | 82335 | 2012-11-14 | 2013-01-01
MORENA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003080/RC/22012034191361 — सी सी खरंजा एवं नाली निर्माण कार्य गढी के सामने से | Completed | 106770 | 69128 | 2014-02-01 | 2014-03-30
MORENA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003080/RC/22012034203323 — सी. सी. खरंजा एंव नाली निर्माण - राजेश शर्मा के मक | Deleted | 120233 | 0 | 2014-01-01
MORENA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701003080/RC/22012034309099 — mitti muram nirman | Deleted | 0 | 0 | 2016-01-26
MORENA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701003080/RC/22012034309103 — mitti muram nirman | Deleted | 0 | 0 | 2016-01-26
MORENA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701003080/RC/22012034328311 — सुदूर ग्राम संपर्क सड्क निर्माण कार्य - मैनरोड गढी के यहां से तालाब के किनारे होते हुए हंसराज के पुर | Completed | 1488000 | 926908.75 | 2017-02-27 | 2018-10-26
MORENA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003080/RC/22012034343984 — सीमेंट कंक्रीट खर्ंजा नाली निर्माण कार्य व्दारिका महाते के घर् से मंगू के घर तक रामदास के घर से अमरस | Completed | 150000 | 100104 | 2017-07-11 | 2018-04-04
MORENA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003080/RC/22012034364164 — सी सी खरंजा एवं नाली निर्माण कार्य कैलाश के मकान से शातीधाम तक ब मैन रोड तक | Completed | 152000 | 118680 | 2017-10-28 | 2018-04-04
MORENA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701003080/RC/22012034367157 — सुदूर संपर्क रोड पडावली के ताल किनारे तक | Completed | 1488000 | 694054.75 | 2017-11-21 | 2018-10-30
MORENA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003080/RC/22012034380239 — C C KHARANJA NIRMAN KARY DWARIKA BABA KE MAKAN SE GABBAR SINGH KE MAKAN SE HOTE HUYE MAIN ROAD TAK | Physically Completed | 127050 | 87696 | 2019-01-03 | 2019-10-18
MORENA | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003080/RC/22012034621458 — सीसी खरंजा एवं नाली निर्माण कार्य - दीनदयाल उपाध्याय के घर से मैन रोड की ओर मजरा हुब्बालाल का पुरा | Closed | 42750 | 0 | 2022-10-02
MORENA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1701003080/RS/22012034508828 — सामुदायक स्वछ्ता परिषर पड़ावली | Completed | 43000 | 40242 | 2021-02-19 | 2021-11-17
MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of NADEP Compost structure for Groups / Construction of NADEP Compost structure for Groups | Construction of NADEP/Vermi Compost Pit | 1701003080/RS/22012034513568 — नाडेप निर्माण रामेश्वर सिह के घरके पास | Closed | 0 | 0 | 2021-04-01
MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of NADEP Compost structure for Groups / Construction of NADEP Compost structure for Groups | Construction of NADEP/Vermi Compost Pit | 1701003080/RS/22012034513569 — नाडिवटाकामनोज के घर के पास | Closed | 0 | 0 | 2021-04-01
MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1701003080/RS/22012034516169 — Sokhta gadda nirman kary churariya handpamp ke pass | Closed | 0 | 0 | 2021-04-14
MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1701003080/RS/22012034516171 — Sokhta gadda nirman kary panchayat bhavan handpamp ke pass | Closed | 0 | 0 | 2021-04-14
MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of NADEP Compost structure for Groups / Construction of NADEP Compost structure for Groups | Construction of NADEP/Vermi Compost Pit | 1701003080/RS/22012034516172 — Sokhta gadda nirman kary hospital ke handpamp ke pass | Closed | 0 | 0 | 2021-04-14
MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1701003080/RS/22012034516173 — Sokhta gadda nirman kary khel medan handpamp ke pass | Closed | 0 | 0 | 2021-04-14
MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1701003080/RS/22012034516174 — Sokhta gadda nirman karypani ki tanki ke pass | Closed | 0 | 0 | 2021-04-14
MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1701003080/RS/22012034516175 — Sokhta gadda nirman kary high school handpamp ke pass | Closed | 0 | 0 | 2021-04-14
MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1701003080/RS/22012034516176 — Sokhta gadda nirman kary high school handpamp ke pass | Closed | 0 | 0 | 2021-04-14
MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Stabilization Pond for Community / Construction of Stabilization Pond for Community | Construction of Tank | 1701003080/RS/22012034528685 — Kachara bhandar sangrahan kendra padhawali | Closed | 0 | 0 | 2021-04-14
MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Community / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1701003080/RS/22012034600079 — सेग्रीगेशन शेड निर्माण कार्य ग्राम पंचायत पड़ावली | Closed | 597931.81 | 0 | 2021-12-02
MORENA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1701003080/WC/203 — सोख्‍ता गनिर्माण कार्य | Completed | 495000 | 11160 | 2008-08-15 | 2009-05-29
MORENA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003080/WC/22012034432303 — नवीन तालाब निर्माण कार्य - | Closed | 0 | 0 | 2019-01-26
MORENA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1701003080/WC/22012034616376 — सोकता गडडा आंगनवाडी के पास (एस.एल.डब्ल्यू.एम.) | Completed | 18200.38 | 8842 | 2021-02-20 | 2023-07-08
MORENA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1701003080/WC/22012034616379 — सोकता गडडा स्वास्थ्य केन्द्र के पास (एस.एल.डब्ल्यू.एम.) | Closed | 18382.8 | 0 | 2021-01-21
MORENA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1701003080/WC/22012034616380 — सोकता गडडा मैनरोड पडावली (एस.एल.डब्ल्यू.एम.) | Closed | 18382.8 | 0 | 2021-01-21
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1701003080/WC/22012034635840 — सोख्ता गड्डा निर्माण जोधा बाबा मन्दिर हंसराज का पुरा SLWM | Closed | 18382.8 | 0 | 2021-04-01
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1701003080/WC/22012034635889 — सोख्ता गद्दा खेलमैदान के पास | Completed | 18382.8 | 9650 | 2021-04-26 | 2023-07-08
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1701003080/WC/22012034635929 — सोखता गद्दा मिडिलस्कूल केपास | Closed | 18382.8 | 0 | 2021-04-01
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Coastal Block Plantation - Farm Forestry-Community / Along the coast Block Plantation of Farm Forestry Trees for Community | Plantation | 1701003080/WC/22012034641646 — rapta nirman kary hansraj ke pura ke raste par | Closed | 0 | 0 | 2021-04-02
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Coastal Afforestation using forstry Trees for Comm / Along the coast Afforestation using forestry Trees for Community | Plantation | 1701003080/WC/22012034641649 — chek dem nirman kary hansraj ke pura ke pass | Closed | 0 | 0 | 2021-04-02
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Coastal Block Plantation - Farm Forestry-Community / Along the coast Block Plantation of Farm Forestry Trees for Community | Plantation | 1701003080/WC/22012034641652 — chek dem nirman kary pur padawali | Completed | 1497705.41 | 1472510 | 2021-04-26 | 2021-12-23
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Coastal Afforestation using forstry Trees for Comm / Along the coast Afforestation using forestry Trees for Community | Plantation | 1701003080/WC/22012034641656 — navin talab nirman kary gole ka pura | Deleted | 1496640.14 | 0 | 2021-04-26
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Coastal Afforestation using forstry Trees for Comm / Along the coast Afforestation using forestry Trees for Community | Plantation | 1701003080/WC/22012034641661 — kantur trench nirman kary hansraj ke pura ke dade par | Closed | 0 | 0 | 2021-04-02
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Brushwood Check Dam for Community / Construction of Brushwood Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003080/WC/22012034650184 — Chek dem nirman kary pahad ke nale par | Completed | 1497705.41 | 1465674 | 2021-04-26 | 2021-12-23
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Coastal Block Plantation-Horticulture-Community / Along the coast Block Plantation of Horticulture Trees for Community | Plantation | 1701003080/WC/22012034650188 — Chek dem nirman kary padawali ke pass nale par | Completed | 1495740.92 | 1442738 | 2021-04-26 | 2022-07-23
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1701003080/WC/22012034650192 — Chek dem nirman kary khadan ke said nale par | Completed | 1499698.91 | 1465786 | 2021-04-26 | 2021-10-04
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1701003080/WC/22012034650199 — Navin talab nirman kary jhoda baba mandir ke pass | Completed | 1496793.39 | 1142324 | 2021-04-26 | 2021-10-25
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Trench for Community | Construction of Trench | 1701003080/WC/22012034722427 — NWS check dem nirman Kary bamur wale nale par | Completed | 1496897.78 | 1474334 | 2021-06-18 | 2022-07-23
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Trench for Community | Construction of Trench | 1701003080/WC/22012034722433 — NWS check dem nirman Kary bamur wale nale par | Closed | 0 | 0 | 2021-04-14
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Renovation of Fisheries Ponds for Community / Renovation of Fisheries Ponds for Community | Repair & maint of Pond/ Tank | 1701003080/WC/22012034722440 — NWS check dem nirman Kary hansraj ka pura wale nale par | Closed | 0 | 0 | 2021-04-14
MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Construction of Stone Spur for Community / Construction of Stone Spur for Community | Construction of Spur | 1701003080/WC/22012034722449 — NWS check dem nirman Kary gurjar ke khet ke pass wale nale par | Closed | 0 | 0 | 2021-04-14
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Raising of Nursery for Groups / Raising of Nursery for Groups | Nursery Development | 1701003080/WC/22012034722473 — NWS check dem nirman Kary babu singh ke khet ke pass nale par | Closed | 1498330.93 | 0 | 2021-04-14
MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Construction of Earthen Spur for Community / Construction of Earthen Spur for Community | Construction of Spur | 1701003080/WC/22012034722489 — NWS check dem nirman Kary road ke pass nale par | Closed | 0 | 0 | 2021-04-14
MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Construction of Earthen Spur for Community / Construction of Earthen Spur for Community | Construction of Spur | 1701003080/WC/22012034722493 — NWS check dem nirman Kary sheetla mata wale nare par | Completed | 1499022.42 | 1349930 | 2021-06-18 | 2022-09-12
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701003080/WC/22012034754527 — NWS navin talab nirman kary neem walijhiri ke pass | Closed | 1496543.83 | 0 | 2021-04-14
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen Gully Plugs for Community / Construction of Earthen Gully Plugs for Community | Boulder Check/Gully Plug | 1701003080/WC/22012034754537 — NWS navin talab nirman kary kala khet ke pass | Completed | 1497286.19 | 1441366 | 2021-06-18 | 2024-03-12
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Grps / Construction of Sand filter for openwell recharge for Groups | Well Recharge | 1701003080/WC/22012034754547 — NWS gali plug nirman kary hansraj ka pura | Completed | 1499327.13 | 467832 | 2021-06-18 | 2022-11-19
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003080/WC/22012034757409 — ctr check dam nirman kua kw nale pr | Completed | 997863.86 | 971736 | 2021-06-18 | 2022-02-01
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003080/WC/22012034757471 — ctr check dam nirman road ke pass nale par purgaon | Completed | 998000.2 | 987836 | 2021-06-18 | 2022-03-27
MORENA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1701003080/WC/22012034760302 — CTR sok pit nirman karya churariya handpamp ke pass | Closed | 0 | 0 | 2021-04-14
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701003080/WC/22012035002920 — ctr earthan dam kary panch singh ke khet ke pass | Completed | 1467662.97 | 1405148 | 2023-05-20 | 2024-03-12
MORENA | 2023-2024 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Construction of Stone Spur for Community / Construction of Stone Spur for Community | Construction of Spur | 1701003080/WC/22012035002924 — ctr earthan dam kary sheetla mandir ke pass | Completed | 1485275.04 | 1410458 | 2023-04-29 | 2024-03-12
MORENA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701003080/WC/22012035002927 — ctr earthan dam kary khoh ke muhare ke pass | Closed | 0 | 0 | 2022-08-16
MORENA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701003080/WC/22012035002934 — ctr earthan dam kary kdela wali khadan ke pass | Closed | 0 | 0 | 2022-08-16
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701003080/WC/22012035002940 — ctr earthan bund kary rajaram khet ke pass | Completed | 834785.05 | 828986 | 2023-04-29 | 2024-03-12
MORENA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1701003080/WC/22012035002943 — ctr earthan bund kary ghadi ke pass padhawali | Closed | 0 | 0 | 2022-08-16
MORENA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701003080/WC/22012035008007 — amrat sarovar talav nirman kary badi kho me | Physically Completed | 1986507.96 | 1923367.25 | 2023-03-01 | 2026-06-12
MORENA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701003080/WC/22012035011001 — amrat sarovar talav nirman kary baagh ki jhor me 2 | Deleted | 0 | 0 | 2022-10-02
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701003080/WC/22012035087645 — AH eardhan dem nirman kary bdi kho ke uper | Completed | 1480203.9 | 1435564 | 2023-07-25 | 2024-03-12
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701003080/WC/22012035092338 — Rapata nirmayan kary pipali ke pass pur gram padhadhawali | Ongoing | 1480409.97 | 1411609.63 | 2024-02-22
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701003080/WC/22012035092341 — Rapata nirmayan kary babhur ke pass pur | Ongoing | 1495307.2 | 1449933.65 | 2024-03-14
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701003080/WC/22012035092344 — Rapata nirmayan kary pur gham se padhawali ke or | Ongoing | 1472159.11 | 1430714.03 | 2024-02-22
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003080/WC/22012035169430 — Nws bolder anicut nirman karya matware me | Closed | 0 | 0 | 2024-01-24
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003080/WC/22012035169431 — Nws bolder anicut nirman karya gadi ke pass | Closed | 0 | 0 | 2024-01-24
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701003080/WC/22012035173623 — Nws talab nirman kary ballebai me | Closed | 0 | 0 | 2024-01-26
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701003080/WC/22012035173624 — Nws talab nirman kary sheetla mata ke mandir ke pass | Ongoing | 1432973.87 | 1371886 | 2024-03-07
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701003080/WC/22012035173626 — Nws talab nirman kary nau bai khoh ke pass | Ongoing | 1494206.35 | 1422800 | 2024-03-07
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Stone contour Bund for Community / Construction of Stone contour Bund for Community | Construction of Bund | 1701003080/WC/22012035173629 — Nws Loose bolder nirman kary bde pahad pr | Ongoing | 797412.93 | 737179.65 | 2024-03-07
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone boulder Gully Plugs for Comm / Construction of Stone boulder Gully Plugs for Community | Boulder Check/Gully Plug | 1701003080/WC/22012035173631 — Nws Loose bolder nirman kary pathar ki khoh ke pass | Ongoing | 795815.04 | 751424.79 | 2024-03-07
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003080/WC/22012035173735 — Nws anicut nirman karya kho me | Closed | 0 | 0 | 2024-02-18
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003080/WC/22012035173736 — Nws anicut nirman karya mata bale har me | Closed | 0 | 0 | 2024-02-18
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003080/WC/22012035173768 — Nws anicut nirman karya gadi ke pass | Closed | 0 | 0 | 2024-02-18
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003080/WC/22012035173769 — Nws anicut nirman karya matware me | Closed | 0 | 0 | 2024-02-18
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003080/WC/22012035184273 — rapta Padhawali62margmukhyakaryanirmana | Closed | 0 | 0 | 2024-02-22
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003080/WC/22012035184277 — rapta Padhawali62margmukhyakaryanirmana | Closed | 0 | 0 | 2024-02-22
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701003080/WC/22012035196538 — नबीन तालव निर्माद कार्य खो के सामने | Closed | 0 | 0 | 2024-01-26
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701003080/WC/22012035196544 — नवीन तालव निर्माण कार्य खरीका के पीछे | Closed | 0 | 0 | 2024-01-26
MORENA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701003080/WC/22012035217251 — Nws talab nirman kary Panda khoh me | Approved | 0 | 0 | 2024-04-15
MORENA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701003080/WC/22012035217252 — Nws talab nirman kary Remza wale me | Approved | 0 | 0 | 2024-04-15
MORENA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701003080/WC/22012035217253 — Nws talab nirman kary kher ke pass | Approved | 0 | 0 | 2024-04-15
MORENA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701003080/WC/22012035217254 — Nws talab nirman kary khando ke jangal me | Approved | 0 | 0 | 2024-04-15
MORENA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701003080/WC/22012035217258 — Nws talab nirman kary Bharnikhoh me | Approved | 0 | 0 | 2024-04-15
MORENA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701003080/WC/22012035217259 — Nws talab nirman kary badekhar me | Approved | 0 | 0 | 2024-04-15
MORENA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701003080/WC/22012035219134 — Nws Perculation talab nirman kary htebai me | Physically Completed | 1471995.73 | 1430375 | 2024-08-24 | 2026-04-27
MORENA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701003080/WC/22012035219135 — Nws Perculation talab nirman kary manderi mata ke pass me | Ongoing | 1484151.71 | 1427245.83 | 2024-08-24
MORENA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701003080/WC/22012035222149 — Nws perculation talab nirman kary panda Khoh me | Physically Completed | 1470465.74 | 1429720.06 | 2024-11-15 | 2026-04-27
MORENA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701003080/WC/22012035222152 — Nws perculation talab nirman kary Remja Bale me | Physically Completed | 1464191.24 | 1366669.53 | 2024-11-15 | 2026-05-20
MORENA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701003080/WC/22012035222154 — Nws perculation talab nirman kary Kher bale me | Physically Completed | 1470465.74 | 1425932.62 | 2024-11-15 | 2026-04-27
MORENA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701003080/WC/22012035222155 — Nws perculation talab nirman kary Bade Khar me | Physically Completed | 1470465.74 | 1426760.35 | 2024-11-15 | 2026-05-26
MORENA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701003080/WC/22012035222156 — Nws perculation talab nirman kary Shitla Mata ke pass | Physically Completed | 1470465.74 | 1428224.87 | 2024-11-15 | 2026-04-27
MORENA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701003080/WC/22012035222158 — Nws perculation tank nirman kary pipal ke pass | Physically Completed | 1490330.73 | 1431966.6 | 2024-11-15 | 2026-04-27
MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1701003080/WC/22012035288781 — Dugwell Recharg Nirmaan karya shantidhaam padhawali me handpump ke pass | Approved | 24899.46 | 0 | 2025-04-14
MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701003080/WC/22012035327762 — Talab nirman karya khudi me | Approved | 0 | 0 | 2026-01-01
MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701003080/WC/22012035327885 — Talab Nirman karaya mandir ke pass | Approved | 0 | 0 | 2026-01-01
MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701003080/WC/22012035327899 — Talab nirman karya khanda bale me | Approved | 0 | 0 | 2026-01-01
MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701003080/WC/22012035327901 — Talab nirman karya ganna bale me | Approved | 0 | 0 | 2026-01-01
MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701003080/WC/22012035327902 — Talab nirman karya dhalan me | Approved | 0 | 0 | 2026-01-01
MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701003080/WC/22012035327903 — Talab nirman karya gadi ke pass | Approved | 0 | 0 | 2026-01-01
MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701003080/WC/22012035327904 — talab niman karya kehre ke pass | Approved | 0 | 0 | 2026-01-01
MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701003080/WC/22012035327905 — talab nirman karya upkar bale me | Approved | 0 | 0 | 2026-01-01
MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701003080/WC/22012035327906 — talab nirman karya jhakuta bale me | Approved | 0 | 0 | 2026-01-01
MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701003080/WC/22012035327908 — Talab nirman karya bohre bale me | Deleted | 0 | 0 | 2026-01-01
MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701003080/WC/22012035327909 — Talab nirman karya bohre bale me | Approved | 0 | 0 | 2026-01-01
MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701003080/WC/22012035328228 — Talab nirman karya khere bale me | Approved | 0 | 0 | 2026-01-01
MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701003080/WC/22012035328238 — Talab nirman karya bade tapu ke pass | Approved | 0 | 0 | 2026-01-01
MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701003080/WC/22012035328239 — Talab nirman karya bale pipal ke pass | Approved | 0 | 0 | 2026-01-01
MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701003080/WC/22012035328241 — Talab nirman karya ganna bale me | New | 0 | 0 | 2026-01-01
MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701003080/WC/22012035328242 — Talab nirman karya ganna bale me | Approved | 0 | 0 | 2026-01-01
MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701003080/WC/22012035328244 — Talab nirman karya chacha bale me | Approved | 0 | 0 | 2026-01-01
MORENA | 2017-2018 | D--RURAL INFRASTUCTURE / Renovation of traditional water bodies | Strengthening of Embankment / Construction of Embankment for community | Renovation of traditional water bodies | 1701003080/WH/22012034332187 — तालाब जीर्णोद्धार कार्य सिसोदिया पुरा पडावली | Closed | 34900000000 | 0 | 2017-10-02
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1701003080/WH/22012034453838 — talab marammat hubalal ka pura | Closed | 0 | 0 | 2021-12-02