## Work List
Exported on: 2026-10-21 14:06:04
Filters applied:
Data source: MGNREGA + VBGRAMG
District: MORENA
Block: All
Panchayat: AITi
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
MORENA | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1701003088/AV/22012034644883 — शांतिधाम निर्माण कार्य बहरावली, ऐंती | Closed | 330972.38 | 0 | 2023-08-16
MORENA | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1701003088/AV/22012034660775 — शांतिधाम निर्माण कार्य बरहावली | Approved | 349729.39 | 0 | 2024-08-16
MORENA | 2023-2024 | D--RURAL INFRASTUCTURE / Coastal Areas | Constr of drain for coastal protection for Comm. / Construction of Storm Water drain for coastal protection for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1701003088/CA/22012034524114 — शांति धाम निर्माण बराहवली | Closed | 0 | 0 | 2023-08-16
MORENA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701003088/DP/01 — व़क्षारोपण शा0 मा0वि0 के पास ऐंती | Completed | 352500 | 15935 | 2008-09-02 | 2013-12-10
MORENA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701003088/DP/02 — व़क्षारोपण ऐती रोड किनारे | Completed | 498000 | 52553 | 2008-09-16 | 2013-12-10
MORENA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701003088/DP/03 — व़क्षारोपण रूदे का पुरा रोड किनारे | Completed | 498000 | 19480 | 2008-09-02 | 2013-12-10
MORENA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701003088/DP/210 — व्रक्षारोपाण कार्य | Completed | 0 | 23508 | 2008-11-28 | 2012-12-11
MORENA | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701003088/DP/211 — ब्रक्षारोपड कार्य ऐंती | Completed | 0 | 74453 | 2009-07-09 | 2012-12-11
MORENA | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701003088/DP/212 — वृक्षारोपड कार्य ऐंती | Completed | 0 | 32214 | 2009-08-13 | 2012-12-11
MORENA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701003088/DP/213 — वृक्षारोपड कार्य ऐंती | Completed | 0 | 6800 | 2008-12-20 | 2012-12-11
MORENA | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701003088/DP/22012034235139 — शैलपर्ण उद्यान, बृक्षारोपण कार्य- शनिचरा मंदिर से पौढे हनुमान मंदिर एवं मंदिर वन चैकी से मुरली मनोहर | Completed | 1012500 | 90600 | 2016-08-24 | 2018-06-30
MORENA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1701003088/DP/22012034539956 — ब्लॉक प्लांटेशन कार्य शनिदेव मंदिर एती | Completed | 277628.48 | 170721 | 2022-04-02 | 2024-10-07
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1701003088/DP/22012034542895 — Ma Ki bagiya Madymik Vidyalay Aithi | Completed | 19963.3 | 12108 | 2022-03-09 | 2022-10-10
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1701003088/DP/22012034542898 — Ma Ki bagiya Prathmik Vidyalay Tode ka pura | Completed | 20445.35 | 10752 | 2022-03-09 | 2022-09-18
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1701003088/DP/22012034577126 — सामुदायिक वृक्षारोपण शंकर जी की बावड़ी पर | Closed | 0 | 0 | 2023-04-14
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Agro Forestry Block Plantation for Community | Plantation | 1701003088/DP/22012034577420 — Vruksharopan sankar ji ki Babri ke pass | Ongoing | 427106.07 | 95000 | 2024-03-19
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Sericulture- in Fields-Community / Block Plantation of Sericulture Trees in Fields for Community | Plantation | 1701003088/DP/22012034580043 — Bracharopan or Samtalikara Sankarji ki babdi k pass | Closed | 0 | 0 | 2023-04-14
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Sericulture- in Fields-Community / Block Plantation of Sericulture Trees in Fields for Community | Plantation | 1701003088/DP/22012034604791 — Samudayik vruksharopan Gousala Aithi | Closed | 0 | 0 | 2023-04-14
MORENA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1701003088/DP/331 — शान्ति धाम निमार्ण कार्य ऐंती | Completed | 309000 | 233333.24 | 2011-04-10 | 2014-08-25
MORENA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701003088/DP/366 — सामुहिक ब्रक्षारोपड | Completed | 2248126 | 1068768 | 2012-07-29 | 2015-12-22
MORENA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701003088/DP/404 — नंन्‍दन फलोदान | Completed | 100000 | 18000 | 2012-08-23 | 2014-08-25
MORENA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701003088/DP/405 — नंन्‍दन फलोदान | Completed | 156000 | 18600 | 2012-08-23 | 2014-08-25
MORENA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701003088/DP/406 — नंन्‍दन फलोदान | Completed | 0 | 24552 | 2012-09-01 | 2014-08-25
MORENA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701003088/DP/407 — नंन्‍दन फलोदान | Completed | 496120 | 24552 | 2012-09-01 | 2014-08-25
MORENA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701003088/DP/408 — नंन्‍दन फलोदान | Completed | 496130 | 42768 | 2012-08-23 | 2014-08-25
MORENA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701003088/DP/9926697034 — बेूघारोपउ शातधिाम निमाणकाय | Completed | 143878 | 48610 | 2013-03-01 | 2014-08-06
MORENA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Road/Canal Side Plantation / Road side line plantation of Forestry Trees for Community | Plantation | 1701003088/DP/9926697037 — नन्‍दनप्‍पलोधाननिमाण काय ऐती | Deleted | 156000 | 0 | 2012-05-10
MORENA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701003088/DP/9926697038 — नन्‍दनप्‍पलोधान निमाण | Completed | 156000 | 14472 | 2013-02-15 | 2013-12-10
MORENA | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701003088/DP/9926697645 — शैलपर्ण उधान पर्वत विकास प्रसाद जौन के पास शनिचरा | Completed | 1713000 | 419041 | 2013-09-05 | 2015-10-10
MORENA | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701003088/DP/9926697647 — शैलपर्ण उधान पर्वत विकास शनीचरा मंदिर ऐंती | Completed | 1713000 | 604474 | 2013-09-01 | 2015-12-22
MORENA | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of intrmediate and Link Water Drain-Comm / Construction of intermediate and Link Storm Water Drain for Community | Works for Flood Control and Protection | 1701003088/FP/22012034629607 — Nala nirman Tode ka Pura | Completed | 1476256.3 | 1396035.42 | 2022-10-31 | 2023-12-10
MORENA | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of intrmediate and Link Water Drain-Comm / Construction of intermediate and Link Storm Water Drain for Community | Works for Flood Control and Protection | 1701003088/FP/22012034630669 — Nala nirman gurmej ka pura se Nehar tak | Completed | 998483.42 | 920202.06 | 2022-12-23 | 2024-10-22
MORENA | 2024-2025 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood or Diversion Channel for Community | Works for Flood Control and Protection | 1701003088/FP/22012034634100 — कच्चा पक्का नाला निर्माण कार्य रूंध का पुरा ऐंती | Ongoing | 1494200.49 | 1320465.33 | 2024-06-20
MORENA | 2010-2011 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1701003088/IF/20081151 — मेड वन्‍धान कार्य रामप्रसाद पुञ हरिविलाश | Completed | 29518 | 13200 | 2010-06-30 | 2011-01-29
MORENA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701003088/IF/22012034345506 — सार्वजनिक परिसर मे व्रक्षारोपण कार्य राजीव गाधी सेवा केन्द्र स्‍कूल परिसर | Deleted | 335000 | 0 | 2017-01-26
MORENA | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation - Shelter Belt for Individuals / Block Plantation of Shelter Belt Trees for Individuals | Plantation | 1701003088/IF/22012034366063 — रोड़ किनारे बृक्षारोपण कार्य - परिक्रमा मार्ग 3 कि.मी शनिचरा मंदिर ऐंती . | Completed | 1005000 | 220533 | 2017-07-27 | 2020-12-23
MORENA | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation - Shelter Belt for Individuals / Block Plantation of Shelter Belt Trees for Individuals | Plantation | 1701003088/IF/22012034405683 — सामुदायिक वृक्षारोपण कार्य ऐती | Closed | 535000 | 0 | 2017-07-10
MORENA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1701003088/IF/22012034661962 — निजी खेत मैं फलोद्यान भूपेंद्र /मेहताव ग्राम पंचायत एती | Ongoing | 142446.41 | 1158 | 2021-09-09
MORENA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701003088/IF/22012034667523 — निजी खेत में फलोद्यान पंजाब सिंह /मेहताब सिंह | Closed | 144199.83 | 0 | 2021-01-21
MORENA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701003088/IF/22012034667524 — निजी खेत में फलोद्यान भारत सिंह /मेहताब सिंह | Closed | 144199.83 | 0 | 2021-01-21
MORENA | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1701003088/IF/377 — मेडवंधान कार्य | Completed | 24000 | 17424 | 2012-07-16 | 2014-08-25
MORENA | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1701003088/IF/378 — मेढवंधान कार्य रामदास | Completed | 14000 | 20592 | 2012-07-23 | 2014-08-25
MORENA | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003088/IF/9993652971 — पशुशैड निर्माण कार्य - सुरेश | Deleted | 84000 | 0 | 2014-08-26
MORENA | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003088/IF/9993652974 — पशुशैड निर्माण कार्य - सुनील/रामसिंह | Deleted | 84000 | 0 | 2014-08-26
MORENA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701003088/IF/9993749088 — नन्दन फलोधान योजना - राजेन्द्र / नृपतिनन्दन फलोधान योजना - राजेन्द्र / नृपति | Completed | 52940 | 22185 | 2016-06-25 | 2018-09-19
MORENA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701003088/IF/9993749102 — नंदन फलोद्यान योजना - पुत्तुसिंह / नृपति | Completed | 105000 | 20322 | 2016-06-25 | 2018-09-19
MORENA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Horticulture / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701003088/IF/9993749104 — नंदन फलोद्यान योजना - अंगूरी देवी / रामप्रसाद | Completed | 52940 | 3835 | 2016-06-24 | 2018-09-19
MORENA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701003088/IF/9993749105 — नंदन फलोद्यान योजना - सज्जो बाई / मेहताब | Completed | 105000 | 36594 | 2016-06-25 | 2018-09-19
MORENA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003088/IF/IAY/114935 — Construction of IAY House -IAY REG. NO. MP-01-003-088-002/155 | Completed | 14310 | 10020 | 2017-03-25 | 2017-10-10
MORENA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003088/IF/IAY/114947 — Construction of IAY House -IAY REG. NO. MP-01-003-088-002/137 | Completed | 14310 | 12024 | 2017-03-25 | 2017-07-20
MORENA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003088/IF/IAY/114951 — Construction of IAY House -IAY REG. NO. MP-01-003-088-002/220 | Completed | 14310 | 8016 | 2017-03-07 | 2017-08-22
MORENA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003088/IF/IAY/199218 — Construction of IAY House -IAY REG. NO. MP-01-003-088-002/251 | Completed | 15030 | 14028 | 2017-03-07 | 2017-05-22
MORENA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003088/IF/IAY/205311 — Construction of IAY House -IAY REG. NO. MP-01-003-088-001/5S | Completed | 15030 | 14028 | 2017-03-07 | 2017-08-22
MORENA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003088/IF/IAY/34810 — Construction of IAY House -IAY REG. NO. MP-01-003-088-001/133 | Completed | 14310 | 14028 | 2017-03-07 | 2017-08-22
MORENA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003088/IF/IAY/34811 — Construction of IAY House -IAY REG. NO. MP-01-003-088-001/140 | Completed | 14310 | 12024 | 2017-03-07 | 2017-06-14
MORENA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003088/IF/IAY/34812 — Construction of IAY House -IAY REG. NO. MP-01-003-088-001/158 | Completed | 14310 | 12024 | 2017-03-07 | 2017-08-22
MORENA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003088/IF/IAY/34813 — Construction of IAY House -IAY REG. NO. MP-01-003-088-002/218 | Completed | 14310 | 12024 | 2017-03-07 | 2017-08-22
MORENA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1701003088/IF/IAY/4707814 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123530997 | Completed | 21870 | 21384 | 2025-01-02 | 2026-07-23
MORENA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003088/IF/IAY/547569 — Construction of IAY House -IAY REG. NO. MP3287740 | Completed | 15030 | 15660 | 2017-02-10 | 2018-09-26
MORENA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003088/IF/IAY/613220 — Construction of IAY House -IAY REG. NO. MP1624825 | Completed | 15030 | 15594 | 2017-03-07 | 2018-09-20
MORENA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003088/IF/IAY/617409 — Construction of IAY House -IAY REG. NO. MP2972471 | Completed | 15030 | 12354 | 2017-03-07 | 2018-04-04
MORENA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003088/IF/IAY/617940 — Construction of IAY House -IAY REG. NO. MP3281788 | Completed | 15030 | 15420 | 2017-03-07 | 2018-01-31
MORENA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003088/IF/IAY/617941 — Construction of IAY House -IAY REG. NO. MP3281985 | Completed | 15030 | 15582 | 2017-03-07 | 2018-09-20
MORENA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003088/IF/IAY/617956 — Construction of IAY House -IAY REG. NO. MP3293892 | Completed | 15030 | 15624 | 2017-02-10 | 2018-09-11
MORENA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003088/IF/IAY/648333 — Construction of IAY House -IAY REG. NO. MP2236543 | Completed | 15030 | 15450 | 2017-03-07 | 2018-01-31
MORENA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003088/IF/IAY/650577 — Construction of IAY House -IAY REG. NO. MP3287204 | Completed | 15030 | 16584 | 2017-03-07 | 2018-08-22
MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003088/IF/IAY/688569 — Construction of IAY House -IAY REG. NO. MP1074305 | Completed | 15030 | 15588 | 2017-04-29 | 2018-09-11
MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003088/IF/IAY/715081 — Construction of IAY House -IAY REG. NO. MP1630446 | Completed | 15030 | 15652 | 2017-10-01 | 2018-01-12
MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003088/IF/IAY/715238 — Construction of IAY House -IAY REG. NO. MP1632804 | Completed | 15030 | 14448 | 2017-04-27 | 2018-04-04
MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003088/IF/IAY/715514 — Construction of IAY House -IAY REG. NO. MP1635494 | Completed | 15030 | 13476 | 2017-04-29 | 2018-07-30
MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003088/IF/IAY/715565 — Construction of IAY House -IAY REG. NO. MP1636238 | Completed | 15030 | 15624 | 2017-04-29 | 2018-09-11
MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003088/IF/IAY/723985 — Construction of IAY House -IAY REG. NO. MP1798635 | Completed | 15030 | 15624 | 2017-04-29 | 2018-09-11
MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003088/IF/IAY/740155 — Construction of IAY House -IAY REG. NO. MP2233630 | Completed | 15030 | 15480 | 2017-04-29 | 2018-01-31
MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003088/IF/IAY/740289 — Construction of IAY House -IAY REG. NO. MP2236525 | Completed | 15030 | 14460 | 2017-04-29 | 2018-04-30
MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003088/IF/IAY/761665 — Construction of IAY House -IAY REG. NO. MP3038411 | Completed | 15030 | 14448 | 2017-10-01 | 2018-04-04
MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003088/IF/IAY/766982 — Construction of IAY House -IAY REG. NO. MP3281187 | Completed | 15030 | 14448 | 2017-04-29 | 2018-04-04
MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003088/IF/IAY/766994 — Construction of IAY House -IAY REG. NO. MP3281636 | Completed | 15030 | 15648 | 2017-10-01 | 2018-09-26
MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003088/IF/IAY/767006 — Construction of IAY House -IAY REG. NO. MP3282101 | Completed | 15030 | 15576 | 2017-04-29 | 2018-08-22
MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003088/IF/IAY/767007 — Construction of IAY House -IAY REG. NO. MP3282163 | Completed | 15030 | 14568 | 2017-04-29 | 2018-08-09
MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003088/IF/IAY/767098 — Construction of IAY House -IAY REG. NO. MP3286171 | Completed | 15030 | 15624 | 2017-04-29 | 2018-09-20
MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003088/IF/IAY/767102 — Construction of IAY House -IAY REG. NO. MP3286233 | Completed | 15030 | 15624 | 2017-04-29 | 2018-09-11
MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003088/IF/IAY/767105 — Construction of IAY House -IAY REG. NO. MP3286301 | Completed | 15030 | 15612 | 2017-04-29 | 2018-09-20
MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003088/IF/IAY/767132 — Construction of IAY House -IAY REG. NO. MP3287588 | Completed | 15030 | 15636 | 2017-04-29 | 2018-10-10
MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003088/IF/IAY/767248 — Construction of IAY House -IAY REG. NO. MP3293094 | Completed | 15030 | 15636 | 2017-04-29 | 2018-10-23
MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003088/IF/IAY/767356 — Construction of IAY House -IAY REG. NO. MP3299104 | Completed | 15030 | 15492 | 2017-04-29 | 2018-05-07
MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003088/IF/IAY/767361 — Construction of IAY House -IAY REG. NO. MP3299246 | Completed | 15030 | 15588 | 2017-04-29 | 2018-08-22
MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003088/IF/IAY/767403 — Construction of IAY House -IAY REG. NO. MP3301595 | Completed | 15030 | 15636 | 2017-04-29 | 2018-10-10
MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003088/IF/IAY/775852 — Construction of IAY House -IAY REG. NO. MP3726392 | Completed | 15030 | 14496 | 2017-04-29 | 2018-09-11
MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003088/IF/IAY/778503 — Construction of IAY House -IAY REG. NO. MP3901656 | Completed | 15030 | 17688 | 2017-04-29 | 2018-09-20
MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003088/IF/IAY/778526 — Construction of IAY House -IAY REG. NO. MP3902970 | Completed | 15030 | 14580 | 2017-04-29 | 2018-09-11
MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003088/IF/IAY/778764 — Construction of IAY House -IAY REG. NO. MP3921206 | Completed | 15030 | 14964 | 2017-04-29 | 2018-05-16
MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003088/IF/IAY/804571 — Construction of IAY House -IAY REG. NO. MP3294222 | Completed | 15480 | 15588 | 2017-04-29 | 2018-08-09
MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003088/IF/IAY/813376 — Construction of IAY House -IAY REG. NO. MP1654707 | Completed | 15480 | 15636 | 2017-04-29 | 2018-09-20
MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003088/IF/IAY/826967 — Construction of IAY House -IAY REG. NO. MP3301481 | Completed | 15480 | 15636 | 2017-04-29 | 2018-09-26
MORENA | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701003088/LD/22012034228913 — राजीव गांधी सेवा केन्द्र की बाउण्ड्रीबाल निर्माण कार्य एंेती | Completed | 195000 | 192790 | 2015-10-26 | 2017-08-22
MORENA | 2015-2016 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1701003088/LD/22012034228917 — खेलमैदान निर्माण कार्य ऐंती | Closed | 499000 | 0 | 2015-07-20
MORENA | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Land Leveling / Levelling/shaping of Wasteland Land for Community | Land Development | 1701003088/LD/22012034248208 — मुरम भराव एवं समतलीकरण कार्य -शनिचरा मंदिर ऐंती | Completed | 701700 | 252004.5 | 2016-01-19 | 2016-11-08
MORENA | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701003088/LD/22012034314370 — चबूतरा निर्माण कार्य - मयूर वन शनि मंदिर ऐंती | Completed | 722000 | 326873.47 | 2017-05-31 | 2018-06-30
MORENA | 2017-2018 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1701003088/LD/22012034316540 — चौपाल एवं बाउण्‍डरीबाल निर्माण - अंगद का पुरा ऐंती | Completed | 575510 | 225660 | 2017-08-12 | 2018-07-25
MORENA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1701003088/LD/22012034466614 — सी.सी. खरंजा के दोनो ओर सोल्डर भराई कार्य - रानी मंदिर पौडे हनुमान मंदिर से ग्राम ऐंती तक | Completed | 90000 | 89383.72 | 2019-07-04 | 2019-10-01
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Fallow Land for Community / Development of Fallow Land for Community | Land Development | 1701003088/LD/22012034592132 — Muram Filling or Samtalikaran Shani mandir | Completed | 1395327.83 | 1352062.05 | 2023-09-12 | 2024-10-22
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1701003088/LD/22012034596614 — भूमि समतलीकरण जूता घर के पास शनि मंदिर | Ongoing | 1446131.03 | 1231748.55 | 2023-10-09
MORENA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701003088/LD/3799387325 — मेढबंधान निर्माण भारत सिंह | Deleted | 0 | 0 | 2013-01-26
MORENA | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701003088/LD/3799419468 — समतलीकरण कार्य - शनीचरा मंदिर के पास ऐंती | Completed | 1495000 | 992669.6 | 2014-01-11 | 2015-07-23
MORENA | 2016-2017 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1701003088/PG/9425891173 — खेलमैदान निर्माण कार्य- ऐंती | Completed | 561000 | 157471.52 | 2016-12-15 | 2018-08-28
MORENA | 2007-2008 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701003088/RC/00t — test | Completed | 500000 | 0 | 2008-02-10 | 2008-02-10
MORENA | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701003088/RC/01 — मिटटी मुरम रोड ऐंती से बरहाबली | Completed | 490000 | 13455 | 2008-04-05 | 2013-12-10
MORENA | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701003088/RC/1037 — पत्‍थर खरंजा पर्वत मंदिर | Completed | 0 | 346330 | 2011-06-10 | 2014-08-25
MORENA | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701003088/RC/1128 — पत्‍थर खरंज शनीदेव मंदिर | Completed | 0 | 296970.4 | 2011-10-12 | 2014-08-25
MORENA | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003088/RC/1129 — सी सी खरंज | Completed | 0 | 74095 | 2012-03-09 | 2014-08-25
MORENA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701003088/RC/22012034159186 — मिटटी बजरी रोड निर्माण कार्य राम के द्वार से श्‍याम के द्वार | Deleted | 0 | 0 | 2013-01-26
MORENA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003088/RC/22012034161476 — सी सी खरंजा एवं नाली निर्माण कार्य पंचपरमेश्‍वर प्रभु के मकान से हैण्‍डपम्‍प तक ऐंती | Deleted | 0 | 0 | 2013-01-26
MORENA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701003088/RC/22012034161477 — मिटटी रोड भराव कार्य पर्वत मंदिर ऐंती | Deleted | 0 | 0 | 2013-01-26
MORENA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003088/RC/22012034161481 — सी सी खरंजा एवं नाली निर्माण कार्य रूंदि का पुरा भारत के मकान ऐंती | Deleted | 0 | 0 | 2013-01-26
MORENA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003088/RC/22012034161482 — पत्‍थर ख्रंरजा निर्माण कार्य सूर्य मंदिर से शांतिधाम तक बहराबली | Deleted | 0 | 0 | 2013-01-26
MORENA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701003088/RC/22012034161483 — मिटटी रोड भराव कार्य शनिदेव मंदिर ऐंती | Deleted | 0 | 0 | 2013-01-26
MORENA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701003088/RC/22012034203927 — पत्‍थर फर्शी निर्माण कार्य - शनिचरा मंदिर ऐंती | Completed | 839339 | 589766 | 2014-02-12 | 2015-07-23
MORENA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Bitumen Top / Construction of Bitumen Top Roads for Community | Construction of Road and Culvert | 1701003088/RC/22012034205889 — मुरम रोड निर्माण कार्य - पौढे हनुमान मंदिर से ग्रा | Completed | 880000 | 404856 | 2014-02-26 | 2015-07-23
MORENA | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003088/RC/22012034225853 — dfffffgfdg | Deleted | 0 | 0 | 2014-07-04
MORENA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701003088/RC/22012034309077 — mitti muram road | Deleted | 0 | 0 | 2016-01-26
MORENA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701003088/RC/22012034309078 — mitti muram road | Deleted | 0 | 0 | 2016-01-26
MORENA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701003088/RC/22012034309079 — mitti muram road | Deleted | 0 | 0 | 2016-01-26
MORENA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701003088/RC/22012034309080 — patthar kharnja | Deleted | 0 | 0 | 2016-01-26
MORENA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701003088/RC/22012034309081 — patthar kharnja | Deleted | 0 | 0 | 2016-01-26
MORENA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003088/RC/22012034320175 — सी सी खरंजा एवं नाली निर्माण कार्य - माता के मंदिर से लेकर कारस बाबा मंदिर से हरिजन बस्ती की ओर ऐंती | Completed | 143356 | 85656 | 2017-07-20 | 2018-03-24
MORENA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003088/RC/22012034329027 — c.c. road aiti | Deleted | 0 | 0 | 2016-10-02
MORENA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701003088/RC/22012034334847 — सुदूर ग्राम समपर्क रोड़ निर्माण ऐती से ग्राम भटपुरा की ओर | Completed | 1498000 | 840139.37 | 2017-04-08 | 2018-10-05
MORENA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003088/RC/22012034335495 — सीमेंट कंक्रीट खरंजा ऐब नाली निर्माण कार्य ऐती | Completed | 264000 | 80496 | 2017-09-15 | 2018-04-04
MORENA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701003088/RC/22012034339149 — सी सी खरंजा की पटरी भराई कार्य - मंदिर परिसर ऐंती | Completed | 166000 | 164889.58 | 2017-06-14 | 2018-05-07
MORENA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701003088/RC/22012034340197 — सुदूर ग्राम संपर्क सडक निर्माण पुलिया सहित - सिकरवार के पुरा से नाउपुराा तक | Closed | 1498000 | 0 | 2017-05-20
MORENA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003088/RC/22012034347835 — सीमैट कांक्रीट खर्ंजा नाली निर्माण कार्य मुन्ना के मकान से हनुमानजी मन्दिर होते हुऐ पटिया वाले मन्दि | Completed | 219600 | 212936 | 2017-10-15 | 2018-04-04
MORENA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003088/RC/22012034350632 — सी सी खरंजा एवं नाली निर्माण कार्य - मुख्य सड़क से स्कूल तक वाया मुख्य सड़क से हेवली तक ऐंती | Closed | 79200 | 0 | 2017-05-05
MORENA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003088/RC/22012034363803 — सुदूर ग्राम सम्‍पर्क रोड निर्माण कार्य पुलिया से सिकरवार के पुरा से नाऊपुरा तक | Deleted | 0 | 0 | 2017-04-14
MORENA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701003088/RC/22012034370130 — सुदुर ग्राम सम्पर्क सडक निर्माण कार्य - पौंडे हनुमान से वन चैकी तक। | Completed | 1318000 | 912618.9 | 2018-04-14 | 2018-10-05
MORENA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003088/RC/22012034470377 — cc खरंजा एवं नाली निर्माण हनुमान मंदिर वाली गली एवं मुख्य मार्ग से cc खरंजा कुम्हारों का पूरा | Completed | 123700 | 121440 | 2019-07-19 | 2019-10-18
MORENA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003088/RC/22012034530207 — सी.सी. खरंजा नाली सहित मैन रोड फूल सिंह के मकान तक | Completed | 86070 | 82080 | 2020-07-20 | 2020-08-18
MORENA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701003088/RC/22012034531430 — सुदूर ग्राम /खेत सड़क रूंदका पुरा से घाटी रोड तक | Completed | 3327516.86 | 2704617.35 | 2020-08-26 | 2023-07-11
MORENA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Mitti Murram Roads for Community / Construction of Farm Roads for Community | Construction of Road and Culvert | 1701003088/RC/22012034681763 — sudur sadak nirman mukya marg se ramesh ke ghar ki or | New | 0 | 0 | 2024-01-24
MORENA | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003088/RC/447 — सीमेन्‍ट कांक्रीट खंरन्‍जा निमार्ण कार्य | Completed | 0 | 19766.33 | 2008-11-14 | 2008-04-01
MORENA | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Metal Second coat / Construction of WBM Roads for Community | Construction of Road and Culvert | 1701003088/RC/448 — पत्‍थर खरन्‍जा निर्माण कार्य ऐटी | Completed | 0 | 204038 | 2009-01-30 | 2011-01-29
MORENA | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Metal First coat / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701003088/RC/512 — पत्‍थर खरजा निर्माण कार्य | Completed | 0 | 376226.25 | 2010-04-01 | 2010-04-01
MORENA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701003088/RS/22012034475500 — Sochal nirman santosh mirdha | Deleted | 0 | 0 | 2019-08-15
MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1701003088/RS/22012034567004 — सामुदायिक स्वछता परिसर एती | Completed | 43000 | 39834 | 2021-11-15 | 2022-09-01
MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1701003088/RS/22012034612718 — samudayak sochalay | Deleted | 43000 | 0 | 2021-04-14
MORENA | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1701003088/RS/22012034664597 — Nadep nirman Brahwali SLWM | Completed | 38477.94 | 28309.76 | 2022-10-27 | 2023-12-18
MORENA | 2013-2014 | D--RURAL INFRASTUCTURE / Bharat Nirman Sewa Kendra | New Construction / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1701003088/SK/625 — Bharat Nirman Rajeev Gandhi Sewa Kendra,AITHI | Completed | 1397000 | 991146.4 | 2013-09-19 | 2015-09-23
MORENA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1701003088/WC/01 — सोख्‍ता गडडा रूद का पुरा | Completed | 11500 | 6650 | 2008-04-23 | 2011-01-29
MORENA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1701003088/WC/02 — सोख्‍ता गडडा ऐती शा0मा0वि0 | Completed | 11500 | 2241 | 2008-04-25 | 2008-01-26
MORENA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003088/WC/16 — वहरावली तालाब का रख रखाव कार्य | Completed | 0 | 9520 | 2008-09-07 | 2016-06-03
MORENA | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003088/WC/18 — ऐती न.1 तालाब का रख रखाव कार्य | Completed | 0 | 0 | 2008-02-15 | 2008-02-15
MORENA | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1701003088/WC/19 — एंती न. 1 तालाब का रख रखाब कार्य | Completed | 10000 | 19692 | 2008-09-12 | 2016-05-18
MORENA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003088/WC/20 — एंती न. 2 तालाब का रख रखाब कार्य | Completed | 20000 | 57369.35 | 2008-09-09 | 2016-06-03
MORENA | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Anicut / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003088/WC/22012034380222 — TALAB GAHRIKARAN | Deleted | 0 | 0 | 2017-10-02
MORENA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003088/WC/22012034432223 — नवीन तालाब निर्माण कार्य - | Closed | 0 | 0 | 2019-01-26
MORENA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003088/WC/22012034475359 — Khet talab | Closed | 0 | 0 | 2019-06-22
MORENA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1701003088/WC/22012034481759 — Khet talab | Completed | 348363.11 | 321790.79 | 2019-10-07 | 2020-09-18
MORENA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1701003088/WC/22012034485761 — Khet talab aenti near road | Deleted | 0 | 0 | 2019-08-15
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003088/WC/22012034785743 — ctr/nws check dam bhupend singh ke khet ke samip | Completed | 1497110.75 | 1457015 | 2021-07-31 | 2022-07-23
MORENA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1701003088/WC/22012034995410 — Sokpit nirma Brahwali Tode ka Pura | Completed | 40225.47 | 29514.5 | 2022-11-10 | 2023-12-18
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Pebble contour Bund for Community / Construction of Pebble contour Bund for Community | Construction of Bund | 1701003088/WC/22012035066965 — Rapta Nirman with ring band Sanishcra parikrma marg | Completed | 1839697.49 | 1733964.24 | 2023-06-28 | 2024-10-29
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701003088/WC/22012035091143 — Rapta Nirman jirna k pass Aithi | Completed | 996304.24 | 938609 | 2023-10-06 | 2024-10-29
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003088/WC/22012035100980 — रपटा निर्माण कार्य मैन रोड से रमेश के पास ऐंती | Ongoing | 1370249.09 | 748080.02 | 2023-10-09
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1701003088/WC/22012035186089 — anikat nirman jirana ke pass | New | 0 | 0 | 2024-01-24
MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1701003088/WC/22012035314689 — Talab Nirmaan Karya Nariya Ke Pass Aiti | Approved | 0 | 0 | 2025-04-14
MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1701003088/WC/22012035314690 — Talab Nirmaan Karya jhariya Ke Pass Aiti | Approved | 0 | 0 | 2025-04-14
MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1701003088/WC/22012035314691 — Talab Nirmaan Karya mandir Bahrawali ki or Aiti | Approved | 0 | 0 | 2025-04-14
MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1701003088/WC/22012035314692 — Talab Nirmaan Karya Bahrawali maarg ke pass Aiti | Approved | 0 | 0 | 2025-04-14
MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1701003088/WC/22012035314694 — Talab Nirmaan Karya Sadak ke pass Aiti | Approved | 0 | 0 | 2025-04-14
MORENA | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1701003088/WC/260 — निर्मल नीर योजना | Completed | 0 | 9134 | 2008-10-29 | 2011-01-29
MORENA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Mini Percolation tank / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1701003088/WC/305 — तलैया निर्माण | Completed | 340000 | 64152 | 2012-07-23 | 2014-08-25
MORENA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Mini Percolation tank / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1701003088/WC/306 — तलैया निर्माण पर्वत मदिर | Completed | 230000 | 75240 | 2012-07-16 | 2014-08-25
MORENA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1701003088/WC/9993650948 — tehrthg | Deleted | 80000 | 0 | 2013-10-02
MORENA | 2007-2008 | D--RURAL INFRASTUCTURE / Renovation of traditional water bodies | Strengthening of Embankment / Construction of Embankment for community | Renovation of traditional water bodies | 1701003088/WH/0test — test | Deleted | 500000 | 0 | 2008-02-10
MORENA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Model Talab / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1701003088/WH/180 — नवीन तालाव निर्माण कार्य | Completed | 0 | 306550 | 2010-04-23 | 2013-12-10
MORENA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1701003088/WH/22012034388742 — तालाब मरम्मत कार्य - बरहावली छोटा तालाब ऐंती | Completed | 536500 | 432208.95 | 2018-07-04 | 2019-06-28
MORENA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1701003088/WH/22012034389061 — तालाब जीर्णोद्धार कार्य - बराहवली बडा तालाब ऐंती। | Completed | 993700 | 786551.06 | 2018-07-04 | 2020-02-13
MORENA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1701003088/WH/22012034444687 — बाबरी मरम्मत कार्य शंकर जी मंदिर के पास | Completed | 787885.47 | 739668.8 | 2020-08-04 | 2022-09-01
MORENA | 2008-2009 | D--RURAL INFRASTUCTURE / Renovation of traditional water bodies | Strengthening of Embankment / Construction of Embankment for community | Renovation of traditional water bodies | 1701003088/WH/45 — ऐती न. 2 तालाब का रख रखाव | Deleted | 171000 | 0 | 2008-06-15
MORENA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1701003/WH/157 — ऐती न-2 तालाब का सुदिकरण ग्राम पंचायत ऐती | Completed | 1937000 | 196882 | 2008-12-30 | 2013-08-12
MORENA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Excavation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1701003/WH/169 — एती 01 उरेहना तालाव का रखरखा कार्य | Deleted | 0 | 12604 | 2009-01-08
MORENA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Excavation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1701003/WH/170 — एती तालाव का रखरखा कार्य | Deleted | 0 | 0 | 2008-09-07
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1701/WC/22012035048891 — अमृत सरोवर तालाब निर्माण कार्य हनुमान मंदिर के पीछे ऐंती | Ongoing | 4892000 | 2656405.16 | 2023-05-15
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1701/WC/22012035048913 — अमुत सरोवर तालाब निर्माण कार्य शनि मंदिर के पीछे ग्राम ऐंती | Ongoing | 5159000 | 2809840.05 | 2023-05-20