## Work List
Exported on: 2026-09-14 13:03:37
Filters applied:
Data source: VBGRAMG
District: MORENA
Block: All
Panchayat: NAUGAON
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
MORENA | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert for Community | Culvert | 1701003094/AV/22012034657385 — nws culvert nirman karya नौगांव | New | 0 | 0 | 2024-06-16
MORENA | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert for Community | Culvert | 1701003094/AV/22012034657391 — nws culvert nirman karya बक्सीपुरा | New | 0 | 0 | 2024-06-16
MORENA | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1701003094/AV/22012034662638 — शांतिधाम निर्माण कार्य नौगांव | New | 0 | 0 | 2024-08-16
MORENA | 2025-2026 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1701003094/AV/22012034666039 — शांतिधाम निर्माण कार्य नौगाँव | New | 0 | 0 | 2025-04-14
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1701003094/DP/22012034577125 — Samudayik vruksharopan Navin talab ke pass | Ongoing | 757490.82 | 0 | 2023-06-16
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Shelter Belt Trees (Comm) / Boundary Line Plantation of Shelter Belt Trees for Community | Plantation | 1701003094/DP/22012034577176 — Samudayik Bricharopan santidam Nougao | Ongoing | 427106.07 | 0 | 2024-03-16
MORENA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Coastal Block Plantation - Farm Forestry-Community / Along the coast Block Plantation of Farm Forestry Trees for Community | Plantation | 1701003094/DP/22012034614521 — सामुदायिक पोषण वाटिका मंदिर के पास | Ongoing | 757490.82 | 0 | 2024-06-25
MORENA | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701003094/FP/22012034629614 — Nws Kaccha Nala Nirman Karya Harveer Prajapati Ke Khet Se Suresh Sharma Ke Khet Ki Or | Ongoing | 1493416.76 | 0 | 2022-09-29
MORENA | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of drain for coastal protection for Comm. / Construction of Storm Water drain for coastal protection for Community | Works for Flood Control and Protection | 1701003094/FP/22012034629616 — Nws Kaccha Nala Nirman Karya Ramkali Ke Khet Se Shanti Dham tak | Ongoing | 1466436.89 | 0 | 2023-09-30
MORENA | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701003094/FP/22012034639388 — KACCHA PAKKA NAALA NIRMAN NAVIN TAALAB SE SASKIY VIDHYALYA KI OR | New | 0 | 0 | 2024-01-24
MORENA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1701003094/IF/22012035528172 — खेत तालाब निर्माण कार्य देवप्रकाश के खेत मे | Approved | 0 | 0 | 2025-04-14
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1701003094/WC/22012035029056 — kaacha nalla nirman phup singh ke khet ke pass | Ongoing | 1214022.5 | 0 | 2023-09-30
MORENA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1701003094/WC/22012035067424 — Pakka nala nirman kary naugaon pejram ke khet se nathuram ke khet ki aur | Ongoing | 1460410.7 | 0 | 2024-07-01