## Work List
Exported on: 2026-09-07 11:21:05
Filters applied:
Data source: MGNREGA + VBGRAMG
District: MORENA
Block: All
Panchayat: JEWRAKHERA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
MORENA | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1701003113/AV/22012034661388 — शांतिधाम निर्माण कार्य जेबराखेडा | New | 0 | 0 | 2024-10-02
MORENA | 2025-2026 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1701003113/AV/22012034666457 — शांतिधाम निर्माण कार्य पंछी का पुरा जेवराखेड़ा | New | 0 | 0 | 2025-04-14
MORENA | 2025-2026 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1701003113/AV/22012034666497 — नवीन शांतिधाम निर्माण कार्य पंछी का पुरा जेवराखेड़ा | New | 0 | 0 | 2025-04-14
MORENA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701003113/DP/01 — रतन ज्‍योति पौध रोपड जेवरा खेडा से पंछी का पुरा रोड किनारे | Completed | 35500 | 9445 | 2008-09-01 | 2013-03-06
MORENA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701003113/DP/171 — नन्‍दन फलोउघोन कार्य | Completed | 0 | 300 | 2010-04-09 | 2009-04-01
MORENA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701003113/DP/172 — नन्‍दन फलोउघोन कार्य दिनेश पुञ हामिक सिह | Deleted | 0 | 0 | 2009-02-10
MORENA | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701003113/DP/173 — नन्‍दन फलोउघोन कार्य दिनेशसिह पुञ हामिक सिह | Completed | 0 | 450 | 2010-01-25 | 2009-04-01
MORENA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701003113/DP/174 — नन्‍दन फलोउघोन कार्य दारासहि पुञ नेतराम | Completed | 0 | 150 | 2010-04-09 | 2009-04-01
MORENA | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701003113/DP/175 — नन्‍दन फलोउघोन कार्य कमल सिह पुञ लालजीत | Completed | 0 | 450 | 2010-01-25 | 2009-04-01
MORENA | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701003113/DP/176 — नन्‍दन फलोउघोन कार्य रमेश पुञ गोधन सिह | Completed | 0 | 480 | 2009-12-03 | 2009-12-01
MORENA | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701003113/DP/22012034328717 — वृक्षारोपण कार्य। | Closed | 0 | 0 | 2017-10-02
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1701003113/DP/22012034596306 — प्लांटेसन कार्य शा प्रा विद्यालय जेवराखेडा मेरी माटी मेरा देश | Closed | 55847.4 | 0 | 2023-07-15
MORENA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Sericulture- in Fields-Community / Block Plantation of Sericulture Trees in Fields for Community | Plantation | 1701003113/DP/22012034621146 — व्रक्षारोपण कार्य शा. प्रा. शाला जेवराखेड़ा | Approved | 0 | 0 | 2024-06-08
MORENA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1701003113/DP/9926694868 — शांतीधाम निर्माण जेबराखेडा | Completed | 420000 | 345249 | 2013-01-19 | 2016-05-22
MORENA | 2015-2016 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Drainage in Water Logged Areas / Drainage of Community Waterlogged Land | Works for Flood Control and Protection | 1701003113/FP/22012034203506 — नाली निर्माण कार्य - रामौतार के मकान से स्‍वराज भवन तक जेबराखेरा | Deleted | 1499000 | 0 | 2016-01-15
MORENA | 2018-2019 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701003113/FP/22012034362888 — पत्थर नाला निर्माण कार्य हॉस्पिटल से बजरंग मंदिर ,सोवरन जाटव के मकान से दोलतराम के मकान तक | Completed | 1498000 | 1217369.81 | 2019-03-08 | 2021-08-10
MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701003113/FP/22012034627786 — सी. सी. नाला निर्माण कार्य बनवारी जाटव के माकन से शेखर कुशवाह के मकान तक एवं सीता के मकान से पोखर तक | Completed | 73650 | 48057 | 2022-02-03 | 2022-04-30
MORENA | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of drain for coastal protection for Comm. / Construction of Storm Water drain for coastal protection for Community | Works for Flood Control and Protection | 1701003113/FP/22012034630597 — patthar nala nirman karya - ramswaroop kushwah ke dwar se kiratram kushwah ki or | Completed | 996591.4 | 805132.62 | 2023-05-17 | 2025-12-11
MORENA | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of drain for coastal protection for Comm. / Construction of Storm Water drain for coastal protection for Community | Works for Flood Control and Protection | 1701003113/FP/22012034630606 — Patthar nala nirman karya - ramkhatyar ke makan se darshanlal ke ghar se hota hua chamunda mata ki | Deleted | 0 | 0 | 2022-08-16
MORENA | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of drain for coastal protection for Comm. / Construction of Storm Water drain for coastal protection for Community | Works for Flood Control and Protection | 1701003113/FP/22012034630748 — Patthar nala nirman karya - rambabu jamadar ke ghar se ramautar kushwah ke plot & puliya ki or | Deleted | 0 | 0 | 2022-08-16
MORENA | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of drain for coastal protection for Comm. / Construction of Storm Water drain for coastal protection for Community | Works for Flood Control and Protection | 1701003113/FP/22012034631444 — Patthar nala nirman karya - rambabu jamadar ke ghar se ramautar kushwah ke plot & puliya ki or | Deleted | 0 | 0 | 2022-11-04
MORENA | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701003113/FP/22012034633979 — नाला निर्माण कार्य मुकेश जाटव के मकान से कमल सिंह जाटव के मकान से होता हुआ अम्बाह रोड की ओर | Ongoing | 1443448.92 | 113577 | 2023-10-06
MORENA | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701003113/FP/22012034633981 — नाला निर्माण कार्य शारदा माता से नरूआ की ओर | Completed | 978534.26 | 924492.61 | 2023-07-21 | 2025-12-17
MORENA | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701003113/FP/22012034633982 — नाला निर्माण कार्य सीता जाटव के मकान से अमित्तलाल जाटव की ओर | Physically Completed | 1381609.34 | 1248171.13 | 2023-10-02 | 2026-08-21
MORENA | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701003113/FP/22012034635789 — नाला निर्माण कार्य सभाराम जाटव के यहाॅ से मुडियाखेडा की ओर | Completed | 1496809.99 | 1431577.06 | 2023-10-05 | 2024-11-09
MORENA | 2012-2013 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Construction of Intermediate and Link Drains / Construction of intermediate and Link Storm Water Drain for Community | Works for Flood Control and Protection | 1701003113/FP/9977521438 — नाला निर्माण हरिजन बस्‍ती जेबराखेडा | Deleted | 0 | 0 | 2013-01-26
MORENA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Fisheries | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1701003113/FR/22012034323302 — तालाब निर्माण कार्य बलवीर के खेत के पास | Deleted | 0 | 0 | 2024-10-02
MORENA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Fisheries | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1701003113/FR/22012034324494 — तालाब निर्माण कार्य बलवीर के खेत के पास | New | 0 | 0 | 2024-10-03
MORENA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Micro Irrigation Works | Construction of water courses Canal for Community / Construction of water courses for Community | Construction of Canal | 1701003113/IC/22012034881509 — water corse nirman karya gp jewrakhera | Deleted | 0 | 0 | 2022-04-14
MORENA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Micro Irrigation Works | Construction of water courses Canal for Community / Construction of water courses for Community | Construction of Canal | 1701003113/IC/22012034881699 — water corse nirman karya gp jewrakhera | Closed | 277394.48 | 0 | 2022-08-30
MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701003113/IF/22012034344009 — vraksharopan karya | Completed | 335000 | 15278 | 2017-06-26 | 2020-12-10
MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1701003113/IF/22012034781760 — नाडेप सियाराम पुत्र गोधन सिंह जेवराखेड़ा | Completed | 18374.27 | 17164 | 2021-06-24 | 2022-07-18
MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1701003113/IF/22012034781767 — नाडेप अशोक पुत्र गोधन सिंह जेवराखेड़ा | Completed | 18374.27 | 17164 | 2021-06-24 | 2022-07-18
MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1701003113/IF/22012034835823 — nadep prabhu s/o godhan singh jewarakheda | Completed | 18552.12 | 16585 | 2021-11-23 | 2022-07-18
MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1701003113/IF/22012034835827 — nadep ramsebak s/o godan singh jewarakheda | Completed | 18552.12 | 16585 | 2021-11-23 | 2022-07-18
MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1701003113/IF/22012034835832 — nadep brajmohan s/o ramcharan jewarakheda | Completed | 18552.12 | 16585 | 2021-11-23 | 2022-07-18
MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1701003113/IF/22012034850458 — नाडेप निर्माण कार्य मुन्नी w/o भरत | Completed | 18552.12 | 16585 | 2021-11-23 | 2022-07-18
MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1701003113/IF/22012034850464 — नाडेप निर्माण कार्य बबिता w/o सतीश | Completed | 18552.12 | 16585 | 2021-11-23 | 2022-07-18
MORENA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1701003113/IF/22012035312478 — खेत तालाब निर्माण कार्य सत्यवीर के खेत मे | Approved | 0 | 0 | 2025-01-24
MORENA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1701003113/IF/22012035312481 — खेत तालाब निर्माण कार्य रामहेत के खेत मे | Deleted | 0 | 0 | 2025-01-24
MORENA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1701003113/IF/22012035312483 — खेत तालाब निर्माण कार्य अंगूरी के खेत मे | Approved | 0 | 0 | 2025-01-24
MORENA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1701003113/IF/22012035312485 — खेत तालाब निर्माण कार्य भूरा उर्फ नरेन्द्र के खेत मे | Approved | 0 | 0 | 2025-01-24
MORENA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1701003113/IF/22012035312487 — खेत तालाब निर्माण कार्य श्रीनिवास के खेत मे | Approved | 0 | 0 | 2025-01-24
MORENA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1701003113/IF/22012035312488 — खेत तालाब निर्माण कार्य धर्मेन्द्र के खेत मे | Approved | 0 | 0 | 2025-01-24
MORENA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1701003113/IF/22012035312493 — खेत तालाब निर्माण कार्य सुरेन्द्र के खेत मे | Approved | 0 | 0 | 2025-01-24
MORENA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1701003113/IF/22012035503211 — Khet Talab Nirmaan Karya Ramhet ke khet me | Closed | 147621.16 | 0 | 2025-05-13
MORENA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003113/IF/9993729872 — पशु शेड निर्माण कार्य केशव सिंह | Deleted | 0 | 0 | 2016-01-26
MORENA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003113/IF/IAY/119205 — Construction of IAY House -IAY REG. NO. MP-01-003-113-001/15 | Approved | 27000 | 0 | 2016-01-14
MORENA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003113/IF/IAY/119208 — Construction of IAY House -IAY REG. NO. MP-01-003-113-001/19 | Approved | 27000 | 0 | 2016-01-14
MORENA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003113/IF/IAY/1909332 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4805211 | Completed | 15660 | 15138 | 2018-11-02 | 2019-04-23
MORENA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003113/IF/IAY/199202 — Construction of IAY House -IAY REG. NO. MP-01-003-113-001/81 | Approved | 27000 | 0 | 2016-01-14
MORENA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003113/IF/IAY/199266 — Construction of IAY House -IAY REG. NO. MP-01-003-113-001/11 | Completed | 15030 | 14028 | 2017-01-02 | 2017-08-22
MORENA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003113/IF/IAY/4325368 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125304263 | Completed | 18360 | 18326 | 2022-09-13 | 2023-05-23
MORENA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003113/IF/IAY/4336297 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125304012 | Completed | 18360 | 18326 | 2022-09-13 | 2023-05-23
MORENA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701003113/LD/22012034951979 — पेरिफेरल स्टोन बण्ड निर्माण कार्य हरजन मौहल्ल बाबा साहेब की प्रतिमा पर | Deleted | 0 | 0 | 2025-01-24
MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701003113/LD/22012034952468 — पेरिफेरल स्टोन बण्ड निर्माण कार्य हरजन मौहल्ल बाबा साहेब की प्रतिमा पर | Ongoing | 1450518.84 | 261 | 2025-05-15
MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701003113/LD/22012034954197 — Periferal stone bund nirmaan karya shasakiya prathmik shala ke pass | Deleted | 0 | 0 | 2025-04-14
MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701003113/LD/22012034954198 — Periferal stone bund nirmaan karya shamshan ghaat ke pass | Approved | 0 | 0 | 2025-04-14
MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701003113/LD/22012034954261 — Periferal stone bund nirmaan karya shaskiya prathmik shala ke pass | Ongoing | 1479546.32 | 6264 | 2025-07-14
MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701003113/LD/22012034954262 — Periferal stone bund nirmaan karya shamshan ghaat ke pass | Ongoing | 1488766.19 | 12528 | 2025-07-14
MORENA | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003113/RC/01 — सीसी खरंजा निर्माण पंछी का पुरा | Completed | 96086 | 43468 | 2008-09-09 | 2009-05-29
MORENA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701003113/RC/1150 — मिटटी बजरी रोड डोंगरपुर रोड से संजय सिंह के पुरा त | Completed | 497000 | 239219 | 2012-06-04 | 2016-06-22
MORENA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003113/RC/1151 — सी सी खरंजा निर्माण जेवराखेडा | Completed | 0 | 154747 | 2012-04-03 | 2012-08-01
MORENA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003113/RC/22012034159628 — सीसी खरंजा एवं नाली निर्माण रामचरन के मकान से डोंगरपुर रोड की तरफ जेबराखेड्ा | Deleted | 0 | 0 | 2012-11-01
MORENA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003113/RC/22012034160574 — सीसी रोड एवं नाली निर्माण चामड माता से डोंगरपुर रोड तक जेबराखेडा | Deleted | 0 | 0 | 2013-01-26
MORENA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003113/RC/22012034160575 — सीसी खरंजा एवं नाली निर्माण रामहेत जाटव गली जेबराखेडा | Deleted | 0 | 0 | 2013-01-26
MORENA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003113/RC/22012034160576 — सीसी खरंजा एवं नाली निर्माण बीच के कुआ से हनुमान मंदिर तक जेबराखेडा | Deleted | 0 | 0 | 2013-01-26
MORENA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003113/RC/22012034160577 — सीसी खरंजा एवं नाली निर्माण जाटव मोहल्‍ला जेबराखेडा | Deleted | 0 | 0 | 2013-01-26
MORENA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701003113/RC/22012034160578 — पत्‍थर खरंजा निर्माण डोंगरपुर रोड से शान्‍तीधाम तक जेबराखेडा | Deleted | 0 | 0 | 2013-01-26
MORENA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003113/RC/22012034162446 — सीसी खरंजा एवं नाली निर्माण कार्य रामचरन के मकान स | Completed | 39232 | 36295 | 2013-04-15 | 2013-12-30
MORENA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003113/RC/22012034200037 — सी. सी. खरंजा एंव नाली निर्माण - हरेश के मकान से र | Completed | 100666 | 92892 | 2014-02-05 | 2015-05-20
MORENA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701003113/RC/22012034206059 — पत्थर खरंजा निर्माण - रामखत्यार के मकान से रामक्षान के पुरा तक जेबराखेडा | Completed | 295000 | 81900 | 2014-03-04 | 2016-09-19
MORENA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701003113/RC/22012034293837 — मिटटी मुरम बजरी रोड निर्माण - मुडियाखेरा रोड से जेबराखेरा रोड तक | Completed | 1189000 | 127041 | 2015-12-25 | 2016-09-19
MORENA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003113/RC/22012034297198 — सी सी खरंजा एवं नाली निर्माण - लच्‍छी के मकान से हनुमान मंदिर तक कुशवाह मौहल्‍ला | Deleted | 72000 | 0 | 2016-01-15
MORENA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701003113/RC/22012034297291 — पत्‍थर खरंजा निर्माण - सरदार के मकान से डोंगरपुर रोड तक | Deleted | 74000 | 0 | 2016-01-15
MORENA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003113/RC/22012034309796 — सी सी खरंजा निर्माण कार्य उप स्वास्थ केंद्र से उत्तम पटेल के मकान | Deleted | 0 | 0 | 2016-01-26
MORENA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003113/RC/22012034327221 — सी सी खरजा एब नाली निर्माण कार्य रामस्वरूप के मकान से रामविलास के मकान तक | Completed | 76950 | 73194 | 2017-02-16 | 2017-11-22
MORENA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701003113/RC/22012034340044 — सुदूर ग्राम संपर्क सड्क जेबराखेडा बिजलीघर से श्रीनिवास के मकान तक अम्‍बाह रोड | Completed | 1100000 | 845001.17 | 2017-06-01 | 2018-11-08
MORENA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003113/RC/22012034342525 — सी सी खरंजा एवं नाली निर्माण कार्य - शिवजी के मकान से शिवचरन के मकान तक जेबराखेडा | Completed | 95000 | 101136 | 2017-08-28 | 2017-11-22
MORENA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003113/RC/22012034351501 — सी सी खरंजा एवं नाली निर्माण कार्य - रामखत्यार के मकान से रामज्ञान के मकान तक जेबराखेरा | Completed | 88000 | 86516 | 2017-09-21 | 2018-04-04
MORENA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003113/RC/22012034371808 — सी.सी.खरंजा निर्माण कार्य सियाराम के मकान से रामसेवक के मकान तक | Deleted | 82500 | 0 | 2017-04-01
MORENA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003113/RC/22012034385512 — c.c.kharanja nirmaan karya siyaram ke makaan se ramsevak ke makaan tak | Completed | 94000 | 94830 | 2018-04-21 | 2018-06-30
MORENA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003113/RC/22012034441605 — c c kharanja & nali nirman karya- vishal ke makan se sanjay ki chakki tak jewarakheda | Completed | 40950 | 40812 | 2019-03-08 | 2019-09-18
MORENA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003113/RC/22012034445247 — c c kharanja & nali nirman-vishal singh ke makan se ramotar kushwah ke makan tak | Completed | 28665 | 28492 | 2019-03-05 | 2019-04-25
MORENA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003113/RC/22012034473787 — सी.सी. खरंजा एवं नाली निर्माण कार्य - वासुदेव के मकान से किलोल के मकान तक, जेबराखेडा | Completed | 43200 | 42944 | 2019-08-31 | 2019-10-21
MORENA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003113/RC/22012034473788 — सी.सी. खरंजा एवं नाली निर्माण कार्य - कप्तान के मकान से चिम्मन के मकान तक, पंछी का पुरा | Completed | 43200 | 42768 | 2019-08-31 | 2019-10-15
MORENA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003113/RC/22012034523285 — सी.सी. खरंजा एवं नाली निर्माण कार्य मैनरोड से शिवकुमार के मकान एवं कमल सिंह के मकान से मुनेश के मकान | Completed | 81450 | 84360 | 2020-06-18 | 2020-08-15
MORENA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701003113/RC/22012034534218 — सुदूर ग्राम /खेत सड़क पंछी का पुरा से माधो का पुरा जेवरा खेड़ा | Completed | 2020706.56 | 933068.61 | 2020-09-27 | 2022-05-27
MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003113/RC/22012034582440 — सी. सी. रोड एवं नाली निर्माण कार्य प्राथमिक विद्यालय से प्राथमिक स्वास्थ केंद्र से बदले के हनुमान मं | Completed | 63150 | 67164 | 2021-09-23 | 2021-11-21
MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003113/RC/22012034582446 — सी. सी. रोड एवं नाली निर्माण कार्य बिजली घर से प्रेमसिंघ के घर तक जिगनी रोड तक जेवराखेड़ा | Deleted | 0 | 0 | 2021-04-14
MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003113/RC/22012034582447 — सी. सी. रोड एवं नाली निर्माण कार्य बिजली घर से प्रेमसिंघ के घर तक जिगनी रोड तक जेवराखेड़ा | Deleted | 0 | 0 | 2021-04-14
MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003113/RC/22012034582943 — सी सी खरंजा एवं नाली निर्माण बिजली घर से प्रेम सिंह के घर तक जीगनी रोड | Completed | 42150 | 42074 | 2021-09-23 | 2021-12-26
MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Repair & maint of Mitti Murram Roads for Comm / Repair and maintenance of Mitti Murram Roads for Community | Repair & maint of Road | 1701003113/RC/22012034584356 — सड़क मरम्मत कार्य जेवराखेड़ा से जिगनी रोड़ तक | Completed | 87654.07 | 86180.15 | 2021-11-08 | 2023-02-28
MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003113/RC/22012034584914 — सी. सी. खरंजा एवं नाली निर्माण सामुदायिक भवन अम्बेडकरपार्क तक जेवराखेड़ा | Completed | 40725 | 39372 | 2021-10-07 | 2021-12-01
MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003113/RC/22012034587043 — सी . सी. खरंजा एवं नाली कार्य अशोक के मकान से प्रभु के मकान तक | Completed | 40725 | 40530 | 2021-10-21 | 2021-12-03
MORENA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003113/RC/22012034643248 — सी.सी. खरंजा एवम नाली निर्माण कार्य राधेश्याम कुशवाह की डी पी से राहुल कुशवाह की ओर पंछी का पुरा | Completed | 34277 | 28509 | 2023-07-19 | 2024-02-27
MORENA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003113/RC/22012034643250 — सीसी खरंजा एवम नाली निर्माण कार्य सूरज जाटव की दूकान सेचामण माता की और | Completed | 36081 | 36023 | 2023-07-21 | 2023-10-25
MORENA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701003113/RC/22012034644659 — सुदूर खेत सड़क निर्माण कार्य रामसेवक के मकान से द्वारिका के ट्यूबबेल तक | Completed | 2493899.13 | 2427410.85 | 2023-07-21 | 2024-11-09
MORENA | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Metal Second coat / Construction of WBM Roads for Community | Construction of Road and Culvert | 1701003113/RC/440 — पत्‍थर खरजा निर्माण कार्य जेवराखेडा मुरैना | Completed | 0 | 81059 | 2010-02-02 | 2010-03-27
MORENA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1701003113/RS/22012035136784 — सामुदायिक स्वच्छता परिसर निर्माण कार्य जेबराखेडा | Ongoing | 81037 | 24237 | 2025-03-27
MORENA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003113/WC/01 — सोख्‍ता गडडा ईजीएस शाला पंछीपुरा | Completed | 11200 | 5432.3 | 2008-06-10 | 2009-05-29
MORENA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003113/WC/22012034432271 — नवीन तालाब निर्माण कार्य - | Closed | 0 | 0 | 2019-01-26
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701003113/WC/22012034739984 — सोक पिट शा प्रा वि पंछी का पुरा जेबराखेडा | Closed | 18382.8 | 0 | 2021-04-15
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701003113/WC/22012034740077 — सोक पिट शा प्रा वि जेवराखेड़ा | Closed | 18382.8 | 0 | 2021-04-15
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701003113/WC/22012034740089 — सोक पिट आगनवाडी भवन जेवराखेड़ा | Closed | 18382.8 | 0 | 2021-04-15
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701003113/WC/22012034740115 — सोक पिट बिजली घर के पास जेवराखेड़ा | Closed | 18382.8 | 0 | 2021-04-15
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701003113/WC/22012034743201 — सोक पिट सुरेश पुत्र बदले जेवराखेड़ा | Closed | 18382.8 | 0 | 2021-04-15
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003113/WC/22012035097857 — रपटा निर्माण कार्य तालाब के पास कुशवाह मौहल्ला जेबराखेडा | Completed | 1461745.37 | 1438579.72 | 2023-10-03 | 2026-01-06
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003113/WC/22012035101465 — रपटा निर्माण कार्य बिजली घर के तालाब के पास | Completed | 1415814.9 | 1387822 | 2023-10-05 | 2025-12-11
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003113/WC/22012035123366 — रपटा निर्माण कार्य मुडियाखेडा जेबराखेडा रोड सभाराम जाटव के पास | Completed | 1487606.38 | 1402105.72 | 2023-10-06 | 2026-01-13
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1701003113/WC/22012035162026 — रपटा निर्माण कार्य प्रहलाद के खेत के पास | Deleted | 0 | 0 | 2023-10-02
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1701003113/WC/22012035162030 — रपटा निर्माण कार्य रामपदम के कुआ रोड | Deleted | 0 | 0 | 2023-10-02
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone boulder Gully Plugs for Comm / Construction of Stone boulder Gully Plugs for Community | Boulder Check/Gully Plug | 1701003113/WC/22012035162036 — रपटा निर्माण कार्य श्रीनिवास के खेत | Deleted | 0 | 0 | 2023-10-02
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone boulder Gully Plugs for Comm / Construction of Stone boulder Gully Plugs for Community | Boulder Check/Gully Plug | 1701003113/WC/22012035162044 — रपटा निर्माण कार्य नेता जाटव के खेत के पास | Deleted | 0 | 0 | 2023-10-02
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701003113/WC/22012035162053 — रपटा निर्माण कार्य शमसान रोड के पास | Deleted | 0 | 0 | 2023-10-02
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701003113/WC/22012035167328 — रपटा निर्माण कार्य प्रहलाद के खेत के पास | Deleted | 0 | 0 | 2023-10-02
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1701003113/WC/22012035167329 — रपटा निर्माण कार्य रामपदम के कुआ रोड | Physically Completed | 1480742.36 | 1440172.16 | 2024-03-12 | 2026-05-20
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Pebble peripheral Bund for Community / Construction of Pebble peripheral/farm/field Bund for Community | Construction of Bund | 1701003113/WC/22012035167612 — रपटा निर्माण कार्य श्रीनिवास के खेत के पास | Deleted | 0 | 0 | 2023-10-02
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701003113/WC/22012035167618 — रपटा निर्माण कार्य श्रीनिवास के खेत के पास | Closed | 0 | 0 | 2023-10-02
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701003113/WC/22012035178631 — रपटा निमार्ण कार्य धीरज के खेत के पास | Physically Completed | 1464388.34 | 1400930.46 | 2024-03-12 | 2026-05-20
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701003113/WC/22012035178638 — रपटा निमार्ण कार्य ताल के पास | Deleted | 0 | 0 | 2024-01-24
MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701003113/WC/22012035178660 — रपटा निमार्ण कार्य शिव जी के खेत के पास | Physically Completed | 1480742.36 | 1143800.21 | 2024-03-13 | 2026-06-09
MORENA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701003113/WC/22012035224114 — परकुलेशन टैंक निर्माण कार्य बलवीर के खेत के पास | Deleted | 0 | 0 | 2024-10-02
MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1701003113/WC/22012035295988 — Dugwell recharge pit nirmaan karya rampadam ke khet ke pass kua | Ongoing | 25899.46 | 10179 | 2025-05-07
MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1701003113/WC/22012035295997 — Dugwell recharge pit nirmaan karya dharmendra ke khet ke pass kua | Ongoing | 25899.46 | 7569 | 2025-05-07
MORENA | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003113/WC/242 — नवीन प्रा.शा.सोख्‍ता गडडा निर्माण कार्य | Completed | 0 | 10788 | 2009-08-08 | 2009-11-02
MORENA | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1701003113/WH/19963345 — तालाब मरम्‍मत कार्य - जेबराखेडा | Completed | 83000 | 76024 | 2017-06-08 | 2017-11-22
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1701003113/WH/22012034452214 — तालाब जीर्णोद्धार बिजली घर के पास जेवरा खेडा | Deleted | 0 | 0 | 2021-10-02
MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1701003113/WH/22012034452215 — जीर्णोद्धार टेका वाली पोखर जेवरा खेडा | Deleted | 0 | 0 | 2021-10-02
MORENA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1701003113/WH/22012034921469 — तालाब मरमत कार्य टेका पाती पोखर पंछी का पुरा | Completed | 279991 | 205836 | 2022-05-05 | 2022-11-17
MORENA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation of Fisheries Ponds for Community / Renovation of Fisheries Ponds for Community | Repair & maint of Pond/ Tank | 1701003113/WH/22012034921475 — तालाब मरमत कार्यबिजली घर के पास | Completed | 105942 | 86700 | 2022-05-02 | 2022-11-17
MORENA | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701/RC/22012034151729 — mitti grawal road Dongarpurkirar road se panchi ka pura morena | Deleted | 879000 | 0 | 2010-05-01