## Work List
Exported on: 2026-10-20 20:02:09
Filters applied:
Data source: MGNREGA + VBGRAMG
District: MORENA
Block: All
Panchayat: ITAWALI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
JOURA | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1701005038/AV/22012034375268 — Shanti dam nirman rajsw gram kemari | Completed | 245000 | 213746.68 | 2018-08-23 | 2020-06-06
JOURA | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1701005038/AV/22012034375282 — Shanti dam nirman jaggupura itawali | Completed | 245000 | 234856.7 | 2018-08-23 | 2020-06-06
JOURA | 2013-2014 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Bharat Nirman Seva Kendra / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1701005038/AV/22012034392302 — Rajeev gandi seva kendra itawali | Deleted | 1000000 | 0 | 2013-04-14
JOURA | 2019-2020 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1701005038/AV/22012034399269 — शांतिधाम निर्माण - इटावली के राजस्‍व ग्राम मुरहान में | Completed | 245000 | 230321.06 | 2019-08-24 | 2020-02-15
JOURA | 2019-2020 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1701005038/AV/22012034399270 — शांतिधाम निर्माण - ग्राम बघेल, इटावली | Completed | 245000 | 225041.06 | 2019-08-24 | 2020-02-15
JOURA | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1701005038/AV/22012034568765 — Shantidham Nirman kary Baghel Basti Itawali | Completed | 287491.74 | 251036.79 | 2021-10-06 | 2022-04-11
JOURA | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1701005038/AV/22012034568780 — Shantidham Nirman kary Gram Gupha | Completed | 287491.74 | 248687.14 | 2021-10-06 | 2023-07-04
JOURA | 2025-2026 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1701005038/AV/22012034666711 — shanti dham nirman karya teen sed avm chabutra bagbala itawali | Deleted | 0 | 0 | 2025-04-14
JOURA | 2025-2026 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1701005038/AV/22012034666712 — shanti dham teensed avm chabutra nirman ranaju bala itawali | Deleted | 0 | 0 | 2025-04-14
JOURA | 2026-2027 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1701005038/AV/22012034666809 — shanti dham nirman teen sed avm chabutra bag bale itawali | Ongoing | 351835.22 | 0 | 2025-04-14
JOURA | 2025-2026 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1701005038/AV/22012034666810 — shanti dham nirman teen sed avm chabutra rana ju bala itawali | Approved | 372180.63 | 0 | 2025-04-14
JOURA | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701005038/DP/104 — वक्षारोपड कार्य इटावली | Completed | 0 | 10300 | 2009-11-11 | 2011-01-16
JOURA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1701005038/DP/150 — शान्‍तीधाम एंव वाउन्‍डीपाल निर्माण | Completed | 0 | 418648.54 | 2011-11-08 | 2012-08-27
JOURA | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Land development / Levelling/shaping of Wasteland Land for Community | Land Development | 1701005038/DP/22012034238471 — shantidham Nirman | Deleted | 0 | 0 | 2017-01-26
JOURA | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1701005038/DP/22012034238677 — शान्तीधाम निर्माण केमारी | Deleted | 180000 | 0 | 2017-03-11
JOURA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1701005038/DP/22012034557403 — बृक्षारोपण कार्य अमृत सरोवर नवीन तालाब झुनिया वाली नरी के पास ईटावली | Deleted | 0 | 0 | 2022-04-14
JOURA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1701005038/DP/22012034557406 — बृक्षारोपण कार्य अमृत सरोवर तालाब कुशवाह वाली नारी पर ईटावली | Deleted | 0 | 0 | 2022-04-14
JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Coastal Afforestation using forstry Trees for Comm / Plantation in Coastal Area for Community | Plantation | 1701005038/DP/22012034620532 — Vraksharopan Karya Amritsararovar ke pass itawali | Approved | 0 | 0 | 2024-06-26
JOURA | 2013-2014 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1701005038/DP/9926697962 — शांतीधाम निर्माण कार्य ठेहागिर्द | Completed | 461000 | 61320 | 2013-09-07 | 2018-08-08
JOURA | 2017-2018 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701005038/FP/22012034360160 — Nala nirman vijay singh ke makan se itawali | Completed | 1187000 | 1110802.08 | 2017-11-04 | 2018-12-02
JOURA | 2018-2019 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701005038/FP/22012034362321 — पत्थर नाला निर्माण कार्य इटावली | Deleted | 0 | 0 | 2018-10-02
JOURA | 2018-2019 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701005038/FP/22012034362774 — nali nirman karya itawali | Deleted | 1135000 | 0 | 2019-03-03
JOURA | 2018-2019 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Repair & maint of Diversn Strm Watr Drain for Comm / Repair and maintenance of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701005038/FP/22012034362784 — नाला निर्माण - बालो के मकान से शमशान होते हुऐ इटावाली | Completed | 1135220 | 1112616.58 | 2019-03-04 | 2020-06-06
JOURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Well for Community | Construction of Well | 1701005038/IC/22012034891556 — khet talab nirman indrveer singh | New | 0 | 0 | 2025-04-14
JOURA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701005038/IF/22012034349687 — सार्वजनिक परिषर वृक्षारोपण कार्य शा. प्रा. स्कूल जग्गू का पूरा ईटावली | Completed | 335000 | 25078.5 | 2017-07-28 | 2020-09-30
JOURA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701005038/IF/22012034368764 — वृक्ष रोपण कार्यं हनुमान मंदिर के पास | Deleted | 335000 | 0 | 2017-08-05
JOURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1701005038/IF/22012035370629 — khet talab nirman deelip gurjar ke khet me itawali | New | 0 | 0 | 2025-04-14
JOURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1701005038/IF/22012035371547 — khet talab nirman deelip gurjar ke khet me | Completed | 269723.85 | 187654.35 | 2025-04-26 | 2026-05-08
JOURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1701005038/IF/22012035371609 — khet talab nirman ramesh ke khet me | Completed | 269723.85 | 187915.92 | 2025-04-26 | 2026-05-05
JOURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1701005038/IF/22012035506917 — khet talab nirman indarveer singh gurjar itawali | New | 0 | 0 | 2025-04-14
JOURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1701005038/IF/22012035506986 — khet talab nirman indrveer singh itawali | New | 0 | 0 | 2025-04-14
JOURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1701005038/IF/22012035507001 — khet talab nirman indrveer singh itawali | Approved | 238159.3 | 0 | 2025-04-14
JOURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1701005038/IF/22012035507014 — khet talab nirman natthi ke khet me itawali | Approved | 237718.98 | 0 | 2025-04-14
JOURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1701005038/IF/22012035507039 — khet talab nirman laxminaryan ke khet me itawali | Approved | 237718.98 | 0 | 2025-04-14
JOURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1701005038/IF/22012035633580 — EK BAGIYA MAA KE NAAM SHEELA MP-01-005-038-001/1146 | Ongoing | 282818.64 | 3129.96 | 2025-11-10
JOURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1701005038/IF/22012035633591 — EK BAGIYA MAA KE NAAM SHRIMATI MP-01-005-038-001/510 | Ongoing | 282818.64 | 3129.96 | 2025-11-10
JOURA | 2011-2012 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1701005038/IF/63 — मेड बधान रामप्रकाश्‍ा / रामदीन | Completed | 0 | 15494 | 2011-06-01 | 2011-06-26
JOURA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005038/IF/IAY/1128814 — Construction of IAY House -IAY REG. NO. MP2286038 | Completed | 15480 | 15480 | 2017-09-30 | 2018-04-02
JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005038/IF/IAY/1532483 — Construction of IAY House -IAY REG. NO. MP2490143 | Completed | 15480 | 15660 | 2019-01-05 | 2019-02-13
JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005038/IF/IAY/1532612 — Construction of IAY House -IAY REG. NO. MP2508079 | Completed | 15480 | 15660 | 2018-12-15 | 2018-12-25
JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005038/IF/IAY/1532653 — Construction of IAY House -IAY REG. NO. MP2520729 | Completed | 15480 | 15660 | 2019-01-06 | 2019-02-13
JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005038/IF/IAY/1532654 — Construction of IAY House -IAY REG. NO. MP2520757 | Completed | 15480 | 15660 | 2018-12-15 | 2018-12-25
JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005038/IF/IAY/1532655 — Construction of IAY House -IAY REG. NO. MP2520777 | Completed | 15480 | 15660 | 2019-01-06 | 2019-02-13
JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005038/IF/IAY/1532667 — Construction of IAY House -IAY REG. NO. MP2524227 | Completed | 15480 | 15660 | 2019-02-27 | 2019-03-07
JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005038/IF/IAY/1532668 — Construction of IAY House -IAY REG. NO. MP2524611 | Completed | 15480 | 15660 | 2019-02-27 | 2019-03-07
JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005038/IF/IAY/1532669 — Construction of IAY House -IAY REG. NO. MP2524616 | Completed | 15480 | 15660 | 2019-01-06 | 2019-02-13
JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005038/IF/IAY/1532675 — Construction of IAY House -IAY REG. NO. MP2526320 | Completed | 15480 | 15660 | 2018-12-15 | 2018-12-25
JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005038/IF/IAY/1532734 — Construction of IAY House -IAY REG. NO. MP2554248 | Completed | 15480 | 15660 | 2018-12-28 | 2019-01-06
JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005038/IF/IAY/1532755 — Construction of IAY House -IAY REG. NO. MP2560861 | Completed | 15480 | 15660 | 2019-02-20 | 2019-03-07
JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005038/IF/IAY/1532767 — Construction of IAY House -IAY REG. NO. MP2564030 | Completed | 15480 | 15660 | 2019-02-13 | 2019-03-29
JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005038/IF/IAY/1532823 — Construction of IAY House -IAY REG. NO. MP2583121 | Completed | 15480 | 15660 | 2019-02-13 | 2019-02-23
JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005038/IF/IAY/1533408 — Construction of IAY House -IAY REG. NO. MP2811994 | Completed | 15480 | 15834 | 2018-12-15 | 2018-12-25
JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005038/IF/IAY/1533433 — Construction of IAY House -IAY REG. NO. MP2817031 | Completed | 15480 | 15660 | 2018-12-15 | 2018-12-25
JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005038/IF/IAY/1533439 — Construction of IAY House -IAY REG. NO. MP2817806 | Completed | 15480 | 15660 | 2018-12-15 | 2019-02-23
JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005038/IF/IAY/1533575 — Construction of IAY House -IAY REG. NO. MP2873894 | Completed | 15480 | 15660 | 2018-12-15 | 2018-12-25
JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005038/IF/IAY/1533614 — Construction of IAY House -IAY REG. NO. MP2888183 | Completed | 15480 | 15660 | 2019-02-20 | 2019-02-26
JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005038/IF/IAY/1533621 — Construction of IAY House -IAY REG. NO. MP2891865 | Completed | 15480 | 15660 | 2019-01-06 | 2019-02-13
JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005038/IF/IAY/1535277 — Construction of IAY House -IAY REG. NO. MP3535372 | Completed | 15480 | 15660 | 2018-09-21 | 2019-02-23
JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005038/IF/IAY/1535388 — Construction of IAY House -IAY REG. NO. MP3580780 | Completed | 15480 | 22968 | 2018-09-21 | 2018-12-31
JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005038/IF/IAY/1536293 — Construction of IAY House -IAY REG. NO. MP3671105 | Completed | 15480 | 22968 | 2018-12-07 | 2018-12-31
JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005038/IF/IAY/1536959 — Construction of IAY House -IAY REG. NO. MP3825675 | Completed | 15480 | 14616 | 2019-02-06 | 2019-02-13
JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005038/IF/IAY/1536960 — Construction of IAY House -IAY REG. NO. MP3825683 | Completed | 15480 | 15660 | 2019-01-06 | 2019-02-13
JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005038/IF/IAY/1537067 — Construction of IAY House -IAY REG. NO. MP3671080 | Completed | 15480 | 17748 | 2018-11-16 | 2018-12-06
JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005038/IF/IAY/1537912 — Construction of IAY House -IAY REG. NO. MP3838053 | Completed | 15480 | 15660 | 2018-12-07 | 2019-02-13
JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005038/IF/IAY/1537946 — Construction of IAY House -IAY REG. NO. MP3860392 | Completed | 15480 | 15660 | 2019-01-06 | 2019-02-13
JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005038/IF/IAY/1564869 — Construction of IAY House -IAY REG. NO. MP2507994 | Completed | 15480 | 15660 | 2018-12-28 | 2019-01-12
JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005038/IF/IAY/1564932 — Construction of IAY House -IAY REG. NO. MP2524018 | Completed | 15480 | 15684 | 2019-03-11 | 2019-04-21
JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005038/IF/IAY/1565963 — Construction of IAY House -IAY REG. NO. MP2825339 | Completed | 15480 | 15660 | 2018-11-23 | 2018-12-31
JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005038/IF/IAY/1566215 — Construction of IAY House -IAY REG. NO. MP2892614 | Completed | 15480 | 15312 | 2019-01-06 | 2019-02-13
JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005038/IF/IAY/1568178 — Construction of IAY House -IAY REG. NO. MP3521237 | Completed | 15480 | 15660 | 2018-09-21 | 2019-02-13
JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005038/IF/IAY/1569109 — Construction of IAY House -IAY REG. NO. MP3723317 | Completed | 15480 | 15660 | 2019-01-04 | 2019-01-12
JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005038/IF/IAY/1569622 — Construction of IAY House -IAY REG. NO. MP3835160 | Completed | 15480 | 15660 | 2019-01-11 | 2019-01-20
JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005038/IF/IAY/1813465 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2825319 | Completed | 15660 | 15660 | 2018-11-16 | 2019-02-13
JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005038/IF/IAY/1813483 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2861161 | Completed | 15660 | 15660 | 2018-12-07 | 2019-01-20
JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005038/IF/IAY/1814089 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3637690 | Completed | 15660 | 15660 | 2018-12-21 | 2019-01-04
JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005038/IF/IAY/1814194 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3834842 | Completed | 15660 | 18792 | 2018-12-07 | 2018-12-31
JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005038/IF/IAY/1907882 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5508003 | Completed | 15660 | 15660 | 2019-01-06 | 2019-02-13
JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005038/IF/IAY/1910955 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4642156 | Completed | 15660 | 15660 | 2019-01-06 | 2019-02-13
JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005038/IF/IAY/1910956 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4642609 | Completed | 15660 | 15660 | 2019-01-06 | 2019-02-13
JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005038/IF/IAY/1910966 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4664153 | Completed | 15660 | 15660 | 2019-01-06 | 2019-02-13
JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005038/IF/IAY/1923715 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4600357 | Completed | 15660 | 15660 | 2019-01-06 | 2019-02-13
JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005038/IF/IAY/1924820 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5155058 | Completed | 15660 | 15660 | 2019-01-06 | 2019-02-13
JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005038/IF/IAY/193304 — Construction of IAY House -IAY REG. NO. MP-01-005-038-003/015 | Completed | 14310 | 15660 | 2018-10-11 | 2018-10-20
JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005038/IF/IAY/193305 — Construction of IAY House -IAY REG. NO. MP-01-005-038-003/05 | Completed | 14310 | 15660 | 2018-10-11 | 2018-10-20
JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005038/IF/IAY/193306 — Construction of IAY House -IAY REG. NO. MP-01-005-038-003/06 | Completed | 14310 | 15660 | 2018-10-11 | 2018-10-20
JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005038/IF/IAY/193307 — Construction of IAY House -IAY REG. NO. MP-01-005-038-003/08 | Completed | 14310 | 15660 | 2018-10-11 | 2018-10-20
JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005038/IF/IAY/193308 — Construction of IAY House -IAY REG. NO. MP-01-005-038-003/14 | Completed | 14310 | 15660 | 2018-10-11 | 2018-10-20
JOURA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005038/IF/IAY/3222186 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4262505 | Completed | 17370 | 3474 | 2021-10-20 | 2023-07-10
JOURA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005038/IF/IAY/420150 — Construction of IAY House -IAY REG. NO. MP1328119 | Completed | 15030 | 16452 | 2017-02-11 | 2018-04-04
JOURA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005038/IF/IAY/445997 — Construction of IAY House -IAY REG. NO. MP1518004 | Completed | 15030 | 14388 | 2017-02-25 | 2018-04-04
JOURA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005038/IF/IAY/517614 — Construction of IAY House -IAY REG. NO. MP2499870 | Completed | 15030 | 16452 | 2017-02-25 | 2018-04-04
JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005038/IF/IAY/52791 — Construction of IAY House -IAY REG. NO. MP-01-005-038-003/03 | Completed | 14310 | 15660 | 2018-10-11 | 2018-10-20
JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005038/IF/IAY/52825 — Construction of IAY House -IAY REG. NO. MP-01-005-038-003/23 | Completed | 14310 | 13572 | 2018-10-11 | 2018-10-17
JOURA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005038/IF/IAY/596122 — Construction of IAY House -IAY REG. NO. MP1559684 | Completed | 15030 | 15420 | 2017-02-25 | 2018-04-04
JOURA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005038/IF/IAY/596287 — Construction of IAY House -IAY REG. NO. MP1859106 | Completed | 15030 | 17484 | 2017-02-11 | 2018-04-04
JOURA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005038/IF/IAY/618157 — Construction of IAY House -IAY REG. NO. MP3415279 | Completed | 15030 | 16482 | 2017-03-04 | 2018-04-04
JOURA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005038/IF/IAY/625705 — Construction of IAY House -IAY REG. NO. MP2274283 | Completed | 15030 | 15480 | 2017-03-04 | 2018-04-04
JOURA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005038/IF/IAY/696030 — Construction of IAY House -IAY REG. NO. MP1375014 | Deleted | 15030 | 0 | 2017-03-04
JOURA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005038/IF/IAY/696573 — Construction of IAY House -IAY REG. NO. MP1381409 | Completed | 15030 | 15480 | 2017-09-30 | 2018-04-04
JOURA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005038/IF/IAY/739012 — Construction of IAY House -IAY REG. NO. MP2203524 | Completed | 15030 | 15480 | 2017-09-30 | 2018-04-04
JOURA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005038/IF/IAY/742117 — Construction of IAY House -IAY REG. NO. MP2289733 | Completed | 15030 | 15540 | 2017-09-30 | 2018-05-15
JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005038/IF/IAY/742586 — Construction of IAY House -IAY REG. NO. MP2302574 | Completed | 15030 | 14616 | 2018-07-19 | 2018-08-04
JOURA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005038/IF/IAY/743545 — Construction of IAY House -IAY REG. NO. MP2332438 | Completed | 15030 | 15492 | 2017-09-30 | 2018-05-15
JOURA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005038/IF/IAY/743551 — Construction of IAY House -IAY REG. NO. MP2332547 | Completed | 15030 | 16340 | 2017-10-31 | 2018-04-04
JOURA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005038/IF/IAY/743561 — Construction of IAY House -IAY REG. NO. MP2332783 | Completed | 15030 | 15308 | 2017-10-31 | 2018-04-04
JOURA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005038/IF/IAY/744237 — Construction of IAY House -IAY REG. NO. MP2351537 | Completed | 15030 | 15308 | 2017-10-31 | 2018-06-15
JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005038/IF/IAY/744263 — Construction of IAY House -IAY REG. NO. MP2352162 | Completed | 15030 | 14616 | 2018-07-28 | 2018-08-10
JOURA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005038/IF/IAY/745140 — Construction of IAY House -IAY REG. NO. MP2375979 | Completed | 15030 | 15308 | 2017-10-31 | 2018-06-15
JOURA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005038/IF/IAY/745143 — Construction of IAY House -IAY REG. NO. MP2376015 | Completed | 15030 | 15308 | 2017-10-31 | 2018-06-15
JOURA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005038/IF/IAY/746383 — Construction of IAY House -IAY REG. NO. MP2412900 | Completed | 15030 | 15308 | 2017-10-31 | 2018-06-15
JOURA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005038/IF/IAY/746455 — Construction of IAY House -IAY REG. NO. MP2414394 | Completed | 15030 | 15308 | 2017-10-31 | 2018-06-15
JOURA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005038/IF/IAY/747230 — Construction of IAY House -IAY REG. NO. MP2443225 | Completed | 15030 | 15308 | 2017-10-31 | 2018-06-15
JOURA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005038/IF/IAY/748160 — Construction of IAY House -IAY REG. NO. MP2472103 | Completed | 15030 | 15332 | 2017-10-31 | 2018-05-15
JOURA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005038/IF/IAY/748176 — Construction of IAY House -IAY REG. NO. MP2472545 | Completed | 15030 | 14964 | 2017-10-31 | 2018-07-08
JOURA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005038/IF/IAY/748381 — Construction of IAY House -IAY REG. NO. MP2478522 | Completed | 15030 | 15172 | 2017-10-31 | 2018-06-15
JOURA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005038/IF/IAY/748396 — Construction of IAY House -IAY REG. NO. MP2478833 | Completed | 15030 | 15308 | 2017-10-31 | 2018-06-15
JOURA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005038/IF/IAY/756270 — Construction of IAY House -IAY REG. NO. MP2786533 | Completed | 15030 | 15308 | 2017-10-31 | 2018-06-15
JOURA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005038/IF/IAY/757120 — Construction of IAY House -IAY REG. NO. MP2826721 | Completed | 15030 | 10148 | 2017-10-31 | 2018-08-04
JOURA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005038/IF/IAY/757311 — Construction of IAY House -IAY REG. NO. MP2834422 | Completed | 15030 | 15476 | 2017-10-31 | 2018-05-15
JOURA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005038/IF/IAY/757856 — Construction of IAY House -IAY REG. NO. MP2860836 | Completed | 15030 | 15320 | 2017-10-31 | 2018-05-15
JOURA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005038/IF/IAY/776101 — Construction of IAY House -IAY REG. NO. MP3739653 | Completed | 15030 | 15308 | 2017-10-31 | 2018-06-15
JOURA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005038/IF/IAY/910107 — Construction of IAY House -IAY REG. NO. MP2277735 | Completed | 15480 | 14432 | 2017-10-31 | 2018-07-25
JOURA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005038/IF/IAY/911287 — Construction of IAY House -IAY REG. NO. MP2293450 | Completed | 15480 | 12344 | 2017-10-31 | 2018-07-24
JOURA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005038/IF/IAY/911611 — Construction of IAY House -IAY REG. NO. MP2297927 | Completed | 15480 | 14432 | 2017-10-31 | 2018-07-25
JOURA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005038/IF/IAY/911639 — Construction of IAY House -IAY REG. NO. MP2298310 | Completed | 15480 | 15476 | 2017-10-31 | 2018-05-15
JOURA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005038/IF/IAY/911737 — Construction of IAY House -IAY REG. NO. MP2299678 | Completed | 15480 | 15476 | 2017-10-31 | 2018-05-15
JOURA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701005038/LD/190 — मेड वंधान परसोत्‍म / करना | Completed | 0 | 17500 | 2010-08-22 | 2010-09-23
JOURA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701005038/LD/191 — श्रीपति / करना मेड वंधान | Completed | 0 | 18000 | 2010-08-24 | 2010-09-23
JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701005038/LD/22012034951340 — periferal ston bund m s school kemari | Physically Completed | 1467726.36 | 1405322.67 | 2025-07-23 | 2026-05-26
JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701005038/LD/22012034951341 — periferal ston bund kali mata mandir kemari | Physically Completed | 1455450.47 | 1389593.69 | 2025-08-06 | 2026-05-23
JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701005038/LD/22012034951342 — periferal ston bund babu baba mandir mandir kemari | Physically Completed | 1430982.62 | 1376625.29 | 2025-08-06 | 2026-05-24
JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701005038/LD/22012034951343 — periferal ston bund shanti dham muran | Physically Completed | 1418622.76 | 1372076.17 | 2025-07-09 | 2026-05-26
JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701005038/LD/22012034951344 — periferal ston bund shanti dham kemari | Ongoing | 1443174.57 | 1357491.35 | 2025-07-09
JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701005038/LD/22012034951345 — periferal ston bund hanuman mandir muran | Physically Completed | 1454612.29 | 1392270.03 | 2025-07-23 | 2026-05-26
JOURA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701005038/LD/261 — मेढवंधान सामलिया / रतनलाल | Completed | 0 | 19440 | 2010-11-01 | 2011-06-14
JOURA | 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701005038/PG/22012034298904 — खेल मैदान निर्माण कैमारी | Completed | 320000 | 265879.92 | 2017-04-01 | 2018-09-20
JOURA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005038/RC/22012034164006 — सी सी खरंजा | Deleted | 0 | 0 | 2012-12-24
JOURA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701005038/RC/22012034164007 — पत्थर खरंजा | Deleted | 0 | 0 | 2012-12-24
JOURA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005038/RC/22012034164913 — पंच परमश्‍ेर सीसी खरंजा निर्माण नाली सिहत सरमन का पुरा में जयसिंह कम माकन से गब्‍ब्‍र के मकान करी ओर | Deleted | 0 | 0 | 2012-10-02
JOURA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005038/RC/22012034164915 — पंच परमेश्‍वर सीसी खरंजा निर्माण नाली सहित सरमन का पुरा | Deleted | 0 | 0 | 2012-10-02
JOURA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005038/RC/22012034164941 — पंच परमेश्‍वर सीसी खरंजा निर्माण एवं नाली निर्माण सरमन का पुरा | Deleted | 0 | 0 | 2012-10-02
JOURA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005038/RC/22012034164946 — pach per cc kharnga nirman | Deleted | 0 | 0 | 2012-10-02
JOURA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005038/RC/22012034165067 — पंच परमश्‍ेवर सीसी खरंजा नाली निर्माण सरमन का पुरा | Deleted | 71193 | 0 | 2012-10-02
JOURA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005038/RC/22012034165096 — पंच परमेश्‍वर सीसी खरंजा नाली सहित समरन का पुरा में जयसिंह के मकान से गब्‍बर के मकान की ओर | Deleted | 0 | 0 | 2012-10-02
JOURA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005038/RC/22012034165332 — पंच परमेश्‍र सीसी खरंजा नाली निर्माण | Deleted | 71193 | 0 | 2012-10-02
JOURA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005038/RC/22012034172452 — सी.सी. खरंजा निर्माण एवं नाली कार्य सरमन का पुरा म | Completed | 71193 | 50682 | 2013-06-21 | 2014-12-10
JOURA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701005038/RC/22012034181370 — पत्‍थर खरंजा जय सिंह के मकान से लक्ष्‍मण के मकान की ओर | Completed | 285000 | 184866 | 2013-09-07 | 2015-05-25
JOURA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701005038/RC/22012034187125 — पत्‍थर खरंजा निर्माण चौकीदार घटा से मेहतर घटा होते | Completed | 495000 | 399726 | 2013-09-29 | 2016-09-22
JOURA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701005038/RC/22012034288835 — पत्थर खरंजा निर्माण जगदीश के मकान से बालू बाबा के मंदिर तक | Completed | 808000 | 735914.98 | 2015-11-14 | 2017-03-20
JOURA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701005038/RC/22012034297795 — पत्थर खरंजा निर्माण विजय सिंह के मकान से खार होकर इटावली की ओर जग्गुपुरा | Completed | 1338000 | 343990.16 | 2016-01-30 | 2017-03-20
JOURA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701005038/RC/22012034297796 — पत्थर खरंजा निर्माण कप्तान सिंह के मकान से दांगी बाबा मुराहान की ओर सरमन का पूरा ठेह गिर्द | Completed | 1162000 | 361204.9 | 2016-01-30 | 2017-03-20
JOURA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701005038/RC/22012034309083 — पत्थर खरंजा निर्माण जय सिंह की चक्की के मोड़ से जग्गू पुरा हरी सिंह के मकान तक | Deleted | 0 | 0 | 2016-01-26
JOURA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701005038/RC/22012034309086 — पत्थर खरंजा निर्माण जग्गू के पुरा से अमर वाले घटा तक | Deleted | 0 | 0 | 2016-01-26
JOURA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701005038/RC/22012034337761 — सुदूर ग्राम संपर्क सड़क निर्माण पी एम् जी एस वाई रोड से वघेल के पुरा तक पार्ट -a पार्ट-b | Completed | 2202000 | 2206079.95 | 2017-05-13 | 2019-09-30
JOURA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701005038/RC/22012034340222 — सुदूर ग्राम सड़क संपर्क निर्माण कार्य टेहागिर्द से केमारी एवं मुराहन तक | Completed | 4596000 | 4373262.39 | 2017-06-03 | 2020-06-06
JOURA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701005038/RC/22012034531003 — sudur gram sampark sadak | Deleted | 0 | 0 | 2020-04-16
JOURA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701005038/RC/22012034534810 — sudur road nirman juggu ke pura se thehageh tak itawali | Completed | 3339509.39 | 3273673.77 | 2020-09-25 | 2022-05-21
JOURA | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Metal Second coat / Construction of WBM Roads for Community | Construction of Road and Culvert | 1701005038/RC/504 — पत्‍थर खरंजा पन्‍ना के घर से आगनवाडी की ओर | Completed | 0 | 73922 | 2011-09-13 | 2011-09-25
JOURA | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Metal Second coat / Construction of WBM Roads for Community | Construction of Road and Culvert | 1701005038/RC/528 — पत्‍थखरंजानिर्माण नदी से महतर घटाता | Completed | 0 | 314178.27 | 2012-01-08 | 2012-06-20
JOURA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701005038/RC/616 — सी.सी. खरंजा करन सिंह के मकान से मैन रोड | Completed | 46815 | 46425.97 | 2012-09-05 | 2012-11-22
JOURA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of NADEP Compost structure for Groups / Construction of NADEP Compost structure for Groups | Construction of NADEP/Vermi Compost Pit | 1701005038/RS/22012034549906 — Nadeb Thehagird unit 1 | Deleted | 0 | 0 | 2021-04-14
JOURA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1701005038/RS/22012034635306 — SAMUDAYIK SHOUCHALAY | Deleted | 0 | 0 | 2021-10-02
JOURA | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005038/WC/190 — सोक्‍ता गडडा स्‍कूल पर जग्‍गू का पुरा | Completed | 0 | 16516 | 2009-07-04 | 2009-08-29
JOURA | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Mini Percolation tank / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1701005038/WC/22012034380627 — naveen talab nirman | Deleted | 0 | 0 | 2017-10-02
JOURA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1701005038/WC/22012034423931 — नवीन तालाब निर्माण - उपरी पाई में जग्‍गू का पुरा | Completed | 1463800 | 1457611.63 | 2018-10-01 | 2020-06-06
JOURA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1701005038/WC/22012034423933 — नवीन तालाब निर्माण - बजरंग मंदिर के नीचे | Completed | 1483000 | 1506776.49 | 2018-10-01 | 2020-07-15
JOURA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & Maint of Earthen Check Dam for Community / Repair and Maintenance of Earthen Check Dam for Community | Repair & Maint of Check Dam/Stop Dam | 1701005038/WC/22012034444638 — नवीन तालाब निर्मान कार्य ऊमर बाबा के पास | Completed | 1300000 | 1198753.32 | 2019-03-04 | 2020-07-15
JOURA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & Maint of Earthen Check Dam for Community / Repair and Maintenance of Earthen Check Dam for Community | Repair & Maint of Check Dam/Stop Dam | 1701005038/WC/22012034444716 — चेक डैम निर्माण कार्य - कुआ खार के पास | Completed | 1422000 | 1373959.08 | 2019-03-04 | 2020-06-06
JOURA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005038/WC/22012034515530 — चैकडेम निर्माण कार्य ग्राम मुराहन कैमारी में | Completed | 1470098.52 | 1433540 | 2020-01-21 | 2020-09-20
JOURA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005038/WC/22012034515531 — चैकडेम निर्माण कार्य ग्राम ठेहागिर्द में | Completed | 1470098.52 | 1422780 | 2020-01-21 | 2020-09-20
JOURA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005038/WC/22012034529607 — चैक डेम निर्माण कार्य कैमरी के पास लोहफ़ूड पर | Completed | 1457069.52 | 1411380 | 2020-04-24 | 2021-11-24
JOURA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005038/WC/22012034529608 — चैक डेम निर्माण कार्य विजय बहादुर के पूरा के पास | Completed | 1467371.52 | 1428340 | 2020-04-24 | 2020-09-20
JOURA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005038/WC/22012034529609 — चैक डेम निर्माण कार्य सरमन के पूरा पर दांगी बाबा के पास | Completed | 1470098.52 | 1465120 | 2020-04-24 | 2020-09-30
JOURA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1701005038/WC/22012034558858 — तालाब निर्माण कार्य भारत बरैठाा के खेत के पास। | Deleted | 0 | 0 | 2020-04-14
JOURA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1701005038/WC/22012034568081 — तालाब निर्माण कार्य भारत बरैठा के खेत के पास। | Completed | 1495483.67 | 1466732 | 2020-09-01 | 2021-04-12
JOURA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1701005038/WC/22012034568082 — तालाब निर्माण कार्य रामदीन गुर्जर के खेत के पास। | Completed | 1491363.45 | 1465522 | 2020-08-10 | 2021-04-14
JOURA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005038/WC/22012034568253 — चैकडेम निर्माण कार्य चेलिया माता के पास। | Completed | 1485190.77 | 1432640 | 2020-08-10 | 2021-03-28
JOURA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005038/WC/22012034568254 — चैकडेम निर्माण कार्य बधेल खिरकाई के पास | Completed | 1487807.57 | 1421126 | 2020-08-23 | 2021-04-22
JOURA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Brushwood Check Dam for Community / Construction of Brushwood Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005038/WC/22012034568255 — चैकडेम निर्माण कार्य कोलू दादा के पास | Completed | 1490424.37 | 1442560 | 2020-08-09 | 2021-04-22
JOURA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005038/WC/22012034580927 — चेक डेम निर्माण कार्य शिव सिंह बघेल के खेत के पास इटावली | Completed | 1479152.24 | 1425420 | 2020-09-28 | 2021-03-30
JOURA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005038/WC/22012034580928 — चेक डेम निर्माण कार्य विंदा के खेत के पास इटावली | Completed | 1457588.57 | 1430756 | 2020-09-27 | 2021-04-22
JOURA | 2020-2021 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Construction of Earthen Spur for Community / Construction of Earthen Spur for Community | Construction of Spur | 1701005038/WC/22012034580929 — रपटा निर्माण कार्य ठेहा गिर्द के पास रोड पर इटावली | Completed | 1495344.88 | 1430352 | 2020-09-25 | 2021-04-22
JOURA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Pebble peripheral Bund for Community / Construction of Pebble peripheral/farm/field Bund for Community | Construction of Bund | 1701005038/WC/22012034580930 — रपटा निर्माण कार्य सुरेश प्रजापति के खेत के पास इटावली | Completed | 1420884.54 | 1387652 | 2020-09-25 | 2021-04-22
JOURA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005038/WC/22012034580931 — चेक डेम निर्माण कार्य कुआ खार कैमारी | Completed | 1489950.8 | 1444920 | 2020-09-27 | 2021-04-22
JOURA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Pebble graded Bund for Community / Construction of Pebble graded Bund for Community | Construction of Bund | 1701005038/WC/22012034648316 — रपटा निर्माण कार्य बज्र सिंह गुर्जर के खेत के पास | Deleted | 0 | 0 | 2021-03-08
JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Pebble peripheral Bund for Community / Construction of Pebble peripheral/farm/field Bund for Community | Construction of Bund | 1701005038/WC/22012034648324 — रपटा निर्माण केमारी रोड पर | Completed | 1492033.27 | 1452300 | 2021-08-18 | 2022-04-11
JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Pebble peripheral Bund for Community / Construction of Pebble peripheral/farm/field Bund for Community | Construction of Bund | 1701005038/WC/22012034648327 — रपटा निर्माण कार्य रुस्तम सिंह गुर्जर के खेत के पास | Completed | 1481834.97 | 1437779 | 2021-08-18 | 2022-08-12
JOURA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Pebble peripheral Bund for Community / Construction of Pebble peripheral/farm/field Bund for Community | Construction of Bund | 1701005038/WC/22012034648332 — रपटा निर्माण कार्य गुफा ग्राम के पास रोड पर | Deleted | 0 | 0 | 2021-03-08
JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & maint of Community Ponds for Comm / Repair and maintenance of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1701005038/WC/22012034648338 — तालाब निर्माण कार्य रामसेवक के बीहड़ पर इटाबलि | Completed | 998505.89 | 1009060 | 2021-05-11 | 2021-08-31
JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & maint of Community Ponds for Comm / Repair and maintenance of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1701005038/WC/22012034648344 — तालाब निर्माण कार्य दस्सू गुर्जर के बीहड़ में केमारी | Completed | 990501.44 | 974523 | 2021-08-11 | 2022-04-19
JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & maint of Community Ponds for Comm / Repair and maintenance of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1701005038/WC/22012034648352 — तालाब निर्माण कार्य पंजाब सिंह गुर्जर के बीहड़ में ईटाबली | Completed | 994150.86 | 1006422 | 2021-05-11 | 2021-08-31
JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Brushwood Check Dam for Community / Construction of Brushwood Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005038/WC/22012034648357 — चेकडैम निर्माण कार्य ध्रुव गुर्जर के बीहड़ में थेहगिर्द | Completed | 998627.24 | 958284 | 2021-05-11 | 2021-11-22
JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Brushwood Check Dam for Community / Construction of Brushwood Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005038/WC/22012034648359 — चेकडैम निर्माण कार्य महेंद्र सिंह के खेत के पास ईटाबली | Completed | 999792.91 | 958927 | 2021-05-11 | 2021-11-22
JOURA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Brushwood Check Dam for Community / Construction of Brushwood Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005038/WC/22012034648362 — चेकडैम निर्माण कार्य महीप सिंह गुर्जर के बीहड़ में | Deleted | 0 | 0 | 2021-03-08
JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005038/WC/22012034703832 — चैकडेम निर्माण कार्य गब्बर गुर्जर के खेत के पास | Completed | 996919.76 | 956865 | 2021-08-11 | 2021-11-22
JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005038/WC/22012034703840 — चैकडेम निर्माण कार्य मेहरवान के बेहड़ में | Completed | 997418.14 | 956908 | 2021-08-11 | 2021-11-22
JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Brushwood Check Dam for Community / Construction of Brushwood Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005038/WC/22012034703846 — चैकडेम निर्माण कार्य बीरवल के खेत के पास | Completed | 997723.81 | 957501 | 2021-08-11 | 2021-11-22
JOURA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1701005038/WC/22012034703853 — तालाव निर्माण कार्य भरतू के बेहड़ में | Completed | 998110.58 | 976530 | 2021-08-11 | 2021-11-22
JOURA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1701005038/WC/22012034703859 — तालाव निर्माण कार्य वीरेंद्र गुर्जर के बेहड़ में | Completed | 997024 | 640210 | 2021-08-11 | 2021-11-22
JOURA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1701005038/WC/22012034703862 — तालाव निर्माण कार्य मुरहान ग्राम के पास | Completed | 998224.31 | 954120 | 2021-08-11 | 2022-03-28
JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1701005038/WC/22012034774240 — soak pit | Deleted | 0 | 0 | 2021-04-14
JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1701005038/WC/22012034774265 — Rain Water Harvesting | Completed | 22229.14 | 21170 | 2021-10-15 | 2021-11-22
JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005038/WC/22012034813323 — Water Harvesting Thehgird school k pass | Deleted | 0 | 0 | 2021-04-14
JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1701005038/WC/22012034813325 — shokhta gadda unit 2 gp itawali | Completed | 36887.67 | 31610 | 2021-10-20 | 2021-11-23
JOURA | 2021-2022 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1701005038/WC/22012034820411 — रपटा निर्माण कार्य ब्रज सिंह गुर्जर के खेत में | Completed | 1474629.07 | 1406650 | 2021-10-06 | 2022-08-12
JOURA | 2021-2022 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1701005038/WC/22012034820416 — रपटा निर्माण कार्य गुफा ग्राम के पास रोड पर | Completed | 1467984.07 | 1402629 | 2021-10-06 | 2022-08-12
JOURA | 2021-2022 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1701005038/WC/22012034827733 — Rapata marmmat kary thehgird se kaimari bale marg pr itawali | Completed | 137224.33 | 132488 | 2021-11-03 | 2022-08-12
JOURA | 2022-2023 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Renovation of Flood/ Diversion Channel for Comm / Renovation of Flood/ Diversion Channel for Community | Terracing | 1701005038/WC/22012034934388 — नवीन तालाब निर्माण बकील सिंह गुर्जर के बेहड मे सरमन का पुरा ईटावली | Completed | 1332310.53 | 1222629.55 | 2022-05-20 | 2023-07-04
JOURA | 2022-2023 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Renovation of Flood/ Diversion Channel for Comm / Renovation of Flood/ Diversion Channel for Community | Terracing | 1701005038/WC/22012034934403 — नवीन तालाब निर्माण झुनिया वाली नरी के पास ईटावली | Completed | 1974373.69 | 1830351.17 | 2022-04-26 | 2023-07-04
JOURA | 2022-2023 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Renovation of Flood/ Diversion Channel for Comm / Renovation of Flood/ Diversion Channel for Community | Terracing | 1701005038/WC/22012034942656 — चैक डैम निर्माण कार्य बरवाई नदी मे कैमारी | Deleted | 0 | 0 | 2022-04-01
JOURA | 2022-2023 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Renovation of Flood/ Diversion Channel for Comm / Renovation of Flood/ Diversion Channel for Community | Terracing | 1701005038/WC/22012034942680 — चैक डैम निर्माण कार्य कोडार के पास नदी मे मुरहान | Deleted | 0 | 0 | 2022-04-01
JOURA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1701005038/WC/22012034942687 — चैक डैम निर्माण कार्य सिन्नाम गुर्जर के बेहड में कैमारी | Deleted | 0 | 0 | 2022-04-01
JOURA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Renovation of Fisheries Ponds for Community / Renovation of Fisheries Ponds for Community | Repair & maint of Pond/ Tank | 1701005038/WC/22012034942695 — चैक डैम निर्माण कार्य रामभजन के बेहड में सरमन का पुरा | Deleted | 0 | 0 | 2022-04-01
JOURA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Renovation of Fisheries Ponds for Community / Renovation of Fisheries Ponds for Community | Repair & maint of Pond/ Tank | 1701005038/WC/22012034942725 — तालाब निर्माण कार्य निहालसिंह के बेहड में कैमारी | Completed | 1002150.87 | 736084.74 | 2022-04-26 | 2023-07-04
JOURA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Renovation of Fisheries Ponds for Community / Renovation of Fisheries Ponds for Community | Repair & maint of Pond/ Tank | 1701005038/WC/22012034942735 — तालाब निर्माण कार्य बिजेन्द्र गुर्जर के बेहड में कैमारी | Completed | 1018548.14 | 912375 | 2022-04-26 | 2023-07-10
JOURA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Renovation of Fisheries Ponds for Community / Renovation of Fisheries Ponds for Community | Repair & maint of Pond/ Tank | 1701005038/WC/22012034942746 — तालाब निर्माण कार्य बकील ंिसह गुर्जर के बेहड में | Deleted | 0 | 0 | 2022-04-01
JOURA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1701005038/WC/22012034942752 — तालाब निर्माण कार्य कुशवाह वाली नरी पर ईटावली | Completed | 1493719.71 | 1368663.87 | 2022-04-26 | 2023-07-04
JOURA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Renovation of Fisheries Ponds for Community / Renovation of Fisheries Ponds for Community | Repair & maint of Pond/ Tank | 1701005038/WC/22012034942757 — तालाब निर्माण कार्य जुनियां की नरी पर ईटावली | Deleted | 0 | 0 | 2022-04-01
JOURA | 2022-2023 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Renovation of Flood/ Diversion Channel for Comm / Renovation of Flood/ Diversion Channel for Community | Terracing | 1701005038/WC/22012034952456 — रूप वाटर हार्वेस्टिंग प्रा.वि. जग्गू का पुरा ईटावली | Deleted | 0 | 0 | 2022-04-01
JOURA | 2022-2023 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Renovation of Flood/ Diversion Channel for Comm / Renovation of Flood/ Diversion Channel for Community | Terracing | 1701005038/WC/22012034952461 — सॉकपिट निर्माण कार्य जग्गू का पुरा ईटावली | Deleted | 0 | 0 | 2022-04-01
JOURA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Renovation of Fisheries Ponds for Community / Repair & Maintenance of Fishery Pond for Community | Repair & maint of Pond/ Tank | 1701005038/WC/22012034980600 — रपटा निर्माण कार्य बघेल पुरा रोड ईटावली | Ongoing | 1499234.87 | 1049571.6 | 2022-11-15
JOURA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & maint of Community Ponds for Comm / Repair & Maintenance of Water Harvesting Pond for Community | Repair & maint of Pond/ Tank | 1701005038/WC/22012034980622 — रपटा निर्माण कार्य मुरहान वाली रोड पर ईटावली | Ongoing | 1477842.32 | 764330.7 | 2022-12-02
JOURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1701005038/WC/22012035098204 — vasundhara ke tahat braksharopad karya school ke pas thea gird | Closed | 0 | 0 | 2023-08-11
JOURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Raising of Nursery for Community / Raising of Nursery for Community | Nursery Development | 1701005038/WC/22012035153326 — Rapta nirman karya Neeche khar me Itawali | Closed | 0 | 0 | 2023-08-16
JOURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone boulder Gully Plugs for Comm / Construction of Stone boulder Gully Plugs for Community | Boulder Check/Gully Plug | 1701005038/WC/22012035153331 — Rapata nirman karya Jaggu ka pura itawali | Closed | 2475600.76 | 0 | 2023-08-16
JOURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1701005038/WC/22012035153333 — Rapta nirman Karya theha road par | Closed | 0 | 0 | 2023-08-16
JOURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Raising of Nursery for Community / Raising of Nursery for Community | Nursery Development | 1701005038/WC/22012035153335 — Rapta nirman Karya murhan kaimari | Closed | 0 | 0 | 2023-08-16
JOURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Raising of Nursery for Groups / Raising of Nursery for Community | Nursery Development | 1701005038/WC/22012035153337 — Talab nirman karya behad me itawali | Ongoing | 1470991.28 | 7956 | 2024-03-15
JOURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Wastelands Block Plantation-Farm Forestry -Comm / Agro Forestry Block Plantation in Waste Lands for Community | Plantation | 1701005038/WC/22012035153339 — Talab nirman karya murhan me kaimari | Ongoing | 1444570.2 | 9282 | 2024-03-15
JOURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Road Line Plantation of Shelter Belt Trees-Comm / Avenue Plantation for Community | Plantation | 1701005038/WC/22012035153342 — Talab nirman karya theha ke behad me | Ongoing | 1452995.59 | 6630 | 2024-03-15
JOURA | 2023-2024 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Renovation of Flood/ Diversion Channel for Comm / Repair & Maintenance of Flood or Diversion Channel for Community | Terracing | 1701005038/WC/22012035153345 — Patthar nala nirman itawali niche khar me | Ongoing | 1425791.15 | 591776.87 | 2024-02-23
JOURA | 2023-2024 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Construction of Stone Spur for Community / Construction of Stone Spur for Community | Construction of Spur | 1701005038/WC/22012035156037 — Rapata nirnam karya karil bale ke pass | Closed | 2497423.66 | 0 | 2023-08-16
JOURA | 2023-2024 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Construction of Stone Spur for Community / Construction of Stone Spur for Community | Construction of Spur | 1701005038/WC/22012035156038 — Rapata nirman karya sedhe raste par | Closed | 2488882.05 | 0 | 2023-08-16
JOURA | 2023-2024 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Construction of Stone Spur for Community / Construction of Stone Spur for Community | Construction of Spur | 1701005038/WC/22012035156039 — Rapata nirman karya neche raste par | Closed | 2487968.7 | 0 | 2023-08-16
JOURA | 2023-2024 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Construction of Stone Spur for Community / Construction of Stone Spur for Community | Construction of Spur | 1701005038/WC/22012035156040 — Rapata nirman karya Tede raste par | Closed | 2487882.05 | 0 | 2023-08-16
JOURA | 2023-2024 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Construction of Stone Spur for Community / Construction of Stone Spur for Community | Construction of Spur | 1701005038/WC/22012035156042 — Rapta nirman karya ubad wale raste par | Closed | 2474128.9 | 0 | 2023-08-16
JOURA | 2023-2024 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Construction of Stone Spur for Community / Construction of Stone Spur for Community | Construction of Spur | 1701005038/WC/22012035156073 — Any cut nirman karya Remja wale me | Closed | 0 | 0 | 2023-08-16
JOURA | 2023-2024 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Construction of Stone Spur for Community / Construction of Stone Spur for Community | Construction of Spur | 1701005038/WC/22012035156075 — Any cut nirman karya babul wale me | Closed | 0 | 0 | 2023-08-16
JOURA | 2023-2024 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Construction of Stone Spur for Community / Construction of Stone Spur for Community | Construction of Spur | 1701005038/WC/22012035156076 — Any cut nirman karya khar wale me | Closed | 0 | 0 | 2023-08-16
JOURA | 2023-2024 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Construction of Stone Spur for Community / Construction of Stone Spur for Community | Construction of Spur | 1701005038/WC/22012035156077 — Any cut nirman karya Donga wale me | Closed | 0 | 0 | 2023-08-16
JOURA | 2023-2024 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Construction of Stone Spur for Community / Construction of Stone Spur for Community | Construction of Spur | 1701005038/WC/22012035156078 — Any cut nirman karya Jhaguaa me | Closed | 0 | 0 | 2023-08-16
JOURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Wastelands Block Plantation-Farm Forestry -Comm / Wasteland Block Plantation of Farm Forestry Trees for Community | Plantation | 1701005038/WC/22012035168319 — Nala nirman karya Mandir ke niche khar me itawali | Closed | 0 | 0 | 2024-01-25
JOURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation in fields-Horticulture-Community / Block Plantation of Horticulture Trees in fields for Community | Plantation | 1701005038/WC/22012035168328 — Nala nirman karya Mandir ke niche khar me itawali | Ongoing | 1450112.47 | 581448.36 | 2024-02-23
JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1701005038/WC/22012035248818 — Nabeen Talab nirman kary kemari behadi me gram panchayat itawali | Ongoing | 1449920.67 | 1347586.57 | 2025-02-22
JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1701005038/WC/22012035248820 — Nabeen Talab nirman kary kemari ghat me gram panchayat itawali | Ongoing | 1497242.86 | 726134.01 | 2025-02-22
JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005038/WC/22012035248822 — Nabeen Talab nirman kary god bali nari itawali | Physically Completed | 1499341.9 | 1438927.1 | 2025-03-04 | 2026-04-16
JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005038/WC/22012035253758 — talab nirman karya puliya ke pass kemari | Physically Completed | 1488209.87 | 1309937.25 | 2025-04-19 | 2026-04-27
JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1701005038/WC/22012035253784 — navin talab nirman baag bali nari kemari | Ongoing | 1494177.13 | 1317656.22 | 2025-10-15
JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1701005038/WC/22012035253786 — navin talab nirman bahari bali nari kemari | Approved | 1464127.57 | 0 | 2025-01-28
JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005038/WC/22012035253787 — navin talab nirman gajar bala nala kemari | Physically Completed | 1458833.61 | 1229687.42 | 2025-05-25 | 2026-04-27
JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005038/WC/22012035253789 — navin talab nirman bamur bali nari kemari | Physically Completed | 1493850.6 | 1424272.27 | 2025-06-01 | 2026-04-16
JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005038/WC/22012035253839 — navin talab nirman panna bali nari kemari | Physically Completed | 1494150.3 | 1418683.08 | 2025-08-06 | 2026-04-24
JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1701005038/WC/22012035253840 — navin talab nirman churela bali nari kemari | Ongoing | 1490510.52 | 1150658.76 | 2025-09-24
JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1701005038/WC/22012035253842 — navin talab nirman kuaa bala nala kemari | Ongoing | 1491759.1 | 1391112.35 | 2025-09-24
JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1701005038/WC/22012035253845 — navin talab nirman deewan ke khet wala nala kemari | Approved | 1494177.13 | 0 | 2025-01-28
JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1701005038/WC/22012035287292 — dug well recharge athai ke pass itawali | Approved | 25899.46 | 0 | 2025-04-24
JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1701005038/WC/22012035287297 — dug well recharge bag ke samne itawali | Approved | 25899.46 | 0 | 2025-04-24
JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1701005038/WC/22012035329086 — TALAB NIRMAN KARYA SEMAR BALA NALA TEHAGIRD ITAWALI | Approved | 1493780.14 | 0 | 2026-01-27
JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1701005038/WC/22012035329088 — TALAB NIRMAN KARYA JHARANA BALA NALA TEHAGIRD | Approved | 1494258.42 | 0 | 2026-01-27
JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1701005038/WC/22012035329089 — TALAB NIRMAN KARYA SEETARAM BALA NALA TEHAGIRD ITAWALI | Approved | 1494258.42 | 0 | 2026-01-27
JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1701005038/WC/22012035329090 — TALAB NIRMAN KARYA BADA BALA NALA TEHAGIRD ITAWALI | Approved | 1492011.78 | 0 | 2026-01-27
JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1701005038/WC/22012035329092 — TALAB NIRMAN KARYA DUDHADHAARI BALA NALA ITAWALI | Approved | 1490095.65 | 0 | 2026-01-24
JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1701005038/WC/22012035329093 — TALAB NIRMAN KARYA PEEPAL KE PASS ITAWALI | Approved | 1489765.13 | 0 | 2026-01-24
JOURA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005038/WC/62 — सोक्‍ट पिट राणा जी के मकान के पास | Completed | 0 | 15592.1 | 2008-08-12 | 2009-01-25
JOURA | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1701005038/WC/63 — सोख्‍ता गडडा निर्र्माण कार्य रामजानुकी मदिर | Completed | 0 | 14642.47 | 2008-08-04 | 2009-02-20
JOURA | 2010-2011 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1701005038/WC/914 — मिटटी वधान कार्य खौटा वाली नदी | Completed | 0 | 22326 | 2011-01-27 | 2011-02-08
JOURA | 2010-2011 | D--RURAL INFRASTUCTURE / Renovation of traditional water bodies | Strengthening of Embankment / Construction of Embankment for community | Renovation of traditional water bodies | 1701005038/WH/207 — मिटटी बन्‍धान कार्य ठाडेपथा वाली नरीमिटटी बन्‍धान कार्य ठाडेपथा वाली नरी | Completed | 0 | 20400 | 2011-01-02 | 2011-01-14