## Work List
Exported on: 2026-10-24 07:07:47
Filters applied:
Data source: MGNREGA
District: MORENA
Block: All
Panchayat: BADONA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
JOURA | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1701005051/AV/22012034374738 — शान्तिधाम उन्नयन कार्य नूरपुर | Completed | 215000 | 212550 | 2018-09-26 | 2020-07-11
JOURA | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1701005051/AV/22012034636408 — शांति धाम निर्माण कार्य कुशवाह पुरा बडोना | Completed | 330972.38 | 295579 | 2023-07-10 | 2023-09-25
JOURA | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1701005051/AV/22012034636409 — शांति धाम निर्माण कार्य हवेली नूरपुर | Completed | 330972.38 | 294253 | 2023-07-10 | 2023-09-27
JOURA | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert / cross drainage structues for Community | Culvert | 1701005051/AV/22012034657984 — पुलिया निर्माण कार्य करुआ के खेत के पास | New | 0 | 0 | 2024-06-10
JOURA | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert / cross drainage structues for Community | Culvert | 1701005051/AV/22012034657985 — पुलिया निर्माण कार्य सुरेश पाल के खेत के पास | New | 0 | 0 | 2024-06-10
JOURA | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert / cross drainage structues for Community | Culvert | 1701005051/AV/22012034657986 — पुलिया निर्माण कार्य राजकुमार के खेत के पास | New | 0 | 0 | 2024-06-10
JOURA | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert / cross drainage structues for Community | Culvert | 1701005051/AV/22012034657987 — पुलिया निर्माण कार्य स्कूल के पास | New | 0 | 0 | 2024-06-10
JOURA | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert / cross drainage structues for Community | Culvert | 1701005051/AV/22012034657988 — पुलिया निर्माण दीवान के मकान के पास | New | 0 | 0 | 2024-06-10
JOURA | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1701005051/AV/22012034659395 — पंचायत भवन निर्माण कार्य शौंचालय एवं बाउण्ड्रीवॉल सहित | Deleted | 0 | 0 | 2024-06-10
JOURA | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1701005051/AV/22012034659396 — पंचायत भवन निर्माण कार्य शौंचालय एवं बाउण्ड्रीवॉल सहित | Completed | 1000000 | 909332.25 | 2024-09-09 | 2025-07-02
JOURA | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play field for Community | Construction of Play field | 1701005051/AV/22012034660081 — खेल मैदान निर्माण कार्य बडोना | Deleted | 0 | 0 | 2024-08-15
JOURA | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1701005051/AV/22012034660082 — शांति धाम निर्माण कार्य हवेली बडोना | Completed | 334906.09 | 299871.86 | 2024-10-14 | 2024-11-29
JOURA | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1701005051/AV/22012034660377 — शांतिधाम निर्माण कार्य नूरपुर | Completed | 334906.09 | 295631.86 | 2024-10-14 | 2025-07-02
JOURA | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play field for Community | Construction of Play field | 1701005051/AV/22012034660543 — खेल मैदान निर्माण कार्य बडोना | Deleted | 0 | 0 | 2024-08-15
JOURA | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play field for Community | Construction of Play field | 1701005051/AV/22012034660876 — खेल मैदान कार्य बडोना | Deleted | 861141 | 0 | 2024-08-16
JOURA | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play field for Community | Construction of Play field | 1701005051/AV/22012034662328 — खेल मैदान निर्माण कार्य बडोना | Deleted | 0 | 0 | 2024-10-02
JOURA | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play field for Community | Construction of Play field | 1701005051/AV/22012034662361 — खेल मैदान निर्माण कार्य बडोना | New | 0 | 0 | 2024-10-02
JOURA | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play field for Community | Construction of Play field | 1701005051/AV/22012034662552 — खेल मैदान निर्माण कार्य बडोना | Completed | 476879.26 | 470065.59 | 2024-12-16 | 2025-07-02
JOURA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701005051/DP/109 — नन्‍दन फलोउधान महेन्‍द पुञ लायक सिह | Completed | 0 | 2730 | 2009-03-08 | 2008-04-01
JOURA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1701005051/DP/140 — शान्‍ती धाम कार्य नूरपूर | Completed | 496808 | 367393.46 | 2011-09-10 | 2015-10-10
JOURA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701005051/DP/17 — बृक्षारोपण निर्माण कार्य | Completed | 0 | 2040 | 2008-08-20 | 2007-10-17
JOURA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701005051/DP/18 — बृक्षारोपण निर्माण कार्य | Completed | 0 | 3440 | 2008-08-20 | 2007-10-17
JOURA | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Land development / Levelling/shaping of Wasteland Land for Community | Land Development | 1701005051/DP/22012034229800 — शान्ति धाम निर्माण कार्य बडोना | Closed | 0 | 0 | 2016-01-26
JOURA | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1701005051/DP/22012034236888 — शांतिधाम निर्माण कार्य बड़ौना | Completed | 180000 | 170967 | 2016-12-27 | 2023-07-01
JOURA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1701005051/DP/22012034523666 — niji khet me vraksharopan karya kishan singh/layak singh | Closed | 168764 | 0 | 2021-01-26
JOURA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1701005051/DP/22012034523669 — niji khet me vraksharopan karya Rajesh / Vaijnath | Closed | 168764 | 0 | 2021-01-26
JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1701005051/DP/22012034540872 — नंदन फल उद्यान उपेन्‍द्र/कुअरपाल | Ongoing | 145171 | 18228 | 2021-12-04
JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Horticulture -Community / Boundary Line Plantation of Horticulture Trees for Community | Plantation | 1701005051/DP/22012034542520 — Maa ki bagiya m s badona | Closed | 0 | 0 | 2021-08-15
JOURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Road Line Plantation of Forestry Trees for Comm / Road side line plantation of Forestry Trees for Community | Plantation | 1701005051/DP/22012034579472 — बृक्षारोपण कार्य आसान नदी से बडोना गांव हनुमान मंदिर तक बडोना | Closed | 427106.07 | 0 | 2023-04-14
JOURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1701005051/DP/22012034602640 — बसुधा बंधन वाटिका ग्राम पंचायत बड़ोंना | Closed | 0 | 0 | 2023-04-14
JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Farm Forestry-Community / Boundary Line Plantation of Farm Forestry Trees for Community | Plantation | 1701005051/DP/22012034620690 — बृक्षारोपण स्कूल परिसर बडोना | Completed | 120180.13 | 67554 | 2024-09-02 | 2026-04-23
JOURA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1701005051/DP/222 — वृक्षारोपण शांतीधाम पर नूरपुर बडोना | Completed | 177297 | 8708 | 2012-09-19 | 2015-10-10
JOURA | 2015-2016 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Construction of Intermediate and Link Drains / Construction of intermediate and Link Storm Water Drain for Community | Works for Flood Control and Protection | 1701005051/FP/22012034204055 — नाला निर्माण कुशवाह के पूरा से नदी की और बडोना | Deleted | 0 | 0 | 2016-01-26
JOURA | 2018-2019 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of intrmediate and Link Water Drain-Comm / Construction of intermediate and Link Storm Water Drain for Community | Works for Flood Control and Protection | 1701005051/FP/22012034361496 — पत्‍थर नाला निर्माण - कुशवाह पुरा से नदी की ओर बडोना | Completed | 632000 | 616031.7 | 2019-01-11 | 2021-06-25
JOURA | 2018-2019 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701005051/FP/22012034362287 — पत्थर नाला निर्माण बडौना | Closed | 0 | 0 | 2018-10-02
JOURA | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701005051/FP/22012034624725 — patthar nala nirman parimal ke makan se ganv ki or nurpur | Completed | 998277.24 | 993256 | 2021-05-13 | 2022-07-25
JOURA | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701005051/FP/22012034624835 — Kacha nalha nermad karya norpur | Completed | 994422.84 | 675240 | 2021-05-25 | 2022-09-11
JOURA | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701005051/FP/22012034624836 — Kacha nalha nermad karya norpur | Closed | 0 | 0 | 2021-04-14
JOURA | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701005051/FP/22012034624838 — Pathar nala nermad kary haneman mader se tabar ke or | Closed | 0 | 0 | 2021-04-14
JOURA | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Repair & Maint of Flood/Diversion Channel for Comm / Repair and Maintenance of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005051/FP/22012034626775 — Pathar nala nirmadhakarya hanuman mader se neche ke or | Completed | 994005.04 | 863412 | 2021-11-19 | 2023-04-12
JOURA | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Renovation of Flood/ Diversion Channel for Comm / Renovation of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005051/FP/22012034629435 — PatharNala nirmad karya m s school se lakar ved ke or | Completed | 1499081.27 | 1422151.6 | 2022-09-29 | 2023-07-12
JOURA | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701005051/FP/22012034630310 — nala nirman karya babu baba ke mandir se behad ki or | Completed | 1471404.87 | 1393675 | 2022-10-30 | 2023-07-27
JOURA | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005051/FP/22012034630312 — पत्थर नाला निर्माण कार्य परिमाल के मकान वाले रास्ते से होकर खोर की ओर | Closed | 0 | 0 | 2022-08-16
JOURA | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005051/FP/22012034630313 — पत्थर नाला निर्माण कार्य परिमाल के मकान वाले रास्ते से होकर खोर की ओर | Closed | 0 | 0 | 2022-08-16
JOURA | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005051/FP/22012034630314 — पत्थर नाला निर्माण कार्य परिमाल के मकान वाले रास्ते से होकर खोर की ओर | Completed | 1474923.15 | 1376881 | 2022-11-06 | 2023-07-27
JOURA | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005051/FP/22012034632037 — पत्त्थर नाला निर्माण कार्य खेल मैदान से पुलिया की ओर बडोना | Completed | 1440707.1 | 1285595.08 | 2023-05-05 | 2023-12-08
JOURA | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005051/FP/22012034632038 — पत्त्थर नाला निर्माण कार्य पंचायत भवन से बेहड़ की ओर बडोना | Completed | 1434915.54 | 1217814.74 | 2023-05-05 | 2023-12-08
JOURA | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Renovation of Flood/ Diversion Channel for Comm / Renovation of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005051/FP/22012034634065 — नाला निर्माण कार्य प्रेम गिर के मकान से पुलिया की और | Completed | 1490229.55 | 1303465.5 | 2023-08-07 | 2024-05-03
JOURA | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Renovation of Flood/ Diversion Channel for Comm / Renovation of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005051/FP/22012034634066 — नाला निर्माण कार्य पुलिया से बीहड़ की और | Completed | 1456639.39 | 1302208.5 | 2023-08-07 | 2024-05-03
JOURA | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Renovation of Flood/ Diversion Channel for Comm / Renovation of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005051/FP/22012034634067 — नाला निर्माण कार्य राजेश के मकान से हार की और | Completed | 1479095.42 | 1384892.5 | 2023-08-07 | 2024-05-03
JOURA | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Renovation of Flood/ Diversion Channel for Comm / Renovation of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005051/FP/22012034634068 — नाला निर्माण कार्य हवेली से पुलिया की और | Completed | 1470541.75 | 940356.5 | 2023-08-07 | 2024-05-03
JOURA | 2013-2014 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Drainage in Water Logged Areas / Drainage of Community Waterlogged Land | Works for Flood Control and Protection | 1701005051/FP/9977521780 — पत्‍थर नाला निर्माण रविन्‍द्र के मकान से तिराहे की | Completed | 359607 | 213640 | 2013-05-28 | 2014-03-25
JOURA | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1701005051/IF/12 — कूप निर्माण महेश /छोटे लाल | Completed | 0 | 2040 | 2008-05-25 | 2007-10-17
JOURA | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1701005051/IF/161 — मैढ बंधान योगेन्‍द्र सिंह/उत्‍तम सिंह | Completed | 19366 | 11164 | 2012-08-24 | 2012-10-01
JOURA | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1701005051/IF/162 — मैढ बंधान गोपाल/छोटे जाटव | Completed | 27024 | 10768 | 2012-08-16 | 2014-04-01
JOURA | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1701005051/IF/163 — मैढ बंधान पूरन/रामगोपाल | Completed | 17663 | 10900 | 2012-08-24 | 2012-10-01
JOURA | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1701005051/IF/176 — मैढ बंधान कार्य नेत्रपाल / नवाव सिंह | Completed | 20045 | 13880 | 2012-08-16 | 2012-10-01
JOURA | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1701005051/IF/198 — मैढ बंधान कार्य रसाल सिंह/पन्‍ना लाल | Completed | 0 | 13408 | 2012-08-16 | 2016-09-27
JOURA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701005051/IF/22012034345216 — सार्वजानिक वृक्षा रोपण स्कूल एवं शान्तिधाम | Completed | 335000 | 9176 | 2017-05-30 | 2021-02-02
JOURA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701005051/IF/22012034354077 — सार्वजनीक परिसर आंगनवाड़ी एवं तालाब के किनारे एवं शान्तिधाम नूरपुर | Completed | 335000 | 3032 | 2017-07-01 | 2021-02-02
JOURA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701005051/IF/22012034359134 — सार्वजनिक व्रक्षारोपण कार्य बाबू महाराज के स्‍थान के पास | Completed | 335000 | 21172 | 2017-07-01 | 2021-02-02
JOURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1701005051/IF/22012035426154 — खेत तालाव निर्माण कार्य गवदा के खेत पर | Completed | 383972.88 | 303801 | 2025-05-03 | 2025-11-03
JOURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1701005051/IF/22012035426203 — खेत तलाव निर्माण कार्य प्रेमपाल के खेत पर | Completed | 383972.88 | 299103 | 2025-05-06 | 2025-11-03
JOURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1701005051/IF/22012035472222 — डगवेल निर्माण कार्य मग्गी के कुआं के पास | Completed | 25899.46 | 14351.84 | 2025-05-12 | 2025-11-03
JOURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1701005051/IF/22012035499163 — खेत तालाव निर्माण कार्य सोनू के खेत के पर | Completed | 384072.88 | 289968.62 | 2025-05-12 | 2025-12-31
JOURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1701005051/IF/22012035499192 — खेत तालाव निर्माण कार्य नेत्रपाल के खेत के पर | Completed | 384072.88 | 289970 | 2025-05-12 | 2025-11-03
JOURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1701005051/IF/22012035499212 — खेत तालाव निर्माण कार्य विनोद के खेत के पर | Completed | 383972.88 | 294668 | 2025-05-12 | 2025-11-05
JOURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1701005051/IF/22012035499231 — डगवेल निर्माण कार्य लोकेन्द्र के कुआं पर | Completed | 25899.46 | 14343.74 | 2025-05-12 | 2025-11-03
JOURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1701005051/IF/22012035499255 — खेत तालाव निर्माण कार्य मंगल सिंह के खेत पर | Completed | 383972.88 | 296234 | 2025-05-12 | 2025-11-03
JOURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701005051/IF/22012035659729 — EK BAGIYA MAA KE NAAM SHEELA YADAVMP-01-005-051-001/1488-A | Approved | 0 | 0 | 2025-12-15
JOURA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701005051/IF/9926709247 — पशु शेड निर्माण लायकसिंह /सीताराम | Completed | 80000 | 72372.17 | 2014-03-01 | 2015-12-25
JOURA | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701005051/IF/9993650747 — पशु शेड निर्माण नेत्रपाल सिंह / नबाब सिंह | Completed | 136000 | 35106.39 | 2014-08-19 | 2018-04-01
JOURA | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701005051/IF/9993650748 — पशु शेड निर्माण विनोद सिंह / नेत्रपाल सिंह | Completed | 136000 | 33861.23 | 2014-08-19 | 2018-04-01
JOURA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701005051/IF/9993721561 — cattle shed pribhu/murari | Deleted | 0 | 0 | 2016-01-26
JOURA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701005051/IF/9993721566 — cattle shed shriman/duareka | Deleted | 0 | 0 | 2016-01-26
JOURA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701005051/IF/9993721569 — cattle shed uttam | Deleted | 0 | 0 | 2016-01-26
JOURA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701005051/IF/9993724974 — Pashu shed | Deleted | 0 | 0 | 2016-01-26
JOURA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701005051/IF/9993725737 — कैटल shed | Deleted | 0 | 0 | 2016-01-26
JOURA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701005051/IF/9993725748 — कैटल शेड़ | Deleted | 0 | 0 | 2016-01-26
JOURA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701005051/IF/9993725763 — कैटल शेड | Deleted | 0 | 0 | 2016-01-26
JOURA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701005051/IF/9993725766 — कैटल शेड | Deleted | 0 | 0 | 2016-01-26
JOURA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701005051/IF/9993725771 — कैटल शेड | Deleted | 0 | 0 | 2016-01-26
JOURA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701005051/IF/9993725773 — कैटल शेड | Deleted | 0 | 0 | 2016-01-26
JOURA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701005051/IF/9993725775 — कैटल शेड | Deleted | 0 | 0 | 2016-01-26
JOURA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701005051/IF/9993725779 — कैटल शेड | Deleted | 0 | 0 | 2016-01-26
JOURA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701005051/IF/9993725783 — कैटल शेड | Deleted | 0 | 0 | 2016-01-26
JOURA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701005051/IF/9993726353 — cattle shed | Deleted | 0 | 0 | 2016-01-26
JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005051/IF/IAY/1898746 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4562894 | Completed | 15660 | 15138 | 2018-10-04 | 2018-12-01
JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005051/IF/IAY/1899300 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4588734 | Completed | 15660 | 15138 | 2018-10-04 | 2018-12-01
JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005051/IF/IAY/1899684 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4634143 | Completed | 15660 | 15660 | 2018-10-04 | 2018-11-26
JOURA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005051/IF/IAY/193312 — Construction of IAY House -IAY REG. NO. MP-01-005-051-001/32 | Completed | 14310 | 14028 | 2016-07-05 | 2018-06-18
JOURA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005051/IF/IAY/193316 — Construction of IAY House -IAY REG. NO. MP-01-005-051-001/37 | Deleted | 14310 | 0 | 2016-07-05
JOURA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005051/IF/IAY/193317 — Construction of IAY House -IAY REG. NO. MP-01-005-051-002/14 | Approved | 23490 | 0 | 2016-02-05
JOURA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005051/IF/IAY/193318 — Construction of IAY House -IAY REG. NO. MP-01-005-051-002/15 | Completed | 14310 | 14028 | 2016-06-28 | 2018-06-18
JOURA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005051/IF/IAY/228324 — Construction of IAY House -IAY REG. NO. MP1277938 | Completed | 15030 | 15336 | 2017-02-21 | 2018-05-25
JOURA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005051/IF/IAY/239981 — Construction of IAY House -IAY REG. NO. MP1509569 | Completed | 15030 | 15528 | 2017-02-14 | 2018-09-19
JOURA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005051/IF/IAY/243168 — Construction of IAY House -IAY REG. NO. MP1627115 | Completed | 15030 | 15372 | 2017-02-14 | 2018-05-25
JOURA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005051/IF/IAY/441806 — Construction of IAY House -IAY REG. NO. MP1480619 | Completed | 15030 | 15324 | 2017-02-21 | 2018-05-25
JOURA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005051/IF/IAY/532214 — Construction of IAY House -IAY REG. NO. MP2855343 | Completed | 15030 | 15420 | 2017-02-21 | 2018-09-19
JOURA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005051/IF/IAY/706291 — Construction of IAY House -IAY REG. NO. MP1517403 | Completed | 15030 | 15576 | 2017-05-02 | 2018-05-25
JOURA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005051/IF/IAY/708637 — Construction of IAY House -IAY REG. NO. MP1543783 | Completed | 15030 | 15636 | 2017-09-26 | 2018-09-19
JOURA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005051/IF/IAY/726925 — Construction of IAY House -IAY REG. NO. MP1878132 | Completed | 15030 | 15504 | 2017-05-02 | 2018-05-25
JOURA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005051/IF/IAY/727896 — Construction of IAY House -IAY REG. NO. MP1902589 | Completed | 15030 | 15612 | 2017-05-02 | 2018-08-23
JOURA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005051/IF/IAY/727944 — Construction of IAY House -IAY REG. NO. MP1903630 | Completed | 15030 | 15480 | 2017-05-02 | 2018-04-12
JOURA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701005051/LD/157 — मेड वन्‍धान कार्य रामदुलारे पुञ जुगनू | Completed | 0 | 20908 | 2009-02-15 | 2014-03-01
JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701005051/LD/22012034950514 — बण्ड कम बाउंड्रीवॉल निर्माण कार्य शांति धाम डंगरिया बडोना | Physically Completed | 1394070.97 | 1353871.84 | 2025-03-04 | 2026-05-22
JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701005051/LD/22012034950515 — बण्ड कम बाउंड्रीवॉल निर्माण कार्य शांति धाम नूरपुर | Physically Completed | 1467726.36 | 1320880.55 | 2025-03-04 | 2026-05-22
JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701005051/LD/22012034950516 — बण्ड कम बाउंड्रीवॉल निर्माण खेल मैदान बडोना | Physically Completed | 1466726.36 | 1340694.98 | 2025-03-04 | 2026-05-22
JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701005051/LD/22012034951714 — Earthen bund kum boundriwall nirman karya hidde baba school ke pass | Physically Completed | 1455512.03 | 1390351.89 | 2025-07-04 | 2026-05-22
JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701005051/LD/22012034951715 — Earthen bund kum boundriwall nirman karya khel maidan phadi part 2 | Physically Completed | 1455512.03 | 1354856.28 | 2025-07-04 | 2026-05-22
JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701005051/LD/22012034957310 — constrution peripheral stone bund shanti dham asan nadi par | Physically Completed | 1492194.21 | 780701.86 | 2025-11-27 | 2026-06-11
JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701005051/LD/22012034957311 — constrution peripheral stone bund shanti dham purana gaon | Physically Completed | 1449211.39 | 815026.17 | 2025-11-27 | 2026-06-11
JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701005051/LD/22012034957312 — constrution peripheral stone bund mata mandir badona | Physically Completed | 1468671.99 | 808767.85 | 2025-11-27 | 2026-06-11
JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701005051/LD/22012034957313 — constrution peripheral stone bund hiraman mandir pahadi | Physically Completed | 1486303.53 | 854910.91 | 2025-11-27 | 2026-06-11
JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701005051/LD/22012034957314 — constrution peripheral stone bund bddh bhagwan mandir | Physically Completed | 1492013.91 | 862472.4 | 2025-11-27 | 2026-06-11
JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701005051/LD/22012034957315 — constrution peripheral stone bund hanuman mandir dangariya | Physically Completed | 1492013.91 | 889075.32 | 2025-11-27 | 2026-06-11
JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701005051/LD/22012034957316 — constrution peripheral stone bund babu baba mandir pahadi | Physically Completed | 1497954.68 | 664096.59 | 2025-11-27 | 2026-06-11
JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701005051/LD/22012034957317 — constrution peripheral stone bund shiddh baba nupr | Physically Completed | 1490283.03 | 885409.2 | 2025-11-27 | 2026-06-11
JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701005051/LD/22012034957342 — Construction of Stone Peripheral Bund choti deeg par nurpur | Physically Completed | 1492013.91 | 938095.8 | 2025-11-28 | 2026-06-11
JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701005051/LD/22012034957344 — construction of stone peripheral bund jagi baba ka mandir dang par badona | Physically Completed | 1491833.61 | 923871.67 | 2025-12-21 | 2026-06-11
JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701005051/LD/22012034961187 — फेरीफेरल स्टोन बंड निर्माण कार्य पुराने खेरे पर बड़ोंना | Physically Completed | 1497003.9 | 1221713.38 | 2026-01-24 | 2026-06-11
JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701005051/LD/22012034961188 — फेरीफेरल स्टोन बंड निर्माण कार्य पुलिया के पास बड़ोंना | Physically Completed | 1494672.53 | 1176580.9 | 2026-01-24 | 2026-06-11
JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701005051/LD/22012034961189 — फेरीफेरल स्टोन बंड निर्माण कार्य पुराना स्थान देवता पर बड़ोंना | Physically Completed | 1494672.53 | 1257748.2 | 2026-01-24 | 2026-06-11
JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701005051/LD/22012034961190 — फेरीफेरल स्टोन बंड निर्माण कार्य पंचायत भवन के पास बड़ोंना | Physically Completed | 1494672.53 | 1192471.92 | 2026-01-24 | 2026-06-19
JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701005051/LD/22012034961191 — फेरीफेरल स्टोन बंड निर्माण कार्य सामुदायिक भवन के पास डंगरिया | Physically Completed | 1497003.9 | 1310427.16 | 2026-01-24 | 2026-06-11
JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701005051/LD/22012034961192 — फेरीफेरल स्टोन बंड निर्माण कार्य कलिका माता मंदिर बड़ोंना | Physically Completed | 1494672.53 | 1307320.3 | 2026-01-24 | 2026-06-11
JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701005051/LD/22012034961193 — फेरीफेरल स्टोन बंड निर्माण कार्य आंगनबाड़ी भवन के पास बड़ोंना | Physically Completed | 1494672.53 | 1293258.9 | 2026-01-24 | 2026-06-11
JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701005051/LD/22012034961194 — फेरीफेरल स्टोन बंड निर्माण कार्य चामड माता मंदिर पुराना गांव बड़ोंना | Physically Completed | 1497003.9 | 1214926.56 | 2026-01-24 | 2026-06-11
JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701005051/LD/22012034961195 — फेरीफेरल स्टोन बंड निर्माण कार्य हनुमान मंदिर बड़ोंना | Physically Completed | 1494686.95 | 1327706.16 | 2026-01-24 | 2026-06-11
JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701005051/LD/22012034961196 — फेरीफेरल स्टोन बंड निर्माण कार्य क्रेसर के पास नूरपुर | Physically Completed | 1494672.53 | 1216803.14 | 2026-01-24 | 2026-06-11
JOURA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005051/RC/22012034163995 — सी सी खरंजा स्कूल से यादव मोहल्ला | Deleted | 0 | 0 | 2013-01-26
JOURA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005051/RC/22012034163996 — सी सी खरंजा कमलेश के माकन से उत्तम के माकन तक | Deleted | 0 | 0 | 2013-01-26
JOURA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701005051/RC/22012034163997 — पत्थर खरंजा स्कूल से नदी तक | Deleted | 0 | 0 | 2013-01-26
JOURA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005051/RC/22012034164895 — पंच परमेश्‍वर सीसी खरेजा नाली निर्माण रविन्‍द्र के मकान से तिराहे की ओर | Deleted | 359607 | 0 | 2012-10-02
JOURA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701005051/RC/22012034188850 — पत्‍थर खरंजा निर्माण स्‍कूल से पुराने गांव की ओर | Completed | 485000 | 447146.29 | 2013-10-04 | 2016-05-19
JOURA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005051/RC/22012034205959 — सी.सी. खरंजा निर्माण कमलेश के मकान से मोजी बरेठा क | Completed | 77031 | 58668 | 2014-02-18 | 2014-11-20
JOURA | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701005051/RC/22012034222962 — मिट्टी ग्रेवल रोड हथरिया रोड से पहाड़ी तक बड़ोना | Completed | 1366000 | 551025.9 | 2014-06-24 | 2016-09-22
JOURA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701005051/RC/22012034289318 — पत्थर खरंजा निर्माण PMGSY रोड से कुशवाह पुरा तक | Completed | 715000 | 527492.03 | 2015-11-17 | 2017-04-02
JOURA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701005051/RC/22012034293530 — पत्थर खरंजा निर्माण हरिजन बस्ती से पंचायत भवन की ओर | Completed | 1120000 | 3816 | 2015-12-22 | 2017-04-02
JOURA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701005051/RC/22012034293532 — पत्थर खरंजा निर्माण खेरा घाट से ककरधा की ओर | Completed | 792000 | 375435 | 2015-12-22 | 2017-04-02
JOURA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701005051/RC/22012034307360 — मिटटी ग्रेवल रोड कुशवाह के पूरा से दुलेह्नी का पूरा की ओर | Deleted | 0 | 0 | 2016-01-26
JOURA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701005051/RC/22012034307361 — पत्थर खरंजा निर्माण हनुमानजी से कुशवाह के पूरा की ओर | Deleted | 0 | 0 | 2016-01-26
JOURA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701005051/RC/22012034328817 — Mitti gravel road badona | Deleted | 0 | 0 | 2017-01-26
JOURA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005051/RC/22012034385430 — c c road may nali brandavan baghel ke makan se hebi jadon ke makan tak | Deleted | 59385 | 0 | 2017-01-26
JOURA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005051/RC/22012034385440 — c.c.road may nali munna yadav ke makan se kamal giri ke makan tak | Deleted | 62208 | 0 | 2017-10-02
JOURA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005051/RC/22012034444712 — सी सी खरंजा निर्माण चिंतामन के मकान से सीता कुशवाह के मकान तक ग्राम बडोना | Closed | 0 | 0 | 2018-10-02
JOURA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005051/RC/22012034444713 — सी सी खरंजा निर्माण चिंतामन के मकान से सीता कुशवाह के मकान तक ग्राम बडोना | Completed | 118518 | 116676 | 2019-03-07 | 2019-09-06
JOURA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005051/RC/22012034505819 — CC kharnaja nirman seema ke makan se PMGSY Road tak | Completed | 144383 | 142044 | 2020-02-18 | 2020-07-11
JOURA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Mitti Murram Roads for Community / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701005051/RC/22012034526322 — sudura sampark road samudayabhan se uchit muly dukan ke or | Completed | 1491228.96 | 1435652 | 2020-06-30 | 2023-04-12
JOURA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005051/RC/22012034594011 — cc kharnja nirman kaptan ke makan se subhash ke makan tak nurpur badona | Completed | 82230 | 79709 | 2021-12-04 | 2022-05-12
JOURA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005051/RC/22012034601461 — see see khranja nirman hanuman mandir se taver ki or | Completed | 66952 | 60216 | 2021-12-04 | 2022-07-10
JOURA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005051/RC/22012034601462 — see see khranja nirman nihal ke makan se shripati ke makan tak | Completed | 27543 | 32231 | 2021-12-04 | 2022-07-15
JOURA | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005051/RC/22012034627362 — C C kharanja Norman karya prathmik shala bhavan we hanuman mandir ki or | Closed | 0 | 0 | 2022-10-02
JOURA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701005051/RC/22012034646518 — सुदूर सम्पर्क रोड बडोना से हवेली पूरा की ओर | Completed | 2442721.79 | 2424178.1 | 2023-09-04 | 2024-10-05
JOURA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701005051/RC/22012034834009 — सुदूर खेत सड़क निर्माण मेन रोड नूरपुर से राजेंद्र यादव के खेत की ओर | Physically Completed | 1709649.32 | 1682331.6 | 2025-03-11 | 2026-05-22
JOURA | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701005051/RC/449 — मिटटी ग्रेवल रोड निर्माण कार्य रघुवर की हवेली से पहाडी तक | Completed | 0 | 424107.55 | 2010-06-02 | 2014-03-01
JOURA | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Metal Second coat / Construction of WBM Roads for Community | Construction of Road and Culvert | 1701005051/RC/502 — पत्‍थर खरंजा निमार्ण हेण्‍ड पम्‍प से रघूवर के मकान तक | Completed | 0 | 187149.54 | 2011-08-04 | 2014-05-01
JOURA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005051/RC/577 — सी.सी. खरंजा बच्‍चू सिंह के मकान से उत्‍तम सिंह के मकान तक | Completed | 38673 | 26929.66 | 2012-05-22 | 2014-04-01
JOURA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701005051/RC/622 — सी.सी. खरंजा निर्माण पातीराम के मकान से हरीशंकर के मकान तक | Completed | 60778 | 38749.7 | 2012-10-09 | 2012-11-01
JOURA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701005051/RC/682 — पत्‍थर खरंजा रविन्‍द्र के मकान से पहाडी तक | Completed | 496000 | 386419.4 | 2013-03-01 | 2015-04-03
JOURA | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701005051/RC/92 — सी सी खरंजा निर्माण कार्य गोटाराम के घर | Completed | 100700 | 45500 | 2009-02-17 | 2009-03-03
JOURA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701005051/RS/22012034399767 — शौचालय निर्माण जयनारायण कुशवाह | Closed | 12000 | 0 | 2018-01-26
JOURA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701005051/RS/22012034399773 — शौचालय निर्माण कमलेश कुशवाह | Closed | 12000 | 0 | 2018-01-26
JOURA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701005051/RS/22012034399775 — शौचालय निर्माण सरनदेइ | Closed | 12000 | 0 | 2018-01-26
JOURA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1701005051/RS/22012034520361 — Nadep karya sankhaya 5badona | Closed | 0 | 0 | 2021-04-14
JOURA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1701005051/RS/22012034520364 — Nadep karya 5 norpur | Completed | 91871.58 | 81946 | 2021-10-01 | 2023-07-01
JOURA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of NADEP Compost structure for Groups / Construction of NADEP Compost structure for Groups | Construction of NADEP/Vermi Compost Pit | 1701005051/RS/22012034574737 — Nadep kary 5 badona | Completed | 94096.09 | 70688 | 2021-11-13 | 2023-10-08
JOURA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1701005051/RS/22012034607873 — naveen swachata parisar samudayak bhavan ke pass kushwaha ka pura badona | Completed | 43000 | 40530 | 2021-11-28 | 2023-07-26
JOURA | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of NADEP Compost structure for Groups / Construction of NADEP Compost structure for Groups | Construction of NADEP/Vermi Compost Pit | 1701005051/RS/22012034666514 — Nadep 14gp badona | Completed | 265454.43 | 230902.32 | 2023-01-15 | 2023-07-01
JOURA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of NADEP Compost structure for Groups / Construction of NADEP Compost structure for Groups | Construction of NADEP/Vermi Compost Pit | 1701005051/RS/22012034688214 — नाडेप कार्य समुदायक 50 बडोना | Completed | 1099963.7 | 991958.9 | 2023-07-10 | 2023-09-27
JOURA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1701005051/RS/22012034699945 — नाडेप निर्माण कार्य संख्या 60 बडोना | Completed | 1287312.36 | 1119734 | 2023-08-07 | 2023-12-08
JOURA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1701005051/RS/22012034703418 — नादेप निर्माण कार्य संख्या 60 | Completed | 1287312.36 | 1087068.75 | 2023-10-16 | 2024-10-05
JOURA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005051/WC/155 — सोक्‍ता गडडा प्रा0 वि0 के पास हैण्‍ड बडौना | Deleted | 10500 | 0 | 2008-04-15
JOURA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005051/WC/156 — सोक फिट गडडा कुशवाह मो0 हेण्‍ड पम्‍प के पास | Completed | 11500 | 11126 | 2009-02-10 | 2010-11-02
JOURA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005051/WC/157 — सोक फिट गडडा अनु0 जा0 मो0 हेण्‍ड पम्‍प के पास | Completed | 11500 | 10411 | 2009-02-17 | 2010-11-29
JOURA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005051/WC/158 — सोक फिट गडडा तिराह के हेण्‍ड पम्‍प के पास | Completed | 11500 | 10462.61 | 2009-01-20 | 2010-11-29
JOURA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005051/WC/159 — सोक फिट गडडा मा0 वि0 के हेण्‍ड पम्‍प के पास | Completed | 11500 | 9610 | 2009-01-27 | 2010-11-22
JOURA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005051/WC/160 — सोक फिट गडडा प्रा0 वि0 हेण्‍ड पम्‍प के पास | Completed | 11500 | 10789 | 2008-12-03 | 2010-11-15
JOURA | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Wasteland Block Plantation-Forstry-Community / Wasteland Block Plantation of Forestry Trees for Community | Plantation | 1701005051/WC/22012034380596 — naveen talab nirman | Closed | 0 | 0 | 2017-10-02
JOURA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & Maint of Earthen Check Dam for Community / Repair and Maintenance of Earthen Check Dam for Community | Repair & Maint of Check Dam/Stop Dam | 1701005051/WC/22012034444706 — चेक डैम निर्माण कार्य -हवेली की उपरी डगईया | Completed | 1451000 | 1423378.95 | 2019-03-04 | 2021-01-02
JOURA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1701005051/WC/22012034561029 — Talab nirman kary railway patri ke pass | Completed | 1473009.04 | 1368348 | 2020-06-20 | 2021-09-22
JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1701005051/WC/22012034674699 — sokhata gadda vinod ke makan ke pas | Closed | 18382.8 | 0 | 2021-04-14
JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1701005051/WC/22012034681265 — Sokhath gadh kapatan ke makan ke pas | Completed | 18382.8 | 17595 | 2021-05-13 | 2021-10-15
JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1701005051/WC/22012034681288 — Sokhat gadha devgiri ka makan ke pass | Completed | 18382.8 | 17570 | 2021-05-13 | 2021-10-15
JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1701005051/WC/22012034681311 — Sokhat gadha samudhaya bhavan ke pass | Completed | 18382.8 | 17632 | 2021-10-25 | 2021-11-17
JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1701005051/WC/22012034681338 — Sokhat gadha rajendra ke makan ke pass | Closed | 18382.8 | 0 | 2021-04-14
JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1701005051/WC/22012034684143 — Sokhat gadha rampalkemakan ke pass | Completed | 18382.8 | 15279 | 2021-05-13 | 2021-10-15
JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1701005051/WC/22012034740358 — Water havesting kary panchyath bhan | Completed | 22173.14 | 18987.2 | 2021-06-16 | 2021-10-15
JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005051/WC/22012034740365 — Water havesting kary school badona | Deleted | 22229.14 | 0 | 2021-04-14
JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005051/WC/22012034740366 — Water havesting kary school badona | Deleted | 22229.14 | 0 | 2021-04-14
JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005051/WC/22012034749634 — water harvesting samudayak bhavan badona | Completed | 22173.14 | 21303.2 | 2021-08-17 | 2021-10-22
JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1701005051/WC/22012034835271 — Sokatha gadha gram panchayat badona3 sn | Completed | 55325.77 | 51500 | 2021-10-18 | 2021-11-17
JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005051/WC/22012034835274 — Water havesting kary samudhayak bhavannorpur | Completed | 22229.14 | 15380 | 2021-10-18 | 2021-11-17
JOURA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701005051/WC/22012034991303 — Rapata nirmad karya puleya ke pass | Completed | 1496611.41 | 1336171.1 | 2022-09-07 | 2023-07-27
JOURA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005051/WC/22012034998630 — Sokhat gadha 14 gpbadona | Completed | 270561.18 | 156179.3 | 2023-01-15 | 2023-07-01
JOURA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005051/WC/22012035006379 — रपटा निर्माण कार्य राजघाट के पुरा वाले रास्ते पर | Completed | 1484270.48 | 1447340.5 | 2022-11-06 | 2023-07-27
JOURA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005051/WC/22012035006382 — रपटा निर्माण कार्य खेल मैदान वाली रोड पर | Completed | 1486702.07 | 1402401.5 | 2022-11-06 | 2023-07-27
JOURA | 2023-2024 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Construction of Embankment for community / Construction of Embankment for community | Construction of Embankment | 1701005051/WC/22012035041070 — रपटा निर्माण कार्य चेक डेम निर्माण वाले रास्ते पर बडोना | Completed | 1435033.51 | 986824.5 | 2023-07-10 | 2023-12-08
JOURA | 2022-2023 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Construction of Embankment for community / Construction of Embankment for community | Construction of Embankment | 1701005051/WC/22012035041074 — रपटा निर्माण कार्य राजेश के मकान वाले रास्ते पर बडोना | Closed | 0 | 0 | 2022-10-02
JOURA | 2023-2024 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Construction of Embankment for community / Construction of Embankment for community | Construction of Embankment | 1701005051/WC/22012035041076 — रपटा निर्माण कार्य हनुमान मंदिर वाले रास्ते पर बडोना | Completed | 1446898.87 | 920167.5 | 2023-07-10 | 2023-12-14
JOURA | 2023-2024 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Construction of Embankment for community / Construction of Embankment for community | Construction of Embankment | 1701005051/WC/22012035041078 — रपटा निर्माण कार्य पंचायत भवन वाले रास्ते पर बडोना | Completed | 1476119.42 | 1024699.5 | 2023-07-10 | 2023-12-08
JOURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005051/WC/22012035073755 — रपटा निर्माण कार्य स्कूल के पास नूरपुर | Closed | 0 | 0 | 2023-04-14
JOURA | 2023-2024 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1701005051/WC/22012035092152 — रपटा निर्माण कार्य राजेश के मकान के पास | Completed | 1477455.34 | 741270 | 2023-08-07 | 2024-05-03
JOURA | 2023-2024 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1701005051/WC/22012035092153 — रपटा निर्माण कार्य स्कूल के पास नूरपुर | Completed | 1481887.13 | 725130.5 | 2023-08-07 | 2024-05-03
JOURA | 2023-2024 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1701005051/WC/22012035092154 — रपटा निर्माण कार्य प्रेम गिर गोस्वामी के मकान से पास | Completed | 1472299.51 | 716219 | 2023-08-07 | 2024-05-03
JOURA | 2023-2024 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1701005051/WC/22012035092155 — रपटा निर्माण कार्य पहाड़ी बाले राशते पर | Completed | 1489278.33 | 1213677 | 2023-08-07 | 2024-05-03
JOURA | 2023-2024 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1701005051/WC/22012035103282 — रपटा निर्माण कार्य पहाड़ी बले रास्ते पर | Completed | 1498640.69 | 1424490.95 | 2023-09-18 | 2024-10-05
JOURA | 2023-2024 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1701005051/WC/22012035103284 — रपटा निर्माण कार्य नूरपुर बाले रास्ते पर | Completed | 1493285.37 | 1404988.95 | 2023-09-18 | 2024-10-05
JOURA | 2023-2024 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1701005051/WC/22012035103287 — रपटा निर्माण कार्य आसान नदी बले रास्ते पर | Completed | 1475270.86 | 1411584.95 | 2023-09-18 | 2024-10-05
JOURA | 2023-2024 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1701005051/WC/22012035103288 — रपटा निर्माण कार्य पुराने गाव के पास | Completed | 1479022.97 | 1447508.95 | 2023-09-18 | 2024-10-05
JOURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1701005051/WC/22012035154392 — rapta nirman kary badi khor | Completed | 1475284.43 | 1392020.5 | 2024-03-18 | 2024-10-05
JOURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1701005051/WC/22012035154395 — rapta nirman kary railvay line ke pass | Completed | 1477684.66 | 1381633.5 | 2024-03-18 | 2024-10-05
JOURA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1701005051/WC/22012035154403 — rapta nirman kary kreshar bale rasta per | Completed | 1472518.93 | 1364269.5 | 2024-04-08 | 2024-10-05
JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005051/WC/22012035154404 — rapta nirman kary haveli bale raste per | Completed | 1487560.95 | 1447026.5 | 2024-04-08 | 2024-10-05
JOURA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1701005051/WC/22012035154406 — rapta nirman kary railve fatak ke pass | Completed | 1489283.27 | 1354228 | 2024-04-08 | 2024-10-05
JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005051/WC/22012035191577 — रपटा निर्माण कार्य दंग वाले रास्ते पर | Completed | 1458170.99 | 1401250 | 2024-05-06 | 2024-10-05
JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005051/WC/22012035191584 — रपटा निर्माण कार्य राजघाट के पुरा वाले रास्ते पर | Completed | 1495691.38 | 1448241.5 | 2024-05-13 | 2024-10-05
JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005051/WC/22012035191587 — रपटा निर्माण कार्य हवेली पुरा वाले रास्ते पर | Completed | 1461990.04 | 1412127.5 | 2024-05-13 | 2024-10-05
JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005051/WC/22012035191594 — रपटा निर्माण कार्य हनुमान मंदिर वाले रास्ते पर | Completed | 1431601.28 | 1334525.5 | 2024-05-13 | 2024-10-05
JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005051/WC/22012035191599 — Rapta Nirman Karya badona wale raste par | Completed | 1450553.59 | 1386428 | 2024-06-10 | 2024-11-29
JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005051/WC/22012035191602 — रपटा निर्माण कार्य कमलेश कुशवाह के पुरा वाले रास्ते पर | Completed | 1429528 | 1392772.6 | 2024-06-10 | 2024-11-29
JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005051/WC/22012035214448 — तालाब निर्माण कार्य मुन्नी के खेत के पास | Completed | 1495047.77 | 1444867 | 2024-07-22 | 2024-11-30
JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005051/WC/22012035217145 — तालाब निर्माण कार्य हनुमान मंदिर के पास डंगरिया | Completed | 1499605.84 | 1454007 | 2024-07-22 | 2024-11-29
JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005051/WC/22012035217146 — तालाब निर्माण कार्य क्रेशर के पास | Approved | 0 | 0 | 2024-06-10
JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005051/WC/22012035217148 — तालाब निर्माण कार्य राजकुमार के खेत के पास | Completed | 1442505.7 | 1378382 | 2024-09-09 | 2024-11-29
JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005051/WC/22012035217149 — तालाब निर्माण कार्य बाबू बाबा के पास डंगरिया | Completed | 1495047.77 | 1453524 | 2024-07-22 | 2024-11-30
JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005051/WC/22012035219704 — परक्युलेशन टैंक पहाड़ी बडोना | Completed | 1499696.3 | 1439353.25 | 2024-09-17 | 2025-07-02
JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005051/WC/22012035220504 — तालाब निर्माण कार्य सिद्धार के खेत के पास बडोना | Approved | 0 | 0 | 2024-08-15
JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005051/WC/22012035220505 — तालाब निर्माण कार्य बनवारी के खेत के पास बडोना | Completed | 1360094.29 | 1318908.25 | 2024-10-14 | 2025-07-02
JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005051/WC/22012035222978 — परक्युलेशन टैंक क्रेशर के पास | Completed | 1462271.19 | 1407724.95 | 2024-10-28 | 2025-07-02
JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005051/WC/22012035223037 — परकुलेशन टैंक सिद्धार के खेत के पास | Completed | 1454452.3 | 1387192.76 | 2024-10-28 | 2025-07-02
JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005051/WC/22012035229790 — परक्युलेशन तालाब निर्माण कार्य राजघाट पूरा के पास नूरपुर | Completed | 1407332.76 | 1367326.1 | 2024-12-30 | 2025-07-02
JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005051/WC/22012035229792 — परक्युलेशन तालाब निर्माण कार्य ओमप्रकाश कुशवाह के खेत के पास | Approved | 0 | 0 | 2024-10-02
JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005051/WC/22012035229794 — परक्युलेशन तालाब निर्माण कार्य सिद्ध बाबा के पास नूरपुर | Approved | 0 | 0 | 2024-10-02
JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005051/WC/22012035229796 — परक्युलेशन तालाब निर्माण कार्य पुराणी पोखर के पास बडोना | Approved | 0 | 0 | 2024-10-02
JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1701005051/WC/22012035235722 — कंटूर ट्रेंच पहाड़ी पर | Completed | 324943.56 | 284309.1 | 2025-02-17 | 2025-06-26
JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1701005051/WC/22012035235727 — कंटूर ट्रेंच निचली खोर | Completed | 380706.45 | 306663.7 | 2025-02-17 | 2026-02-25
JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005051/WC/22012035250927 — तालाब निर्माण कार्य बड़ी खो बडोना | Physically Completed | 1493850.6 | 1426989.31 | 2025-03-04 | 2026-04-16
JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005051/WC/22012035250928 — तालाब निर्माण कार्य निचली पहाड़ी बडोना | Physically Completed | 1484654.32 | 1402059.47 | 2025-03-04 | 2026-04-16
JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005051/WC/22012035250930 — तालाब निर्माण कार्य छोटी पहाड़ी नूरपुर | Physically Completed | 1480987.7 | 1392067.62 | 2025-03-04 | 2026-04-16
JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005051/WC/22012035250933 — तालाब निर्माण कार्य निचली खो नूरपुर | Physically Completed | 1495523.8 | 1434333.57 | 2025-03-04 | 2026-04-16
JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005051/WC/22012035250934 — तालाब निर्माण कार्य शान्तिधाम के पास | Physically Completed | 1495476.82 | 1419485.76 | 2025-03-04 | 2026-04-16
JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005051/WC/22012035250935 — तालाब निर्माण कार्य खेल मैदान के पास | Physically Completed | 1488419.02 | 1421426.35 | 2025-03-04 | 2026-04-16
JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005051/WC/22012035250936 — तालाब निर्माण कार्य उत्तम के खेत के पास | Physically Completed | 1495523.8 | 1440066.78 | 2025-03-04 | 2026-04-16
JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005051/WC/22012035250938 — तालाब निर्माण कार्य विजय सिंह के खेत के पास | Physically Completed | 1494385.32 | 1432457.26 | 2025-03-04 | 2026-04-16
JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005051/WC/22012035250939 — तालाब निर्माण कार्य राकेश के खेत के पास | Physically Completed | 1488419.02 | 1417658.13 | 2025-03-04 | 2026-04-16
JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005051/WC/22012035250941 — तालाब निर्माण कार्य रेलवे क्रासिंग के पास | Physically Completed | 1498244.66 | 1421764.19 | 2025-03-04 | 2026-04-16
JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005051/WC/22012035255272 — talab nirman karay holu ke khet ke pass | Physically Completed | 1487272.59 | 1418881.86 | 2025-07-04 | 2026-04-16
JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005051/WC/22012035255273 — talab nirman karay baijnath ke khet ke pass | Physically Completed | 1487272.59 | 1421755.07 | 2025-07-04 | 2026-04-16
JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005051/WC/22012035255276 — Talav Nirman Karaya badi mori ke pass | New | 0 | 0 | 2025-01-26
JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005051/WC/22012035255277 — Talav Nirman Karaya badi mori ke pass | Physically Completed | 1496305.48 | 1415930.94 | 2025-07-04 | 2026-04-16
JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005051/WC/22012035255397 — Talav Nirman karaya main road nurpur | Physically Completed | 1496893.98 | 1430529.43 | 2025-07-04 | 2026-04-16
JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005051/WC/22012035255399 — Talav nirman karya nari wale khar par | Physically Completed | 1492503.93 | 1405248.43 | 2025-07-04 | 2026-04-16
JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005051/WC/22012035255400 — Talav nirman karya jharna wale nare par | Physically Completed | 1490412.43 | 1414358.67 | 2025-07-04 | 2026-04-16
JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005051/WC/22012035255401 — Talav nirman karya purani khor par | Physically Completed | 1484654.32 | 1394344.07 | 2025-07-04 | 2026-04-16
JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005051/WC/22012035255402 — talav nirman karya choti nari ke pass | Physically Completed | 1482562.82 | 1406591.71 | 2025-07-04 | 2026-04-16
JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005051/WC/22012035255403 — talav nirman karya choti puliya ke pass | Physically Completed | 1488364.09 | 1424978.51 | 2025-07-04 | 2026-04-16
JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005051/WC/22012035255404 — talav nirman karya tularam ke khet ke pass | Physically Completed | 1494595.43 | 1423779.21 | 2025-07-04 | 2026-04-16
JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005051/WC/22012035328860 — talab nirman karya purane gao ke pass | Physically Completed | 1488327.29 | 1145032.34 | 2026-03-01 | 2026-06-21
JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005051/WC/22012035328861 — talab nirman bade par ke paas | Physically Completed | 1487996.78 | 1125192.93 | 2026-03-01 | 2026-06-21
JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005051/WC/22012035328863 — Talab nirman karya dhrub ke khet ke pass | Physically Completed | 1489765.13 | 1233434.25 | 2026-03-01 | 2026-06-21
JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005051/WC/22012035328864 — talab nirman karya moji ke khet ke pass | Physically Completed | 1489095.65 | 1154354.17 | 2026-03-01 | 2026-06-21
JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005051/WC/22012035328866 — talab nirman karya pujari ke khet ke pass | Ongoing | 1489663.8 | 1151138.88 | 2026-03-01
JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005051/WC/22012035328867 — talab nirman karya chaine bale ke khet ke pass | Ongoing | 1489765.13 | 932185.41 | 2026-03-01
JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005051/WC/22012035328868 — talab nirman karya badi teer ke pass | Physically Completed | 1488776.62 | 1159213 | 2026-03-02 | 2026-06-21
JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005051/WC/22012035328869 — talab nirman karya dhaniram ke khet ke pass | Ongoing | 1489765.13 | 1232206.24 | 2026-03-08
JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005051/WC/22012035328870 — talab nirman karya ladbay ke pass | Physically Completed | 1489046.21 | 1305621 | 2026-03-02 | 2026-06-21
JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005051/WC/22012035328871 — talab nirman karya chote kuaa ke pass | Ongoing | 1489765.13 | 1132238.77 | 2026-03-01
JOURA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005051/WC/52 — सोखता गडडा निर्माण कार्य | Completed | 0 | 1020 | 2008-05-21 | 2010-06-11
JOURA | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005051/WC/912 — सोक्‍ता गडडा प्रा0 वि0 के पास हैण्‍ड बडौना | Completed | 10500 | 10422 | 2010-02-22 | 2008-04-15
JOURA | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005051/WC/913 — सोक पिट कार्य शा. प्रा. विद्यालय | Completed | 10500 | 11116 | 2010-03-26 | 2010-10-29
JOURA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Excavation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1701005051/WH/2 — कूप निर्माण कार्य | Completed | 0 | 11250 | 2008-05-25 | 2011-06-11
JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation of Fisheries Ponds for Community / Renovation of Fisheries Ponds for Community | Repair & maint of Pond/ Tank | 1701005051/WH/22012034447962 — contour trench pahadi per | Completed | 981624.15 | 568771 | 2021-05-30 | 2022-05-06
JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1701005051/WH/22012034941693 — तालाब निर्माण कार्य मुन्नी के खेत के पास | Approved | 0 | 0 | 2024-04-14
JOURA | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Excavation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1701005051/WH/3 — कूप निर्माण कार्य | Deleted | 0 | 0 | 2007-10-17