## Work List
Exported on: 2026-09-09 18:41:29
Filters applied:
Data source: MGNREGA + VBGRAMG
District: MORENA
Block: All
Panchayat: NANDPURA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
JOURA | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1701005065/AV/22012034636519 — सामुदायिक स्वच्छता परिसर डाबरपुरा के शिम्भुपूरी बाबा के स्थान पर | Closed | 0 | 0 | 2023-04-14
JOURA | 2015-2016 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | AWC / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1701005065/AV/3734 — Anganwadi/Other Rural Infrastructure,JOURA | Completed | 297768 | 247444.23 | 2015-09-28 | 2018-08-14
JOURA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Land Development / Levelling/shaping of Wasteland Land for Community | Land Development | 1701005065/DP/162 — शांतीधाम निर्माण कार्य म‍थुरापुरा | Completed | 481235 | 490997.73 | 2011-11-25 | 2012-06-17
JOURA | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1701005065/DP/22012034238398 — शांतिधाम मय टीन शेड सहित ग्राम डाबरपुरा | Deleted | 180000 | 0 | 2017-02-27
JOURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005065/DP/22012034610134 — Rapta nirman kary hem Singh ke khet ke pas | Closed | 0 | 0 | 2023-08-15
JOURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005065/DP/22012034610135 — Rapta nirman kary bhoora ke khet ke niche | Closed | 0 | 0 | 2023-08-15
JOURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005065/DP/22012034610137 — Rapta nirman kary kesi ke khet ke pas | Closed | 0 | 0 | 2023-08-15
JOURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005065/DP/22012034610138 — Rapta nirman kary lallu ke khet ke pas | Closed | 0 | 0 | 2023-08-15
JOURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005065/DP/22012034610139 — Rapta nirman kary seru ke khet ke pas | Closed | 0 | 0 | 2023-08-15
JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701005065/DP/22012034618494 — brachharopad karya panchayat bhavan ke pas | Closed | 149493.38 | 0 | 2024-09-17
JOURA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701005065/DP/50 — हरियाली महोत्‍सव सम्‍भू पुरीबाग | Completed | 0 | 5372 | 2009-02-07 | 2016-10-04
JOURA | 2017-2018 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Construction of Storm Water Drains / Construction of Storm Water drain for coastal protection for Community | Works for Flood Control and Protection | 1701005065/FP/22012034314326 — पत्थर नाला निर्माण कार्य रघुवीर सिंह के माकन से बेहड़ की ओर | Completed | 1496500 | 885355.48 | 2017-12-04 | 2018-06-16
JOURA | 2016-2017 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Drainage in Water Logged Areas / Drainage of Community Waterlogged Land | Works for Flood Control and Protection | 1701005065/FP/22012034314329 — पत्थर नाला निर्माण हनुमान मंदिर से तालाब तक नंदपुरा | Completed | 943000 | 808707.05 | 2017-03-06 | 2017-09-11
JOURA | 2017-2018 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Drainage in Water Logged Areas / Drainage of Community Waterlogged Land | Works for Flood Control and Protection | 1701005065/FP/22012034328942 — पत्थर नाला निर्माण कार्य शिवचरण के मकान से बड़े तालाब के ओर नंदपुरा | Completed | 762000 | 494991 | 2017-08-28 | 2018-06-12
JOURA | 2017-2018 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Drainage in Water Logged Areas / Drainage of Community Waterlogged Land | Works for Flood Control and Protection | 1701005065/FP/22012034328943 — पत्थर नाला निर्माण कार्य कालीचरण के मकान से हनुमान मंदिर होते हुए शिवचरण के मकान की ओर नंदपुरा | Completed | 1267000 | 1089366.16 | 2017-08-22 | 2018-06-29
JOURA | 2017-2018 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Drainage in Water Logged Areas / Drainage of Community Waterlogged Land | Works for Flood Control and Protection | 1701005065/FP/22012034360057 — पत्थर नाला निर्माण कार्य सुन्दर सिंह के घर से भूरी वाले तालाब की और | Completed | 1024498 | 782737.09 | 2017-10-30 | 2018-07-15
JOURA | 2018-2019 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701005065/FP/22012034362339 — पत्थर नाला निर्माण कार्य नन्दपुरा | Closed | 0 | 0 | 2018-10-02
JOURA | 2020-2021 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005065/FP/22012034369337 — नाला निर्माण कार्य रामभजन के घर से मिडिल स्कूल की ओर | Completed | 1433923.4 | 1184503.2 | 2021-03-06 | 2022-12-12
JOURA | 2020-2021 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005065/FP/22012034369338 — नाला निर्माण कार्य अमर सिंह के घर से मैन रोड की ओर | Completed | 1458107.46 | 1246974.6 | 2021-03-06 | 2022-12-12
JOURA | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005065/FP/22012034628340 — पत्थर नाला केनाल रोड से गुड्डू के आम की ओर | Completed | 1487670.8 | 1428244 | 2022-03-25 | 2023-07-20
JOURA | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005065/FP/22012034628341 — पत्थर नाला गुड्डू के आम बेहर की ओर | Ongoing | 1485227.43 | 1468728 | 2022-03-25
JOURA | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005065/FP/22012034628342 — पत्थर नाला केनाल से बासुदेव के खेत की ओर | Completed | 1482784.09 | 1396060 | 2022-03-25 | 2022-09-25
JOURA | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005065/FP/22012034628343 — पत्थर नाला वासुदेव के खेत से बेहड की ओर | Completed | 1480340.74 | 1296482.27 | 2022-03-25 | 2023-09-30
JOURA | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005065/FP/22012034628615 — pathar nala ramnivash ke ghar se hanuman ji ke mandir tak | Physically Completed | 1493093.57 | 1372156 | 2022-05-03 | 2026-05-21
JOURA | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Repair & Maint of Flood/Diversion Channel for Comm / Repair and Maintenance of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005065/FP/22012034628616 — rapta nirman santosh ki ghar par savada road | Completed | 1388377.23 | 1199232.66 | 2022-05-12 | 2023-09-30
JOURA | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Repair & Maint of Flood/Diversion Channel for Comm / Repair and Maintenance of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005065/FP/22012034628617 — rapta nirman ret ghata par samda raod | Closed | 1394874.42 | 0 | 2022-04-01
JOURA | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005065/FP/22012034628650 — kachha nala kenal se hanuman ji ke mandir ki or | Completed | 982866 | 976752 | 2022-05-02 | 2022-07-10
JOURA | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005065/FP/22012034628651 — kaccha nala tal se bade talab ki or | Completed | 989418.44 | 974304 | 2022-05-02 | 2022-07-12
JOURA | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Renovation of Flood/ Diversion Channel for Comm / Renovation of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005065/FP/22012034628652 — kachha nala kenal se ramuji vale ki or | Closed | 0 | 0 | 2022-04-01
JOURA | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Renovation of Flood/ Diversion Channel for Comm / Renovation of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005065/FP/22012034628733 — Pathar nala gurjar ke makan se pipri ki or | Completed | 1489539.07 | 1248246 | 2022-05-18 | 2023-09-30
JOURA | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005065/FP/22012034628928 — पत्थर नाला नरुआ से pmgy रोड की ओर नंदपुरा | Completed | 1460843.84 | 1350797 | 2022-05-18 | 2023-09-30
JOURA | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Renovation of Flood/ Diversion Channel for Comm / Renovation of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005065/FP/22012034628929 — पत्थर नाला निर्माण मुन्ना के घर से आम की ओर | Completed | 1449817.74 | 1434202 | 2022-05-18 | 2023-09-30
JOURA | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Renovation of Flood/ Diversion Channel for Comm / Renovation of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005065/FP/22012034628930 — पत्थर नाला छोटे तालाब से ढाब की ओर | Completed | 1477177.25 | 1189952.28 | 2022-05-18 | 2023-09-30
JOURA | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005065/FP/22012034628931 — पत्थर नाला निर्माण कार्य नंदपुरा | Closed | 1484531.93 | 0 | 2022-04-01
JOURA | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005065/FP/22012034628932 — पत्थर नाला निर्माण कार्य मथुरापुर | Completed | 1487014.44 | 1399538 | 2022-05-18 | 2023-07-20
JOURA | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Renovation of Flood/ Diversion Channel for Comm / Renovation of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005065/FP/22012034628933 — रपटा भूरा के खेत के पास नंदपुरा | Completed | 1485400.37 | 1193759.17 | 2022-05-18 | 2023-09-30
JOURA | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Renovation of Flood/ Diversion Channel for Comm / Renovation of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005065/FP/22012034633436 — पत्थर नाला निर्माण कार्य मथुरापुर बदले प्रजापति के मकान से जंगल की ओर | Completed | 1434267.07 | 1210864.3 | 2023-10-10 | 2024-12-11
JOURA | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Renovation of Flood/ Diversion Channel for Comm / Renovation of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005065/FP/22012034633437 — पत्थर नाला निर्माण कार्य डाबर का पूरा मान सिंह के मकान से आगनबाड़ी की ओर | Completed | 1483958.56 | 1232451 | 2023-08-14 | 2024-12-11
JOURA | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Renovation of Flood/ Diversion Channel for Comm / Renovation of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005065/FP/22012034633438 — पत्थर नाला निर्माण कार्य रामवीर के मकान से सामुदायिक शौंचालय की ओर नंदपुरा | Ongoing | 1496493.44 | 765733 | 2023-07-31
JOURA | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005065/FP/22012034633440 — कच्चा नाला निर्माण कार्य सुरेश के खेत से बढ़ाने बाले के खेत की ओर | Closed | 0 | 0 | 2023-04-14
JOURA | 2024-2025 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701005065/FP/22012034639675 — Patthar nallah nirman rinku ke ghar se ramautar ki or avm gulli ke makan se raste ki or | Ongoing | 1495713.57 | 322682.35 | 2024-10-18
JOURA | 2024-2025 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701005065/FP/22012034639676 — patthar nala nirman hariom ke ghar se jaina ke plot ke raste avm ramnaresh ke ghar ke raste ki or | Ongoing | 1499959.9 | 325581.17 | 2024-10-18
JOURA | 2024-2025 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701005065/FP/22012034639678 — patthar nala nirman rajesh ke khet se pillu ke khet ki or avm tal se ghansu ke ghar se raste ki or | Ongoing | 1499959.9 | 321656.48 | 2024-10-18
JOURA | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701005065/FP/22012034639679 — patthar nala nirman lokendra ke khet se kulbe ke raste avm faal ki or | Deleted | 0 | 0 | 2024-01-26
JOURA | 2024-2025 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701005065/FP/22012034639680 — patthar nala nirman lokendra ke khet se kulbe ke raste avm faal ki or | Ongoing | 1495713.57 | 11664 | 2024-10-18
JOURA | 2024-2025 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701005065/FP/22012034639684 — patthar nala nirman surendra ke khet se mau ke raste avm pradhanmantri sadak ki or | Ongoing | 1499959.9 | 325584.55 | 2024-10-18
JOURA | 2024-2025 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701005065/FP/22012034639686 — patthar nala nirman jitendra singh ke makan se puran ke makan ke raste sonu ke ghar se raste ki or | Ongoing | 1499959.9 | 325644.61 | 2024-10-18
JOURA | 2024-2025 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701005065/FP/22012034639688 — patthar nala nirman pradhanmantri sadak se shankar ji ke mandir avm kalla ke ghar se raste ki or | Ongoing | 1496713.57 | 498980.05 | 2024-10-18
JOURA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701005065/IF/22012034357379 — सड़क किनारे वृक्षारोपण नंदपुरा से शान्तिधाम तक | Closed | 335000 | 0 | 2017-04-26
JOURA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701005065/IF/22012034357385 — सार्वजनिक परिषर राजीवगांधी सेवा केंद्र एवं आंगनवाड़ी नंदपुरा | Suspended | 335000 | 12900 | 2017-07-28
JOURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1701005065/IF/22012035571409 — Khet Talab Nirman Karya Ramraj Ke Khet me | Approved | 0 | 0 | 2025-04-14
JOURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1701005065/IF/22012035571411 — Khet Talab Nirman Karya Shivraj Ke Khet me | Approved | 0 | 0 | 2025-04-14
JOURA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701005065/IF/9993724434 — pashu sed | Deleted | 0 | 0 | 2016-01-26
JOURA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701005065/IF/9993724438 — pashu catle | Deleted | 0 | 0 | 2016-01-26
JOURA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701005065/IF/9993724442 — pashu catle | Deleted | 0 | 0 | 2016-01-26
JOURA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701005065/IF/9993724445 — pashu sed | Deleted | 0 | 0 | 2016-01-26
JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005065/IF/IAY/1889031 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4899508 | Completed | 15660 | 15660 | 2018-10-20 | 2018-12-09
JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005065/IF/IAY/1890117 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5608238 | Completed | 15660 | 15486 | 2018-10-20 | 2018-12-02
JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005065/IF/IAY/1890126 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5585977 | Completed | 15660 | 15660 | 2018-10-20 | 2018-12-09
JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005065/IF/IAY/1890127 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5585973 | Completed | 15660 | 15312 | 2018-12-23 | 2019-05-16
JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005065/IF/IAY/1902922 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5578248 | Completed | 15660 | 15804 | 2019-02-09 | 2019-10-23
JOURA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005065/IF/IAY/1947308 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3685470 | Completed | 17100 | 15960 | 2020-04-29 | 2020-08-21
JOURA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005065/IF/IAY/1947309 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3686244 | Completed | 17100 | 15960 | 2020-08-24 | 2021-05-12
JOURA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005065/IF/IAY/489289 — Construction of IAY House -IAY REG. NO. MP2123104 | Completed | 15030 | 15540 | 2018-02-13 | 2018-10-22
JOURA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005065/IF/IAY/490526 — Construction of IAY House -IAY REG. NO. MP2136112 | Completed | 15030 | 15498 | 2017-02-20 | 2018-08-15
JOURA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005065/IF/IAY/53014 — Construction of IAY House -IAY REG. NO. MP-01-005-065-001/19 | Completed | 14310 | 15456 | 2017-02-20 | 2018-08-23
JOURA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005065/IF/IAY/557700 — Construction of IAY House -IAY REG. NO. MP3580953 | Completed | 15030 | 15444 | 2017-02-20 | 2018-08-15
JOURA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005065/IF/IAY/559631 — Construction of IAY House -IAY REG. NO. MP3645604 | Completed | 15030 | 15432 | 2017-02-20 | 2018-08-15
JOURA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005065/IF/IAY/564026 — Construction of IAY House -IAY REG. NO. MP3808650 | Completed | 15030 | 15498 | 2017-02-20 | 2018-08-23
JOURA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005065/IF/IAY/778961 — Construction of IAY House -IAY REG. NO. MP3933896 | Completed | 15030 | 15552 | 2018-02-13 | 2018-11-26
JOURA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005065/IF/IAY/779187 — Construction of IAY House -IAY REG. NO. MP3947895 | Completed | 15030 | 15540 | 2017-05-01 | 2018-09-19
JOURA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005065/IF/IAY/818815 — Construction of IAY House -IAY REG. NO. MP2116799 | Completed | 15480 | 15486 | 2017-05-01 | 2019-03-20
JOURA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005065/IF/IAY/828579 — Construction of IAY House -IAY REG. NO. MP3633153 | Completed | 15480 | 15528 | 2017-05-01 | 2018-08-15
JOURA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701005065/LD/11 — मैढ बंधान कार्य | Completed | 0 | 9191 | 2009-02-04 | 2009-08-07
JOURA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1701005065/LD/22012034369890 — पंचायत भवन परिसर की बॉउंडरीबॉल का निर्माण, नंदपुरा | Closed | 490460 | 0 | 2018-09-14
JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Development of chaur Land for Community | Land Development | 1701005065/LD/22012034574623 — bhumi samtalikaran karya nandpura | Closed | 0 | 0 | 2021-10-02
JOURA | 2016-2017 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1701005065/PG/9425892204 — खेल मैदान नंदपुरा | Deleted | 320000 | 0 | 2016-10-02
JOURA | 2016-2017 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1701005065/PG/9425892256 — खेल मैदान नंदपुरा | Completed | 320000 | 224043.31 | 2017-01-09 | 2017-07-21
JOURA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005065/RC/22012034164771 — पंच परमेश्‍वर सीसी खरेजा नाी निर्माण कार्य भागीरथ के मकान से घनश्‍याम के मकान तक | Deleted | 65597 | 0 | 2012-10-02
JOURA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005065/RC/22012034184832 — सी.सी. खरंजा निर्माण मेहताव के घर से राजाराम हरिजन के मकान की ओर | Completed | 100666 | 111645.5 | 2013-09-26 | 2015-12-20
JOURA | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005065/RC/22012034227239 — सी ० सी ० खरंजा निर्माण नहर से गुड्डा परमार के घर | Deleted | 0 | 0 | 2014-05-27
JOURA | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005065/RC/22012034227259 — सी ० सी ० खरंजा निर्माण नहर से गुड्डा परमार के घर | Completed | 108304 | 92264 | 2014-08-15 | 2015-10-09
JOURA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701005065/RC/22012034284980 — पत्थर खरंजा निर्माण कार्य राधे गोपी के माकन की और तथा पटेल के मकान से बहादुर के मकान की और | Completed | 799643 | 608648.77 | 2015-09-17 | 2017-01-03
JOURA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005065/RC/22012034292146 — सी सी खरंजा निर्माण बिसम्भर सिह के घर से कल्ला गब्दुआ की और तथा रामनिवास के दूकान से कन्हाई के घर की | Completed | 60862 | 69483 | 2015-12-14 | 2016-03-09
JOURA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701005065/RC/22012034295309 — पत्थर खरंजा निर्माण कार्य नहर से गजेन्द्र के मकान तक डावरपुरा | Completed | 1450536 | 474303.66 | 2016-01-04 | 2017-01-03
JOURA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701005065/RC/22012034295310 — पत्थर खरंजा निर्माण भूकन की दुकान से रामावतार के बाबा के मकान की ओर | Completed | 1425322 | 326639.59 | 2016-01-11 | 2017-01-03
JOURA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701005065/RC/22012034308569 — पुरानी पुलिया से सावदा गाँव की ओर मिटटी ग्रेवल रोड | Deleted | 0 | 0 | 2016-01-26
JOURA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701005065/RC/22012034308570 — नहर से मरघट से होते हुए जण्डेल के कुआ तक | Deleted | 0 | 0 | 2016-01-26
JOURA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701005065/RC/22012034308571 — पिपरी से प्रहलाद के पूरा तक | Deleted | 0 | 0 | 2016-01-26
JOURA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701005065/RC/22012034308572 — जहार सिंह के मकान से भदौरिया के मकान की ओर पत्थर खरंजा | Deleted | 0 | 0 | 2016-01-26
JOURA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701005065/RC/22012034308574 — लाखन सिंह के कुआ से रघुवीर के मकान की ओर पत्थर खरंजा | Deleted | 0 | 0 | 2016-01-26
JOURA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005065/RC/22012034319779 — सी.सी खरंजा एवं नाली निर्माण दुर्जन सिंह के मकान से मैंन रोड तक नंदपुरा | Suspended | 160460 | 132431.1 | 2017-01-09
JOURA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701005065/RC/22012034328956 — सुदूर ग्राम सड़क संपर्क निर्माण कार्य पुरानी पुलिया से साबदा गावं की और नंदपुरा | Completed | 1389000 | 1239824.78 | 2017-02-27 | 2017-09-11
JOURA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701005065/RC/22012034329703 — मिट्टी रोड | Closed | 0 | 0 | 2017-02-18
JOURA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701005065/RC/22012034339653 — सुदूर ग्राम संपर्क सड़क निर्माण कार्य कैनाल रोड से गडरिआ पुरा | Completed | 4785000 | 3705328.77 | 2017-05-29 | 2018-08-17
JOURA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701005065/RC/22012034340553 — सुदूर ग्राम संपर्क सड़क नंदपुरा से शान्तिधाम की और | Completed | 1224000 | 903636.44 | 2017-06-05 | 2018-08-14
JOURA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005065/RC/22012034342847 — सी. सी. खरंजा एवं नाली निर्माण भोले बाबा मंदिर से नरेंद्र के मकान की और | Completed | 546000 | 74304 | 2017-06-26 | 2017-08-05
JOURA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005065/RC/22012034342848 — सी. सी. खरंजा एवं नाली निर्माण जहार सिंह के मकान से बदले प्रजापति के मकान की और मथुरापुरा | Completed | 76950 | 74304 | 2017-06-26 | 2017-09-10
JOURA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005065/RC/22012034434325 — c c road rakesh ke ghar se sevaram k ghar ki or | Closed | 83902.5 | 0 | 2017-08-15
JOURA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Repair & maint of Gravel Road Roads for Comm / Repair and maintenance of Gravel Road Roads for Community | Repair & maint of Road | 1701005065/RC/22012034535179 — सुदूर संपर्क रोड निर्माण कार्य नन्दपुरा से होतम सिंह सिकरवार के पुरा नंदपुरा | Completed | 1205804.35 | 1137837.1 | 2020-09-09 | 2021-02-09
JOURA | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005065/RC/22012034615717 — तालाब निर्माण कार्य बासुदेव के खेत के पास | Closed | 0 | 0 | 2022-04-01
JOURA | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005065/RC/22012034615724 — रपटा निर्माण कार्य चामड़ वाली माता के रोड पर नंदपुरा | Closed | 0 | 0 | 2022-04-01
JOURA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701005065/RC/22012034652102 — सुदूर सड़क निर्माण कार्य प्रधानमंत्री सड़क से देवता की ओर | Closed | 0 | 0 | 2023-08-15
JOURA | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005065/RC/32 — सी.सी. खरंजा निर्माण कार्य | Completed | 0 | 94557 | 2009-02-12 | 2009-03-24
JOURA | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005065/RC/546 — सी.सी. खरंजा निर्माण आगनवाडी से उम्‍मेद के द्वार | Completed | 85204 | 92244.6 | 2012-03-05 | 2012-06-17
JOURA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701005065/RC/611 — पत्‍थर खरंजा निर्माण प्रधानमंत्री रोड से बनवारी के मकान तक | Completed | 421906 | 264976 | 2012-10-07 | 2013-02-25
JOURA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701005065/RC/643 — पत्‍थर खरंजा निर्माण पी.एम.जी.एस.वाय रोड से हंसराज के मकान तक | Completed | 245269 | 174168 | 2012-12-04 | 2014-05-14
JOURA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701005065/RC/673 — सी.सी. खरंजा भागीरथ के मकान से घनश्‍याम की चक्‍की की तरफ | Completed | 0 | 46788 | 2013-02-15 | 2014-08-30
JOURA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1701005065/RS/22012034697039 — सामुदायिक स्वच्छता परिसर डाबरपुरा के शिम्भुपूरी बाबा के स्थान पर | Ongoing | 69000 | 35802 | 2023-10-23
JOURA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1701005065/RS/22012034697041 — सामुदायिक स्वच्छता परिसर राजीव गाँधी सेवा केंद्र के पास | Ongoing | 69000 | 47736 | 2023-09-10
JOURA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1701005065/RS/22012034703262 — Sudur sadak Pradhan mantri sadak devta ki or gram | Deleted | 0 | 0 | 2023-08-15
JOURA | 2013-2014 | D--RURAL INFRASTUCTURE / Bharat Nirman Sewa Kendra | New Construction / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1701005065/SK/921 — Bharat Nirman Rajeev Gandhi Sewa Kendra,NANDPURA | Completed | 1425000 | 946986.8 | 2013-09-26 | 2017-04-20
JOURA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Artificial Recharge of Well Through Sand Filter / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1701005065/WC/101 — सोक पिट निर्माण कार्य | Completed | 0 | 9192 | 2008-07-26 | 2016-10-06
JOURA | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005065/WC/22012034380395 — CHECK DAM NIRMAN KARY RAGHUVEER KI NARI PAR GRAM MATHURAPURA | Completed | 1470000 | 1333859.72 | 2017-12-04 | 2018-07-15
JOURA | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005065/WC/22012034380398 — CHECK DAM NIRMAN KARY JAHAR SINGH KI NARI PAR GRAM MATHURA PURA | Completed | 1470000 | 1544816.5 | 2017-12-04 | 2018-06-26
JOURA | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005065/WC/22012034380401 — CHECK DAM NIRMAN KARY HANSA KE RAPATA KE PASS GRAM MATHURA PURA | Completed | 1470000 | 1314320 | 2017-12-04 | 2018-06-11
JOURA | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Mini Percolation tank / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1701005065/WC/22012034380645 — naveen talab nirman | Closed | 0 | 0 | 2017-10-02
JOURA | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Sunken Pond / Construction of Community Water Harvesting Ponds | Farm Pond | 1701005065/WC/22012034384509 — तालाब निर्माण कार्य मथुरा पुरा | Completed | 1499500 | 1502361.7 | 2017-12-19 | 2020-08-21
JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1701005065/WC/22012034385780 — नवीन तालाब निर्माण कार्य मथुरापुरा | Completed | 1364000 | 1309971.76 | 2018-06-09 | 2018-08-28
JOURA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005065/WC/22012034395790 — Naveen talab nirman - Bhangikhar gram nandpura | Completed | 1484000 | 1057245.35 | 2018-08-07 | 2019-08-20
JOURA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005065/WC/22012034395791 — Naveen talab nirman - Kalla ki nari ke pas nandpura | Completed | 1484000 | 922509.86 | 2018-09-02 | 2019-08-20
JOURA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Coastal Block Plantation of Forestry-Community / Along the coast Block Plantation of Forestry Trees for Community | Plantation | 1701005065/WC/22012034426509 — चैक डैम निर्माण कार्य गधाखार | Closed | 1484651 | 0 | 2018-04-14
JOURA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Coastal Block Plantation - Farm Forestry-Community / Along the coast Block Plantation of Farm Forestry Trees for Community | Plantation | 1701005065/WC/22012034426529 — चैक डैम निर्माण कार्य पार्वती नाले के पास नंदपुरा | Closed | 1476197 | 0 | 2018-04-14
JOURA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1701005065/WC/22012034625056 — तालाव निर्माण कार्य नंदपुरा | Closed | 0 | 0 | 2021-01-28
JOURA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1701005065/WC/22012034625057 — तालाव निर्माण कार्य मथुरापुर | Closed | 0 | 0 | 2021-01-28
JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1701005065/WC/22012034733474 — वाटर हार्वेस्टिंग कार्य राजीव गाँधी केंद्र नंदपुरा | Closed | 0 | 0 | 2021-04-14
JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1701005065/WC/22012034733487 — वाटर हार्वेस्टिंग कार्य आंगनवाड़ी भबन नंदपुरा | Closed | 0 | 0 | 2021-04-14
JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005065/WC/22012034746548 — अर्थन डेम निर्माण कार्य हिंगोरिया पर | Deleted | 0 | 0 | 2021-04-14
JOURA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1701005065/WC/22012034746563 — अर्थन डेम निर्माण कार्य हरिओम बाबा के खेत पर | Closed | 0 | 0 | 2021-04-14
JOURA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1701005065/WC/22012034746573 — अर्थन डेम निर्माण कार्य चामड़ माता के पास | Deleted | 0 | 0 | 2021-04-14
JOURA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1701005065/WC/22012034746582 — अर्थन डेम निर्माण कार्य बासे के खार पर | Deleted | 0 | 0 | 2021-04-14
JOURA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1701005065/WC/22012034746589 — अर्थन डेम निर्माण कार्य महावीर के पास | Deleted | 0 | 0 | 2021-04-14
JOURA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1701005065/WC/22012034746592 — अर्थन डेम निर्माण कार्य अवदेश के खेत के पास | Deleted | 0 | 0 | 2021-04-14
JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005065/WC/22012034746601 — चैक डेम निर्माण कार्य बजरा वाले खर पर | Deleted | 0 | 0 | 2021-04-14
JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005065/WC/22012034746608 — चैक डेम निर्माण कार्य मंदीबाई खेत पर | Deleted | 0 | 0 | 2021-04-14
JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005065/WC/22012034746614 — चैक डेम निर्माण कार्य डाड के पास | Deleted | 0 | 0 | 2021-04-14
JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701005065/WC/22012034771248 — अर्थन डेम निर्माण कार्य संदीबाई के पास | Deleted | 0 | 0 | 2021-04-14
JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701005065/WC/22012034771249 — अर्थन डेम निर्माण कार्य दात के पास | Deleted | 0 | 0 | 2021-04-14
JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701005065/WC/22012034771250 — अर्थन डेम निर्माण कार्य दात के खार में | Deleted | 0 | 0 | 2021-04-14
JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005065/WC/22012034869332 — चेक डेम निर्माण कार्य कृष्णा के खेत के पास | Deleted | 0 | 0 | 2021-04-14
JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005065/WC/22012034869336 — चेक डेम निर्माण कार्य प्रियांशु के खेत के पास | Deleted | 0 | 0 | 2021-04-14
JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005065/WC/22012034869338 — चेक डेम निर्माण कार्य महावीर के खेत के पास | Deleted | 0 | 0 | 2021-04-14
JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005065/WC/22012034869340 — तालाब निर्माण कार्य लल्लू के खेत के पास | Deleted | 0 | 0 | 2021-04-14
JOURA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1701005065/WC/22012034869344 — तालाब निर्माण कार्य पशुराम के खेत के पास | Deleted | 0 | 0 | 2021-04-14
JOURA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1701005065/WC/22012034869349 — तालाब निर्माण कार्य सोवरन के खेत के पास | Deleted | 0 | 0 | 2021-04-14
JOURA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1701005065/WC/22012034869352 — तालाब निर्माण कार्य प्रदीप के खेत के पास | Deleted | 0 | 0 | 2021-04-14
JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1701005065/WC/22012034927784 — Talab niram ramu ki nari me | Deleted | 0 | 0 | 2022-01-26
JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1701005065/WC/22012034927785 — Talab niram ramu ki nari me | Deleted | 0 | 0 | 2022-01-26
JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1701005065/WC/22012034927787 — Talab niram ramu ki nari me | Deleted | 0 | 0 | 2022-01-26
JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1701005065/WC/22012034927788 — Talab niram ramu ki nari me | Completed | 993784.53 | 952419.6 | 2022-03-25 | 2023-07-02
JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1701005065/WC/22012034927791 — Talab niram ramu ki nari me | Deleted | 0 | 0 | 2022-01-26
JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1701005065/WC/22012034927792 — Talab niram ramu ki nari me | Deleted | 0 | 0 | 2022-01-26
JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1701005065/WC/22012034927796 — Talab niram ramu ki nari me | Deleted | 0 | 0 | 2022-01-26
JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1701005065/WC/22012034927797 — Talab niram ramu ki nari me | Deleted | 0 | 0 | 2022-01-26
JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1701005065/WC/22012034927853 — talab nirman ramu ki nari me | Deleted | 0 | 0 | 2022-01-26
JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1701005065/WC/22012034927857 — talab nirman lalla ki nari me | Completed | 990566.61 | 926763.6 | 2022-03-25 | 2024-03-09
JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1701005065/WC/22012034927858 — talab nirman lalla ki nari me | Deleted | 0 | 0 | 2022-01-26
JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1701005065/WC/22012034927867 — talab nirman ajay ki nari | Physically Completed | 993301.63 | 898712.29 | 2022-03-25 | 2026-04-16
JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1701005065/WC/22012034927871 — talab nirman pradeep ki nari | Completed | 998999.06 | 982025.6 | 2022-03-25 | 2023-09-30
JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1701005065/WC/22012034927876 — talab nirman pradeep ki nari | Deleted | 0 | 0 | 2022-01-26
JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1701005065/WC/22012034927878 — talab nirman pradeep ki nari | Deleted | 0 | 0 | 2022-01-26
JOURA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1701005065/WC/22012034927884 — talab nirman dhera ki nari | Completed | 1004696.49 | 931252.32 | 2022-04-01 | 2024-03-09
JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1701005065/WC/22012034928076 — Talab nirman yogendra ki nari me | Closed | 0 | 0 | 2022-01-26
JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1701005065/WC/22012034928271 — Talab niram dharmendra ki nari | Closed | 0 | 0 | 2022-01-26
JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1701005065/WC/22012034928272 — Talab nirman raja ki nari | Closed | 0 | 0 | 2022-01-26
JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1701005065/WC/22012034928662 — तालाब बाँदी खार के पास नंदपुरा | Closed | 0 | 0 | 2022-01-26
JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1701005065/WC/22012034928670 — तालाब पहलबान खार के पास नंदपुरा | Deleted | 0 | 0 | 2022-01-26
JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1701005065/WC/22012034928675 — तालाब ओमवीर नरी के पास ग्राम नंदपुरा | Deleted | 0 | 0 | 2022-01-26
JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1701005065/WC/22012034928680 — तालाब निर्माण ऊंट घाट के पास | Deleted | 0 | 0 | 2022-01-26
JOURA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1701005065/WC/22012034931127 — Talab nirman yogendra ki nari me | Physically Completed | 1410172.61 | 1352368.94 | 2022-05-06 | 2026-04-16
JOURA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1701005065/WC/22012034931130 — Talab nirman dharmendra ki nari me | Deleted | 0 | 0 | 2022-04-01
JOURA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1701005065/WC/22012034931131 — Talab nirman raja ki nari me | Deleted | 0 | 0 | 2022-04-01
JOURA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1701005065/WC/22012034949528 — talab nirman kary gabdu ka khar vale bandh par | Completed | 1491250.41 | 1328932.17 | 2022-05-18 | 2023-07-02
JOURA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1701005065/WC/22012034949542 — talab nirman bavnna ki neev vali nari par | Completed | 1498634.52 | 1438629.66 | 2022-05-18 | 2023-07-20
JOURA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1701005065/WC/22012034950511 — talab bade khar par | Completed | 1496870.35 | 1427123.43 | 2022-05-18 | 2023-07-20
JOURA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1701005065/WC/22012034968427 — तालाब निर्माण नीम वाले खार पर नंदपुरा | Completed | 1451791.65 | 1251815.51 | 2022-05-18 | 2023-09-30
JOURA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1701005065/WC/22012034968433 — तालाब निर्माण स्वराज की नरी नंदपुरा | Completed | 1469878.6 | 1398935.48 | 2022-05-18 | 2024-03-09
JOURA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005065/WC/22012034983829 — तालाब निर्माण कार्य छोटी घाट पर नंदपुरा | Deleted | 0 | 0 | 2022-04-01
JOURA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005065/WC/22012034983846 — तालाब निर्माण कार्य जाटव के खेत के पास नंदपुरा | Deleted | 0 | 0 | 2022-04-01
JOURA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005065/WC/22012034983875 — तालाब निर्माण कार्य रेत घाट के पास नंदपुरा | Deleted | 0 | 0 | 2022-04-01
JOURA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005065/WC/22012034983877 — तालाब निर्माण कार्य रेत घाट के पास नंदपुरा | Closed | 0 | 0 | 2022-04-01
JOURA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005065/WC/22012034983882 — तालाब निर्माण कार्य रेत घाट के पास नंदपुरा | Deleted | 0 | 0 | 2022-04-01
JOURA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005065/WC/22012034983883 — तालाब निर्माण कार्य रेत घाट के पास नंदपुरा | Closed | 0 | 0 | 2022-04-01
JOURA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005065/WC/22012034983895 — तालाब निर्माण कार्य भीकम के खेत के पास नंदपुरा | Deleted | 0 | 0 | 2022-04-01
JOURA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005065/WC/22012034983906 — तालाब निर्माण कार्य रमेशके खेत के पास नंदपुरा | Deleted | 0 | 0 | 2022-04-01
JOURA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005065/WC/22012034984040 — तालाब निर्माण कार्य रामनिवास के खार पर नंदपुरा | Deleted | 0 | 0 | 2022-04-01
JOURA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005065/WC/22012034984041 — तालाब निर्माण कार्य रामनिवास के खार पर नंदपुरा | Closed | 0 | 0 | 2022-04-01
JOURA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005065/WC/22012034984051 — तालाब निर्माण कार्य बासुदेव के खेत के पास नंदपुरा | Deleted | 0 | 0 | 2022-04-01
JOURA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005065/WC/22012034984052 — तालाब निर्माण कार्य बासुदेव के खेत के पास नंदपुरा | Closed | 0 | 0 | 2022-04-01
JOURA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005065/WC/22012034984062 — तालाब निर्माण कार्य पप्पू के खेत के पास नंदपुरा | Deleted | 0 | 0 | 2022-04-01
JOURA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005065/WC/22012034984066 — तालाब निर्माण कार्य महेश के खेत के नीचे नंदपुरा | Deleted | 0 | 0 | 2022-04-01
JOURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701005065/WC/22012035093839 — rapta nirman karya khar par | Closed | 0 | 0 | 2023-04-15
JOURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1701005065/WC/22012035093841 — rapta nirman karya nandi wale khar me | Physically Completed | 1350358.68 | 1305444.15 | 2023-10-10 | 2026-05-21
JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1701005065/WC/22012035093843 — Rapta nirman karya maaua wale khar me | Ongoing | 1347080.49 | 549324 | 2024-10-18
JOURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1701005065/WC/22012035093847 — Rapta Nirman Karya kharkhanda dev ke pass | Physically Completed | 1369726.29 | 1311504.44 | 2023-11-21 | 2026-05-21
JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1701005065/WC/22012035093851 — Rapta nirman karya bheju wala khar | Ongoing | 1367145.12 | 891260.46 | 2024-08-16
JOURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701005065/WC/22012035093857 — Anicut Nirman Karya tede naale par | Deleted | 0 | 0 | 2023-04-15
JOURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701005065/WC/22012035093860 — Anicut Nirman Karya beeri wale ke paas | Deleted | 0 | 0 | 2023-04-15
JOURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1701005065/WC/22012035093862 — Anicut Nirman Karya remaja ke pass | Deleted | 0 | 0 | 2023-04-15
JOURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1701005065/WC/22012035093863 — Anicut Nirman Karya katile wale ke pass | Deleted | 0 | 0 | 2023-04-15
JOURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701005065/WC/22012035093865 — Anicut Nirman Karya dhoman ke pass | Deleted | 0 | 0 | 2023-04-15
JOURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Boundary Line Plantation of Forestry-Community / Boundary Line Plantation of Forestry Trees for Community | Plantation | 1701005065/WC/22012035095506 — TALAB NIRMAN KARY SANTOSH KE KHET KE PASS | Closed | 0 | 0 | 2023-07-28
JOURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plntation-Biodrainage-fields-Comm / Block Plantation of Biodrainage Trees in fields for Community | Plantation | 1701005065/WC/22012035095508 — TALAB NIRMAN KARY RAMDEEN KE KHET KE PASS | Closed | 0 | 0 | 2023-07-28
JOURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plntation-Biodrainage-Wastelands for comm / Block Plantation of Biodrainage trees in Wastelands for community | Plantation | 1701005065/WC/22012035095514 — TALAB NIRMAN KARY RADHESHYAM KE KHET KE PASS | Deleted | 0 | 0 | 2023-07-28
JOURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plntation-Biodrainage-Wastelands for comm / Block Plantation of Biodrainage trees in Wastelands for community | Plantation | 1701005065/WC/22012035095517 — TALAB NIRMAN KARY BADE KHAR ME TILE KE PASS | Completed | 1492341.06 | 1321539.33 | 2023-08-07 | 2024-12-11
JOURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Boundary Line Plantation of Forestry-Community / Boundary Line Plantation of Forestry Trees for Community | Plantation | 1701005065/WC/22012035095542 — talab nirman kary rachpal ki narike pass | Completed | 1492341.06 | 1313209 | 2023-09-10 | 2024-12-11
JOURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Boundary Line Plantation-Horticulture -Community / Boundary Line Plantation of Horticulture Trees for Community | Plantation | 1701005065/WC/22012035095543 — talab nirman kary pittal ke keht ke pass | Completed | 1492341.06 | 1356933.92 | 2023-09-02 | 2024-12-11
JOURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1701005065/WC/22012035102810 — Talab Nirman karya raveha wale khar | Deleted | 0 | 0 | 2023-08-15
JOURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1701005065/WC/22012035102814 — Anicut nirman karya ghachhar ke khat par | Closed | 0 | 0 | 2023-08-15
JOURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1701005065/WC/22012035102815 — Anicut nirman karya Guddan Ke khet par | Closed | 0 | 0 | 2023-08-15
JOURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1701005065/WC/22012035103147 — Anicut nirman karya suju ke khet ke pas | Closed | 0 | 0 | 2023-08-15
JOURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005065/WC/22012035111402 — Anicut nirman karya sandeep ke khet ke pas | Closed | 0 | 0 | 2023-08-15
JOURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005065/WC/22012035111404 — Anicut nirman karya sandeep ke khet ke pas | Deleted | 0 | 0 | 2023-08-15
JOURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005065/WC/22012035111410 — Anicut nirman karya feeling ki khad par | Closed | 0 | 0 | 2023-08-15
JOURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005065/WC/22012035111421 — Anicut nirman karya lali ke khar pr | Closed | 0 | 0 | 2023-08-15
JOURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005065/WC/22012035111425 — Anicut nirman karya debu ki par pr | Closed | 0 | 0 | 2023-08-15
JOURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005065/WC/22012035146507 — Anicut nirman karya sandeep ke khet ke pas nare me | Closed | 0 | 0 | 2023-08-15
JOURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005065/WC/22012035146515 — Anicut nirman karya Filing ke khar par | Closed | 0 | 0 | 2023-08-15
JOURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005065/WC/22012035146522 — Anicut nirman karya Lali ke khar par | Closed | 0 | 0 | 2023-08-15
JOURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005065/WC/22012035146526 — Anicut nirman karya debu ke khar par | Deleted | 0 | 0 | 2023-08-15
JOURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005065/WC/22012035146530 — Anicut nirman karya pintu ke khar par | Deleted | 0 | 0 | 2023-08-15
JOURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1701005065/WC/22012035146532 — rapta nirman karya baba ke khet ke pas | Closed | 0 | 0 | 2023-08-15
JOURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1701005065/WC/22012035146534 — rapta nirman karya bheru ke khet ke pas | Closed | 0 | 0 | 2023-08-15
JOURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1701005065/WC/22012035146539 — rapta nirman karya mata ke khet ke pas | Closed | 0 | 0 | 2023-08-15
JOURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701005065/WC/22012035146543 — rapta nirman karyashyam ke khet ke pas | Closed | 0 | 0 | 2023-08-15
JOURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1701005065/WC/22012035146546 — rapta nirman karya bhim ke khar par | Closed | 0 | 0 | 2023-04-15
JOURA | 2023-2024 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1701005065/WC/22012035190280 — rapta nirman karyaparmar ke khet ke raste par | Closed | 0 | 0 | 2024-01-26
JOURA | 2023-2024 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1701005065/WC/22012035190288 — rapta nirman karya guddu ke tor ke raste ki or | Closed | 0 | 0 | 2024-01-26
JOURA | 2023-2024 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1701005065/WC/22012035190294 — rapta nirman karya sabda road raste par | Closed | 0 | 0 | 2024-01-26
JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005065/WC/22012035224264 — Percolation tank nirman karya kesi ki nari | Approved | 0 | 0 | 2024-08-15
JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005065/WC/22012035224268 — Percolation tank nirman karya Shyam ki nari | Deleted | 0 | 0 | 2024-08-15
JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005065/WC/22012035224273 — Percolation tank nirman karya bansi ki nari | Approved | 0 | 0 | 2024-08-15
JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005065/WC/22012035224289 — Percolation tank nirman karya Bhuraram ki nari | Deleted | 0 | 0 | 2024-08-15
JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005065/WC/22012035224292 — Percolation tank nirman karya Chotu ki nari | Approved | 0 | 0 | 2024-08-15
JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005065/WC/22012035224293 — Percolation tank nirman karya bade ki nari | Deleted | 0 | 0 | 2024-08-15
JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005065/WC/22012035224294 — Percolation tank nirman karya ramnibas ki nari | Deleted | 0 | 0 | 2024-08-15
JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005065/WC/22012035224296 — Percolation tank nirman karya dinesh ki nari | Deleted | 0 | 0 | 2024-08-15
JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005065/WC/22012035224298 — Percolation tank nirman karya pappu ki nari | Deleted | 0 | 0 | 2024-08-15
JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005065/WC/22012035224299 — Percolation tank nirman karya ramdayal ki nari | Deleted | 0 | 0 | 2024-08-15
JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005065/WC/22012035224300 — Percolation tank nirman karya haridas ki nari | Deleted | 0 | 0 | 2024-08-15
JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005065/WC/22012035224306 — Percolation tank nirman karya kesi ki nari | Approved | 0 | 0 | 2024-08-15
JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005065/WC/22012035224307 — Percolation tank nirman Shyam ki nari | Approved | 0 | 0 | 2024-08-15
JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005065/WC/22012035224308 — Percolation tank nirman karya bansi ki nari | Deleted | 0 | 0 | 2024-08-15
JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005065/WC/22012035224309 — Percolation tank nirman karya bhuraram ki nari | Deleted | 0 | 0 | 2024-08-15
JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005065/WC/22012035224310 — Percolation tank nirman karya chotu ki nari | Approved | 0 | 0 | 2024-08-15
JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005065/WC/22012035224311 — Percolation tank nirman karya bade ki nari | Deleted | 0 | 0 | 2024-08-15
JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005065/WC/22012035232764 — Talab nirman karya Bhura ram ki nari me | Deleted | 0 | 0 | 2024-08-15
JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005065/WC/22012035232765 — Talab nirman karya Chhotu ki nari me | Deleted | 0 | 0 | 2024-08-15
JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005065/WC/22012035232766 — Talab nirman karya Kesi ki nari me | Deleted | 0 | 0 | 2024-08-15
JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005065/WC/22012035232767 — Talab nirman karya Shyam ki nari me | Deleted | 0 | 0 | 2024-08-15
JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005065/WC/22012035232768 — Talab nirman karya bansi ki nari me | Deleted | 0 | 0 | 2024-08-15
JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005065/WC/22012035238299 — Talab nirman karya Bhela ki par me | Approved | 1317385.18 | 0 | 2024-08-15
JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005065/WC/22012035238301 — Talab nirman karya datiko ki nari | Approved | 0 | 0 | 2024-08-15
JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005065/WC/22012035238302 — Talab nirman karya besli ki nari | Physically Completed | 1418729.6 | 1271978.5 | 2025-02-06 | 2026-04-27
JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005065/WC/22012035238303 — Talab nirman karya kue bale me | Physically Completed | 1325456.52 | 1221418.42 | 2025-01-06 | 2026-04-16
JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005065/WC/22012035239176 — Talab nirman karya Moriko me | Deleted | 0 | 0 | 2024-08-15
JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005065/WC/22012035239177 — Talab nirman karya dhekha bali me | Deleted | 0 | 0 | 2024-08-15
JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005065/WC/22012035239179 — Talab nirman karya Kui wala pamo | Approved | 0 | 0 | 2024-08-15
JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005065/WC/22012035315558 — Talab Nirman Karya Patiko Ki Nari me | Approved | 0 | 0 | 2025-04-14
JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005065/WC/22012035316267 — Talab nirman karya saiyad bali nari ke pas | Approved | 0 | 0 | 2025-04-01
JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005065/WC/22012035316268 — Talab nirman karya duda bali nari ke pas | Approved | 0 | 0 | 2025-04-01
JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005065/WC/22012035316269 — Talab nirman karya kans bali nari ke pas | Approved | 0 | 0 | 2025-04-01
JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005065/WC/22012035316271 — Talab nirman karya bansh bali nari ke pas | Approved | 0 | 0 | 2025-04-01
JOURA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Artificial Recharge of Well Through Sand Filter / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1701005065/WC/86 — सोक पिट मथुरा पुर | Completed | 0 | 15919 | 2008-07-26 | 2016-10-06
JOURA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005065/WC/87 — सोक पिट निर्माण नंदपुरा | Completed | 0 | 9212.9 | 2008-07-28 | 2009-07-16
JOURA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005065/WC/88 — सोक्‍ता गढढा निर्माण | Completed | 0 | 12913 | 2008-07-26 | 2009-07-16
JOURA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Artificial Recharge of Well Through Sand Filter / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1701005065/WC/89 — सोक पिट निर्माण नंदपुरा | Completed | 0 | 10702 | 2008-07-26 | 2016-10-06
JOURA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005065/WC/90 — सोक पिट विधायक के मकान के पास नंदपुरा | Completed | 0 | 25850.9 | 2008-07-10 | 2009-07-16
JOURA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1701005065/WC/VB/22012035332054 — Sokhta gadda nirman karya bde kue ke pass | Deleted | 0 | 0 | 2026-04-14
JOURA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1701005065/WC/VB/22012035332723 — पंचायतभवन रूपवॉटरनंदपुरा | Approved | 0 | 0 | 2026-07-27
JOURA | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1701005065/WH/184 — सोकपिट निर्माण कार्य परसराम के मकान के पास | Completed | 0 | 10495 | 2009-06-06 | 2016-10-06
JOURA | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1701005065/WH/185 — सोकपिट निर्माण कार्य काशीराम के मकान के पास | Completed | 0 | 10768 | 2009-07-03 | 2016-10-06
JOURA | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1701005065/WH/186 — सोकपिट निर्माण कार्य रामनिवास सहि के मकान के पास | Completed | 0 | 10768 | 2009-06-06 | 2016-10-06
JOURA | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1701005065/WH/187 — सोकपिट निर्माण कार्य राधेश्‍याम के मकान के पास | Completed | 0 | 10221.58 | 2009-07-03 | 2016-10-06
JOURA | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1701005065/WH/188 — सोकपिट निर्माण कार्य मानसिह के मकान के पास | Completed | 0 | 10767.36 | 2009-06-06 | 2016-10-06
JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1701005065/WH/22012034452204 — Renovation of Talab Khasra no.192 | Closed | 194479.02 | 0 | 2021-10-02
JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1701005065/WH/22012034452206 — Renovation of Talab Umesh wala | Closed | 0 | 0 | 2021-10-02