## Work List
Exported on: 2026-10-11 19:58:10
Filters applied:
Data source: MGNREGA + VBGRAMG
District: MORENA
Block: All
Panchayat: BARHANA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
JOURA | 2025-2026 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1701005066/AV/22012034667522 — Shantidhaam Nirman Karya Barhana | New | 0 | 0 | 2025-04-14
JOURA | 2025-2026 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1701005066/AV/22012034667523 — Shantidhaam Nirman Karya Bawadi | New | 0 | 0 | 2025-04-14
JOURA | 2025-2026 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1701005066/AV/22012034667557 — शान्तिधाम निर्माण कार्य बरहाना | Approved | 347299.82 | 0 | 2025-08-18
JOURA | 2025-2026 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1701005066/AV/22012034667558 — शान्तिधाम निर्माण कार्य बावड़ी | Approved | 347299.82 | 0 | 2025-08-18
JOURA | 2011-2012 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1701005066/DP/179 — शांतीधाम निर्माण बरहाना | Completed | 364687 | 130621 | 2011-12-26 | 2013-06-30
JOURA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701005066/DP/21 — पोधा रोपण कार्य नदी रपटा से वावडी तक | Completed | 0 | 7820 | 2008-08-15 | 2008-04-01
JOURA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701005066/DP/22 — पोधा रोपण कार्य ग्राम वावडी से नाले की पुलिय तक | Completed | 0 | 6205 | 2008-08-22 | 2008-04-01
JOURA | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1701005066/DP/22012034237269 — शान्तिधाम निर्माण टीनशेड सहितग्राम टीकरी बरहाना | Completed | 180000 | 173071.24 | 2017-01-21 | 2017-06-12
JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in fields for Community | Plantation | 1701005066/DP/22012034623673 — व्रक्षारोपण कार्य स्कूल के पास टीकरी ग्राम पंचायत बरहाना | Approved | 159649.64 | 0 | 2024-06-10
JOURA | 2015-2016 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Spurs and Torrent Control Measures / Construction of Earthen Spur for Community | Works for Flood Control and Protection | 1701005066/FP/22012034203669 — नाला निर्माण हनुमान मंदिर से नदी की ओर टेकरी | Deleted | 0 | 0 | 2015-10-02
JOURA | 2015-2016 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Spurs and Torrent Control Measures / Construction of Earthen Spur for Community | Works for Flood Control and Protection | 1701005066/FP/22012034203670 — नाला निर्माण नहर पुलिया से हरिजन मोहल्ला की ओर | Deleted | 0 | 0 | 2015-10-02
JOURA | 2016-2017 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Strengthening of Embankment / Construction of Embankment for community | Strengthening of Embankment | 1701005066/FP/22012034314368 — पत्थर नाली निर्माण नहर की पुलिया से गड़ी की और | Completed | 1146900 | 1090252.1 | 2017-03-11 | 2017-10-27
JOURA | 2018-2019 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701005066/FP/22012034362292 — पत्थर नाला निर्माण कार्य बरहाना | Closed | 0 | 0 | 2018-10-02
JOURA | 2020-2021 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005066/FP/22012034366512 — नाला निर्माण कार्य होतम के मकान से तालाब की ओर पीपरी मजरा | Completed | 553248.91 | 524594.34 | 2020-09-11 | 2023-02-02
JOURA | 2020-2021 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005066/FP/22012034366539 — नाला निर्माण कार्य होयँ के मकान से तालाब की ओर पीपरी मजरा | Closed | 0 | 0 | 2020-04-14
JOURA | 2020-2021 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of intrmediate and Link Water Drain-Comm / Construction of intermediate and Link Storm Water Drain for Community | Works for Flood Control and Protection | 1701005066/FP/22012034367206 — RAPTA NIRMAN KARYA BARHANA | Closed | 0 | 0 | 2020-04-14
JOURA | 2020-2021 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of intrmediate and Link Water Drain-Comm / Construction of intermediate and Link Storm Water Drain for Community | Works for Flood Control and Protection | 1701005066/FP/22012034367207 — RAPTA NIRMAN KARYA BARHANA | Completed | 910621.05 | 861010 | 2020-09-11 | 2021-02-10
JOURA | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of drain for coastal protection for Comm. / Construction of Storm Water drain for coastal protection for Community | Works for Flood Control and Protection | 1701005066/FP/22012034626181 — पत्थर नाला निर्माण कार्य रामओतार के घर से पत्थर नाले तक | Completed | 618076.46 | 542231 | 2021-09-24 | 2023-02-02
JOURA | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005066/FP/22012034628726 — nala nirman karya lakhan ke makan se nadee ki or barahana | Completed | 1489496.92 | 1286782 | 2022-05-11 | 2023-02-02
JOURA | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005066/FP/22012034628727 — nala nirman karya mahendra ke makan se behad ki or barhana | Completed | 1482954.29 | 1423412 | 2022-05-11 | 2023-02-02
JOURA | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005066/FP/22012034630419 — Nala nirman karya Hanuman mandir se nadee ki or teekari barahana | Completed | 1389165.51 | 1299451 | 2022-11-25 | 2023-12-29
JOURA | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005066/FP/22012034633066 — patthar Nala nirman karya deewan avm makhan ke ghar se dagare ki or | Completed | 1076274.91 | 815867 | 2023-07-29 | 2024-12-17
JOURA | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005066/FP/22012034633125 — talab nirman karya sire bali naree | Completed | 1217715.75 | 704059 | 2023-07-29 | 2024-12-17
JOURA | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005066/FP/22012034636074 — पत्थर नाला निर्माण कार्य भारत के मकान से नाले की ओर | Completed | 1474276.67 | 534044 | 2023-10-08 | 2024-10-09
JOURA | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood or Diversion Channel for Community | Works for Flood Control and Protection | 1701005066/FP/22012034636075 — पत्थर नाला निर्माण कार्य भदौरिया के घर से नदी की ओर | Ongoing | 1474276.67 | 980660 | 2023-10-08
JOURA | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005066/FP/22012034638074 — पत्थर नाला निर्माण कार्य पत्थर नाले से नाले की ओर | Completed | 1411841.41 | 1079319 | 2024-03-12 | 2025-11-16
JOURA | 2013-2014 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Construction of Intermediate and Link Drains / Construction of intermediate and Link Storm Water Drain for Community | Works for Flood Control and Protection | 1701005066/FP/9977522192 — पत्‍थर नाला निर्माण साई बाबा के घर से तालाब की ओर | Completed | 414500 | 272198.39 | 2013-12-28 | 2015-11-27
JOURA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701005066/IF/1000044027 — पशु आश्रय केन्‍द्र कमल सिंह / चौथे सिंह | Completed | 80000 | 67160.48 | 2013-10-04 | 2017-04-01
JOURA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701005066/IF/1000044029 — पशु आश्रय केन्‍द्र अहमद / राज खां | Completed | 80000 | 70435.73 | 2013-10-04 | 2015-10-10
JOURA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701005066/IF/1000044032 — पशु आश्रय केन्‍द्र जगदीश / छोटे सिंह | Completed | 80000 | 27605.04 | 2013-10-04 | 2017-04-01
JOURA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701005066/IF/22012034368049 — सडक किनारे नहर कि पुलिया से पीपरी तक� | Completed | 335000 | 61290 | 2017-07-01 | 2020-12-25
JOURA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701005066/IF/22012034368051 — सार्वजिनक व्रक्षारोपण्‍ा कार्य शाॅितधाम टीकरी | Completed | 335000 | 19274 | 2017-08-05 | 2020-12-12
JOURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1701005066/IF/22012035481626 — खेत तालाब निर्माण कार्य प्रमोद के खेत मे | Completed | 383273.46 | 294669 | 2025-05-12 | 2025-11-16
JOURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1701005066/IF/22012035481639 — खेत तालाब निर्माण कार्य भागवेंद्र के खेत मे | Completed | 450885.64 | 272745 | 2025-05-14 | 2025-11-16
JOURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1701005066/IF/22012035481645 — खेत तालाब निर्माण कार्य विशंभर के खेत मे | Completed | 386049.95 | 282141 | 2025-05-12 | 2025-09-10
JOURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1701005066/IF/22012035481652 — खेत तालाब निर्माण कार्य कोमल के खेत मे | Completed | 450885.64 | 256824 | 2025-05-12 | 2025-09-10
JOURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1701005066/IF/22012035481659 — खेत तालाब निर्माण कार्य मोहर सिंह के खेत मे | Completed | 386049.95 | 305892 | 2025-05-12 | 2025-09-10
JOURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1701005066/IF/22012035504719 — डग वेल निर्माण कार्य माखन के कुआ पर | Deleted | 0 | 0 | 2025-04-14
JOURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1701005066/IF/22012035504725 — डग वेल निर्माण कार्य गंगा सिंह के कुआ पर | Deleted | 0 | 0 | 2025-04-14
JOURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1701005066/IF/22012035504735 — डग वेल निर्माण कार्य दीवान के कुआ पर | Deleted | 0 | 0 | 2025-04-14
JOURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1701005066/IF/22012035504747 — डग वेल निर्माण कार्य अटल बिहारी के कुआ पर | Deleted | 0 | 0 | 2025-04-14
JOURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1701005066/IF/22012035504756 — डग वेल निर्माण कार्य बनिया के कुआ पर | Deleted | 0 | 0 | 2025-04-14
JOURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1701005066/IF/22012035504895 — डग वेल निर्माण कार्य माखन के कुआ पर | Completed | 22959.9 | 12789 | 2025-05-14 | 2025-09-10
JOURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1701005066/IF/22012035504904 — डग वेल निर्माण कार्य गंगा सिंह के कुआ पर | Completed | 22959.9 | 12789 | 2025-05-14 | 2025-09-10
JOURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1701005066/IF/22012035504909 — डग वेल निर्माण कार्य दीवान के कुआ पर | Completed | 22959.9 | 12789 | 2025-05-14 | 2025-09-10
JOURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1701005066/IF/22012035504914 — डग वेल निर्माण कार्य अटल बिहारी के कुआ पर | Completed | 22959.9 | 12789 | 2025-05-14 | 2025-09-10
JOURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1701005066/IF/22012035504918 — डग वेल निर्माण कार्य बनिया के कुआ पर | Completed | 22959.9 | 12789 | 2025-05-14 | 2025-09-10
JOURA | 2011-2012 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1701005066/IF/91 — मेड वन्‍धान कार्य चन्‍दन सिह पुञ नारायण सिह | Completed | 22342 | 13908 | 2011-10-12 | 2011-10-18
JOURA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701005066/IF/9926714308 — पशु शेड निर्माण शीला / पप्पू | Completed | 70500 | 64995.63 | 2014-03-05 | 2015-10-09
JOURA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701005066/IF/9926714312 — पशु शेड निर्माण धर्मवीर / खचेरा | Completed | 70500 | 65315.63 | 2014-03-05 | 2015-10-10
JOURA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701005066/IF/9926714316 — पशु शेड निर्माण रामसहाय / सिरिया | Completed | 70500 | 64520.63 | 2014-03-05 | 2015-10-10
JOURA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701005066/IF/9926714324 — पशु शेड निर्माण देवी सिंह / सोवरन | Completed | 70500 | 19473.13 | 2014-03-05 | 2017-04-01
JOURA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701005066/IF/9926714327 — पशु शेड निर्माण शांति / रामस्वरूप | Completed | 70500 | 8323.38 | 2014-03-05 | 2017-04-01
JOURA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005066/IF/IAY/1176602 — Construction of IAY House -IAY REG. NO. MP3023541 | Completed | 15480 | 15636 | 2018-01-30 | 2018-12-30
JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005066/IF/IAY/1884207 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5501559 | Completed | 15660 | 15816 | 2019-02-21 | 2019-09-12
JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005066/IF/IAY/1910915 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4566747 | Completed | 15660 | 15816 | 2019-02-21 | 2019-08-22
JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005066/IF/IAY/1910941 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4613386 | Completed | 15660 | 15816 | 2019-02-21 | 2019-08-22
JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005066/IF/IAY/1915101 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4666423 | Completed | 15660 | 15816 | 2019-02-21 | 2019-10-08
JOURA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005066/IF/IAY/193122 — Construction of IAY House -IAY REG. NO. MP-01-005-066-001/27AA | Completed | 14310 | 15031 | 2016-12-24 | 2018-12-30
JOURA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005066/IF/IAY/208592 — Construction of IAY House -IAY REG. NO. MP1043126 | Completed | 15030 | 15366 | 2017-02-04 | 2018-12-17
JOURA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005066/IF/IAY/208798 — Construction of IAY House -IAY REG. NO. MP1045972 | Completed | 15030 | 15564 | 2017-03-04 | 2019-09-18
JOURA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005066/IF/IAY/210463 — Construction of IAY House -IAY REG. NO. MP1073012 | Completed | 15030 | 15456 | 2017-03-04 | 2018-12-17
JOURA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005066/IF/IAY/210815 — Construction of IAY House -IAY REG. NO. MP1078421 | Completed | 15030 | 13090 | 2017-03-04 | 2019-02-15
JOURA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005066/IF/IAY/211047 — Construction of IAY House -IAY REG. NO. MP1081811 | Completed | 15030 | 16524 | 2017-03-11 | 2018-12-30
JOURA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005066/IF/IAY/211048 — Construction of IAY House -IAY REG. NO. MP1081817 | Completed | 15030 | 13060 | 2017-03-04 | 2019-02-15
JOURA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005066/IF/IAY/262684 — Construction of IAY House -IAY REG. NO. MP2804470 | Completed | 15030 | 15048 | 2017-02-04 | 2018-04-21
JOURA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005066/IF/IAY/279329 — Construction of IAY House -IAY REG. NO. MP3966028 | Completed | 15030 | 15789 | 2017-03-11 | 2019-09-18
JOURA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005066/IF/IAY/53015 — Construction of IAY House -IAY REG. NO. MP-01-005-066-001/78B | Completed | 14310 | 14863 | 2016-12-24 | 2018-04-21
JOURA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005066/IF/IAY/53016 — Construction of IAY House -IAY REG. NO. MP-01-005-066-002/13 | Completed | 14310 | 16032 | 2016-06-18 | 2017-04-01
JOURA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005066/IF/IAY/53017 — Construction of IAY House -IAY REG. NO. MP-01-005-066-002/58 | Completed | 14310 | 14863 | 2016-06-18 | 2017-04-01
JOURA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005066/IF/IAY/564186 — Construction of IAY House -IAY REG. NO. MP3814748 | Completed | 15030 | 13986 | 2017-02-04 | 2018-04-21
JOURA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005066/IF/IAY/595417 — Construction of IAY House -IAY REG. NO. MP1043118 | Completed | 15030 | 15564 | 2017-03-18 | 2018-12-09
JOURA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005066/IF/IAY/601083 — Construction of IAY House -IAY REG. NO. MP1077247 | Completed | 15030 | 14830 | 2017-03-04 | 2018-08-30
JOURA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005066/IF/IAY/604444 — Construction of IAY House -IAY REG. NO. MP3995856 | Completed | 15030 | 14902 | 2017-03-11 | 2019-01-25
JOURA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005066/IF/IAY/623000 — Construction of IAY House -IAY REG. NO. MP1055315 | Closed | 17100 | 0 | 2017-02-08
JOURA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005066/IF/IAY/831416 — Construction of IAY House -IAY REG. NO. MP1043136 | Deleted | 15480 | 0 | 2017-04-21
JOURA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005066/IF/IAY/831441 — Construction of IAY House -IAY REG. NO. MP1046674 | Completed | 15480 | 14244 | 2018-02-15 | 2019-01-30
JOURA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005066/IF/IAY/831724 — Construction of IAY House -IAY REG. NO. MP1081756 | Completed | 15480 | 14580 | 2018-01-30 | 2019-01-30
JOURA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005066/IF/IAY/831754 — Construction of IAY House -IAY REG. NO. MP1085114 | Completed | 15480 | 15624 | 2018-02-06 | 2018-12-09
JOURA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005066/IF/IAY/944840 — Construction of IAY House -IAY REG. NO. MP2913016 | Completed | 15480 | 15636 | 2018-01-30 | 2018-12-09
JOURA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005066/IF/IAY/982168 — Construction of IAY House -IAY REG. NO. MP3967764 | Completed | 15480 | 15636 | 2018-01-30 | 2018-12-09
JOURA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701005066/LD/22012034523013 — Retaining Wall Teekari | Closed | 0 | 0 | 2020-04-14
JOURA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701005066/RC/22012034161730 — cckaranja | Deleted | 0 | 0 | 2013-01-26
JOURA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005066/RC/22012034164647 — पंच परमश्‍ेवर सीसी खरंजा नाली निर्माण जगदीश सिंह बघेल के मकान से राज खां के मकान तक | Deleted | 44940 | 0 | 2012-10-02
JOURA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005066/RC/22012034184669 — सी.सी. खरंजा एवं नाली निर्माण कार्य जगदीश सिंह बघे | Completed | 44940 | 26847 | 2013-09-21 | 2015-11-05
JOURA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005066/RC/22012034186812 — सी. सी. खरंजा राजखा के मकान से कुशवाह मोहल्ला | Completed | 88220 | 116752 | 2013-09-28 | 2015-11-05
JOURA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701005066/RC/22012034196356 — पत्‍थर खरंजा निर्माण हनुमान मन्दिर से बीरबल के मका | Completed | 484500 | 455807.05 | 2013-12-28 | 2015-10-16
JOURA | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701005066/RC/22012034222966 — सुदूर ग्राम सडक यौज्ना के अंतर्गत मिट्टी बजरी रोड पिपृरी पुरा से नहर पुलिया तक | Completed | 1382688 | 232674 | 2014-06-25 | 2016-09-09
JOURA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701005066/RC/22012034288608 — पत्थर खरंजा निर्माण कार्य हनुमान मंदिर से स्कूल की और | Completed | 121800 | 108119.1 | 2015-11-07 | 2015-11-27
JOURA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701005066/RC/22012034289126 — पत्थर खरंजा निर्माण पुराना गाँव गडी से हरिजन महोल्ला की ओर | Completed | 408000 | 397762.99 | 2015-11-21 | 2016-02-01
JOURA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701005066/RC/22012034292447 — पत्थर खरंजा निर्माण विनोद के मकान से सी सी खरंजा की ओर | Completed | 722000 | 324138.6 | 2015-12-12 | 2016-09-09
JOURA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701005066/RC/22012034292450 — पत्थर खरंजा निर्माण पी एम् जी एस रोड से परिमल के मकान की ओर वाबडी | Completed | 722000 | 216062.6 | 2015-12-12 | 2016-09-09
JOURA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005066/RC/22012034299700 — सी सी खरंजा एवं नाली निर्माण नहर स्कूल से राशेल के मकान की ओर | Deleted | 0 | 0 | 2015-10-02
JOURA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005066/RC/22012034299701 — सी सी खरंजा निर्माण ग्राम स्वराज भवन से हरिजन मोहल्ला की ओर | Deleted | 0 | 0 | 2015-10-02
JOURA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701005066/RC/22012034299702 — मिट्ठी ग्रेवल रोड नहर से हार के लिए | Deleted | 0 | 0 | 2015-10-02
JOURA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701005066/RC/22012034299712 — पत्थर खरंजा निर्माण प्रधान मंत्री रोड से बीरेंद्र के मकान की ओर | Deleted | 0 | 0 | 2015-10-02
JOURA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701005066/RC/22012034299713 — पत्थर खरंजा निर्माण जितेंद्र के घर से राम हेत के मकान की ओर | Deleted | 0 | 0 | 2015-10-02
JOURA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701005066/RC/22012034299714 — मीठी मुरम रोड टीकरी से बाबरी की ओर | Deleted | 0 | 0 | 2015-10-02
JOURA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005066/RC/22012034299715 — सी सी खरंजा निर्माण साईं बाबा के मकान से असगर के मकान की ओर | Deleted | 0 | 0 | 2015-10-02
JOURA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005066/RC/22012034299716 — सी सी खरंजा निर्माण भूरा के मकान से राम सेवक चौहान के मकान की ओर | Deleted | 0 | 0 | 2015-10-02
JOURA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701005066/RC/22012034328466 — सुदूर ग्राम सड़क निर्माण कार्य बरहाना से मजरा पीपरी तक | Completed | 1389000 | 1205168.04 | 2017-02-25 | 2018-06-09
JOURA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701005066/RC/22012034340861 — सुदूर ग्राम संपर्क सड़क बाबड़ी से टीकरी | Completed | 3672000 | 3440969.86 | 2017-06-10 | 2020-06-10
JOURA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701005066/RC/22012034341963 — सुदूर ग्राम संपर्क सड़क नहर से पीपरी तक | Completed | 681250 | 623451.23 | 2017-06-17 | 2018-06-17
JOURA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005066/RC/22012034463512 — सी सी रोड निर्माण कार्य नहर मंदिर से शेर सिंह के घर की ओर | Completed | 67395 | 50688 | 2019-09-03 | 2020-01-15
JOURA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005066/RC/22012034463865 — c c road nirman karya nahar puliya se jeetu ke ghar ki or | Closed | 31050 | 0 | 2017-08-15
JOURA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005066/RC/22012034474254 — c c road panchayat bhavan se jatav mohalla tak | Completed | 66375 | 58080 | 2019-09-13 | 2019-12-15
JOURA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005066/RC/22012034474255 — c c road nirman pathar kharanja se papppu ke makan tak | Completed | 48150 | 20064 | 2019-10-01 | 2020-01-15
JOURA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005066/RC/22012034474346 — c c road nirman karya school se c c kharanja tak | Completed | 60187 | 48636 | 2021-04-17 | 2021-09-01
JOURA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701005066/RC/22012034526539 — Sudur gramin sampark sadak | Completed | 3551945.94 | 3454051.01 | 2020-07-06 | 2023-02-02
JOURA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701005066/RC/22012034537188 — SUDUR GRAM/KHET SADAK NAHAR SE SHIVLAL KA PURA PURANA GAW | Completed | 4168718.7 | 4068892.21 | 2020-09-19 | 2023-02-02
JOURA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005066/RC/22012034550271 — सी सी रोड निर्माण कार्य सूरज के मकान से पत्थर खरंजा तक | Completed | 40125 | 31266 | 2021-04-24 | 2021-09-01
JOURA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005066/RC/22012034550273 — सी सी रोड निर्माण कार्य स्कूल से सी सी खरंजा तक | Closed | 60183 | 0 | 2020-04-14
JOURA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005066/RC/22012034568478 — सी सी रोड नहर से स्कूल की और बरहाना | Closed | 0 | 0 | 2021-01-26
JOURA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005066/RC/22012034568479 — सी सी रोड नहर पुलिया से राजेश के घर की और बरहाना | Closed | 0 | 0 | 2021-01-26
JOURA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005066/RC/22012034568480 — सी सी रोड नहर से चक्की की ओर बरहाना | Closed | 0 | 0 | 2021-01-26
JOURA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005066/RC/22012034568481 — सी सी रोड नहर से मंदिर की ओर बरहाना | Closed | 0 | 0 | 2021-01-26
JOURA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005066/RC/22012034568482 — सी सी रोड नहर से आगनबाड़ी की ओर बरहाना | Closed | 0 | 0 | 2021-01-26
JOURA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005066/RC/22012034568483 — सी सी रोड मेन रोड स्कूल से सुल्तान एवं रामबरन के घर की ओर बाबड़ी | Closed | 0 | 0 | 2021-01-26
JOURA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005066/RC/22012034568484 — सी सी रोड मुन्ना के घर से गड़ी की ओर बरहाना | Closed | 0 | 0 | 2021-01-26
JOURA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005066/RC/22012034568604 — C C ROAD NAHAR SE SCHOOL KI OR | Completed | 9562.5 | 9264 | 2021-04-17 | 2021-08-22
JOURA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005066/RC/22012034568605 — C C ROAD NAHAR PULIYA SE RAJESH KE GHAR KI OR | Completed | 9562.5 | 9264 | 2021-04-17 | 2021-08-22
JOURA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005066/RC/22012034568609 — C C ROAD NAHAR SE CHAKKI KI OR | Completed | 9562.5 | 9264 | 2021-04-17 | 2021-08-22
JOURA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005066/RC/22012034568610 — C C ROAD NAHAR SE MANDIR KI OR | Completed | 9562.5 | 9264 | 2021-04-17 | 2021-08-22
JOURA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005066/RC/22012034568611 — C C ROAD NAHAR SE ANGANBADI KI OR | Completed | 9562.5 | 9264 | 2021-04-17 | 2021-09-06
JOURA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005066/RC/22012034568612 — NIL | Closed | 0 | 0 | 2021-01-26
JOURA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005066/RC/22012034568613 — C C ROAD MAIN ROAD SE SULTAN AIVM RAMVARAN K GHAR KI OR | Completed | 81450 | 63690 | 2021-05-08 | 2021-08-31
JOURA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005066/RC/22012034568614 — C C ROAD MUNNA KE GHAR SE GADI KI OR | Completed | 76500 | 74112 | 2021-04-17 | 2021-08-31
JOURA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005066/RC/22012034577317 — सी सी रोड राजेश के घर से पंचायत भवन की ओर | Completed | 57375 | 57321 | 2021-07-12 | 2021-08-31
JOURA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701005066/RC/22012034672642 — सुदूर सम्पर्क सड़क निर्माण कार्य सी सी रोड से ताल की ओर | Closed | 0 | 0 | 2023-10-02
JOURA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701005066/RC/22012034672643 — सुदूर सम्पर्क सड़क निर्माण कार्य PMGSY रोड से नाले की ओर | Closed | 0 | 0 | 2023-10-02
JOURA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701005066/RC/22012034673199 — सुदूर सम्पर्क सड़क निर्माण कार्य सी सी रोड से ताल की ओर | Closed | 0 | 0 | 2023-10-02
JOURA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701005066/RC/22012034673200 — सुदूर सम्पर्क सड़क निर्माण कार्य PMGSY रोड से नाले की ओर | Closed | 0 | 0 | 2023-10-02
JOURA | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Metal Second coat / Construction of WBM Roads for Community | Construction of Road and Culvert | 1701005066/RC/518 — पत्‍थर खरजा निर्माण नहर की पुलिया से हरजन पुलिया की ओर | Completed | 0 | 439450.52 | 2011-11-06 | 2012-10-30
JOURA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005066/RC/596 — सी.सी. खरंजा निर्माण नाली सहित स्‍वराज भवन की ओर | Completed | 79145 | 69617 | 2012-07-13 | 2012-09-06
JOURA | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701005066/RC/77 — मिटटी ग्रवेल रोड बाबडी से टीकम बहराना | Completed | 0 | 340127.83 | 2008-12-25 | 2012-08-01
JOURA | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cross Drainage / Construction of Culvert / cross drainage structues for Community | Culvert | 1701005066/RC/78 — सोख्‍ता गडडा मुरारी हरिजन पुरा बहराना | Completed | 0 | 7329 | 2009-01-29 | 2016-10-10
JOURA | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005066/RC/79 — सी.सी. खंरजा निर्माण कार्य बाबडी गांव बहराना | Deleted | 0 | 0 | 2008-04-26
JOURA | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701005066/RC/81 — सी.सी. खंरजा निर्माण कार्य बाबाडी पुरा बरहाना | Completed | 0 | 51688 | 2009-03-20 | 2008-12-29
JOURA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1701005066/RS/22012034604222 — सामुदायिक शोचालय निर्माण कार्य बरहना | Completed | 43000 | 42074 | 2021-11-14 | 2022-04-20
JOURA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1701005066/RS/22012034604225 — सामुदायिक शोचालय निर्माण कार्य बाबड़ी | Completed | 43000 | 41688 | 2021-11-14 | 2022-04-20
JOURA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1701005066/RS/22012034647301 — पत्थर नाला निर्माण कार्य शेर सिंह के घर से बेहड़ की ओर | Closed | 0 | 0 | 2022-01-26
JOURA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1701005066/RS/22012034647306 — पत्थर नाला निर्माण कार्य शेर सिंह के घर से बेहड की ओर | Completed | 639318.56 | 610744 | 2022-03-23 | 2023-02-02
JOURA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005066/WC/139 — सौख्‍ता गडडे राजेन्‍द्र सिंह पुवना गाव गढी बरहाना | Deleted | 0 | 0 | 2008-04-15
JOURA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005066/WC/186 — सोक्‍ता गडडा हरिया महेन्‍तर वरहाना | Completed | 0 | 10475.9 | 2009-03-15 | 2015-07-03
JOURA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005066/WC/188 — सोक्‍ता गडडा मुन्‍नालाला कार्य वरहाना | Completed | 0 | 9808 | 2009-03-15 | 2015-07-03
JOURA | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Mini Percolation tank / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1701005066/WC/22012034380601 — naveen talab nirman | Closed | 0 | 0 | 2017-10-02
JOURA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005066/WC/22012034395857 — Naveen talab nirman - shamshan ghat ke pas tikari GP barhana | Completed | 1484000 | 1455454.31 | 2018-09-01 | 2020-12-12
JOURA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1701005066/WC/22012034499641 — Talab nirman karya-Gram Teekari | Completed | 1435740.48 | 1372720.53 | 2019-10-16 | 2020-01-20
JOURA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1701005066/WC/22012034518626 — तालाब निर्माण कार्य मजरा टीकरी में। | Completed | 1435741.13 | 1392734.38 | 2020-01-21 | 2021-01-29
JOURA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1701005066/WC/22012034528247 — तालाब निर्माण कार्य कस्वाली। | Completed | 1435741.13 | 1418576.15 | 2020-05-23 | 2020-12-30
JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1701005066/WC/22012034727579 — तालाब निर्माण कार्य झंडकौला बरहाना | Closed | 0 | 0 | 2021-04-14
JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1701005066/WC/22012034727581 — तालाब निर्माण कार्य झंडकौला बरहाना | Completed | 994939.03 | 960053.45 | 2021-08-20 | 2024-11-30
JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Renovation of Fisheries Ponds for Community / Renovation of Fisheries Ponds for Community | Repair & maint of Pond/ Tank | 1701005066/WC/22012034727590 — तालाब निर्माण कार्य ग्राम बरहाना | Closed | 0 | 0 | 2021-04-14
JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1701005066/WC/22012034731301 — Roof top water harvesting | Completed | 22173.14 | 22335 | 2021-09-10 | 2021-10-28
JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1701005066/WC/22012034731309 — Roof top water harvesting | Completed | 22173.14 | 20734 | 2021-09-10 | 2021-10-28
JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & maint of Community Ponds for Comm / Repair and maintenance of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1701005066/WC/22012034857749 — तालाब जीर्णोद्धार बरहाना | Closed | 0 | 0 | 2021-10-02
JOURA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Canal Line Plantation of Forestry-Community / Canal Line Plantation for Community | Plantation | 1701005066/WC/22012034957678 — talab nirman karya jhirna ke pass | Ongoing | 1062832.31 | 667157.01 | 2022-05-11
JOURA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Canal Line Plantation of Forestry-Community / Canal Line Plantation of Forestry Trees for Community | Plantation | 1701005066/WC/22012034957685 — talab nirman karya kakar bali baharana | Completed | 1087533.02 | 894119.69 | 2022-05-11 | 2023-02-02
JOURA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005066/WC/22012034957688 — Artam chek dam mahendra ke khet ke pass | Closed | 0 | 0 | 2022-04-22
JOURA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005066/WC/22012034967962 — Earthern Dam Nirman Karya Mahendra Ke Khet Ke Pass | Completed | 966955.99 | 849680 | 2022-08-18 | 2023-12-29
JOURA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005066/WC/22012034967963 — Earthern Dam Nirman Karya Mahendra Ke Khet Ke Pass | Deleted | 0 | 0 | 2022-04-14
JOURA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1701005066/WC/22012035008317 — Talab nirman karya Fer Barahana | Completed | 1208301.68 | 1099043.5 | 2022-12-02 | 2024-12-09
JOURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701005066/WC/22012035073555 — talab nirman karya shyaru bali naree | Completed | 1209125.16 | 379722 | 2023-08-05 | 2025-05-10
JOURA | 2023-2024 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1701005066/WC/22012035073572 — taTalab nirman karya makanpur bali naree | Completed | 1200534.58 | 1102702 | 2023-08-14 | 2025-05-10
JOURA | 2023-2024 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1701005066/WC/22012035073575 — Talab nirman karya babriya bali naree | Completed | 1197460.52 | 460890 | 2023-07-29 | 2025-05-10
JOURA | 2023-2024 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1701005066/WC/22012035074601 — talab niman karya donaee ke pass | Closed | 1214242.81 | 0 | 2023-04-14
JOURA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1701005066/WC/22012035122190 — तालाब निर्माण कार्य 22 बीघा के पास | Completed | 1292100.01 | 1246459 | 2023-10-08 | 2024-12-09
JOURA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1701005066/WC/22012035122191 — तालाब निर्माण सिद्ध बाबा की नारी के पास | Completed | 1278024.2 | 858678 | 2023-10-01 | 2025-05-10
JOURA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1701005066/WC/22012035122195 — तालाब निर्माण कार्य बैताल वाली नरी के पास | Completed | 1313071.77 | 964013 | 2023-10-08 | 2025-11-16
JOURA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Construction of Fisheries Ponds for Community / Construction of Fishery Pond for Community | Construction of Tank | 1701005066/WC/22012035132957 — तालाब निर्माण कार्य गुफा के पास | Ongoing | 1326133.49 | 691484 | 2023-10-09
JOURA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Construction of Fisheries Ponds for Community / Construction of Fishery Pond for Community | Construction of Tank | 1701005066/WC/22012035132961 — तालाब निर्माण कार्य संदीप के खेत के पास | Ongoing | 1283447.73 | 959027 | 2023-10-09
JOURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701005066/WC/22012035155051 — रपटा निर्माण कार्य सियारू वाले के पास | Completed | 1267827.52 | 1163369.75 | 2024-03-09 | 2024-12-17
JOURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701005066/WC/22012035155054 — रपटा निर्माण कार्य ककरेट घटा के पास | Closed | 0 | 0 | 2023-10-02
JOURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701005066/WC/22012035155205 — रपटा निर्माण कार्य सेठ वाली के पास | Closed | 0 | 0 | 2023-10-02
JOURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701005066/WC/22012035155206 — रपटा निर्माण कार्य सिमराया के पास | Closed | 0 | 0 | 2023-10-02
JOURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701005066/WC/22012035155207 — रपटा निर्माण कार्य तलैया के पास | Closed | 0 | 0 | 2023-10-02
JOURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701005066/WC/22012035157340 — रपटा निर्माण कार्य सियारू वाले के पास | Closed | 0 | 0 | 2023-10-02
JOURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701005066/WC/22012035157341 — रपटा निर्माण कार्य ककरेट घटा के पास | Completed | 1240474.57 | 1164950.43 | 2024-03-09 | 2024-12-17
JOURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701005066/WC/22012035157342 — रपटा निर्माण कार्य सेठ वाली के पास | Completed | 1276283.03 | 1228494.25 | 2024-03-09 | 2024-12-17
JOURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701005066/WC/22012035157343 — रपटा निर्माण कार्य सिमराया के पास | Completed | 1250355.36 | 1058589.45 | 2024-03-09 | 2025-05-10
JOURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701005066/WC/22012035157344 — रपटा निर्माण कार्य तलैया के पास | Completed | 1225066.83 | 1204077.55 | 2024-03-09 | 2024-11-30
JOURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701005066/WC/22012035157680 — रपटा निर्माण कार्य टीकरी | Deleted | 0 | 0 | 2023-10-02
JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1701005066/WC/22012035218821 — तालाब निर्माण कार्य नाले के पास | Approved | 0 | 0 | 2024-06-10
JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1701005066/WC/22012035218822 — तालाब निर्माण कार्य झोर मे | Approved | 0 | 0 | 2024-06-10
JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1701005066/WC/22012035218823 — तालाब निर्माण कार्य ज्योति मे | Approved | 0 | 0 | 2024-06-10
JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1701005066/WC/22012035218824 — तालाब निर्माण कार्य शेड के पास | Approved | 0 | 0 | 2024-06-10
JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1701005066/WC/22012035218826 — तालाब निर्माण कार्य पिरोठाई मे | Ongoing | 1398813.8 | 1128741.12 | 2024-10-26
JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005066/WC/22012035219574 — Percolation Tank Nirman Karya Naale Ke Pass | Completed | 1397052.79 | 1088074 | 2024-11-02 | 2025-09-10
JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005066/WC/22012035219575 — Percolation Tank Nirman Karya Kaliyan Ke Khet Ke Pass | Completed | 1398160.95 | 1210618 | 2024-11-02 | 2025-09-10
JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005066/WC/22012035219576 — Percolation Tank Nirman Karya Rahul Ke Khet Ke Pass | Completed | 1388319.95 | 1231446.56 | 2024-11-02 | 2025-10-14
JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005066/WC/22012035219577 — Percolation Tank Nirman Karya Shed Ki Nari Ke Pass | Completed | 1399701.98 | 1347311.16 | 2024-11-02 | 2025-10-14
JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1701005066/WC/22012035219578 — Percolation Tank Nirman Karya Jyoti Me | Ongoing | 1399589.37 | 1341861.18 | 2024-10-26
JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1701005066/WC/22012035251090 — Talab Nirman Karya Bachchu Ke Khet Ke Pass | Ongoing | 1428257.16 | 1034153.44 | 2025-03-27
JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005066/WC/22012035251091 — Talab Nirman Karya Roshan Ki Nari me | Deleted | 0 | 0 | 2025-01-26
JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1701005066/WC/22012035251092 — Talab Nirman Karya Roshan Ki Nari me | Ongoing | 1426362.49 | 1179685.24 | 2025-03-27
JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1701005066/WC/22012035251093 — Talab Nirman Karya Kua Wala | Ongoing | 1428257.16 | 1082011.24 | 2025-03-27
JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005066/WC/22012035251094 — Talab Nirman Karya Chaukhariya ki Nari | Physically Completed | 1430348.66 | 1315502.14 | 2025-03-27 | 2026-05-04
JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1701005066/WC/22012035251095 — Talab Nirman Karya Guda Khar me | Ongoing | 1428257.16 | 1348959.19 | 2025-07-26
JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005066/WC/22012035251096 — Talab Nirman Karya Ramsewak Ke Khet Ke Pass | Physically Completed | 1431792.22 | 1291594.1 | 2025-03-27 | 2026-05-04
JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1701005066/WC/22012035315615 — Talab Nirman Karya Lalu ke Khet Ke Pass | Ongoing | 1459912.77 | 523825.39 | 2026-02-13
JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1701005066/WC/22012035315616 — Talab Nirman Karya Seetu Ke Khet Ke Pass | Ongoing | 1481106.1 | 669259.08 | 2026-02-13
JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1701005066/WC/22012035315617 — Talab Nirman Karya Shera ke Khet Ke Pass | Ongoing | 1466720.09 | 1095261.65 | 2025-09-28
JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005066/WC/22012035315618 — Talab Nirman Karya Ajay Ke Khet Ke Pass | Physically Completed | 1446298.13 | 1369610.46 | 2025-10-05 | 2026-05-04
JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1701005066/WC/22012035315619 — Talab Nirman Karya Bhullan Ke Khet Ke Pass | Ongoing | 1461428.5 | 856302.67 | 2026-02-13
JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1701005066/WC/22012035315621 — Talab Nirman Karya Jitendra Ke Khet Ke Pass | Ongoing | 1471267.3 | 869071.12 | 2026-02-13
JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005066/WC/22012035315622 — Talab Nirman Karya Gokarm Ke Khet Ke Pass | Physically Completed | 1450073.97 | 1285123.59 | 2025-11-20 | 2026-05-04
JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005066/WC/22012035315623 — Talab Nirman Karya Road Ke Pass | Physically Completed | 1443266.65 | 1375308.32 | 2025-10-19 | 2026-04-16
JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1701005066/WC/22012035315624 — Talab Nirman Karya Sovran Ke Khet Ke Pass | Ongoing | 1454621.18 | 691458.24 | 2025-11-20
JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1701005066/WC/22012035315625 — Talab Niman Karya Mahendra Ke Khet Ke Pass | Ongoing | 1461428.5 | 535413.32 | 2026-02-13
JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1701005066/WC/22012035320117 — Talab Nirman Karya Sonu ke Khet Ke pass | Ongoing | 1494736.42 | 983820.8 | 2025-11-20
JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1701005066/WC/22012035320118 — Talab Nirman Karya Kallu ke Khet Ke pass | Ongoing | 1489466.98 | 772412.14 | 2025-11-20
JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1701005066/WC/22012035320119 — Talab Nirman Karya Chhotu ke Khet Ke pass | Ongoing | 1485332.79 | 566980.29 | 2026-02-13
JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1701005066/WC/22012035320120 — Talab Nirman Karya Bhupendra ke Khet Ke pass | Ongoing | 1487660.57 | 712460.26 | 2026-02-13
JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1701005066/WC/22012035320121 — Talab Nirman Karya Arru Wali nari | Ongoing | 1489919.04 | 802242.73 | 2026-02-13
JOURA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Artificial Recharge of Well Through Sand Filter / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1701005066/WC/78 — सोख्‍ता गडडा मुरारी हरिजन पुरा बहराना | Completed | 0 | 3238 | 2011-10-09 | 2016-10-10
JOURA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005066/WC/9 — सौखता गडडा राजेन्‍द्र सिंह पुराना गांव गढी बरहाना | Completed | 0 | 10395 | 2009-02-12 | 2015-07-03
JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1701005066/WH/22012034451774 — Talab Renovation Bhaveswari wala | Completed | 49511.22 | 34354 | 2022-02-20 | 2022-04-20
JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1701005066/WH/22012034451776 — Talab Renovation Jhor wala | Completed | 49843.47 | 47340 | 2022-03-26 | 2022-04-20
JOURA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1701005066/WH/9 — सौखता गडडा राजेन्‍द्र सिंह पुराना गांव गढी बरहाना | Completed | 0 | 7238 | 2009-01-29 | 2016-10-10
JOURA | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701/RC/22012034151759 — mitti grawal road A.B.Cenal road se Tikari joura | Completed | 2350000 | 1367384.3 | 2011-06-16 | 2012-07-04