## Work List
Exported on: 2026-09-11 14:01:09
Filters applied:
Data source: VBGRAMG
District: MORENA
Block: All
Panchayat: BAWADIPURA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
SABALGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Fisheries | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1701007001/FR/22012034323113 — Percolation tank Nirman karya Ramesh ki khet ke pass bawadipura | Ongoing | 1484450.17 | 0 | 2025-03-20
SABALGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Fisheries | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1701007001/FR/22012034323114 — Talab Nirman karya kacha ki ke pass | New | 0 | 0 | 2024-08-15
SABALGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Afforestation of wasteland Forestry trees for ind / Afforestation of wasteland Forestry trees for individual | Plantation | 1701007001/IF/22012035375329 — Khet Talab Nirman karya Atar ke khet par Bawadipura | Ongoing | 450885.64 | 0 | 2025-04-28
SABALGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Afforestation of wasteland Forestry trees for ind / Afforestation of wasteland Forestry trees for individual | Plantation | 1701007001/IF/22012035375333 — Khet Talab Nirman karya ramlakhan khet par manpur | Ongoing | 450885.64 | 0 | 2025-04-28
SABALGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1701007001/IF/22012035601250 — EK BAGIYA MAA KE NAME MATHURA JATAV MP01007001001/1311 | Ongoing | 283615.02 | 0 | 2026-01-01
SABALGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1701007001/IF/22012035601259 — EK BAGIYA MAA KE NAME SIYA BAI JATAV MP01007001001/432 | Ongoing | 282716.95 | 0 | 2026-01-01
SABALGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1701007001/IF/22012035601267 — EK BAGIYA MAA KE NAME KAMLESH JATAV MP01007001001/806 | Ongoing | 282718.85 | 0 | 2026-01-01
SABALGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1701007001/IF/22012035601273 — EK BAGIYA MAA KE NAME SHRIMATI BAI JATAV | Ongoing | 282716.95 | 0 | 2026-01-01
SABALGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1701007001/IF/22012035631508 — EK BAGIYA MAA KE NAAM MEERA RAWAT MP-01-007-001-001/1354 | Ongoing | 282718.25 | 0 | 2026-01-01
SABALGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1701007001/IF/22012035641520 — EK BAGIYA MAA KE NAME MAYAVATI JATAV MP01007001002/863 | Ongoing | 266578.64 | 0 | 2026-01-01
SABALGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1701007001/IF/22012035641526 — EK BAGIYA MAA KE NAME PREETI JATAV MP01007001002/744 | Ongoing | 266578.64 | 0 | 2026-01-01
SABALGARH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701007001/IF/IAY/199230 — Construction of IAY House -IAY REG. NO. MP-01-007-001-002/71 | Approved | 27000 | 0 | 2015-11-18
SABALGARH | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of WBM Roads for Community / Construction of WBM Roads for Community | Construction of Road and Culvert | 1701007001/RC/22012034617557 — rapata Nirman kary khareri par manpur | Ongoing | 1453187.5 | 0 | 2023-06-27
SABALGARH | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Interlocking block/tiles Roads for Comm / Construction of Inter-locking cement block/tiles Roads for Community | Constr of Cement Concrete Roads | 1701007001/RC/22012034651142 — rapata nirman karya ramuji rawat ke khet ke pass khareri nale par | Ongoing | 1442290.8 | 0 | 2023-09-13
SABALGARH | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Interlocking block/tiles Roads for Comm / Construction of Inter-locking cement block/tiles Roads for Community | Constr of Cement Concrete Roads | 1701007001/RC/22012034651234 — rapata nirman karya bilabare nale par bawadipura | Ongoing | 2296120.25 | 0 | 2023-12-29
SABALGARH | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Kharanja (brick/stone) Roads for Comm / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701007001/RC/22012034669498 — सुदूर /खेत सड़क निर्माण कार्य गोंदोली रोड़ से सुमेर शर्मा के खेत की ओर बाबडीपुरा | Ongoing | 2481019.31 | 0 | 2025-01-08
SABALGARH | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1701007001/RS/22012034667106 — Nali nirman karya Hari Sharma ke ghar se bilware ki or | Ongoing | 1496999.43 | 0 | 2022-11-16
SABALGARH | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1701007001/RS/22012034668211 — पक्की नाली निर्माण कार्य आंगनवाड़ी से खरई पुलिया की ओर मानपुर | Ongoing | 1418319.05 | 0 | 2022-11-02
SABALGARH | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701007001/WC/22012035037903 — Manrega watershed earthen bund nirman karya Hanuman mandra ke pas babdipura | Ongoing | 1496341.51 | 0 | 2023-05-02
SABALGARH | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701007001/WC/22012035236610 — Loose folder Nirman karya pokhar ke pass | Approved | 0 | 0 | 2024-08-15
SABALGARH | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701007001/WC/22012035236613 — Talab Nirman karya KharenBali pokhar ke pass bavdi pura | Ongoing | 1477351.29 | 0 | 2025-03-20
SABALGARH | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701007001/WC/22012035236614 — Trench Nirman karya gaushala ke pass pavdi pura | Approved | 399932.57 | 0 | 2024-08-15
SABALGARH | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701007001/WC/22012035236616 — Loose folder Nirman karya jamaniya ke pass bavdi pura | Approved | 0 | 0 | 2024-08-15
SABALGARH | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701007001/WC/22012035236617 — Percolation tank Nirman karya Bunty ke khet ke pass bavdi pura | Ongoing | 1334590.33 | 0 | 2025-03-20
SABALGARH | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701007001/WC/22012035236618 — trench Nirman karya ramswaroop ki kherakari ke paas Wabadipura | Ongoing | 414889.09 | 0 | 2025-03-20
SABALGARH | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701007001/WC/22012035236623 — Talab Nirman karya karil wali ke pass Wabadipura | Ongoing | 1428981.96 | 0 | 2025-03-20
SABALGARH | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701007001/WC/22012035236626 — Percolation tank Nirman karya Hanuman mandra ke pass bawadipura | Ongoing | 1493383.79 | 0 | 2025-03-20
SABALGARH | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701007001/WC/22012035236627 — Percolation tank Nirman karya cheta wali ke pass Wabadipura | Approved | 0 | 0 | 2024-08-15
SABALGARH | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701007001/WC/22012035236629 — Trench Nirman karya kherakari ke paas Wabadipura | Approved | 410714.57 | 0 | 2024-08-15
SABALGARH | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701007001/WC/22012035236818 — Talab Nirman karya Murari jatav ke khet ke pass bavdi pura | Ongoing | 1281142.39 | 0 | 2025-03-20
SABALGARH | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701007001/WC/22012035236822 — Talab Nirman karya Rajesh ke khet ke pass Wabadipura | Ongoing | 1466096.25 | 0 | 2025-03-20
SABALGARH | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701007001/WC/22012035247585 — Amrat sarobar talab dangpura manpur | Approved | 0 | 0 | 2025-01-27
SABALGARH | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701007001/WC/22012035250769 — Talav nirman kary Ramu ke khet ke pas gp Bawadipura | Ongoing | 1445141.99 | 0 | 2025-03-20
SABALGARH | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701007001/WC/22012035253285 — Gali Plug Nirman karya shriram ke khet ke pas Bawadipura | Approved | 0 | 0 | 2025-01-27
SABALGARH | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701007001/WC/22012035253286 — Percolation tank Nirman karya futera ke pass Bawadipura | Approved | 0 | 0 | 2025-01-27
SABALGARH | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701007001/WC/22012035253288 — Gali plug Nirman karya Saman puriya ke khet ke pass Bawadipura | Approved | 0 | 0 | 2025-01-27
SABALGARH | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701007001/WC/22012035253289 — Gali plug Nirman karya Mora Khar ke pass Bawadipura | Approved | 0 | 0 | 2025-01-27
SABALGARH | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701007001/WC/22012035253291 — Gali plug Nirman karya Ram Singh ke khet ke pass Bawadipura | Approved | 0 | 0 | 2025-01-27
SABALGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701007001/WC/22012035310414 — AMRIT SAROVAR DANGPURA MANPUR GP BABDIPURA | Approved | 0 | 0 | 2025-04-15