## Work List
Exported on: 2026-10-13 08:23:47
Filters applied:
Data source: VBGRAMG
District: MORENA
Block: All
Panchayat: All
Status: Physically Completed
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
AMBAH / DHANSULA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1701001041/IF/22012035356190 — KHET TALAB NIRMAN RAMPRAKASH KE KHET PAR DHANSULA | Physically Completed | 147621.16 | 0 | 2025-04-27 | 2026-08-16
AMBAH / DHANSULA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1701001041/IF/22012035458867 — KHET TALAB NIRMAN MAHESH BAGHEL KE KHET PAR DHANSULA | Physically Completed | 147621.16 | 0 | 2025-05-05 | 2026-08-16
AMBAH / DHANSULA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1701001041/IF/22012035459094 — KHET TALAB NIRMAN BAJRANG KE KHET PAR DHANSULA | Physically Completed | 147621.16 | 0 | 2025-05-05 | 2026-08-16
AMBAH / DHANSULA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1701001041/IF/IAY/4528697 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP134383540 | Physically Completed | 23490 | 0 | 2025-01-20 | 2026-07-19
AMBAH / DHANSULA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1701001041/IF/IAY/4719246 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP134320169 | Physically Completed | 23490 | 0 | 2025-01-24 | 2026-07-19
PORSA / GARHIAPORSA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701002003/WC/22012034737259 — ARDHAN DEM NIRMAN KRAMANK 01 | Physically Completed | 1496320.62 | 0 | 2024-03-15 | 2026-08-18
PORSA / GARHIAPORSA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701002003/WC/22012034737298 — ARDHAN DEM NIRMAN KRAMANK 04 | Physically Completed | 1493447.14 | 0 | 2024-03-15 | 2026-08-18
PORSA / MATIYAPURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1701002004/WC/22012035015707 — अमृत ​​सरोवर निर्माण कार्य रवींद्र सिंह के खेत के पास ग्राम रिठवारी ग्राम पंचायत मटियापुरा जनपद पंचा | Physically Completed | 2495623.11 | 0 | 2023-05-16 | 2026-08-18
PORSA / DOHROTA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Brushwood Check Dam for Community / Construction of Brushwood Gully Plug for Community | Construction of Check Dam/Stop Dam | 1701002005/WC/22012034879912 — c.c.cheek dem no.9 | Physically Completed | 1487990.31 | 0 | 2023-03-23 | 2026-08-18
PORSA / MEHDORA | 2025-2026 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Centre Building for Community | Constr of Aganwadi | 1701002006/AV/22012034668492 — ANGANWADI BHAVAN NIRMAN LAKHPAT KA PURA MEHDORA | Physically Completed | 500000 | 0 | 2025-12-31 | 2026-08-18
PORSA / TARSAMA | 2025-2026 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1701002007/AV/22012034668472 — SHANTIDHAM NIRMAN KARYA TARSAMA KA PURA | Physically Completed | 347299.31 | 0 | 2026-01-15 | 2026-08-18
PORSA / TARSAMA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1701002007/IF/22012035311258 — खेत तालाब निर्माण कार्य महेन्द्र के खेत के पास तरसमा | Physically Completed | 497822.06 | 0 | 2025-03-29 | 2026-08-18
PORSA / TARSAMA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Gov blding premises-Block Plantation-Horticulture / Plantation in Institutions for Community | Plantation | 1701002007/WC/22012035127809 — खेत तालाब निर्माण कार्य अजमेर के खेत के पास तरसमा | Physically Completed | 490273.72 | 0 | 2023-10-06 | 2026-08-18
PORSA / SAINTHRAAHIR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1701002011/IF/IAY/4916047 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100485574 | Physically Completed | 27000 | 1800 | 2025-04-09 | 2026-09-06
PORSA / SAINTHRAAHIR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1701002011/IF/IAY/4916048 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100485578 | Physically Completed | 23490 | 1800 | 2025-04-09 | 2026-08-23
PORSA / SAINTHRAAHIR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1701002011/IF/IAY/4916791 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100614167 | Physically Completed | 27000 | 9000 | 2025-04-09 | 2026-09-06
PORSA / SAINTHRAAHIR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1701002011/IF/IAY/4917292 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100716177 | Physically Completed | 27000 | 3300 | 2025-04-09 | 2026-09-06
PORSA / SAINTHRAAHIR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1701002011/IF/IAY/4933202 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100714346 | Physically Completed | 27000 | 0 | 2025-04-09 | 2026-09-06
PORSA / SAINTHRAAHIR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1701002011/RC/22012034836035 — Cc Road rambaran ke makan se main road ki or kachchi ki gadiya senthra | Physically Completed | 54000 | 0 | 2025-03-03 | 2026-08-18
PORSA / HINGAWALI | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1701002012/RC/22012034614267 — सीसी रोड एवं नाली निर्माण कार्य माता के मन्दिर से शांतिधाम तक तोरकुम्भ हिंगावली | Physically Completed | 83000 | 0 | 2023-07-15 | 2026-08-18
PORSA / BARWAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Fisheries | Construction of Fisheries Ponds for Community / Construction of Fishery Pond for Community | Construction of Tank | 1701002013/FR/22012034324262 — NAVEEN TALAB NIRMAN KARYA 23 JANE KE KHET KE PASS GP BARBAI | Physically Completed | 1487171.43 | 0 | 2025-03-27 | 2026-08-18
PORSA / BARWAI | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Mitti Murram Roads for Community / Construction of Farm Roads for Community | Construction of Road and Culvert | 1701002013/RC/22012034653264 — SUDOOR / KHET NIRMAN HARISHCHANDRA PURA SE BHOOPATI VA PMGSY SE GYAN SINGH KE PURA KI OR GP BARBAI | Physically Completed | 2479452.79 | 0 | 2023-10-06 | 2026-08-18
PORSA / BARWAI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701002013/WC/22012035020188 — GWIMP PERCOLATION TANK NEECHALE KHAR BHADORIYA PURA GP BARBAI | Physically Completed | 1482627.8 | 0 | 2023-09-30 | 2026-08-18
PORSA / AJHENDA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1701002017/RC/22012034652128 — cc road nali nirman karya chopal karyalay se Mata mandir tak Ajhenda | Physically Completed | 87450 | 0 | 2023-10-06 | 2026-08-18
PORSA / AJHENDA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1701002017/RC/22012034849257 — cc roads nirman karya pradhanmantri sadak se ravindra sakhwar ke darwaje ki or Ajhenda | Physically Completed | 188122 | 0 | 2026-01-15 | 2026-08-18
PORSA / SAINTHRABADHAI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Coastal Afforestation using forstry Trees for Comm / Plantation in Coastal Area for Community | Plantation | 1701002019/DP/22012034617094 — बृक्ष रोपण कार्य हनुमान गढ़ गौशाला परिसर | Physically Completed | 1236777.81 | 0 | 2024-07-05 | 2026-08-18
PORSA / SAINTHRABADHAI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Coastal Afforestation using forstry Trees for Comm / Plantation in Coastal Area for Community | Plantation | 1701002019/DP/22012034617096 — बृक्ष रोपण कार्य सेंथरा बढ़ाई | Physically Completed | 490869.72 | 0 | 2024-07-05 | 2026-08-18
PORSA / SAINTHRABADHAI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Coastal Afforestation using forstry Trees for Comm / Plantation in Coastal Area for Community | Plantation | 1701002019/DP/22012034617270 — बृक्ष रोपण कार्य माजरा लखरियाई | Physically Completed | 576821.8 | 0 | 2024-07-05 | 2026-08-18
PORSA / SAINTHRABADHAI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Coastal Afforestation using forstry Trees for Comm / Plantation in Coastal Area for Community | Plantation | 1701002019/DP/22012034619947 — बृक्ष रोपण कार्य मुक्ति धाम सेंथरा बढ़ाई परिसर | Physically Completed | 856670.88 | 0 | 2024-09-04 | 2026-08-18
PORSA / SAINTHRABADHAI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Wasteland Block Plantation-Forstry-Community / Wasteland Block Plantation of Forestry Trees for Community | Plantation | 1701002019/DP/22012034620001 — Miyabwaki Dence plantation gp senthara badhai | Physically Completed | 2495902.98 | 0 | 2024-07-04 | 2026-08-18
PORSA / PALI | 2020-2021 | C--COMMON INFRASTRUCTURE FOR NRLM COMPLIANT SELF HELP GROUPS / Anganwadi/Other Rural Infrastructure | Constr of agri produce storage building for groups / Construction of Agricultural Produce Storage Building for Community | Constr of Food Grain storage | 1701002020/AV/22012034514667 — GOSHALA NIRMAN KARYA PALI | Physically Completed | 3784582.21 | 0 | 2020-09-24 | 2026-08-18
PORSA / KASMDA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1701002021/RC/22012034825626 — cc road and nali nirman gohri main road se sanjay ke bangla ki or kasmada | Physically Completed | 78900 | 0 | 2024-10-24 | 2026-08-18
PORSA / VIJAYGARH | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701002022/WC/22012035069651 — ardhan dam nirman karya pipara wali nariya piprai | Physically Completed | 1382586.23 | 0 | 2024-03-12 | 2026-09-21
PORSA / JOTAI | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Flood Diversion Drain for Community | Works for Flood Control and Protection | 1701002024/FP/22012034630976 — NALA NIRMAN KARYA SIROMN SINGH KE GHAR SE CHHUTANI TALAB KI OR JOTAI | Physically Completed | 1410859.47 | 0 | 2023-01-29 | 2026-08-18
PORSA / JOTAI | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1701002024/RC/22012034847664 — CC ROAD DAMODAR SINGH TOMAR KE GHAR SE RAMENDRA SINGH TOMAR KE GHAR KI OR | Physically Completed | 91000 | 0 | 2025-08-25 | 2026-08-18
PORSA / USETH | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1701002029/WC/22012035220182 — Parkulation tank nirman bade khar ke pass gp useth | Physically Completed | 1387299.7 | 0 | 2024-12-03 | 2026-08-18
PORSA / LUDHAWALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Fisheries | Construction of Fisheries Ponds for Community / Construction of Fishery Pond for Community | Construction of Tank | 1701002031/FR/22012034323508 — naveen talab nirman patel ke khet ke paas me | Physically Completed | 1474863.25 | 0 | 2025-03-07 | 2026-08-18
PORSA / LUDHAWALI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1701002031/WC/22012035141107 — एनी कट निर्माण दाताराम के खेत के पास | Physically Completed | 1470963.93 | 0 | 2024-03-14 | 2026-08-18
PORSA / MAHUA | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Flood Diversion Drain for Community | Works for Flood Control and Protection | 1701002032/FP/22012034638687 — nala nirman karya deepak ke makan se thana hote hue jangal ki or | Physically Completed | 1495000.29 | 0 | 2024-03-14 | 2026-08-18
PORSA / KHADIYAPORSA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1701002037/RC/22012034631325 — सीसी रोड एवं नालीनिर्माण कार्य शिवकरन के घर से लक्ष्मण के घर की ओर खड़िया पोरसा | Physically Completed | 76000 | 0 | 2023-06-21 | 2026-08-18
PORSA / KHADIYAPORSA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1701002037/RC/22012034638245 — सीसी रोड और नाली निर्माण कार्य प्रधानमंत्री रोड से गोविन्द के घर की ओर खड़ियापोरसा | Physically Completed | 65000 | 0 | 2023-09-15 | 2026-08-18
PORSA / RAJAUDHA | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Centre Building for Community | Constr of Aganwadi | 1701002040/AV/22012034659324 — ANGANBADI BHAVAN NIRMAN PANKAPURA RAJODHA | Physically Completed | 500000 | 0 | 2025-02-24 | 2026-08-18
PORSA / RAJAUDHA | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Centre Building for Community | Constr of Aganwadi | 1701002040/AV/22012034659393 — Aanganwadi Bhavan nirman karya Dharmpura GP Rajaudha | Physically Completed | 500000 | 0 | 2024-09-29 | 2026-08-18
PORSA / RAJAUDHA | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood or Diversion Channel for Community | Works for Flood Control and Protection | 1701002040/FP/22012034634464 — NALA NIRMAD KARYA OMPRAKASH KE DARBAJE SE TALAB KI OR UDYABHAN KA PURA | Physically Completed | 168750 | 0 | 2023-08-16 | 2026-08-18
PORSA / DONDARI | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Flood Diversion Drain for Community | Works for Flood Control and Protection | 1701002044/FP/22012034633700 — NALA NIRMAN KARYA RAMAVTAR KUSHWAH KE MAKAN SE TALAB KETARAF BADANKI DONDRI | Physically Completed | 1485250.13 | 0 | 2023-09-18 | 2026-08-18
PORSA / CHAPAK | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Upland Bench Terrace Terrace for Comm / Construction of Upland Bench Terrace for Community | Terracing | 1701002046/WC/22012035188680 — AH rapta nirman kary mata ke mandir ke pass | Physically Completed | 1418281.86 | 0 | 2024-03-14 | 2026-08-18
PORSA / CHAPAK | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1701002046/WC/22012035259132 — NAVEEN TALAB NIRMAN KARAY NARENDRA KE KHET KE PAAS CHAPAK | Physically Completed | 1438874.19 | 0 | 2025-06-09 | 2026-08-18
PORSA / BHADAWALI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry Check Dam for Community | Construction of Check Dam/Stop Dam | 1701002047/WC/22012035320153 — NAVEEN TALAB NIRMAN KARYA NAVIN UP SWASTHYA KENDRA KE SAMNE BHADAWALI | Physically Completed | 1492045.36 | 0 | 2025-10-15 | 2026-08-18
PORSA / HAMIRPURA | 2024-2025 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Construction of Embankment for community / Construction of Embankment for Community | Construction of Embankment | 1701002051/FP/22012034641510 — cc nali nirman karya dhakkan sahit girraj singh ke makan se jagdish singh ke makan ki or hamirpura | Physically Completed | 53000 | 0 | 2024-11-19 | 2026-08-18
PORSA / RANHERA | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Flood Diversion Drain for Community | Works for Flood Control and Protection | 1701002052/FP/22012034629420 — Nala nirman kary brajesh ke makan se rambaran ke ghar ki our khushalpura | Physically Completed | 1440565.3 | 0 | 2022-09-24 | 2026-08-18
MORENA / MAITHANA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation - Shelter Belt for Individuals / Line Plantation of Forestry Trees for Individual | Plantation | 1701003004/IF/22012035033539 — उद्यान से उद्यानिकी की ओर निजी खेत में नन्दन फलोउद्यान अरविंद पुत्र हाकिम सिंह | Physically Completed | 279367.77 | 0 | 2022-12-08 | 2026-08-21
MORENA / MAITHANA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1701003004/WC/22012035220842 — Nws parculation tank nirman kary narendra bale khaar ke pass | Physically Completed | 1477212.99 | 0 | 2024-10-16 | 2026-08-21
MORENA / PIPRAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1701003008/IF/IAY/4526917 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126500173 | Physically Completed | 27000 | 0 | 2024-10-26 | 2026-10-04
MORENA / PIPRAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1701003008/IF/IAY/5636551 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126636079 | Physically Completed | 23490 | 0 | 2025-06-04 | 2026-08-02
MORENA / PIPRAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1701003008/IF/IAY/5743083 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150640144 | Physically Completed | 23490 | 0 | 2025-08-21 | 2026-08-02
MORENA / PALPURA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1701003019/IF/IAY/4710751 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125754817 | Physically Completed | 23490 | 0 | 2024-11-30 | 2026-07-26
MORENA / PALPURA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1701003019/IF/IAY/4711447 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126377902 | Physically Completed | 23490 | 0 | 2024-11-13 | 2026-07-26
MORENA / PALPURA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1701003019/IF/IAY/4713140 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126633896 | Physically Completed | 23490 | 0 | 2024-11-30 | 2026-07-26
MORENA / PALPURA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1701003019/IF/IAY/4726876 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151158912 | Physically Completed | 23490 | 0 | 2024-11-30 | 2026-07-26
MORENA / SIKRAUDA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701003026/WC/22012035192844 — रपटा निर्माण कार्य पीपरखेडा रोड पर नारही पर | Physically Completed | 1472932.91 | 0 | 2024-03-16 | 2026-07-23
MORENA / RASEELPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701003040/LD/YD/22012034958890 — pheripheral stone bund nirman narua se ke khet se sevaram ke pura ki ore | Physically Completed | 995001.69 | 0 | 2025-11-07 | 2026-07-23
MORENA / PARIKSHA | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood or Diversion Channel for Community | Works for Flood Control and Protection | 1701003053/FP/22012034634705 — नाला निर्माण कार्य सर्वांगनाथ से टंकी की ओर | Physically Completed | 1171074.58 | 0 | 2024-02-19 | 2026-07-24
MORENA / SANGOLI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701003056/LD/22012034953382 — Periferal stone bund nirmaan karya mandir par | Physically Completed | 944114.03 | 0 | 2025-07-03 | 2026-07-23
MORENA / MADANBASAI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701003057/LD/22012034955286 — peripheral stone bund nirman karya holu singh ke khet ke pass | Physically Completed | 991277.15 | 0 | 2026-01-29 | 2026-07-23
MORENA / MADANBASAI | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003057/WC/22012035018028 — नवीन तालाब निर्माण कार्य मदनबसई | Physically Completed | 1293485.9 | 0 | 2022-12-29 | 2026-08-19
MORENA / BAMRAULI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1701003058/IF/22012035312345 — Khet talab nirman karya Ramchitra ke khet par | Physically Completed | 147621.16 | 0 | 2025-05-03 | 2026-08-19
MORENA / BAMRAULI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701003058/LD/22012034946911 — Peripheral stone bund nirman kary ramchitra ke ghar ke neeche | Physically Completed | 895582.56 | 0 | 2025-02-17 | 2026-07-01
MORENA / BAMRAULI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701003058/LD/22012034946912 — Peripheral stone bund nirmaan kary bhairro baba ke peeche | Physically Completed | 826069.98 | 0 | 2025-02-17 | 2026-07-01
MORENA / BAMRAULI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701003058/LD/22012034946913 — Peripheral stone bund nirmaan kary tenki ke pass | Physically Completed | 835620 | 0 | 2025-02-17 | 2026-07-01
MORENA / BAMRAULI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701003058/LD/22012034952312 — Periferal Stone Bund Nirmaan kary Ramnath ke khet ke pass | Physically Completed | 978510.97 | 0 | 2025-07-12 | 2026-07-01
MORENA / BAMRAULI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701003058/LD/22012034952314 — Periferal Stone Bund Nirmaan kary Mukesh ke khet ke pass | Physically Completed | 985534.33 | 0 | 2025-07-12 | 2026-07-01
MORENA / BAMRAULI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701003058/LD/22012034952315 — Periferal Stone Bund Nirmaan kary Veer ke khet ke pass | Physically Completed | 989645.36 | 0 | 2025-07-12 | 2026-07-01
MORENA / BAMRAULI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701003058/LD/22012034952316 — Periferal Stone Bund Nirmaan kary Jagram Mastar ke khet ke pass | Physically Completed | 997922.91 | 0 | 2025-07-12 | 2026-07-01
MORENA / BAMRAULI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701003058/LD/22012034957537 — Periferal stone bund nirmaan karya Aidal Kiledar ke khet ke pass | Physically Completed | 984078.84 | 0 | 2026-03-16 | 2026-07-01
MORENA / GIRGONI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701003060/LD/22012034952310 — Periferal Stone Bund Nirmaan kary Narayan ke khet ke pass | Physically Completed | 986534.33 | 0 | 2025-07-08 | 2026-07-23
MORENA / CHURHELA | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood or Diversion Channel for Community | Works for Flood Control and Protection | 1701003062/FP/22012034630973 — नाला निर्माण कार्य - चित्र सिंह के घर से तालाब तक, चुरहेला | Physically Completed | 1341929.41 | 0 | 2023-05-05 | 2026-07-23
MORENA / CHURHELA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701003062/LD/22012034954384 — Periferal stone bund nirmaan karya Charagah ke pass | Physically Completed | 942473.3 | 0 | 2025-07-05 | 2026-07-23
MORENA / JARONI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701003063/LD/22012034956252 — पेरिफेरल स्टोन बण्ड निर्माण कार्य सिनाम के खेत से गौशाला की ओर, जारौनी | Physically Completed | 987960.94 | 0 | 2026-01-03 | 2026-07-23
MORENA / LOHGARH | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood or Diversion Channel for Community | Works for Flood Control and Protection | 1701003066/FP/22012034634148 — नाला निर्माण कार्य के वी एल फैक्ट्री से भोजा का पुरा | Physically Completed | 1460749.95 | 0 | 2023-08-10 | 2026-07-22
MORENA / LOHGARH | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood or Diversion Channel for Community | Works for Flood Control and Protection | 1701003066/FP/22012034634149 — नाला निर्माण कार्य प्रकाश के घर के पीछे से नरे तक | Physically Completed | 1487009.34 | 0 | 2023-07-27 | 2026-07-22
MORENA / BAMURBASAI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701003067/WC/22012035006037 — nws talav nirman kary bhumiya waale nare me | Physically Completed | 1482945.68 | 0 | 2023-10-09 | 2026-08-21
MORENA / BAMURBASAI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701003067/WC/22012035007578 — amrat sarovar talav nirman kary chauk waale daade par | Physically Completed | 1992921.74 | 0 | 2025-07-16 | 2026-08-21
MORENA / DHANELA | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood or Diversion Channel for Community | Works for Flood Control and Protection | 1701003068/FP/22012034636377 — नाला निर्माण कार्य केदार बाथम के घर से महेन्द्र बाल्मिक के घर की ओर | Physically Completed | 1498269.22 | 0 | 2023-10-05 | 2026-07-23
MORENA / DHANELA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1701003068/IF/IAY/4508302 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151933796 | Physically Completed | 23490 | 0 | 2024-12-01 | 2026-07-19
MORENA / NAUPURA | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Flood Diversion Drain for Community | Works for Flood Control and Protection | 1701003072/FP/22012034630957 — नाला निर्माड कार्य महेंद्र सिंह के कुआ से माता के नरे तक | Physically Completed | 1479027.85 | 0 | 2023-01-16 | 2026-09-10
MORENA / NAUPURA | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Flood Diversion Drain for Community | Works for Flood Control and Protection | 1701003072/FP/22012034630958 — नाला निर्माड कार्य रामसहाय के घर से ोरुआ के नरे तक | Physically Completed | 1487132.47 | 0 | 2023-09-13 | 2026-09-10
MORENA / GULENDRA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701003073/WC/22012035216877 — nws talab nirman karya yogendra ke khet ke pass | Physically Completed | 1469242.9 | 0 | 2025-11-14 | 2026-08-21
MORENA / RANCHULI | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel / Mitti Murram Road for Community | Construction of Road and Culvert | 1701003078/RC/22012034650719 — सुदुर/खेत सडक निर्माण गुलेन्द्री से खटाने का पुरा | Physically Completed | 2491190.98 | 0 | 2023-10-04 | 2026-08-21
MORENA / MITAWALI | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood or Diversion Channel for Community | Works for Flood Control and Protection | 1701003081/FP/22012034631570 — नवीन तालाब निर्माण कार्य पैटाेराेल पम्प के पास मितावली | Physically Completed | 1486706.47 | 0 | 2023-02-13 | 2026-07-23
MORENA / MITAWALI | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood or Diversion Channel for Community | Works for Flood Control and Protection | 1701003081/FP/22012034633152 — नाला निर्माण कार्य मुंशी के पुरा पर कुआ से साफयन की ओर | Physically Completed | 1491625.67 | 0 | 2023-07-24 | 2026-08-21
MORENA / MITAWALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1701003081/IF/IAY/4527606 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132479935 | Physically Completed | 23490 | 0 | 2024-12-29 | 2026-07-27
MORENA / MITAWALI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701003081/LD/22012034955716 — Periferal Stone Bund Nirmaan Karya Nare Ke Pass | Physically Completed | 937900.48 | 0 | 2025-11-20 | 2026-07-23
MORENA / MITAWALI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701003081/LD/22012034955717 — Periferal Stone Bund Nirmaan Karya Jhare Ke Pass | Physically Completed | 936962.92 | 0 | 2025-11-20 | 2026-07-23
MORENA / MITAWALI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701003081/LD/22012034955718 — Periferal Stone Bund Nirmaan Karya Bamur Ke Pass | Physically Completed | 935827.03 | 0 | 2025-11-20 | 2026-07-23
MORENA / MITAWALI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701003081/LD/22012034955720 — Periferal Stone Bund Nirmaan Karya Neem Ke Pass | Physically Completed | 934078.12 | 0 | 2026-01-30 | 2026-07-23
MORENA / MITAWALI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701003081/LD/22012034957141 — Periferal stone bund nirmaan karya Bamur ke pass | Physically Completed | 961268.32 | 0 | 2025-11-20 | 2026-07-23
MORENA / MITAWALI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1701003081/WC/22012035218586 — परकुलेशन टैकं निर्माण कार्य गौशाला के पास | Physically Completed | 1489859.26 | 0 | 2024-10-04 | 2026-08-21
MORENA / PIPARSEVA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel / Mitti Murram Road for Community | Construction of Road and Culvert | 1701003087/RC/22012034653010 — सुदूर सड़क निर्माण कार्य रेलवे फाटक से चुन्नी सिंह के पूरा की ओर | Physically Completed | 2489198.49 | 0 | 2023-10-07 | 2026-07-24
MORENA / KHIRAWALI | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel / Mitti Murram Road for Community | Construction of Road and Culvert | 1701003089/RC/22012034534802 — सुदूर ग्राम खेत सड़क महाराज सिंह के पुरासे रामरूप के पुरा रांसू गांव की और | Physically Completed | 1499606.77 | 0 | 2020-09-16 | 2026-08-21
MORENA / KHIRAWALI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003089/WC/22012035065392 — anicut nirman kary sanjeev ke khet ke pass | Physically Completed | 1478539.69 | 0 | 2024-01-21 | 2026-07-23
MORENA / PARAULI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701003091/LD/22012034946919 — Peripheral stone bund nirman kary potli ki naiyaa ke peeche parauli | Physically Completed | 970323.57 | 0 | 2025-11-27 | 2026-07-23
MORENA / PARAULI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701003091/LD/22012034952322 — Periferal Stone Bund Nirmaan kary Bakeel Khan ke khet ke pass | Physically Completed | 977815.24 | 0 | 2025-07-12 | 2026-07-23
MORENA / PARAULI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701003091/LD/22012034952326 — Periferal Stone Bund Nirmaan kary Rajkumar ke khet ke pass | Physically Completed | 991700.88 | 0 | 2025-10-31 | 2026-07-23
MORENA / RITHAURAKALAN | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Line Plantation of Horticulture Trees for Individual | Plantation | 1701003093/IF/22012034821754 — niji khet me falouddan lakhan putra amar singh | Physically Completed | 171206.07 | 0 | 2021-09-07 | 2026-09-21
MORENA / MADRAI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701003106/LD/22012034952894 — पेरिफेरल स्टोन बण्ड निर्माण कार्य खेल मैदान के पास सिकरोड़ी | Physically Completed | 995347.97 | 0 | 2025-05-19 | 2026-07-23
MORENA / MADRAI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701003106/WC/22012035164855 — talab nirman kary sultan ke khet ke pas madarai | Physically Completed | 1497041.16 | 0 | 2024-03-13 | 2026-07-23
MORENA / JEWRAKHERA | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood or Diversion Channel for Community | Works for Flood Control and Protection | 1701003113/FP/22012034633982 — नाला निर्माण कार्य सीता जाटव के मकान से अमित्तलाल जाटव की ओर | Physically Completed | 1381609.34 | 0 | 2023-10-02 | 2026-08-21
MORENA / JINGNI | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1701003114/RC/22012034827522 — सीसी खरंजा एवं नाली निर्माण कार्य दिलीप के घर से रामप्रकाश के घर तक एवं शन्तू ठेकेदार के घर तक | Physically Completed | 51900 | 0 | 2025-02-18 | 2026-08-21
MORENA / BANMORKHURD | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701003118/LD/22012034955731 — Periferal Stone Bund Nirmaan Karya Badri singh ke khet se Ajad Ke khet ki or | Physically Completed | 995811.88 | 0 | 2025-07-03 | 2026-07-23
PAHADGARH / MANPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1701004057/IF/IAY/5726534 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152071815 | Physically Completed | 23490 | 0 | 2025-09-04 | 2026-08-16
PAHADGARH / KANHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1701004058/IF/IAY/4915540 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151767474 | Physically Completed | 23490 | 0 | 2025-10-25 | 2026-07-19
JOURA / BILGAONCHAUDHRI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1701005020/IF/IAY/4507559 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151774437 | Physically Completed | 23490 | 0 | 2025-02-13 | 2026-08-09
JOURA / SHAHADPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701005047/LD/22012034958935 — peripheral stone bund nirman karya shiv mandir part 2 kiratpur shahadpur | Physically Completed | 1487628.22 | 0 | 2026-02-13 | 2026-10-05
JOURA / SHAHADPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1701005047/WC/22012035294275 — JGSA डगवेल रिचार्ज पिट आंगनबाड़ी भवन के पास ग्राम शहदपुर | Physically Completed | 25899.46 | 0 | 2025-05-10 | 2026-10-05
JOURA / SHAHADPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1701005047/WC/22012035294280 — JGSA डगवेल रिचार्ज पिट आंगनबाड़ी भवन के पास ग्राम किरतपुर | Physically Completed | 25899.46 | 0 | 2025-05-07 | 2026-10-05
JOURA / MODHANISAMANT | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1701005071/IF/IAY/4924556 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106586473 | Physically Completed | 27000 | 0 | 2025-10-17 | 2026-10-01
JOURA / MODHANISAMANT | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1701005071/IF/IAY/5202395 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106585951 | Physically Completed | 23490 | 0 | 2025-08-08 | 2026-08-09
KAILARAS / JARENA MANGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1701006014/LD/22012034958262 — PERIPHERAL STON BAND NIRMAN KARY ROAD SE RPATE KI OUR ROAD SIDE | Physically Completed | 1473733.05 | 0 | 2026-02-06 | 2026-09-02
KAILARAS / JARENA MANGARH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1701006014/WC/22012034776859 — rapta nirman karya shanti dham k pass kishangarhi | Physically Completed | 1423806.55 | 0 | 2021-07-08 | 2026-09-02
KAILARAS / JARENA MANGARH | 2023-2024 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Construction of Stone Spur for Community / Construction of Stone Spur for Community | Construction of Spur | 1701006014/WC/22012035048458 — Rapata nirman karya Mahendra kushwah ke makan ke pass aam raste par jarena mangarh | Physically Completed | 1372570.17 | 0 | 2023-05-12 | 2026-09-02
KAILARAS / JARENA MANGARH | 2023-2024 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Construction of Stone Spur for Community / Construction of Stone Spur for Community | Construction of Spur | 1701006014/WC/22012035049796 — rapata nirman karya mahesh kushwah ke khet ke pass aam raste par jarena mangad | Physically Completed | 1361804.24 | 0 | 2023-05-12 | 2026-09-02
KAILARAS / JARENA MANGARH | 2023-2024 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Construction of Stone Spur for Community / Construction of Stone Spur for Community | Construction of Spur | 1701006014/WC/22012035102260 — Rapata Nirman karya Suresh kushwah ke khet ke pass aam raste par jarena | Physically Completed | 1470987.26 | 0 | 2023-09-12 | 2026-09-02
KAILARAS / ANTRI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1701006016/IF/IAY/5629707 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125564274 | Physically Completed | 23490 | 0 | 2026-05-16 | 2026-08-09
KAILARAS / DONGARPUR MANGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701006024/LD/22012034956015 — PERIPHERL BAND NIRMAN KARY BASTOLI ROAD KR RPTA SE NARUA KI OUR | Physically Completed | 1496110.64 | 0 | 2025-07-05 | 2026-09-02
KAILARAS / DONGARPUR MANGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701006024/LD/22012034956016 — PERIPHERL BAND NIRMAN KARY SHRIPTI KE KHET SE BASTOLI ROAD KI OUR | Physically Completed | 1416026.24 | 0 | 2025-07-05 | 2026-09-02
KAILARAS / DONGARPUR MANGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701006024/LD/22012034956018 — PERIPHERL BAND NIRMAN KARY NALE BALE RPTA SE KHUMAN KE PURA ROAD KI OUR | Physically Completed | 1496435.63 | 0 | 2025-07-05 | 2026-09-02
KAILARAS / DONGARPUR MANGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701006024/LD/22012034956019 — PERIPHERL BAND NIRMAN KARY RIJHONI MOD SE NALE KI OUR | Physically Completed | 1489313.21 | 0 | 2025-07-05 | 2026-09-02
KAILARAS / DONGARPUR MANGARH | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701006024/LD/22012034956061 — PERIPHERAL STON BUND NIRMAN KARY MURGA PHARM SE RAMDYAL KE KHET KI OUR | Physically Completed | 1422553.84 | 0 | 2026-04-02 | 2026-09-02
KAILARAS / TILONJARI | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Food grain storage / Construction of Food Grain Storage Building for Community | Constr of Food Grain storage | 1701006032/AV/22012034565995 — प्राथमि क़षि साख सह0 सं0 मार्या तिलोंजरी चबूतरा निर्माण कार्य 1 | Physically Completed | 804741.09 | 0 | 2021-05-15 | 2026-09-02
KAILARAS / TILONJARI | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Centre Building for Community | Constr of Aganwadi | 1701006032/AV/22012034660410 — Shanti dham gadipura tilonjari | Physically Completed | 334906.09 | 0 | 2024-12-12 | 2026-09-02
KAILARAS / TILONJARI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1701006032/IF/22012035376314 — Khet talav sajjan ke khet ke pass kaimara tilonjari | Physically Completed | 147621.16 | 0 | 2025-05-12 | 2026-09-02
KAILARAS / TILONJARI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1701006032/LD/22012034952515 — Periferal Stone bund nirman kary Ramsevak das school par tilonjari | Physically Completed | 1485689.26 | 0 | 2025-06-23 | 2026-09-02
KAILARAS / TILONJARI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701006032/LD/22012034956291 — Periferal bund nirman kary kaimara rod se Rajaram ke khet ki or tilonjari | Physically Completed | 1453328.04 | 0 | 2026-01-19 | 2026-09-02
KAILARAS / TILONJARI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701006032/LD/22012034956292 — Periferal bund nirman kary kaimara rod se nathhi sharma ke khet ki or tilonjari | Physically Completed | 1471741.28 | 0 | 2026-01-19 | 2026-09-02
KAILARAS / TILONJARI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701006032/LD/22012034956294 — Periferal bund nirman kary bachchu adivashi ke khet serod ki or tilonjari | Physically Completed | 1448807.38 | 0 | 2026-01-19 | 2026-09-02
KAILARAS / TILONJARI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701006032/LD/22012034956295 — Periferal bund nirman kary haluke adivashi ke khet se raghundan ke khet ki or tilonjari | Physically Completed | 1448807.38 | 0 | 2026-01-19 | 2026-09-02
KAILARAS / TILONJARI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701006032/LD/22012034957285 — Periferal bund nirman kary Naruaa se darshan dhakad ke khet ki or tilonjari | Physically Completed | 1487611.3 | 0 | 2026-01-19 | 2026-09-02
KAILARAS / TILONJARI | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701006032/WC/22012034575209 — RAPTA NIRMAN KARY KAIMRA ROAD KHOR ME | Physically Completed | 1023958.62 | 0 | 2021-12-11 | 2026-09-02
KAILARAS / PIPRONYA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Pebble peripheral Bund for Community / Construction of Pebble peripheral/farm/field Bund for Community | Construction of Bund | 1701006034/WC/22012034793789 — NAVIN TALAB NIRMAN KARY BEECH KI NARI PAR ARRAT (WATER SHEED) CTR | Physically Completed | 1494040.54 | 0 | 2021-07-15 | 2026-09-02
KAILARAS / BHILSAIYA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Fisheries | Construction of Fisheries Ponds for Community / Construction of Fishery Pond for Community | Construction of Tank | 1701006048/FR/22012034323741 — TALAB NIRMAN KARY MUNNA SHRIWASH KE KHET KE PAS | Physically Completed | 1462225.12 | 0 | 2025-01-28 | 2026-09-01
KAILARAS / BHILSAIYA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Fisheries | Construction of Fisheries Ponds for Community / Construction of Fishery Pond for Community | Construction of Tank | 1701006048/FR/22012034323742 — TALAB NIRMAN KARY MATADEEN SHRIWASH KE KHET KE PAS | Physically Completed | 1497281.85 | 0 | 2025-01-28 | 2026-09-01
KAILARAS / BHILSAIYA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Fisheries | Construction of Fisheries Ponds for Community / Construction of Fishery Pond for Community | Construction of Tank | 1701006048/FR/22012034323744 — TALAB NIRMAN KARY RAMSINGH KUSHWAH KE KHET KE PAS | Physically Completed | 1450727.93 | 0 | 2025-01-28 | 2026-09-01
KAILARAS / BHILSAIYA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Fisheries | Construction of Fisheries Ponds for Community / Construction of Fishery Pond for Community | Construction of Tank | 1701006048/FR/22012034323745 — TALAB NIRMAN KARY DURGA KUSHWAH KE KHET KE PAS | Physically Completed | 1328519.66 | 0 | 2025-01-28 | 2026-09-01
KAILARAS / BHILSAIYA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1701006048/WC/22012035173634 — MNREGA WATER SED EARTHEN BAND NIRMAN KARYA BUBU KE BEHAD ME BHILSAIYA | Physically Completed | 1494673.63 | 0 | 2024-03-15 | 2026-09-01
KAILARAS / BHILSAIYA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1701006048/WC/22012035227196 — Talab nirman karya bhogiram ke behad ke pass | Physically Completed | 2497515.76 | 0 | 2025-01-08 | 2026-09-01
KAILARAS / BHILSAIYA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1701006048/WC/22012035227197 — Talab nirman karya roshan jatav ke behad ke pass | Physically Completed | 2466762.88 | 0 | 2025-01-08 | 2026-09-01
KAILARAS / BHILSAIYA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1701006048/WC/22012035227199 — Talab nirman karya soneram ke behad ke pass | Physically Completed | 2453990.54 | 0 | 2025-01-08 | 2026-09-01
KAILARAS / PANIHARI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1701006056/IF/IAY/4900039 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151971780 | Physically Completed | 23490 | 0 | 2025-06-24 | 2026-08-02
KAILARAS / BEHARARAJAGIR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1701006059/IF/IAY/4898648 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152066560 | Physically Completed | 23490 | 0 | 2024-10-18 | 2026-07-05
KAILARAS / BEHARARAJAGIR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1701006059/IF/IAY/4898650 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152066563 | Physically Completed | 23490 | 0 | 2024-10-18 | 2026-08-16
KAILARAS / BEHARARAJAGIR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1701006059/IF/IAY/5730610 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152066511 | Physically Completed | 23490 | 0 | 2024-10-18 | 2026-08-16
KAILARAS / KHIRI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1701006061/IF/IAY/5610269 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151782758 | Physically Completed | 27000 | 0 | 2025-06-06 | 2026-09-13
SABALGARH / JAWAHARGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1701007006/IF/IAY/4722200 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145498961 | Physically Completed | 23490 | 0 | 2025-03-15 | 2026-08-09
SABALGARH / JAWAHARGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1701007006/IF/IAY/4722564 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144420620 | Physically Completed | 27000 | 0 | 2025-01-21 | 2026-10-11
SABALGARH / JAWAHARGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1701007006/IF/IAY/4894161 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151951175 | Physically Completed | 23490 | 0 | 2025-03-06 | 2026-08-02
SABALGARH / JAWAHARGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1701007006/IF/IAY/4894169 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151951212 | Physically Completed | 23490 | 1800 | 2025-03-06 | 2026-08-02
SABALGARH / BAMSOLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1701007050/IF/IAY/5303428 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148225386 | Physically Completed | 27000 | 0 | 2025-08-28 | 2026-10-11
SABALGARH / BAMSOLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1701007050/IF/IAY/5313977 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148266270 | Physically Completed | 27000 | 0 | 2025-08-28 | 2026-10-11
SABALGARH / BAMSOLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1701007050/IF/IAY/5324926 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148216485 | Physically Completed | 23490 | 0 | 2025-08-28 | 2026-08-09
SABALGARH / PACHER | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1701007061/IF/IAY/4528989 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146606671 | Physically Completed | 23490 | 0 | 2025-02-10 | 2026-08-02
SABALGARH / PACHER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1701007061/IF/IAY/5492645 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147277410 | Physically Completed | 23490 | 1500 | 2025-12-01 | 2026-08-02