## Work List
Exported on: 2026-10-11 21:57:54
Filters applied:
Data source: MGNREGA
District: BHIND
Block: All
Panchayat: GOARKHURD
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
ATER | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play field for Community | Construction of Play field | 1702001024/AV/22012034636681 — Khel Maidhan Nirman-Govt. Primary/Middle School, Goarkhurd | Closed | 0 | 0 | 2023-04-14
ATER | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play field for Community | Construction of Play field | 1702001024/AV/22012034652952 — Khel Maidhan Nirman Karya- Goarkhurd | Closed | 0 | 0 | 2024-01-26
ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | AWC / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1702001024/AV/4122 — Aanganbadi Bhaban Goarkhurd | Completed | 330000 | 329955 | 2015-12-07 | 2017-10-15
ATER | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Sericulture- in Fields-Community / Block Plantation of Sericulture Trees in Fields for Community | Plantation | 1702001024/DP/22012034596945 — Vraksharopan Karya amrit vatika govt. Middle school , Goarkhurd | Ongoing | 55847.4 | 1326 | 2023-08-19
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702001024/FP/22012034369920 — RCC Nali Nirman Babu Singh Ke Than Se Jatav Mohalla Ke Kunya Ki Or, Sonpura, Goarkhurd | Completed | 13000 | 12738 | 2021-06-10 | 2021-08-14
ATER | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1702001024/FP/22012034630430 — kool nirman - mukhya nahar se kishori lal patiram ke khet ke or goarkhurd | Ongoing | 173606.64 | 110976 | 2022-11-06
ATER | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1702001024/FP/22012034630431 — kool nirman - mukhya nahar se bablu ke kua ke or goarkhurd | Completed | 216258.3 | 142800 | 2022-11-06 | 2025-06-08
ATER | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of drain for coastal protection for Comm. / Construction of Storm Water drain for coastal protection for Community | Works for Flood Control and Protection | 1702001024/FP/22012034630432 — Nala nirman - mata mandir ke pichhe se khar ke or goarkhurd | Ongoing | 247558.8 | 190927 | 2022-11-10
ATER | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of drain for coastal protection for Comm. / Construction of Storm Water drain for coastal protection for Community | Works for Flood Control and Protection | 1702001024/FP/22012034630433 — Nala nirman - mata mandir ke pass se pachera ke or goarkurd | Closed | 0 | 0 | 2022-08-16
ATER | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of drain for coastal protection for Comm. / Construction of Storm Water drain for coastal protection for Community | Works for Flood Control and Protection | 1702001024/FP/22012034630434 — Nala nirman - mata mandir ke pass didona bale sahar ke or | Closed | 0 | 0 | 2022-08-16
ATER | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of drain for coastal protection for Comm. / Construction of Storm Water drain for coastal protection for Community | Works for Flood Control and Protection | 1702001024/FP/22012034630435 — Nala nirman - govt midil school goarkhurd | Closed | 0 | 0 | 2022-08-16
ATER | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of drain for coastal protection for Comm. / Construction of Storm Water drain for coastal protection for Community | Works for Flood Control and Protection | 1702001024/FP/22012034632629 — kachha nala nirman -angad singh jatav ek khet se sattar khan khan ke khet ke or | Completed | 532474.5 | 320229 | 2023-05-13 | 2025-06-08
ATER | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of drain for coastal protection for Comm. / Construction of Storm Water drain for coastal protection for Community | Works for Flood Control and Protection | 1702001024/FP/22012034632630 — kool nirman - mukhya sadak se vyash ke jagga | Completed | 169341.6 | 135694 | 2023-07-08 | 2025-06-08
ATER | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of drain for coastal protection for Comm. / Construction of Storm Water drain for coastal protection for Community | Works for Flood Control and Protection | 1702001024/FP/22012034632631 — kachha nala nirman Prahlad kushwah ke khet se hakim singh ke khet ke or | Completed | 797211.75 | 571506 | 2023-05-13 | 2025-06-08
ATER | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of drain for coastal protection for Comm. / Construction of Storm Water drain for coastal protection for Community | Works for Flood Control and Protection | 1702001024/FP/22012034632632 — kachha nala nirman Prahlad kushwah ke khet se beniram ke khet ke or | Completed | 797211.75 | 529737 | 2023-07-08 | 2025-06-08
ATER | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702001024/FP/22012034633323 — Kool Nirman Mukhya Sadak Mishranpura ke pass se Vyas Ki Jagga Ki Or, Goarkhurd | Closed | 0 | 0 | 2023-04-14
ATER | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of drain for coastal protection for Comm. / Construction of Storm Water drain for coastal protection for Community | Works for Flood Control and Protection | 1702001024/FP/22012034633325 — Kaccha Nala Nirman Shri Pahlad Kushwah Ke Khet Se Beniram Ke Khet Ki Or, Goarkhurd | Closed | 0 | 0 | 2023-04-14
ATER | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of drain for coastal protection for Comm. / Construction of Storm Water drain for coastal protection for Community | Works for Flood Control and Protection | 1702001024/FP/22012034633326 — Kaccha Nala Nirman Shri Mevati baba Than Ke Pass, Mata Mandir Ki or, Goarkhurd | Closed | 0 | 0 | 2023-04-14
ATER | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702001024/FP/22012034634862 — Kool Nirman Bambiya Se Sher Bahadur Singh Ke Khet Ki Or, Sonpura | Completed | 133972.8 | 79339 | 2023-10-11 | 2025-06-08
ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001024/IF/22012034300124 — Cons Of Compost Pit- Vashudev/ Mungaram | Completed | 12000 | 11042 | 2016-09-26 | 2017-10-20
ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001024/IF/22012034300126 — Cons .of Compost Pit- Gyan Singh/Bhogiram | Completed | 12000 | 11042 | 2016-09-26 | 2017-10-20
ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001024/IF/22012034300127 — Cons Of Compost Pit- Ram prakash/ Baijnath | Completed | 12000 | 11042 | 2016-09-26 | 2017-10-20
ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001024/IF/22012034300129 — Cons. Of Compost Pit- Tunderam/ Kriparam | Completed | 12000 | 10374 | 2016-09-26 | 2017-10-20
ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001024/IF/22012034300130 — Cons Of Compost Pit- Khem Singh/ Bhogiram | Completed | 12000 | 11042 | 2016-09-26 | 2017-10-20
ATER | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702001024/IF/22012034352624 — वृक्षारोपण कार्य मुख्यमंत्री सड़क पर सोनपुरा | Completed | 335000 | 7128 | 2017-06-19 | 2020-12-21
ATER | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702001024/IF/22012034352905 — वृक्षारोपण आगनबाडी भवन एवं प्राइमरी मिडिल शासकीय स्कूल बाग़ का पुरा गोहर्खुर्द | Completed | 335000 | 43428 | 2017-06-19 | 2020-12-21
ATER | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702001024/IF/22012034368257 — vriksharopan main raod pithanpura road se sc basti ki sonpura | Completed | 335000 | 9192 | 2017-07-30 | 2020-12-21
ATER | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702001024/IF/22012034368341 — Vriksharopan PM Sadak se sc basti ki or goharkhurd | Completed | 335000 | 11256 | 2017-07-15 | 2020-12-21
ATER | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001024/IF/22012034490125 — cattle shed | Deleted | 0 | 0 | 2019-06-28
ATER | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001024/IF/22012034490148 — cattle shed siyaram/ ramswaroop | Deleted | 0 | 0 | 2019-06-29
ATER | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001024/IF/22012034490149 — cattle shed krashanveer singh/ramsewak | Deleted | 0 | 0 | 2019-06-29
ATER | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001024/IF/22012034490151 — cattle shed mahaveer singh / shivchran singh | Deleted | 0 | 0 | 2019-06-29
ATER | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001024/IF/22012034579762 — Khet Talab Nirman-Sultan Singh/Shri narayan, Sonpura | Completed | 332572.21 | 258780 | 2020-07-29 | 2021-08-14
ATER | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001024/IF/22012034579763 — Khet Talab-Pan Singh/Babu Singh. Sonpura | Completed | 332572.21 | 264100 | 2020-07-21 | 2021-08-14
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001024/IF/22012034881518 — Nandep Nirman Karya Pan Singh/Babu Singh, Sonpura | Closed | 0 | 0 | 2021-08-15
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001024/IF/22012034881520 — Nandep Nirman Karya- Ater Singh/Babu Singh, Sonpura | Closed | 0 | 0 | 2021-08-15
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001024/IF/22012034881522 — Nandep Nirman Karya- Dev Singh/ Mahadev, Sonpura | Closed | 0 | 0 | 2021-08-15
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001024/IF/22012034881525 — Nandep Nimran Karya- Omkar /Uday Singh, Sonpura | Closed | 0 | 0 | 2021-08-15
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001024/IF/22012034881526 — Nandep Nirman Karya- Raghuraj/Jhamman, Sonpura | Closed | 0 | 0 | 2021-08-15
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001024/IF/22012034881530 — Nandep Nirman karya Hari Singh/Kriparam, Sonpura | Closed | 0 | 0 | 2021-08-15
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001024/IF/22012034881532 — Nandep Nirman Karya-Vrindavan/Chotelal, Sonpura | Closed | 0 | 0 | 2021-08-15
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001024/IF/22012034881533 — Nandep Nirman Karya-Ranveer/Mangal Singh, Sonpura | Closed | 0 | 0 | 2021-08-15
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001024/IF/22012034881534 — Nandep Nirman Karya- Kiran Devi/Munna Singh, Sonpura | Closed | 0 | 0 | 2021-08-15
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001024/IF/22012034881536 — Nandep Nirman Karya- Megh Singh/Jaswant Singh, Sonpura | Closed | 0 | 0 | 2021-08-15
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001024/IF/22012034881537 — Nandep Nirman Karya- Bahadur Singh/Chote Singh, Sonpura | Closed | 0 | 0 | 2021-08-15
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001024/IF/22012034881541 — Nandep Nirman Karya- Sujan Singh/Sabdhan Singh, Sonpura | Closed | 0 | 0 | 2021-08-15
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001024/IF/22012034881544 — Nandep Nirman Karya- Tejendra Singh/Phool Singh, Sonpura | Closed | 0 | 0 | 2021-08-15
ATER | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001024/IF/22012035144417 — Khet Talab Nirman Angad Singh Jatav Ke Khet Par, Goarkhurd | Closed | 0 | 0 | 2023-08-15
ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001024/IF/22012035492407 — khet talab nekram ke khet par goarkhurd | Physically Completed | 147621.16 | 109620 | 2025-05-12 | 2026-04-17
ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001024/IF/22012035492417 — khet talab ramanand ke khet par | Ongoing | 147621.16 | 10962 | 2025-05-12
ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001024/IF/22012035555968 — khet talab surendra ke khet par | Deleted | 0 | 0 | 2025-04-14
ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702001024/IF/22012035638660 — Ek bagiya maa ke name hitgirahi usha sharma | Deleted | 0 | 0 | 2025-08-15
ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702001024/IF/22012035638880 — maa ke bagiya Usha sharma | Ongoing | 257341.57 | 0 | 2025-11-14
ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702001024/IF/22012035653524 — maa ke bagiya usha wo kishanveer | Deleted | 0 | 0 | 2025-04-14
ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702001024/IF/22012035654732 — maa ke bagiya usha wo kishanveer | Ongoing | 266578.64 | 28188 | 2026-03-23
ATER | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001024/IF/9993694045 — Cattle Shed- Ramji lal/ Baba ji | Completed | 90000 | 89509 | 2016-08-22 | 2016-09-20
ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001024/IF/9993694046 — Cattle Shed-Hari Singh/ Kriparam | Deleted | 90000 | 0 | 2015-12-07
ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001024/IF/9993694047 — Cattle Shed- Tunderam/ Kriparam | Deleted | 90000 | 0 | 2015-12-07
ATER | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001024/IF/9993694049 — Cattle Shed- Ramveer/ ramgopal | Completed | 90000 | 86670 | 2016-06-27 | 2016-08-22
ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001024/IF/9993694053 — Cattle Shed-ramprakash/ Baijnath | Deleted | 90000 | 0 | 2015-12-07
ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001024/IF/9993694055 — Cattle Shed- Rajesh Kumar/ Vashudev | Deleted | 90000 | 0 | 2015-12-07
ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001024/IF/9993694057 — Cattle Shed-Ram Dhakeli/ Rameshwar | Deleted | 90000 | 0 | 2015-12-07
ATER | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001024/IF/9993694059 — Cattle Shed- Kiledar/ Latoori Lal | Deleted | 90000 | 0 | 2016-06-27
ATER | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001024/IF/9993694070 — Cattle Shed- Khem Singh/ Bhogiram | Completed | 90000 | 89509 | 2016-06-27 | 2016-08-25
ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001024/IF/9993694071 — Cattle Shed- Latoori Lal/ Bedari Prasad | Deleted | 90000 | 0 | 2015-12-07
ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001024/IF/9993694072 — Cattle Shed- Gyan Singh/ Bhogiram | Deleted | 90000 | 0 | 2015-12-07
ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001024/IF/9993694073 — Cattle Shed-Ram Niwas / latoori Lal | Deleted | 90000 | 0 | 2015-12-07
ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001024/IF/9993694074 — Cattle Shed- Sattar Khan/ Sabdal Khan | Deleted | 90000 | 0 | 2015-12-07
ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001024/IF/9993696242 — Cattle Shed- Urmila/ Ranjeet | Deleted | 90000 | 0 | 2015-10-02
ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001024/IF/9993696247 — Cattle Shed- Jabaan Singh/ Sabdhan Singh | Deleted | 90000 | 0 | 2015-10-02
ATER | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001024/IF/9993696249 — Cattle Shed- Atar Singh/ Banshi Singh | Completed | 90000 | 89509 | 2016-06-27 | 2016-09-10
ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001024/IF/9993696251 — Cattle Shed- Vrindavan/ Chotelal | Deleted | 90000 | 0 | 2015-10-02
ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001024/IF/9993696254 — Cattle Shed- Kalyan Singh/ Babu Singh | Deleted | 90000 | 0 | 2015-10-02
ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001024/IF/9993696255 — Cattle Shed- Pan Singh/ Babu Singh | Deleted | 90000 | 0 | 2015-10-02
ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001024/IF/9993696257 — Cattle Shed- Mithlesh/ Hari Singh | Deleted | 90000 | 0 | 2015-12-14
ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001024/IF/9993696317 — Cattle Shed- Mukhtyaar Singh/ Chote Singh | Deleted | 90000 | 0 | 2015-10-02
ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001024/IF/9993696318 — Cattle Shed- Kamlesh/ Ganga Singh | Deleted | 90000 | 0 | 2015-10-02
ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001024/IF/9993696319 — Cattle Shed- Pooran Singh/ Jhamman Singh | Deleted | 90000 | 0 | 2015-11-05
ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001024/IF/9993696326 — Cattle Shed- Ajmer Singh/ Gyan Singh | Deleted | 90000 | 0 | 2015-10-02
ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001024/IF/9993696327 — Cattle Shed- Ramjilal/ Asharam | Deleted | 90000 | 0 | 2015-10-02
ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001024/IF/9993696329 — Cattle Shed- Rakesh/ Ramlakhan | Deleted | 90000 | 0 | 2015-10-02
ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001024/IF/9993696330 — Cattle Shed- Ram Swaroop / Shri Karan Lal | Deleted | 90000 | 0 | 2015-10-02
ATER | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702001024/IF/9993733821 — farom bunding | Deleted | 0 | 0 | 2016-04-02
ATER | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702001024/IF/9993733825 — farom bunding gayanavd | Deleted | 0 | 0 | 2016-04-02
ATER | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001024/IF/9993733826 — cattle shed mahesh singh | Deleted | 0 | 0 | 2016-04-02
ATER | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001024/IF/9993733830 — cattle shed kekidar | Deleted | 0 | 0 | 2016-04-02
ATER | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001024/IF/9993733834 — cattle shed ramnivas | Deleted | 0 | 0 | 2016-04-02
ATER | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001024/IF/9993733837 — cattle shed ramnivas | Deleted | 0 | 0 | 2016-04-02
ATER | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001024/IF/9993733907 — cattle shad dayaram agnu | Deleted | 0 | 0 | 2016-04-02
ATER | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001024/IF/9993733909 — cattle shad brajesh ajnu | Deleted | 0 | 0 | 2016-04-02
ATER | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001024/IF/9993733910 — cattle shad ramhet bhiram | Deleted | 0 | 0 | 2016-04-02
ATER | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001024/IF/9993733911 — cattle shad ramshvrup | Deleted | 0 | 0 | 2016-04-02
ATER | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702001024/IF/9993733913 — Const. of Farm buinding jeeram | Deleted | 0 | 0 | 2016-04-02
ATER | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702001024/IF/9993733914 — Const. of Farm buinding brajsh | Deleted | 0 | 0 | 2016-04-02
ATER | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702001024/IF/9993733915 — Const. of Farm buinding bhavanshing | Deleted | 0 | 0 | 2016-04-02
ATER | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702001024/IF/9993733916 — Const. of Farm buinding kiledar | Deleted | 0 | 0 | 2016-04-02
ATER | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702001024/IF/9993733917 — Const. of Farm buinding ramnivas | Deleted | 0 | 0 | 2016-04-02
ATER | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702001024/IF/9993733918 — Const. of Farm buinding angad | Deleted | 0 | 0 | 2016-04-02
ATER | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702001024/IF/9993733919 — Const. of Farm buinding manju | Deleted | 0 | 0 | 2016-04-02
ATER | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702001024/IF/9993733920 — Const. of Farm buinding ramnath | Deleted | 0 | 0 | 2016-04-02
ATER | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702001024/IF/9993733921 — Const. of Farm buinding mulchand | Deleted | 0 | 0 | 2016-04-02
ATER | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702001024/IF/9993733922 — Const. of Farm buinding nekram | Deleted | 0 | 0 | 2016-04-02
ATER | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702001024/IF/9993733923 — Const. of Farm buinding ramswrup | Deleted | 0 | 0 | 2016-04-02
ATER | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702001024/IF/9993733924 — Const. of Farm buinding ramvarn | Deleted | 0 | 0 | 2016-04-02
ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001024/IF/9993734429 — cattle shed heri shing | Deleted | 0 | 0 | 2016-01-27
ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001024/IF/9993734433 — cattle shed khime shing | Deleted | 0 | 0 | 2016-01-27
ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001024/IF/9993734436 — cattle shed yanshing | Deleted | 0 | 0 | 2016-01-27
ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001024/IF/9993734439 — cattle shed lturilal | Deleted | 0 | 0 | 2016-01-27
ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001024/IF/9993734441 — cattle shed tundayram | Deleted | 0 | 0 | 2016-01-27
ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001024/IF/9993734443 — cattle shed rampraksh | Deleted | 0 | 0 | 2016-01-27
ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001024/IF/9993734445 — cattle shed rajsh kumar | Deleted | 0 | 0 | 2016-01-27
ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001024/IF/9993734447 — cattle shed vindavan | Deleted | 0 | 0 | 2016-01-27
ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001024/IF/9993734449 — cattle shed panshing | Deleted | 0 | 0 | 2016-01-27
ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001024/IF/9993734451 — cattle shed purnshing | Deleted | 0 | 0 | 2016-01-27
ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001024/IF/9993734452 — cattle shed ramver | Deleted | 0 | 0 | 2016-01-27
ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001024/IF/9993734454 — cattle shed ramjilal | Deleted | 0 | 0 | 2016-01-27
ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001024/IF/9993734455 — cattle shed atrshing | Deleted | 0 | 0 | 2016-01-27
ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001024/IF/9993734456 — cattle shed kamlish | Deleted | 0 | 0 | 2016-01-27
ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001024/IF/9993734457 — cattle shed metlish | Deleted | 0 | 0 | 2016-01-27
ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001024/IF/9993734458 — cattle shed kalyanshing | Deleted | 0 | 0 | 2016-01-27
ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001024/IF/9993734459 — cattle shed ajmirshing | Deleted | 0 | 0 | 2016-01-27
ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001024/IF/9993734460 — cattle shed yashpalshing | Deleted | 0 | 0 | 2016-01-27
ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001024/IF/9993734462 — cattle shed jyanshing | Deleted | 0 | 0 | 2016-01-27
ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001024/IF/9993734464 — cattle shed mukhlyarshing | Deleted | 0 | 0 | 2016-01-27
ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001024/IF/9993734465 — cattle shed diveshing | Deleted | 0 | 0 | 2016-01-27
ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001024/IF/9993734466 — cattle shed urmela | Deleted | 0 | 0 | 2016-01-27
ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001024/IF/9993734467 — cattle shed ramdkile | Deleted | 0 | 0 | 2016-01-27
ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001024/IF/9993734469 — cattle shed klyanshing | Deleted | 0 | 0 | 2016-01-27
ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001024/IF/9993734470 — cattle shed lakhnshing | Deleted | 0 | 0 | 2016-01-27
ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001024/IF/9993734471 — cattle shed hjarelal | Deleted | 0 | 0 | 2016-01-27
ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001024/IF/9993734472 — cattle shed ramkrn | Deleted | 0 | 0 | 2016-01-27
ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001024/IF/9993734473 — cattle shed sema dive | Deleted | 0 | 0 | 2016-01-27
ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001024/IF/9993734474 — cattle shed sema umish | Deleted | 0 | 0 | 2016-01-27
ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001024/IF/9993736198 — Cattle shed Ramsiya | Deleted | 0 | 0 | 2016-01-26
ATER | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001024/IF/9993749514 — Cattle Shed- Mahesh / Harigyan | Completed | 90000 | 89509 | 2016-06-27 | 2016-08-25
ATER | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001024/IF/9993749518 — Cattle Shed- Hari Singh/ Kripa Ram | Completed | 90000 | 84564 | 2016-06-27 | 2016-08-10
ATER | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001024/IF/IAY/1589243 — Construction of IAY House -IAY REG. NO. MP1080887 | Completed | 15660 | 13572 | 2018-05-18 | 2018-09-12
ATER | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001024/IF/IAY/1872101 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5190965 | Completed | 15660 | 14712 | 2018-10-21 | 2020-06-02
ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001024/IF/IAY/192845 — Construction of IAY House -IAY REG. NO. MP-02-001-024-002/104 | Approved | 23490 | 0 | 2016-02-19
ATER | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001024/IF/IAY/1930144 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4986357 | Completed | 15660 | 15660 | 2018-10-29 | 2018-12-04
ATER | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001024/IF/IAY/326294 — Construction of IAY House -IAY REG. NO. MP1082685 | Completed | 15030 | 15210 | 2017-02-09 | 2017-10-20
ATER | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001024/IF/IAY/326906 — Construction of IAY House -IAY REG. NO. MP1084247 | Completed | 15030 | 15210 | 2017-02-09 | 2017-11-10
ATER | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001024/IF/IAY/326910 — Construction of IAY House -IAY REG. NO. MP1084260 | Completed | 15030 | 15180 | 2017-02-09 | 2017-10-20
ATER | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001024/IF/IAY/4066742 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113960664 | Physically Completed | 18360 | 18292 | 2022-12-20 | 2024-11-21
ATER | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001024/IF/IAY/4073454 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115865192 | Physically Completed | 18360 | 18173 | 2022-11-10 | 2024-11-21
ATER | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001024/IF/IAY/4283688 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113950887 | Physically Completed | 18360 | 17986 | 2022-12-20 | 2024-11-21
ATER | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001024/IF/IAY/4285693 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106975574 | Physically Completed | 18360 | 18190 | 2022-11-10 | 2024-11-21
ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001024/IF/IAY/4743738 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113952915 | Ongoing | 23490 | 23490 | 2025-04-19
ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001024/IF/IAY/4750681 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116872084 | Ongoing | 23490 | 23229 | 2025-04-19
ATER | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001024/IF/IAY/523571 — Construction of IAY House -IAY REG. NO. MP2631434 | Completed | 15030 | 23496 | 2017-03-16 | 2017-10-20
ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001024/IF/IAY/5284063 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113973917 | Ongoing | 23490 | 12528 | 2025-05-08
ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001024/IF/IAY/5320350 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113979021 | Ongoing | 23490 | 3132 | 2025-05-08
ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001024/IF/IAY/5562003 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113962912 | Ongoing | 23490 | 17226 | 2025-09-09
ATER | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001024/IF/IAY/6057831 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113881041 | Ongoing | 23490 | 21924 | 2026-05-10
ATER | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001024/IF/IAY/6219433 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113865078 | Ongoing | 23490 | 23490 | 2026-05-12
ATER | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001024/IF/IAY/6219474 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113862995 | Ongoing | 23490 | 3132 | 2026-05-05
ATER | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001024/IF/IAY/6219503 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116872041 | Approved | 23490 | 0 | 2025-03-13
ATER | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001024/IF/IAY/6219680 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113875801 | Ongoing | 23490 | 23490 | 2026-05-10
ATER | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001024/IF/IAY/6219721 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113875753 | Ongoing | 23490 | 21924 | 2026-05-10
ATER | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001024/IF/IAY/683461 — Construction of IAY House -IAY REG. NO. MP1046698 | Completed | 15030 | 14448 | 2017-06-19 | 2017-11-10
ATER | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001024/IF/IAY/683464 — Construction of IAY House -IAY REG. NO. MP1084252 | Completed | 15030 | 15480 | 2017-06-19 | 2017-10-20
ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1702001024/LD/22012034292179 — Shanti Dham- gram sonpura | Completed | 438000 | 332325 | 2016-09-26 | 2017-11-15
ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1702001024/LD/22012034292183 — Shanti Dham- Mishran ka pura | Completed | 273000 | 240213 | 2016-09-26 | 2017-11-15
ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1702001024/LD/22012034309547 — Shanti Dham- Goharkhurd | Completed | 245000 | 244365.78 | 2017-11-01 | 2018-02-20
ATER | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Development of chaur Land for Community | Land Development | 1702001024/LD/22012034507028 — mitti bharab karya samudhuak bhawan ke prangad sonpura | Deleted | 0 | 0 | 2020-01-26
ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Other Works | Maintenance of rural public assets / Repair and Maintenance of Gram Panchayat/Panchayat Bhavan Building for Community | Repair & Maint of Community infrastructure | 1702001024/OP/9425890493 — santi dham vikash sonpura | Deleted | 0 | 0 | 2016-01-26
ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1702001024/OP/9425890730 — Shanti dham Vikas Misharn ka pura | Deleted | 273000 | 0 | 2016-08-15
ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Other Works | Maintenance of rural public assets / Repair and Maintenance of Gram Panchayat/Panchayat Bhavan Building for Community | Repair & Maint of Community infrastructure | 1702001024/OP/9425890731 — Shanti dham Vikas Sonpura | Deleted | 438000 | 0 | 2016-08-15
ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1702001024/PG/22012034304327 — Play Ground- Goharkhurd | Deleted | 186000 | 0 | 2017-01-01
ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1702001024/PG/22012034304328 — Play Ground- Sonpura | Deleted | 186000 | 0 | 2017-04-11
ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001024/RC/22012034210330 — C.C.road p.m. Sadak kuya se shankar ji mandir ki o | Completed | 279000 | 278808 | 2014-03-03 | 2014-06-20
ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001024/RC/22012034210744 — C.C.Road Primary Shala bhawan Patiram ka pura se | Completed | 156000 | 151692 | 2014-03-03 | 2014-06-20
ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001024/RC/22012034210757 — C.C.Road Bhaiya sharma ke makan se Habaldar ka pur | Completed | 272000 | 271416 | 2014-03-03 | 2014-06-20
ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001024/RC/22012034210796 — C.C.Road P.M. Road posar ka pura se surendra singh | Completed | 156000 | 22776 | 2014-03-03 | 2016-07-30
ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001024/RC/22012034282519 — C.C.Road Janak Singh Ke Makan Se Hajoori Singh Ke Makan Ki or Avam Tillu ke ghar se hari singh | Completed | 245000 | 243008 | 2015-08-03 | 2015-12-15
ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702001024/RC/22012034291395 — Pahuch Margh Nirman Gormi Sunarpura Road Se Jatav Mohalla Ki Or | Completed | 1495000 | 626061 | 2015-12-07 | 2016-09-30
ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001024/RC/22012034310064 — CC ROAD | Deleted | 0 | 0 | 2016-04-01
ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001024/RC/22012034311797 — cc road Ramprakash house to Ramkumar house | Deleted | 0 | 0 | 2016-01-26
ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001024/RC/22012034311798 — cc road Ramdas house to Machalsingh house | Deleted | 0 | 0 | 2016-01-26
ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702001024/RC/22012034311799 — App. road Jabasa-Sunarpura road to Basudev house | Deleted | 0 | 0 | 2016-01-26
ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001024/RC/22012034312809 — C.C.Road Mata mandir Se Devi Singh Ke Makan Ki Or Avam Brindavan Ke Makan Se Latoori Ke Makan Ki or | Completed | 161000 | 159724 | 2016-05-16 | 2016-08-30
ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001024/RC/22012034319518 — CC road patiram ka pura | Completed | 221000 | 220866 | 2017-01-16 | 2017-10-15
ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001024/RC/22012034320277 — CC road CHHote singh ke makan se harijan basti | Completed | 150662 | 145343 | 2017-02-01 | 2017-10-15
ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001024/RC/22012034344631 — सी.सी. रोड मुख्यमंत्री रोड से पण सिंह के माकन की और सोनपुरा | Completed | 20063 | 20640 | 2017-07-17 | 2017-11-10
ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001024/RC/22012034344633 — सी.सी.रोड रणवीर के माकन से रामसिया के माकन की और सोनपुरा | Completed | 108338 | 107156 | 2017-07-17 | 2017-11-10
ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001024/RC/22012034345463 — सी.सी.रोड राम प्रकाश के माकन से रामकुमार के मकान की और गोहरखुर्द | Completed | 147750 | 147576 | 2017-07-24 | 2017-11-10
ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001024/RC/22012034350102 — सी.सी.रोड निर्माण शंकरजी के मंदिर से अशोक के मकान की ओर | Completed | 58125 | 58136 | 2017-08-21 | 2017-11-25
ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001024/RC/22012034373240 — cc road | Deleted | 0 | 0 | 2018-01-26
ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001024/RC/22012034381925 — cc road | Closed | 0 | 0 | 2017-10-02
ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001024/RC/22012034382444 — cc road | Closed | 0 | 0 | 2017-10-02
ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001024/RC/22012034385587 — C.C. Nali Nirman Mahesh Ke Makan Se Mool Chand Ke Makan Ki Or Goharkhurd | Completed | 20625 | 20574 | 2018-03-05 | 2019-12-16
ATER | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001024/RC/22012034433742 — सी सी ( मैन रोड से शा0 मा0 विधालय की ओर & मुमताज के मकान की ओर गोअर खुर्द ) | Completed | 69750 | 69696 | 2019-05-18 | 2020-06-02
ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001024/RC/22012034433743 — सी सी रोड ( विधासागर के मकान से शा0 प्रा0 वि0 की ओर मिश्रन का पुरा ) | Completed | 46500 | 44004 | 2019-03-07 | 2020-04-02
ATER | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001024/RC/22012034433744 — सी सी रोड ( कुशवाह थोक से राहुल मिश्रा के मकान की ओर गोअरखुर्द ) | Completed | 70600 | 71808 | 2019-06-01 | 2019-12-16
ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001024/RC/22012034442371 — cc road | Closed | 0 | 0 | 2019-01-26
ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001024/RC/22012034448094 — सी सी रोड ( सबदल खान के मकान से कुशवाह थोक की ओर गोअरखुर्द ) | Completed | 61200 | 58848 | 2019-03-10 | 2020-04-02
ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001024/RC/22012034449965 — सी सी रोड ( राम सेवक राठौर के मकान से शा0 प्रा0 वि0 की ओर ) | Completed | 40800 | 32992 | 2019-03-10 | 2020-04-02
ATER | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001024/RC/22012034470872 — c c road ( moolchandra ke makan se bhujariya ke tal ke or goarkhurd ) | Completed | 84750 | 83776 | 2020-02-03 | 2020-06-02
ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001024/RC/22012034480410 — सी सी रोड ( लाखन सिंह के मकान से राम ढ्केली के मकान की ओर सोनपुरा ) | Closed | 27900 | 0 | 2018-12-30
ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001024/RC/22012034480414 — सी सी रोड ( महेश के मकान से हजारी के मकान & श्री क्रष्ण के मकान की ओर ) | Deleted | 30600 | 0 | 2018-12-30
ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001024/RC/22012034507885 — c c road ( ram ji lal nat ke makan se basudev kushwah ke makan ke or sonpura ) | Deleted | 26775 | 0 | 2018-04-14
ATER | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001024/RC/22012034514721 — cc road | Closed | 0 | 0 | 2019-10-02
ATER | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001024/RC/22012034515983 — c c road ( ram ji lal nat ke makan se basudev kushwah ke makan ke or sonpura ) | Completed | 26775 | 27456 | 2020-02-19 | 2020-04-02
ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001024/RC/22012034524267 — c c road - pradhanmantri sadak se amar singh ke makan ke or sonpura | Completed | 25500 | 20520 | 2020-06-11 | 2020-10-18
ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702001024/RC/22012034528114 — Sudur Samprak Sadak Mukhya Marg Govt.Primary School Mishran Ka Pura Ki Or, | Completed | 785860.83 | 551333 | 2020-07-14 | 2022-10-29
ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001024/RC/22012034534681 — c c road ( pradhan mantri road se nathuram mishra ke makan ke or ) | Completed | 110175 | 67830 | 2020-12-11 | 2021-02-25
ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001024/RC/22012034538430 — c c road ( pooran ke darwaje se atar singh ke darwaje ke or ) | Completed | 76500 | 72960 | 2020-09-18 | 2021-02-25
ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001024/RC/22012034539409 — c c road ( ramsiya ke darwaje se sultan singh ke darwaje ke or ) | Ongoing | 19125 | 14928 | 2021-02-12
ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001024/RC/22012034558051 — c c road ( mata mandir se phool singh gurjar ke baithak ke or ) | Completed | 93000 | 92580 | 2021-02-12 | 2021-05-22
ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001024/RC/22012034558065 — C.C.Road Nirman Mata Ke mandir Se Phool Singh Gurjar KI Baithak Ki Or, Sonpura | Closed | 84750 | 0 | 2020-12-10
ATER | 2026-2027 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001024/RC/22012034851133 — C C Road - Main Road Pradhan Mantri Sadak Se Ajay Mishra Ke Makan Ke Or Goarkhurd | Closed | 52000 | 0 | 2026-06-06
ATER | 2026-2027 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001024/RC/22012034851134 — C C Road rakesh kushwah ke makan se suresh mishra ke makan ke or goarkhurd | Closed | 78000 | 0 | 2026-06-06
ATER | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001024/RC/275 — cc road pm road se dewata prasad ke door ke or | Deleted | 0 | 0 | 2012-01-26
ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1702001024/RS/22012034495601 — community toilet gram sonpura | Completed | 43000 | 42940 | 2020-09-18 | 2021-01-12
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702001024/RS/22012034547196 — Soak Pit Nirman Bharat Singh ke Ghar ke pass, Sonpura | Deleted | 0 | 0 | 2021-04-14
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702001024/RS/22012034547197 — Soak Pit Nirman Bharat Singh ke Ghar ke pass, Sonpura | Completed | 4600 | 4439 | 2021-09-16 | 2021-11-15
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702001024/RS/22012034547198 — Soak Pit Nirman Sujan Singh Ke Ghar Ke Pass, Sonpura | Completed | 4600 | 4439 | 2021-09-16 | 2021-11-15
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702001024/RS/22012034547199 — Soak Pit Nirman Mata Mandir Ke Pass, Sonpura | Completed | 4600 | 4439 | 2021-09-23 | 2021-11-15
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702001024/RS/22012034547200 — Soak Pit Nirman Kok Singh Ke Ghar Ke Pass, Sonpura | Completed | 4600 | 4439 | 2021-09-23 | 2021-11-15
ATER | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Vermi Compost structure for Community / Construction of Vermi Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1702001024/RS/22012034680728 — Segrigation sed - Goarkhurd | Ongoing | 33667 | 32487 | 2023-05-29
ATER | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702001024/WC/22012034428727 — मिट्टी बांध ( रामप्रसाद के खेत के बगल से ) | Completed | 191000 | 214734 | 2019-03-09 | 2020-06-02
ATER | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702001024/WC/22012034428729 — मिट्टी बांध ( अंगद ओर नेकराम के खेत के बगल से ) | Completed | 175000 | 171204 | 2019-01-10 | 2020-06-02
ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1702001024/WC/22012034555967 — Mitti Bandh Nirman-Ajay Mishra Avam Pulandar Singh Ke Khet Ke Pass, Goarkhurd | Completed | 221007 | 186960 | 2020-07-29 | 2021-04-18
ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001024/WC/22012034610414 — Naveen Talab Nirman Karasdev Ke Than Ke Pass, Sonpura | Ongoing | 1207555.57 | 44004 | 2021-04-22
ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001024/WC/22012034749019 — Earthan Dem Nirman Pappu Ke Khet Ke Pass, Goarkhurd | Closed | 0 | 0 | 2021-04-14
ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001024/WC/22012034749030 — Earthan Dem Chotelal Ke Khet Ke Pass, Goarkhurd | Closed | 0 | 0 | 2021-04-14
ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Upland Bench Terrace Terrace for Comm / Construction of Upland Bench Terrace for Community | Terracing | 1702001024/WC/22012034760729 — Kool Nirman Mukhya Nahar Se Megh Singh Ke Khet Ki Or, Sonpura | Completed | 80965.9 | 71244 | 2021-10-14 | 2023-04-23
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1702001024/WC/22012034760744 — Kool Nirman Mukhya Nahar Se Kailash Ke Kua Ki Or, Sonpura | Completed | 80965.9 | 71244 | 2021-10-21 | 2023-04-23
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1702001024/WC/22012034760760 — Kool Nirman Mukhya Nahar Se Nathuram Samadhiya Ke Khet Ki Or, Sonpura | Closed | 0 | 0 | 2021-04-14
ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1702001024/WC/22012034761948 — Soak Pit Nirman Rajesh Kumar Ke Ghar Ke Samne, Sonpura | Completed | 4600 | 4439 | 2021-07-08 | 2021-11-15
ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1702001024/WC/22012034761950 — Soak Pit Nirman Hari Singh Ke Darwaje Ke Samne, Sonpura | Completed | 4600 | 4439 | 2021-07-08 | 2021-11-15
ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1702001024/WC/22012034761952 — Soak Pit Nirman Pan Singh Ke Darwaje Ke Samne, Sonpura | Completed | 4600 | 4439 | 2021-07-15 | 2021-11-15
ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1702001024/WC/22012034761955 — Soak Pit Nirman Raghuraj Ke Darwaje Ke Pass, Sonpura | Completed | 4600 | 4632 | 2021-07-15 | 2021-11-15
ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1702001024/WC/22012034761959 — Soak Pit Nirman Hanuman Ji Mandir Ke Pass, Sonpura | Completed | 4600 | 4439 | 2021-07-23 | 2021-11-15
ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1702001024/WC/22012034761963 — Soak Pit Nirman Charan Singh Ke Darwaje Ke Pass, Sonpura | Completed | 4600 | 4439 | 2021-07-23 | 2021-11-15
ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1702001024/WC/22012034761966 — Soak Pit Nirman Mohan Singh Ke Makan Ke pass, Sonpura | Completed | 4600 | 4439 | 2021-08-09 | 2021-11-15
ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1702001024/WC/22012034761969 — Soak Pit Nirman Mahendra Singh Ke Darwaje Ke Samne, Sonpura | Completed | 4600 | 4439 | 2021-08-09 | 2021-11-15
ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1702001024/WC/22012034761972 — Soak Pit Nirman Hajari Ke Makan Ke Pass, Sonpura | Completed | 4600 | 4439 | 2021-08-16 | 2021-11-15
ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1702001024/WC/22012034794257 — Kool Nirman Karya Mukhya Nahar Se Pithanpura Chauraha Ki Or, Goarkhurd | Completed | 80965.9 | 69866 | 2021-08-10 | 2023-04-23
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1702001024/WC/22012034861889 — Cool Nirman Karya Bamba Se Pithanpura Ke Shahar Ki Or, Goarkhurd | Closed | 0 | 0 | 2021-10-02
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1702001024/WC/22012034861915 — Cool Nirman Bamba Se Mishranpura Ke Shahar Ki Or, Sonpura | Completed | 161407.44 | 140808 | 2021-11-12 | 2023-04-23
ATER | 2022-2023 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1702001024/WC/22012034973444 — Kool Nirman Karya Bamba Se Mishran Ka Pura Ki Or, Goarkhurd | Completed | 170606.64 | 70992 | 2022-05-22 | 2025-06-08
ATER | 2022-2023 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1702001024/WC/22012034973446 — Kool Nirman Bamba Se Ratiram ki Tibariya Ki Or, Goarkhurd | Completed | 102363.99 | 86904 | 2022-05-22 | 2025-06-08
ATER | 2022-2023 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1702001024/WC/22012034973456 — Kool Nirman Patirampura Bamba Ki Or, Goarkhurd | Completed | 127954.98 | 112608 | 2022-05-22 | 2025-06-08
ATER | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702001024/WC/22012034973501 — Earthan bund nirman mata mandir khand ke pass, goarkhurd | Closed | 0 | 0 | 2022-04-14
ATER | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Brushwood Check Dam for Community / Construction of Brushwood Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001024/WC/22012034993023 — Banda nirman - hanuman mandir ke pass | Completed | 624803.98 | 357510 | 2022-11-06 | 2025-06-08
ATER | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Brushwood Check Dam for Community / Construction of Brushwood Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001024/WC/22012034993024 — Banda nirman - hanuman mandir ke pass ajay mishara ke khet ke pass | Closed | 0 | 0 | 2022-08-16
ATER | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Brushwood Check Dam for Community / Construction of Brushwood Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001024/WC/22012034993028 — Banda nirman - Suendra Thakur ke khet ke pass | Completed | 686984.37 | 582964 | 2022-09-14 | 2025-05-13
ATER | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702001024/WC/22012035079956 — Naveen Talab Nirman Kolu Sahar Ke Pass, Goarkhurd | Closed | 0 | 0 | 2023-04-14
ATER | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001024/WC/22012035079977 — Mitti Bharav Shri Rinku Purohit Ke Makan Se Kolu Bale Sahar Ki or, Goarkhurd | Closed | 0 | 0 | 2023-04-14
ATER | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702001024/WC/22012035103883 — Bandha Nirman Teekaram Jatav Ke Khet Ke Pass, Goarkhhurd | Closed | 0 | 0 | 2023-08-15
ATER | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702001024/WC/22012035103885 — Bandha Nirman Angad Singh Jatav Ke Khet ke pass, Goarkhurd | Closed | 0 | 0 | 2023-08-15
ATER | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702001024/WC/22012035103886 — Naveen Talab Nirman Kabristan Ke Pass, Goarkhurd | Closed | 0 | 0 | 2023-08-15
ATER | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702001024/WC/22012035132450 — Earthan Bund Nirman Kabristhan Ke Pass, Goarkhurd | Completed | 848714.49 | 538008 | 2023-10-11 | 2025-06-08
ATER | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702001024/WC/22012035169902 — Earthan Bund Nirman Shri Brij Bihari Sharma Ke Khet Ke Pass, Goarkhurd | Physically Completed | 1242217.83 | 443554.2 | 2024-03-12 | 2026-06-11
ATER | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702001024/WC/22012035169903 — Earthan Bund Nirman Shri Ramsiya Sharma Ke Khet Ke Pass, Goarkhurd | Closed | 0 | 0 | 2024-01-26
ATER | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen Gully Plugs for Community / Construction of Earthen Gully Plugs for Community | Boulder Check/Gully Plug | 1702001024/WC/22012035182988 — Earthan Gully Plug-Shri Brijbihari Sharma Ke Khet Ke Pass, Goarkhurd | Closed | 0 | 0 | 2024-01-26
ATER | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen Gully Plugs for Community / Construction of Earthen Gully Plugs for Community | Boulder Check/Gully Plug | 1702001024/WC/22012035182992 — Earthan Gully Plug- Shri Ramsiya Sharma Ke Khet Ke Pass, Goarkhurd | Physically Completed | 1148065.07 | 516526.74 | 2024-03-12 | 2026-06-18
ATER | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001024/WC/22012035317829 — Earthan gali plug shanti dam ke pass goarkhurd | Approved | 0 | 0 | 2025-06-05
ATER | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001024/WC/22012035317830 — Earthan gali plug jagveer thakur ke khet ke pass goarkhurd | Approved | 0 | 0 | 2025-06-05
ATER | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Desilting / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1702001024/WH/19955504 — Desilting of talab | Deleted | 0 | 0 | 2016-01-26
ATER | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1702001024/WH/19955761 — talab sonpura | Deleted | 0 | 0 | 2016-01-26
ATER | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1702001024/WH/19956437 — Talab Gahrikaran- Sonpura | Completed | 94000 | 43086 | 2016-05-23 | 2016-07-30
ATER | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1702001024/WH/19962215 — Renovation Of Pond- Sujan Singh ke Makan Ke Pass, Goharkhurd | Completed | 97000 | 91848 | 2017-05-29 | 2017-08-05
ATER | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation of Fisheries Ponds for Community / Renovation of Fisheries Ponds for Community | Repair & maint of Pond/ Tank | 1702001024/WH/22012034388978 — naveen talab niraman goarkhurd | Physically Completed | 1037000 | 918528 | 2018-06-28 | 2026-04-17