## Work List
Exported on: 2026-10-12 02:30:05
Filters applied:
Data source: VBGRAMG
District: BHIND
Block: All
Panchayat: LAWAN
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702001031/AV/22012034509417 — Shantidham Nirman Golan Ka Pura | Ongoing | 283566.25 | 0 | 2020-06-27
ATER | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound Wall for Government School for Community | Constr of Compound wall | 1702001031/AV/22012034625049 — Boundrywall nirman - shanti dham lawan | Ongoing | 588000 | 0 | 2022-11-19
ATER | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat Building for Community | Constr of GP Bhawan | 1702001031/AV/22012034625052 — Hat Bazar - Gram pancahyat lawan | Ongoing | 700000 | 0 | 2022-11-27
ATER | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702001031/AV/22012034633021 — Shanti dham - lawan | Ongoing | 427767.9 | 0 | 2023-08-28
ATER | 2026-2027 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Centre Building for Community | Constr of Aganwadi | 1702001031/AV/22012034669394 — Aganwadi no 2 Amlehdi | Ongoing | 500000 | 89100 | 2026-07-08
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Flood Diversion Drain for Community | Works for Flood Control and Protection | 1702001031/FP/22012034625207 — kool suddrikaran mitti karya - bamba se hardol bale sahar tak | Ongoing | 147334.01 | 0 | 2021-05-29
ATER | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of drain for coastal protection for Comm. / Construction of Storm Water Drain for Community | Works for Flood Control and Protection | 1702001031/FP/22012034628714 — Nala nirman khudai - lawan se batmaspura ke nariya ke or | Ongoing | 899441.42 | 0 | 2022-05-22
ATER | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Repair & Maint of Flood/Diversion Channel for Comm / Repair & Maintenance of Flood or Diversion Channel for Community | Works for Flood Control and Protection | 1702001031/FP/22012034631301 — bamba khudai karya - main road se tufan singh ke khet ke or lawan | Ongoing | 739821.26 | 0 | 2023-04-20
ATER | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Flood Diversion Drain for Community | Works for Flood Control and Protection | 1702001031/FP/22012034631302 — kachha nala nirman - bambaa se jesupura ke or | Ongoing | 485720.7 | 0 | 2023-04-11
ATER | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Flood Diversion Drain for Community | Works for Flood Control and Protection | 1702001031/FP/22012034632416 — kachha nala nirman - main road se batmaspura ke or lawan | Ongoing | 967614 | 0 | 2023-06-25
ATER | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of drain for coastal protection for Comm. / Construction of Storm Water Drain for Community | Works for Flood Control and Protection | 1702001031/FP/22012034634195 — Nala nirman - bandh se Lawan ke or | Ongoing | 909489.38 | 0 | 2023-10-08
ATER | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood or Diversion Channel for Community | Works for Flood Control and Protection | 1702001031/FP/22012034634196 — Kool nirman - bamba se prakash ke khet ke or | Ongoing | 422112.96 | 0 | 2023-10-08
ATER | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of drain for coastal protection for Comm. / Construction of Storm Water Drain for Community | Works for Flood Control and Protection | 1702001031/FP/22012034638786 — kachha nala nirman - bamba se main road ke or | Ongoing | 813616.59 | 0 | 2024-03-14
ATER | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of drain for coastal protection for Comm. / Construction of Storm Water Drain for Community | Works for Flood Control and Protection | 1702001031/FP/22012034638787 — kachha nala nirman - hardol se lawan bamba ke or | Ongoing | 968019.75 | 0 | 2024-03-14
ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1702001031/IF/22012035377236 — khet talab bheem sen ke khet par | Ongoing | 149905.72 | 0 | 2025-05-12
ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1702001031/IF/22012035556279 — khet talab jardan singh s/o bheekam singh | Approved | 147621.16 | 0 | 2025-04-14
ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1702001031/IF/22012035556314 — khet talab shri krishna ke khet par | Approved | 0 | 0 | 2025-04-14
ATER | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1702001031/IF/22012035641248 — maa ke bagiya mula devi | Ongoing | 263511.37 | 0 | 2026-04-28
ATER | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1702001031/IF/22012035650953 — maa ke bagiya soni | Ongoing | 286198.01 | 0 | 2026-04-28
ATER | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1702001031/IF/22012035652048 — maa ke bagiya kunja devi | Ongoing | 263511.37 | 300 | 2026-05-11
ATER | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1702001031/IF/22012035657281 — maa ke bagiya varsha w/o bhav singh | Ongoing | 263511.37 | 0 | 2026-05-15
ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1702001031/IF/22012035658013 — maa ke bagiya mamta | New | 0 | 0 | 2025-04-14
ATER | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1702001031/IF/22012035658044 — maa ke bagiya mamta w/o balram singh | Ongoing | 261748.57 | 0 | 2026-05-15
ATER | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1702001031/IF/22012035658046 — Maa ke bagiya Rashmi w/o Raghvendra singh | Ongoing | 261748.57 | 0 | 2026-05-15
ATER | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702001031/IF/IAY/4519916 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115015144 | Approved | 27000 | 0 | 2024-09-14
ATER | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702001031/IF/IAY/4861889 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115206192 | Ongoing | 27000 | 0 | 2026-05-15
ATER | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702001031/IF/IAY/4861890 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115211465 | Ongoing | 27000 | 0 | 2026-04-04
ATER | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702001031/IF/IAY/4863103 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115213482 | Ongoing | 27000 | 1500 | 2026-05-15
ATER | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702001031/IF/IAY/4915522 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124738746 | Ongoing | 27000 | 0 | 2026-06-09
ATER | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702001031/IF/IAY/4915597 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130831299 | Ongoing | 27000 | 1500 | 2026-04-04
ATER | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702001031/IF/IAY/4915738 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115151366 | Ongoing | 27000 | 0 | 2026-05-15
ATER | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702001031/IF/IAY/4924442 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147786804 | Ongoing | 27000 | 0 | 2026-04-04
ATER | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702001031/IF/IAY/4924454 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115147849 | Approved | 27000 | 0 | 2025-02-13
ATER | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702001031/IF/IAY/4924476 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124802344 | Ongoing | 27000 | 0 | 2026-04-28
ATER | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702001031/IF/IAY/5265016 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114782062 | Ongoing | 27000 | 1500 | 2026-04-04
ATER | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702001031/IF/IAY/5721515 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115224883 | Ongoing | 27000 | 0 | 2026-04-28
ATER | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702001031/IF/IAY/5723473 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106621612 | Ongoing | 27000 | 0 | 2026-09-15
ATER | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702001031/IF/IAY/5843541 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143651177 | Approved | 27000 | 0 | 2025-03-17
ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel / Mitti Murram Road for Community | Construction of Road and Culvert | 1702001031/RC/22012034535571 — Sudur Samprak Sadak Shaskiya Ucchatar Madhamik VidhyalayaLawan Se Kailash Kurbariya Ke Kunya KE or | Ongoing | 1937969.67 | 0 | 2020-09-12
ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1702001031/RC/22012034561969 — CCRaod Ramu Ke Ghar Se School evam main Road EvamVishambar Ke Ghar Se MandirEvamMainRoadSe Santosh | Ongoing | 46500 | 0 | 2021-03-23
ATER | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1702001031/WC/22012035316976 — dag pond jesupura talab mata mandir ke pass | Approved | 0 | 0 | 2025-04-14
ATER | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1702001031/WC/22012035316979 — dag pond jesupura talab bijli ghar ke pass | Approved | 0 | 0 | 2025-04-14