## Work List
Exported on: 2026-09-07 15:25:31
Filters applied:
Data source: MGNREGA + VBGRAMG
District: BHIND
Block: All
Panchayat: BIJORA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
ATER | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1702001033/AV/22012034615755 — construction work of boundry wall nirman - shashkiya prathmik vidhayala padit ka pura | Completed | 114000 | 113832 | 2022-05-12 | 2022-08-10
ATER | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1702001033/AV/22012034618026 — Boundry wall nirman - govt primary school padit ka pura | Completed | 66000 | 65076 | 2022-08-06 | 2022-11-16
ATER | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1702001033/AV/22012034618029 — Sarvjanik Chabutra - shashkiya prathmik vidhayala padit ka pura | Completed | 37000 | 35496 | 2022-08-13 | 2022-11-16
ATER | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702001033/FP/22012034636964 — Kachcha Nala-Rakesh ke tyube ke bagal se behad ki or bijora | Closed | 0 | 0 | 2023-08-16
ATER | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702001033/IF/22012034356712 — वृक्षारोपण शंकर जी मंदिर परिसर पर एवं प्राइमरी स्कूल बिजोरा | Completed | 335000 | 18056 | 2017-07-15 | 2021-12-01
ATER | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702001033/IF/22012034356714 — वृक्षारोपण शान्तिधाम एवं हाई स्कूल बिजोरा | Closed | 335000 | 0 | 2017-06-15
ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1702001033/IF/22012034769739 — Med bandhan Karya Rakesh singh | Closed | 0 | 0 | 2021-04-21
ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1702001033/IF/22012034769747 — Med Bandhan Karya Raju singh | Closed | 0 | 0 | 2021-04-21
ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1702001033/IF/22012034769754 — Med Bandhan Karya Vijay singh | Closed | 0 | 0 | 2021-04-21
ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702001033/IF/22012034769758 — Med Bandhan Karya Shivsant singh | Closed | 0 | 0 | 2021-04-21
ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1702001033/IF/22012034769765 — Med Bandhan Karya Shisupal singh | Closed | 0 | 0 | 2021-04-21
ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1702001033/IF/22012034769772 — Med Bandhan Karya Jay singh | Closed | 0 | 0 | 2021-04-21
ATER | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001033/IF/22012035074333 — KHET TALAB NIRMAR KARYA SHANKUNTLA DEVI BIJORA | Closed | 0 | 0 | 2023-01-26
ATER | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001033/IF/22012035074334 — KHET TALAB NIRMAN RAJENDRA SINGH BIJORA | Closed | 0 | 0 | 2023-01-26
ATER | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001033/IF/22012035074335 — KHET TALAB NIRMAN RAJENDRA SINGH BIJORA | Physically Completed | 385261.22 | 291057 | 2023-05-19 | 2026-04-17
ATER | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001033/IF/22012035082872 — KHET TALAB SHAKUNTALADEVI W/ O SOBRAN SINGH | Ongoing | 385261.22 | 92599 | 2023-06-01
ATER | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation-Farm Forestry Trees(Individual) / Boundary Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1702001033/IF/22012035127596 — बृक्षारोपण निर्माण कार्य ग्राम पंचायत विजोरा | Closed | 0 | 0 | 2023-04-01
ATER | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Coastal Shelter Belt-line plntation - Individual / Line Plantation of Coastal Shelter Belt Trees for Individuals | Plantation | 1702001033/IF/22012035130334 — brajsharopan nirman karya gram panchayat bijora | Physically Completed | 429720.58 | 219011 | 2023-10-06 | 2026-06-13
ATER | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Coast Line plntation of Forestry Trees-Individuals / Along the coast Line Plantation of Forestry Trees for Individuals | Plantation | 1702001033/IF/22012035134740 — gram panchayat bijora me tal ke pura par braksharopan karya | Closed | 0 | 0 | 2023-04-01
ATER | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Coast Line plntation of Forestry Trees-Individuals / Along the coast Line Plantation of Forestry Trees for Individuals | Plantation | 1702001033/IF/22012035134741 — gram panchayat bijora me tal ke pura par braksharopan karya | Physically Completed | 429720.58 | 167297 | 2023-10-06 | 2026-06-13
ATER | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Block Plantation of Farm Forestry Trees in Fields for Individuals | Plantation | 1702001033/IF/22012035137024 — अमृत वाटिका विजोरा | Ongoing | 55847.4 | 221 | 2023-10-06
ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001033/IF/22012035465945 — khet talab dhruv prasad ke khet par | Ongoing | 147621.16 | 261 | 2025-05-14
ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001033/IF/22012035466031 — khet talab virendra singh ke khet par | Ongoing | 147621.16 | 261 | 2025-05-12
ATER | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001033/IF/9926708370 — Cattle Shed Krishna pal Singh | Deleted | 44200 | 0 | 2013-11-14
ATER | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001033/IF/9926708371 — Cattle Shed Sukhpal Singh | Deleted | 44200 | 0 | 2013-11-14
ATER | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001033/IF/9926708372 — Cattle Shed Gajendra singh /Jagmohan | Deleted | 44200 | 0 | 2013-11-14
ATER | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001033/IF/9926708373 — Cattle Shed Brijbhan singh /Roop Singh | Deleted | 44200 | 0 | 2013-11-14
ATER | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001033/IF/9926708374 — Cattle Shed Subedar singh Bhadoriya | Deleted | 44200 | 0 | 2013-11-14
ATER | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001033/IF/9926708375 — Cattle Shed Jay SIngh /Sukhdev Singh | Deleted | 44200 | 0 | 2013-11-14
ATER | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001033/IF/9926708376 — Cattle Shed Shiv Pratap Singh | Deleted | 44200 | 0 | 2013-11-14
ATER | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001033/IF/9926708377 — Cattle Shed Swami charan / Gajadhar | Deleted | 44200 | 0 | 2013-11-14
ATER | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001033/IF/9926708379 — Cattle Shed Balbhardh / Harpal Singh | Deleted | 44200 | 0 | 2013-11-14
ATER | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001033/IF/9926708380 — Cattle Shed Devendra / Jagmohan | Deleted | 44200 | 0 | 2013-11-14
ATER | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001033/IF/9926708381 — Cattle Shed Ganga charan / Gajadhar | Deleted | 44200 | 0 | 2013-11-14
ATER | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001033/IF/9926708382 — Cattle Shed Chatrapal / Puttu Singh | Deleted | 44200 | 0 | 2013-11-14
ATER | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001033/IF/9926708383 — Cattle Shed Rambaran / Buddhe Singh | Completed | 44200 | 45362 | 2014-09-26 | 2014-12-30
ATER | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001033/IF/9926708384 — Cattle Shed Brij kishore / Vidhya ram | Deleted | 44200 | 0 | 2013-11-14
ATER | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001033/IF/9926708387 — Cattle Shed Sonu / Nathu | Deleted | 44200 | 0 | 2013-11-14
ATER | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001033/IF/9926708388 — Cattle Shed Run Singh / Anne Singh | Completed | 44200 | 45362 | 2014-10-17 | 2015-01-20
ATER | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001033/IF/9926708389 — Cattle Shed Pramod / Nathu | Deleted | 44200 | 0 | 2013-11-14
ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001033/IF/9993729956 — cattle shed ramsingh | Deleted | 0 | 0 | 2016-01-26
ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702001033/IF/9993729957 — cattle shed ramsingh | Deleted | 0 | 0 | 2016-01-26
ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001033/IF/9993729959 — cattle shed raju singh | Deleted | 0 | 0 | 2016-01-26
ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001033/IF/9993729962 — cattle shed Balak ram | Deleted | 0 | 0 | 2016-01-26
ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001033/IF/9993729963 — cattle shed ramvilash | Deleted | 0 | 0 | 2016-01-26
ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001033/IF/9993729964 — cattle shed ram prasad | Deleted | 0 | 0 | 2016-01-26
ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001033/IF/9993729965 — cattle shed mebaram | Deleted | 0 | 0 | 2016-01-26
ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702001033/IF/9993729966 — Const. of Farm buinding Rajaram | Deleted | 0 | 0 | 2016-01-26
ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702001033/IF/9993729967 — Const. of Farm buinding Gorelal | Deleted | 0 | 0 | 2016-01-26
ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702001033/IF/9993729968 — Const. of Farm buinding Vijay singh | Deleted | 0 | 0 | 2016-01-26
ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702001033/IF/9993729969 — Const. of Farm buinding Lallu ram | Deleted | 0 | 0 | 2016-01-26
ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001033/IF/IAY/125558 — Construction of IAY House -IAY REG. NO. MP-02-001-033-001/24 | Approved | 27000 | 0 | 2016-02-01
ATER | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001033/IF/IAY/4085565 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125579503 | Physically Completed | 18360 | 14688 | 2023-01-03 | 2024-11-21
ATER | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001033/IF/IAY/4772275 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125526579 | Ongoing | 27000 | 12636 | 2025-02-04
ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001033/IF/IAY/5553935 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125600569 | Ongoing | 27000 | 15660 | 2025-10-28
ATER | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001033/IF/IAY/5554546 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125580848 | Approved | 27000 | 0 | 2025-03-05
ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001033/IF/IAY/5565895 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125575701 | Physically Completed | 23490 | 0 | 2025-05-13 | 2026-02-05
ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001033/IF/IAY/5723206 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127568376 | Ongoing | 27000 | 20358 | 2025-10-28
ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001033/IF/IAY/5724250 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125608777 | Ongoing | 27000 | 20358 | 2025-10-28
ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001033/IF/IAY/5729929 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127567058 | Ongoing | 27000 | 20358 | 2025-10-28
ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001033/IF/IAY/5870469 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125602316 | Approved | 27000 | 0 | 2025-09-12
ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001033/IF/IAY/5870474 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125582412 | Approved | 27000 | 0 | 2025-09-12
ATER | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001033/LD/168 — मेडबन्‍धान विटटी देवी वेवा जिलेदार सिहं जाति ठाकुर | Deleted | 4400 | 0 | 2010-04-14
ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1702001033/LD/22012034294371 — Shanti dham bijora | Completed | 996000 | 51102 | 2016-12-25 | 2021-12-01
ATER | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001033/LD/230 — मेड बन्‍धान कार्य छत्रपाल सिंह / पुत्‍तू सिंह भदौरिया | Completed | 14000 | 2200 | 2010-05-10 | 2010-09-15
ATER | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001033/LD/231 — मेड बन्‍धान कार्य वीरपाल सिंह / ग्‍यासिंह | Completed | 14000 | 900 | 2010-05-11 | 2010-07-15
ATER | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001033/LD/232 — मेड बन्‍धान कार्य गरीब / ग्‍यादीन रतनश्री वेवा सुमेर सिंह | Completed | 4300 | 1700 | 2010-05-13 | 2010-09-15
ATER | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001033/LD/233 — मेड बन्‍धान कार्य विटटी देवी / जिलेदार सिंह ठाकुर | Completed | 4300 | 1600 | 2010-05-13 | 2010-07-15
ATER | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001033/LD/234 — मेड बन्‍धान कार्य रायसिंह / कमल सिंह | Completed | 7400 | 7600 | 2010-08-21 | 2010-10-20
ATER | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001033/LD/235 — मेड बन्‍धान कार्य रामभवन सिंह | Completed | 7400 | 6850 | 2010-08-23 | 2010-09-15
ATER | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001033/LD/236 — मेड बन्‍धान कार्य मेवाराम / पातीराम | Completed | 7400 | 6000 | 2010-08-29 | 2010-09-15
ATER | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001033/LD/237 — मेंढबन्‍धान मौजमसिंह / महावीर सिंह | Completed | 0 | 7200 | 2010-08-25 | 2010-09-15
ATER | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001033/LD/238 — मेड बन्‍धान कार्य अजय / दधिराम | Completed | 7400 | 7700 | 2010-08-27 | 2010-09-15
ATER | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001033/LD/239 — मेड बन्‍धान कार्य उमा देवी वेवा / प्रहलाद दुवे | Completed | 7400 | 4200 | 2010-08-31 | 2010-09-15
ATER | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001033/LD/3799416508 — Gramin kridagan vikas kary old temple of shankar j | Completed | 331500 | 312732 | 2014-01-10 | 2014-03-30
ATER | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001033/LD/3799416588 — santi dham vikas kary Bijora | Completed | 488000 | 318260.6 | 2014-03-14 | 2014-08-10
ATER | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001033/LD/6 — मेढ बन्‍धान | Deleted | 10650 | 0 | 2008-12-04
ATER | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001033/LD/70 — मेड् बंधान लक्ष्‍मण सिंह s/o सुखराम सिंह बिजौरा | Completed | 11000 | 9828 | 2009-02-28 | 2009-03-15
ATER | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001033/LD/71 — मेड बंधान निर्माण शादीलाल मनीाम / जिमीपाल हरिजन | Completed | 80000 | 7098 | 2009-10-10 | 2009-10-21
ATER | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001033/LD/90 — मेडबन्‍धान विजयसिंह/वरनाम सिंह | Completed | 8500 | 7098 | 2009-10-29 | 2009-11-06
ATER | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001033/LD/91 — मेडबन्‍धान राजाराम/गंगाराम | Completed | 5100 | 3822 | 2009-10-10 | 2009-10-21
ATER | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001033/LD/92 — मेडबन्‍धान छोटेलाल/ अन्‍तराम | Completed | 9000 | 6552 | 2009-10-22 | 2009-10-28
ATER | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001033/LD/93 — मेडबन्‍धान रामसनेही/ ग्‍यादीन | Completed | 4700 | 3822 | 2009-11-07 | 2009-11-13
ATER | 2014-2015 | D--RURAL INFRASTUCTURE / Other Works | Maintenance of rural public assets / Repair and Maintenance of Gram Panchayat/Panchayat Bhavan Building for Community | Repair & Maint of Community infrastructure | 1702001033/OP/9425885248 — Mangal bhawan shankar ji mandir ke pass | Completed | 135000 | 134855 | 2014-06-20 | 2014-12-30
ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1702001033/PG/9425891120 — KHEL MAIDAN BIJORA | Completed | 526815 | 101536 | 2016-12-03 | 2021-12-01
ATER | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702001033/RC/104 — पुराना गांव शंकर जी मंदिर से रूपा वाव मंदिर की ओर | Completed | 474200 | 472364 | 2009-06-06 | 2011-05-24
ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001033/RC/22012034203575 — cc road balbhadra house to surendra house | Deleted | 133300 | 0 | 2013-04-14
ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001033/RC/22012034204179 — cc road main road jagnayak singh house khadiyani | Completed | 90400 | 75560 | 2014-02-28 | 2014-03-30
ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001033/RC/22012034204196 — cc road balbhadra house to surendra singh house | Completed | 133300 | 94904.4 | 2014-02-21 | 2014-03-20
ATER | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001033/RC/22012034217650 — cc road Hargen Basti se Ravilal singh ke ghar ki | Completed | 185000 | 183270.8 | 2014-05-16 | 2014-07-20
ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001033/RC/22012034267659 — C.C. Road from Munnesh house to Nathuram jatav Harijan basti house | Completed | 88800 | 79403.36 | 2015-08-14 | 2015-12-25
ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001033/RC/22012034284990 — C.C. Road Gov. School Mahuri to Harijan Basti | Completed | 55500 | 20244 | 2015-11-27 | 2016-04-25
ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001033/RC/22012034284991 — C.C. Road from Lashman Singh house to Gov. Middle School Khadidani | Completed | 39500 | 39815 | 2016-10-18 | 2017-09-01
ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001033/RC/22012034309797 — cc road Ramvilash house to e g s Shala Pandit ka pura | Deleted | 0 | 0 | 2016-01-26
ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001033/RC/22012034309821 — cc road ramviash house to e g s shala | Deleted | 0 | 0 | 2016-01-26
ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001033/RC/22012034310460 — CC Road from Ramvilas house to Shala bhavan | Deleted | 88000 | 0 | 2016-01-01
ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001033/RC/22012034310461 — CC Road from Shala bhavan to Munesh singh house | Deleted | 110000 | 0 | 2016-01-01
ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001033/RC/22012034316825 — CC road shala bhawan se munesh singh ke makan tak | Completed | 110000 | 88814 | 2016-11-26 | 2021-12-01
ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702001033/RC/22012034320981 — pahuch marg pradhanmantri sadak se purane gao ki ore | Completed | 1430638 | 535860 | 2017-01-22 | 2021-12-01
ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001033/RC/22012034373212 — cc road | Deleted | 0 | 0 | 2018-01-26
ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001033/RC/22012034381911 — cc road | Closed | 0 | 0 | 2017-10-02
ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001033/RC/22012034382429 — cc road | Closed | 0 | 0 | 2017-10-02
ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001033/RC/22012034442354 — cc road | Closed | 0 | 0 | 2019-01-26
ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001033/RC/22012034511990 — c c road ( main road pahuch marg se purane gram shankar ji mandir ke or ) | Ongoing | 177750 | 58308 | 2020-04-24
ATER | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001033/RC/22012034514702 — cc road | Closed | 0 | 0 | 2019-10-02
ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001033/RC/22012034527095 — c c road - mukhya marg se devi dayal ke makan ke or | Closed | 186000 | 0 | 2020-05-05
ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001033/RC/22012034527096 — c c road ( ram bilas singh ke darwaje se shashkiya prathimik vidhalaya panditan ke pura ke or bijora | Closed | 23250 | 0 | 2020-05-05
ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001033/RC/22012034542463 — c c road ( harpal singh ke makan se shashkiya prathmik shala bhawan ke or ) | Physically Completed | 30900 | 28500 | 2021-01-03 | 2026-05-26
ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001033/RC/22012034554876 — c c road ( braj kishor ke makan se mojam ke makan tak ) | Ongoing | 27900 | 23940 | 2021-01-13
ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001033/RC/22012034554878 — c c road ( ran singh ke darwaje se devidayal ke darwaje ke or ) | Closed | 69750 | 0 | 2020-11-01
ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001033/RC/22012034562199 — c c road ( ramdas ke makan se arogyadham ke or ) | Closed | 139500 | 0 | 2021-01-21
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001033/RC/22012034562201 — c c road ( shivsant ke makan se devidayal ke makan tak ) | Closed | 84750 | 0 | 2021-04-01
ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001033/RC/22012034562202 — c c road ( rambilas ke darwaje se mayaram ke darwaje ke or ) | Ongoing | 7650 | 6840 | 2021-03-08
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001033/RC/22012034581539 — c c road ( damar road se basant singh ke makan ke or ) | Ongoing | 38250 | 25476 | 2021-08-30
ATER | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001033/RC/22012034608366 — cc road ( amar singh ke dwar se shiv singh ke dwar ke or ) | Completed | 120000 | 119544 | 2022-05-15 | 2022-08-10
ATER | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001033/RC/22012034842429 — c c road nagendra singh ke dwar se pramod kotwar ke dwar ke or gram bijora | Approved | 92000 | 0 | 2025-04-14
ATER | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001033/RC/298 — 1702001033/RC/298 | Completed | 0 | 91400 | 2012-03-15 | 2012-04-20
ATER | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001033/RC/372 — cc nirman work bijora men road se devi mandir ke or | Completed | 0 | 67904 | 2012-07-06 | 2012-09-30
ATER | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702001033/RC/4 — पहॅुचमार्ग निर्माण | Completed | 300000 | 148232 | 2009-05-08 | 2009-05-15
ATER | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001033/RC/417 — सी स‍ी रोड प्रमोद के घर से मुख्‍य सडे की ओर | Completed | 294800 | 117952 | 2012-12-05 | 2013-03-30
ATER | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001033/RC/495 — 1702001033/RC/495 | Completed | 0 | 47952 | 2013-03-14 | 2013-03-30
ATER | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702001033/RC/5 — पहॅुच मार्ग | Completed | 400000 | 253190.9 | 2009-03-06 | 2009-01-15
ATER | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702001033/RC/6 — पहॅुचमार्ग | Completed | 300000 | 69739 | 2009-04-23 | 2009-05-06
ATER | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702001033/RC/93 — पहॅुच मार्ग | Completed | 360000 | 115068 | 2009-02-02 | 2009-02-02
ATER | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001033/RS/187 — 1702001033/RS/187 | Completed | 4500 | 4440 | 2013-02-22 | 2013-03-30
ATER | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001033/RS/188 — 1702001033/RS/188 | Completed | 4500 | 4440 | 2013-02-22 | 2013-03-30
ATER | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001033/RS/189 — 1702001033/RS/189 | Completed | 4500 | 4440 | 2013-02-22 | 2013-03-30
ATER | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001033/RS/190 — 1702001033/RS/190 | Completed | 4500 | 4440 | 2013-02-22 | 2013-03-30
ATER | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001033/RS/191 — 1702001033/RS/191 | Completed | 4500 | 4440 | 2013-02-22 | 2013-03-30
ATER | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001033/RS/192 — 1702001033/RS/192 | Completed | 4500 | 4440 | 2013-02-22 | 2013-03-30
ATER | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001033/RS/193 — 1702001033/RS/193 | Completed | 4500 | 4440 | 2013-02-22 | 2013-03-30
ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001033/RS/22012034184653 — Ramgopal singh Maryada abhiyan | Completed | 4500 | 4428 | 2013-12-27 | 2014-02-10
ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001033/RS/22012034184662 — Gappu maryada abhiyan | Completed | 4500 | 4428 | 2013-12-27 | 2014-02-18
ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001033/RS/22012034184667 — Navneet maryada abhiyan | Completed | 4500 | 4428 | 2013-12-27 | 2014-02-18
ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001033/RS/22012034184670 — Rajnu Singh Maryada | Completed | 4500 | 4428 | 2013-12-27 | 2014-02-18
ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001033/RS/22012034184672 — Devesh Singh Maryada | Completed | 4500 | 4428 | 2013-12-27 | 2014-02-18
ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001033/RS/22012034184673 — Indresh Maryada | Completed | 4500 | 4428 | 2013-12-27 | 2014-02-18
ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001033/RS/22012034184677 — Beti kumbar NBA | Completed | 4500 | 4428 | 2013-12-27 | 2014-02-18
ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001033/RS/22012034184679 — Umesh Singh NBA | Completed | 4500 | 4428 | 2013-12-27 | 2014-02-18
ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001033/RS/22012034184694 — Nayab Singh NBA | Completed | 4500 | 4428 | 2013-12-27 | 2014-02-18
ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001033/RS/22012034184695 — Ajeet Singh NBA | Completed | 4500 | 4428 | 2013-12-27 | 2014-02-18
ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001033/RS/22012034184696 — Shiv Pratap NBA | Completed | 4500 | 2628 | 2013-12-27 | 2014-12-30
ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001033/RS/22012034185417 — Suresh NBA | Completed | 4500 | 4428 | 2013-12-16 | 2014-02-10
ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001033/RS/22012034185419 — Chote Singh NBA | Completed | 4500 | 4428 | 2013-12-16 | 2014-02-10
ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001033/RS/22012034185421 — Shiv Singh NBA | Completed | 4500 | 4428 | 2013-12-16 | 2014-02-10
ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001033/RS/22012034185424 — Raj Kumar NBA | Completed | 4500 | 4428 | 2013-12-16 | 2014-02-10
ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001033/RS/22012034185425 — Harnarayan NBA | Completed | 4500 | 4428 | 2013-12-16 | 2014-02-10
ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001033/RS/22012034185426 — Dhrub prasad NBA | Completed | 4500 | 4428 | 2013-12-16 | 2014-02-10
ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001033/RS/22012034185428 — Lajjavati NBA | Completed | 4500 | 4428 | 2013-12-20 | 2014-01-29
ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001033/RS/22012034185430 — Rajkumar NBA | Completed | 4500 | 4428 | 2013-12-20 | 2014-01-29
ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001033/RS/22012034185432 — Bittigovind NBA | Completed | 4500 | 4428 | 2013-12-16 | 2014-02-10
ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001033/RS/22012034185433 — Girendra Singh NBA | Completed | 4500 | 4428 | 2013-12-16 | 2014-02-10
ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001033/RS/22012034185443 — Lal Ji NBA | Completed | 4500 | 4428 | 2013-12-20 | 2014-01-29
ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001033/RS/22012034185445 — Virendra singh NBA | Completed | 4500 | 4428 | 2013-12-16 | 2014-02-10
ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001033/RS/22012034185448 — Sunil / Ram Sebak NBA | Completed | 4500 | 2628 | 2013-12-20 | 2014-12-30
ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001033/RS/22012034185451 — Ashok Singh / Sarada Singh NBA | Completed | 4500 | 4428 | 2013-12-16 | 2014-02-10
ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001033/RS/22012034185453 — Prempal Singh /Mojam singh NBA | Completed | 4500 | 4428 | 2013-12-16 | 2014-02-10
ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001033/RS/22012034185455 — Sarita Devi Beba Sukhpal Singh NBA | Completed | 4500 | 2628 | 2013-12-16 | 2014-12-30
ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001033/RS/22012034185456 — Smt. ramayani devi NBA | Completed | 4500 | 4428 | 2013-12-16 | 2014-02-10
ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001033/RS/22012034185458 — Subhash /Pramod NBA | Completed | 4500 | 6228 | 2013-12-16 | 2014-12-30
ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001033/RS/22012034185459 — Nagendra singh/Harpal Singh NBA | Completed | 4500 | 4428 | 2013-12-16 | 2014-02-10
ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001033/RS/22012034185460 — Nandram /ratiram NBA | Completed | 4500 | 4428 | 2013-12-16 | 2014-02-10
ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001033/RS/22012034185473 — Raju/kamata NBA | Completed | 4500 | 4428 | 2013-12-16 | 2014-02-10
ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001033/RS/22012034185474 — Mohane beba Samokhan NBA | Completed | 4500 | 4428 | 2013-12-16 | 2014-02-10
ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001033/RS/22012034185614 — Jay Singh /Sukhdev Singh NBA | Completed | 4500 | 4428 | 2013-12-16 | 2014-02-10
ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001033/RS/22012034185802 — Rameshwar/Bachan lal NBA | Completed | 4500 | 4428 | 2013-12-27 | 2014-02-18
ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001033/RS/22012034185803 — Ramprakash/Soupal NBA | Completed | 4500 | 4428 | 2013-12-27 | 2014-02-18
ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001033/RS/22012034185805 — Balbhardh/Harpal NBA | Completed | 4500 | 4428 | 2013-12-27 | 2014-02-18
ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001033/RS/22012034185810 — Kok Singh /Khube Singh NBA | Completed | 4500 | 4428 | 2013-12-27 | 2014-02-18
ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001033/RS/22012034185811 — Narendra singh/Preetam singh NBA | Completed | 4500 | 4428 | 2013-12-27 | 2014-02-18
ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001033/RS/22012034185812 — Mansharam /Mungaram NBA | Completed | 4500 | 4428 | 2013-12-27 | 2014-02-18
ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001033/RS/22012034185813 — Meenendra /Gajendra NBA | Completed | 4500 | 4428 | 2013-12-27 | 2014-02-18
ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001033/RS/22012034185815 — Smt. Amola devi/devendra NBA | Completed | 4500 | 4428 | 2013-12-27 | 2014-02-18
ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001033/RS/22012034185818 — Jogendra singh/Sahajade NBA | Completed | 4500 | 4428 | 2013-12-27 | 2014-02-18
ATER | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001033/RS/22012034251450 — Toilet 1 Munnesh 2 Vijay 3 Anil 4 Vikash 5 Ramji | Completed | 54000 | 53929 | 2014-07-25 | 2014-07-31
ATER | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001033/RS/22012034251473 — Toilet 1 Sonu 2 Kalichran 3 Arvind 4 Nishu 5 Rekes | Completed | 54000 | 53929 | 2014-08-01 | 2014-08-07
ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001033/RS/31419 — maryada abhiyan kirat singh | Completed | 4500 | 3552 | 2013-06-14 | 2014-02-18
ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001033/RS/31422 — maryada abhiyan omprakesh | Completed | 4500 | 4428 | 2013-06-14 | 2014-04-12
ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001033/RS/33799 — maryada abhiyan sopal | Completed | 4500 | 4428 | 2013-08-09 | 2014-02-10
ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001033/RS/33801 — Maryada abhiyan Ramraj | Completed | 4500 | 4428 | 2013-06-14 | 2014-02-10
ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001033/RS/33803 — Maryada abhiyan jaipal | Completed | 4500 | 4428 | 2013-06-14 | 2014-02-10
ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001033/RS/33890 — Maryada abhiyan guddi | Completed | 4500 | 4428 | 2013-06-14 | 2014-02-10
ATER | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001033/RS/33895 — Maryada abhiyan jupal | Deleted | 4500 | 0 | 2012-08-15
ATER | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001033/RS/33900 — Maryada abhiyan jupal | Deleted | 4500 | 0 | 2012-08-15
ATER | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001033/RS/33904 — Maryada abhiyan | Deleted | 0 | 0 | 2012-08-15
ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001033/RS/38304 — Maryada abhiyan jupal | Completed | 4500 | 4428 | 2013-08-09 | 2014-02-10
ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001033/RS/38305 — Maryada abhiyan NAMAN | Completed | 4500 | 4428 | 2013-08-09 | 2014-02-10
ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001033/RS/38306 — Maryada abhiyan thaman singh | Completed | 4500 | 4428 | 2013-08-09 | 2014-02-10
ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001033/RS/38307 — Maryada abhiyan kapure singh | Completed | 4500 | 4428 | 2013-08-10 | 2014-02-10
ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001033/RS/38308 — Maryada abhiyan Ratan singh | Completed | 4500 | 4428 | 2013-08-10 | 2014-02-10
ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001033/RS/38309 — Maryada abhiyan surendra | Completed | 4500 | 4428 | 2013-08-09 | 2014-02-10
ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001033/RS/38310 — Maryada abhiyan brajmohan | Completed | 4500 | 4428 | 2013-08-09 | 2014-02-10
ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001033/RS/38311 — Maryada abhiyan charandbhan | Completed | 4500 | 4428 | 2013-08-08 | 2014-02-10
ATER | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001033/WC/19 — नवीन तालाब बडा भरक के पास बिजौरा | Deleted | 294000 | 0 | 2008-10-02
ATER | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001033/WC/20 — नवीन तालाब निर्माण्‍ा बगिया के पास बिजौरा | Completed | 368000 | 354787.5 | 2009-06-20 | 2011-04-21
ATER | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702001033/WC/22012034324731 — Khadiyana talab Bijora | Completed | 467445 | 185760 | 2017-05-18 | 2021-12-01
ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1702001033/WC/22012034910768 — talab nirman | Closed | 0 | 0 | 2022-02-10
ATER | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001033/WC/22012035142898 — Earthen dam -karan singh ki fer ki nichhe pandit ka pura Bijora | Closed | 504240.21 | 0 | 2023-08-16
ATER | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001033/WC/22012035183116 — Earthen chek dam - karan singh ke fer ke pass pandit ka pura bijora | Closed | 0 | 0 | 2024-01-24
ATER | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001033/WC/22012035198146 — Earthen check dam nirman-chhote dhanuk ke fer ke niche pandit ka pura bijora | Closed | 0 | 0 | 2024-01-24
ATER | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001033/WC/3 — नवीन तालाब निर्माण | Completed | 54000 | 49948 | 2009-03-06 | 2009-01-15
ATER | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1702001033/WC/52 — Water conservnew | Completed | 0 | 153532 | 2012-04-29 | 2012-06-30
ATER | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001033/WC/9 — नवीन तालाब निर्माण | Completed | 294000 | 273528 | 2009-02-28 | 2011-01-07
ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702001033/WH/22012034459348 — तालाब जीर्णोद्धार खांद के पास माहुरी पर चिलोंगा | Closed | 0 | 0 | 2022-01-24