## Work List
Exported on: 2026-10-27 03:17:03
Filters applied:
Data source: MGNREGA + VBGRAMG
District: BHIND
Block: All
Panchayat: BHUJPURA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1702001042/AV/22012034399451 — आगनवाडी भवन निर्माण भुजपुरा | Completed | 330000 | 332112 | 2019-03-07 | 2019-06-15
ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702001042/AV/22012034510644 — shanti dham - bhujpura | Completed | 283566.25 | 278326.5 | 2020-06-20 | 2021-03-03
ATER | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play field for Community | Construction of Play field | 1702001042/AV/22012034648237 — Khel maidan - bhujpura | Closed | 0 | 0 | 2023-08-16
ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1702001042/AV/4140 — Aanganbadi/Other Rural Infrastructure,ATER | Completed | 330000 | 325960 | 2015-12-14 | 2021-06-30
ATER | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Farm Forestry-Community / Boundary Line Plantation of Farm Forestry Trees for Community | Plantation | 1702001042/DP/22012034596128 — अमृत बाटिका - मन्दिर के पास तालाब भुजपुरा | Physically Completed | 55847.4 | 20995 | 2023-08-27 | 2026-05-14
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1702001042/FP/22012034369852 — Construction work of RCC Nala - Gram swaraj bhawan se railway line ke pul & bambba ke or | Completed | 205000 | 202650 | 2021-04-02 | 2024-10-22
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of drain for coastal protection for Comm. / Construction of Storm Water Drain for Community | Works for Flood Control and Protection | 1702001042/FP/22012034626456 — Construction work of RCC Nala nirman - parsuram ke makan ke samane se bamba ke or | Ongoing | 113000 | 111385 | 2022-02-10
ATER | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of drain for coastal protection for Comm. / Construction of Storm Water drain for coastal protection for Community | Works for Flood Control and Protection | 1702001042/FP/22012034637621 — RCC Nala - govt midil school se talab ke or | Closed | 46000 | 0 | 2024-01-08
ATER | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702001042/FP/22012034639734 — Kachha nala nirman - ravindra singh ke khet se tirahe ke or | Closed | 0 | 0 | 2024-01-21
ATER | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of drain for coastal protection for Comm. / Construction of Storm Water drain for coastal protection for Community | Works for Flood Control and Protection | 1702001042/FP/22012034639899 — Flood diversion channel- ravindra singh ke khet se tirahe ke or | Closed | 241263.52 | 0 | 2024-01-21
ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001042/IF/22012034305871 — Cons. OF Compost Pit- Rajendra Singh/ Amar Singh | Deleted | 12000 | 0 | 2016-12-05
ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001042/IF/22012034305872 — Cons. of Compost Pit- Jaynarayan/ Habaldar | Deleted | 12000 | 0 | 2016-12-05
ATER | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702001042/IF/22012034352800 — प्रधानमंत्री सड़क पुराने रेलबे स्टेशन से कुशमार तक भुजपुरा | Completed | 335000 | 6192 | 2017-07-13 | 2020-10-20
ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1702001042/IF/22012034685737 — sok pit - ramsiya | Closed | 0 | 0 | 2021-01-21
ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1702001042/IF/22012034685741 — sok pit - upendra prajapati | Closed | 0 | 0 | 2021-01-21
ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1702001042/IF/22012034685742 — sok pit - uttam singh bhagel | Closed | 0 | 0 | 2021-01-21
ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1702001042/IF/22012034685745 — sokpit - ramkaran | Closed | 0 | 0 | 2021-01-21
ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1702001042/IF/22012034685751 — sok pit - Maheshwari | Closed | 0 | 0 | 2021-01-21
ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1702001042/IF/22012034710990 — sok pit - lakhami chand/ ramjeet | Closed | 0 | 0 | 2021-04-14
ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1702001042/IF/22012034710991 — sokpit - sudhakar karaiya / kishan | Closed | 0 | 0 | 2021-04-14
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1702001042/IF/22012034710994 — sokpit - bheeshm singh | Closed | 0 | 0 | 2021-04-14
ATER | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001042/IF/9926721291 — Cattle shed Ramswrup | Completed | 44200 | 42057 | 2014-03-03 | 2016-02-15
ATER | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001042/IF/9926721292 — cattle shed Munnalal | Completed | 44200 | 42057 | 2014-03-03 | 2016-02-15
ATER | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001042/IF/9926721293 — cattle shed Kaliyan | Completed | 44200 | 42057 | 2014-03-03 | 2016-02-15
ATER | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001042/IF/9926721294 — cattle shed Rameswar | Completed | 44200 | 42057 | 2014-03-03 | 2016-02-15
ATER | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001042/IF/9926721295 — Cattle shed Jasram | Completed | 44200 | 42057 | 2014-03-03 | 2016-02-15
ATER | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001042/IF/9926721296 — cattle shed ashok | Completed | 44200 | 42057 | 2014-03-03 | 2016-02-15
ATER | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001042/IF/9926721297 — cattle shed Ranbeer | Completed | 44200 | 32794 | 2014-03-03 | 2016-07-30
ATER | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001042/IF/9926721298 — cattle shed Angad singh | Completed | 44200 | 32794 | 2014-03-03 | 2016-08-30
ATER | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001042/IF/9926721299 — cattle shed badshah singh | Completed | 44200 | 32794 | 2014-03-03 | 2016-07-30
ATER | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001042/IF/9926721300 — Cattle shed Hari singh | Completed | 44200 | 32794 | 2014-03-03 | 2016-07-30
ATER | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001042/IF/9926721301 — cattle shed Balbeer singh | Completed | 44200 | 42057 | 2014-03-03 | 2016-02-15
ATER | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001042/IF/9926721302 — Cattle shed Parasram | Completed | 44200 | 32794 | 2014-03-03 | 2016-07-30
ATER | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001042/IF/9926721303 — Cattle shed Jagdeesh | Completed | 44200 | 42057 | 2014-03-03 | 2016-02-15
ATER | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001042/IF/9926721304 — Cattle shed VishvNath | Completed | 44200 | 42057 | 2014-03-03 | 2016-02-15
ATER | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001042/IF/9926721305 — Cattle Shed Prabhakar | Deleted | 44200 | 0 | 2014-01-26
ATER | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001042/IF/9926721306 — Cattle shed Jagdeesh | Completed | 44200 | 42057 | 2014-03-03 | 2016-02-15
ATER | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001042/IF/9926721307 — cattle Shed Rameshwer | Completed | 44200 | 42057 | 2014-03-03 | 2016-02-15
ATER | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001042/IF/9926721308 — Cattle shed Dileep singh | Completed | 44200 | 42057 | 2014-03-03 | 2016-02-15
ATER | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001042/IF/IAY/247497 — Construction of IAY House -IAY REG. NO. MP1770669 | Completed | 15030 | 15216 | 2017-02-09 | 2018-11-13
ATER | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001042/IF/IAY/247658 — Construction of IAY House -IAY REG. NO. MP1777873 | Completed | 15030 | 14148 | 2017-02-09 | 2018-08-01
ATER | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001042/IF/IAY/248080 — Construction of IAY House -IAY REG. NO. MP1793609 | Completed | 15030 | 15216 | 2017-02-09 | 2018-11-13
ATER | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001042/IF/IAY/4284691 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113464345 | Physically Completed | 18360 | 3978 | 2023-06-05 | 2024-11-21
ATER | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702001042/IF/IAY/4742235 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113464414 | Approved | 27000 | 0 | 2024-10-04
ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702001042/IF/IAY/5560551 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113463950 | Ongoing | 27000 | 3132 | 2025-11-19
ATER | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702001042/IF/IAY/5561679 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113464248 | Approved | 27000 | 0 | 2025-02-24
ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702001042/LD/22012034313218 — Shanti Dham- Kushmar, Bhujpura | Completed | 245000 | 244811 | 2017-05-17 | 2018-12-28
ATER | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001042/LD/3799397521 — land develoment sheela | Deleted | 26400 | 0 | 2013-04-14
ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1702001042/PG/22012034311341 — Play Ground- Kusmar, Bhujpura | Deleted | 186000 | 0 | 2017-01-28
ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001042/RC/22012034176445 — c.c. road bhajan lal ke makan se | Completed | 80000 | 42048 | 2014-01-06 | 2014-03-20
ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001042/RC/22012034191415 — cc road radhelal ke gonda to ram lal gonda | Completed | 141000 | 39996 | 2014-02-10 | 2016-03-25
ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001042/RC/22012034226220 — C.C.Raod Surendra Singh Ke Dwar Se Bholaram Ke Dwar Ki OR | Deleted | 0 | 0 | 2014-01-26
ATER | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001042/RC/22012034230930 — C.C. Roaad form Narend singh baghel house to Param | Completed | 104000 | 34854 | 2014-10-20 | 2016-03-23
ATER | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001042/RC/22012034231655 — C.C. Road from Prahlad singh house to Ramotaar to house | Completed | 270000 | 14130 | 2014-10-20 | 2015-03-30
ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001042/RC/22012034282579 — CC Road Dinesh sharma House to Ramlakhan Ojha house | Completed | 252000 | 234888 | 2015-08-10 | 2016-04-20
ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001042/RC/22012034288647 — CC Road from Ramesh house to Ashok house | Deleted | 224000 | 0 | 2015-12-14
ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001042/RC/22012034310052 — CC ROAD | Deleted | 0 | 0 | 2016-04-01
ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001042/RC/22012034324928 — C.C.Road Punchayat Bhawan Se Sudama Ke Ghar Ki Or | Completed | 107000 | 78168 | 2017-02-04 | 2018-12-18
ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001042/RC/22012034348078 — C C ROAD DINESH SHARMA KE DARWAJE SE BHAGIRATH KE DARWAJE TAK KUSHMAR | Completed | 132750 | 139056 | 2017-09-28 | 2020-09-28
ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001042/RC/22012034348249 — c c road ( rinku ke darwaje se talab ke or ) | Completed | 154875 | 128736 | 2017-09-28 | 2019-07-30
ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001042/RC/22012034373208 — cc road | Deleted | 0 | 0 | 2018-01-26
ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001042/RC/22012034381909 — cc road ( bhure ke darwaje se kashi ram ke darwaje & shala bhawan ke or ) | Completed | 69750 | 55332 | 2018-12-27 | 2019-05-15
ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001042/RC/22012034382427 — cc road | Deleted | 0 | 0 | 2017-10-02
ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001042/RC/22012034386556 — cc road bamma se chhakki lal ke darwaje ki ore | Completed | 93000 | 118836 | 2019-03-07 | 2019-12-01
ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001042/RC/22012034386557 — cc road bumma se rajendra ke darwaje ki ore pura | Deleted | 139500 | 0 | 2017-04-14
ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001042/RC/22012034396751 — सी सी रोड ( श्याम सिंह के दरवाजे से अमर सिंह के दरवाजे ) | Completed | 32000 | 32364 | 2018-10-09 | 2019-01-05
ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001042/RC/22012034396757 — सी सी रोड ( रैलवे लाईन से सेवाराम के मकान तक ) | Completed | 46500 | 45936 | 2018-10-09 | 2019-01-05
ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001042/RC/22012034398302 — सी सी रोड ( शा0 प्रा0 विधालय भुजपुरा परिसर मे ) | Completed | 46500 | 41760 | 2018-12-08 | 2018-12-30
ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001042/RC/22012034442352 — cc road | Deleted | 0 | 0 | 2019-01-26
ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001042/RC/22012034442518 — सी सी रोड ( ग्राम स्वराज परिसर मे भुजपुरा ) | Completed | 32813 | 30276 | 2019-03-03 | 2019-03-30
ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001042/RC/22012034446003 — सी सी रोड ( रामदत्त सिंह सरपंच के दरवाजे से महाराज सिंह के दरवाजे की ओर ) | Completed | 93000 | 89556 | 2019-03-07 | 2020-04-25
ATER | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001042/RC/22012034446004 — सी सी रोड ( मैन रोड से रामदास व रामकरन के मकान की ओर अ जा वस्ती ) | Completed | 69750 | 85536 | 2019-06-23 | 2019-12-01
ATER | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001042/RC/22012034468844 — c c road - angad singh ke makan se bhure sharmae and main road TO munna lal AND BADSHAH KE MAKAN KE | Completed | 120900 | 119680 | 2019-08-09 | 2020-02-01
ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001042/RC/22012034469071 — C C ROAD - KOK SINGH KE MAKAN SE SHRI NARAYAN KE MAKAN KE OR | Completed | 27900 | 26220 | 2020-06-04 | 2021-03-26
ATER | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001042/RC/22012034469072 — C C ROAD ( MAIN ROAD SE HAKIM SINGH KE MAKAN KE OR ) | Completed | 60450 | 48396 | 2019-10-15 | 2020-09-28
ATER | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001042/RC/22012034514700 — cc road | Deleted | 0 | 0 | 2019-10-02
ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702001042/RC/22012034524560 — sudoor road ( purane railway Line kadere pura se kushmar ke or ) | Closed | 0 | 0 | 2020-05-14
ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702001042/RC/22012034530164 — khet sadak ( bhujpura se shanti dham ke or ) | Deleted | 0 | 0 | 2020-05-05
ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001042/RC/22012034531870 — c c road ( balmukund ke makan se mukesh ke makan ke or ) | Completed | 18600 | 17100 | 2020-09-27 | 2020-12-15
ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702001042/RC/22012034534740 — sudoor road ( bhujpura se shanti dham ke or ) | Completed | 1473633.53 | 847474 | 2020-08-29 | 2024-10-22
ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001042/RC/22012034542395 — c c road ( abdul khan ke makan se master ke makan ke or ali nagar ) | Completed | 91800 | 83220 | 2020-09-27 | 2021-02-18
ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001042/RC/22012034556501 — c c road ( main road se keshwav & munna singh ke makan se kedar bhutariya ke dwar ke or ) | Completed | 61462 | 59280 | 2021-02-06 | 2021-03-26
ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001042/RC/22012034556506 — c c road ( Ummed ke makan se Ajmer ke goda ke or ) | Completed | 15862 | 14820 | 2021-02-27 | 2021-03-26
ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001042/RC/22012034556774 — c c road ( ummed ke makan se murari ke makan ke or ) | Completed | 19687 | 14820 | 2021-03-06 | 2021-06-25
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001042/RC/22012034597971 — c c road -megh singh ke makan se shashkiya madhaymik vidhalya railway line ke or bhujpura | Closed | 73125 | 0 | 2021-10-02
ATER | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1702001042/RC/22012034845152 — c c road laxminarayn ke darwaje se rajendra ke darwaje ke or bhujpura | Approved | 35000 | 0 | 2025-04-01
ATER | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1702001042/RC/22012034845250 — c c roaad kali mata mandir se phool singh ke makan ke or bhujpura | Approved | 115000 | 0 | 2025-04-14
ATER | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1702001042/RC/22012034845251 — c c road main road se rakesh ke darwaje ke or bhujpura | Approved | 35000 | 0 | 2025-04-14
ATER | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1702001042/RC/22012034845252 — C C Road - Pappu Ke Makan Se Raju Ke Makan Tak Balmik Ka Pura | Approved | 77000 | 0 | 2025-04-14
ATER | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001042/RC/240 — cc road govt. meddle schoole to bhujpura tak | Completed | 167000 | 164777 | 2012-04-06 | 2013-02-04
ATER | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001042/RC/422 — सीसी रोड प्र0म0 रोड से बावूराम के दरवाजे तक | Completed | 152400 | 150550 | 2012-09-11 | 2014-04-30
ATER | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001042/RC/423 — सी सी रोड शा0मा0वि0 मान सिह वघेल की ओर | Completed | 60000 | 52750 | 2012-10-30 | 2013-01-02
ATER | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001042/RS/22012034280686 — Toilet 10 | Completed | 54000 | 53929 | 2014-11-10 | 2016-05-30
ATER | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001042/RS/22012034281329 — Maryada rameshwar,ramsiya,sudhakar,ramprakash,ramnath,ramswaroop,koksingh,dasrath,ahibaran,shyam | Completed | 54000 | 53929 | 2014-11-16 | 2016-05-30
ATER | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex for Community | Community Sanitary Complex | 1702001042/RS/22012034587634 — community senetry complex bhujpura | Ongoing | 43000 | 14433 | 2022-09-26
ATER | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Vermi Compost structure for Groups / Construction of Vermi Compost Structure for Groups | Construction of NADEP/Vermi Compost Pit | 1702001042/RS/22012034692111 — Segrigation sed - bhujpura | Ongoing | 33000 | 18343 | 2023-07-09
ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702001042/WC/22012034558514 — Talab nirman - mandir ke paas bhujpura | Physically Completed | 1006164.42 | 647023 | 2020-09-22 | 2026-04-29
ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702001042/WC/22012034558523 — Talab nirman - shakya thok kushmar | Completed | 724316.77 | 544510 | 2020-06-27 | 2024-10-22
ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1702001042/WC/22012034631222 — sokpit - PANCHAYAT BHAWAN KE PASS | Completed | 4600 | 4632 | 2021-04-23 | 2025-05-11
ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1702001042/WC/22012034631227 — SOK PIT - MURARI KE GHAR KE PASS | Closed | 4600 | 0 | 2021-01-21
ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1702001042/WC/22012034634243 — talab nirman - baghel thok bhujpura | Suspended | 1006283.67 | 488286 | 2021-04-23
ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1702001042/WC/22012034634244 — Talab nirman - maharaj singh ke makan ke pass kushmar | Closed | 0 | 0 | 2021-01-21
ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702001042/WC/22012034769446 — roof water Harvesting work - panchayat bhawan bhujpura | Closed | 0 | 0 | 2021-04-14
ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702001042/WC/22012034769448 — roof water Harvesting work - Aganwadi kendra bhujpura | Closed | 0 | 0 | 2021-04-14
ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702001042/WC/22012034769449 — roof water Harvesting work - govt school kushmar | Closed | 0 | 0 | 2021-04-14
ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702001042/WC/22012034769450 — roof water Harvesting work - govt school kushwmar | Deleted | 0 | 0 | 2021-04-14
ATER | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1702001042/WC/22012034791951 — Sok pit - upendra singh / raj kishor | Completed | 4600 | 4488 | 2022-11-05 | 2026-04-18
ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1702001042/WC/22012034791954 — Sok pit - hakim singh | Closed | 4600 | 0 | 2021-04-14
ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1702001042/WC/22012034791957 — Sok pit - kok singh / umram | Closed | 4600 | 0 | 2021-04-14
ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1702001042/WC/22012034791965 — Sok pit - maheshwari | Closed | 4600 | 0 | 2021-04-14
ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1702001042/WC/22012034791970 — Sok pit - uttam singh / kedar singh | Closed | 4600 | 0 | 2021-04-14
ATER | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1702001042/WC/22012034791975 — Sok pit - veerbal singh | Completed | 4600 | 4488 | 2022-09-11 | 2025-05-11
ATER | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1702001042/WC/22012034910766 — talab nirman | Closed | 0 | 0 | 2022-02-10
ATER | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702001042/WC/22012035139660 — talab nirman - kushmar | Closed | 0 | 0 | 2023-08-16
ATER | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702001042/WC/22012035142935 — Earth bund - gram kushmar | Closed | 0 | 0 | 2023-08-16
ATER | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Desilting / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1702001042/WH/19955492 — Desilting of talab | Deleted | 0 | 0 | 2016-01-26
ATER | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1702001042/WH/19960010 — Renovatiom Of Pond- Pooran Singh Ke Kunya Ke Pass, Kusmaar | Deleted | 95085 | 0 | 2017-05-17