## Work List
Exported on: 2026-09-05 13:13:21
Filters applied:
Data source: MGNREGA + VBGRAMG
District: BHIND
Block: All
Panchayat: KADHURA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Bharat Nirman Seva Kendra / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1702001047/AV/22012034372942 — Samudayak Bhawan Nirman Kadora | Completed | 75000 | 78300 | 2018-05-09 | 2020-01-25
ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1702001047/AV/22012034534331 — आगनवाडी भवन कदौरा | Completed | 180000 | 179930 | 2020-09-03 | 2021-01-05
ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1702001047/AV/22012034535330 — Samudayak Swacchata Parishar- Kadora | Completed | 43000 | 42940 | 2020-09-17 | 2021-01-05
ATER | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of drain for coastal protection for Comm. / Construction of Storm Water drain for coastal protection for Community | Works for Flood Control and Protection | 1702001047/FP/22012034629021 — Kaccha Nala Nirman Rustam Singh Baghel Ke Gonda Ke Neeche Se Remja Bali Mata Ki Or, Kadora | Completed | 894300.22 | 780504 | 2022-05-21 | 2022-11-27
ATER | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of drain for coastal protection for Comm. / Construction of Storm Water drain for coastal protection for Community | Works for Flood Control and Protection | 1702001047/FP/22012034629022 — Kaccha Nala Nirman Sonu Balmik Ke Ghar Ke Neeche Se Behad Mai Shantidham Ki Or, Kadora | Completed | 860586.61 | 749700 | 2022-05-25 | 2022-11-27
ATER | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702001047/IF/22012034297618 — Fram bunding Vijay shingh | Completed | 32000 | 33066 | 2016-08-30 | 2016-09-25
ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702001047/IF/22012034297620 — Fram bunding Bateswar dayal | Deleted | 21300 | 0 | 2015-10-02
ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702001047/IF/22012034297622 — Fram bunding Jabarshingh | Deleted | 26600 | 0 | 2015-10-02
ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702001047/IF/22012034297624 — Fram bunding Ram dulare | Deleted | 21300 | 0 | 2015-10-02
ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702001047/IF/22012034297625 — Fram bunding Rupshingh | Deleted | 26600 | 0 | 2015-10-02
ATER | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001047/IF/22012034297626 — Cattle shed Rada kishan | Completed | 90000 | 89618 | 2016-08-30 | 2017-09-01
ATER | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001047/IF/22012034297627 — Cattle shed Ramdulare | Deleted | 90000 | 0 | 2016-08-29
ATER | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001047/IF/22012034297628 — Cattle shed Jagat narayan | Completed | 90000 | 89618 | 2016-08-30 | 2017-09-01
ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001047/IF/22012034300822 — Cons. OF Compost Pit- Pancham/ Raghuveer | Deleted | 12000 | 0 | 2016-10-04
ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001047/IF/22012034300823 — Cons. Of Compost Pit- Jabar Singh/ Kalyan Singh | Deleted | 12000 | 0 | 2016-10-04
ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001047/IF/22012034300825 — Cons. OF Compost Pit- Krishna bihari/ Ramdulare | Deleted | 12000 | 0 | 2016-10-04
ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001047/IF/22012034300826 — Con. Of Compost Pit- Ajeet Kumar/ Keshav | Deleted | 12000 | 0 | 2016-10-04
ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001047/IF/22012034300827 — Cons. Of Compost Pit- Vishvanath/ Jagatnarayan | Deleted | 12000 | 0 | 2016-10-04
ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001047/IF/22012034300828 — Cons. Of Compost Pit- Kalicharan/ Dhaniram | Deleted | 12000 | 0 | 2016-10-04
ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001047/IF/22012034300829 — Cons. OF Compost Pit- Sonu/ Radha krishna | Deleted | 12000 | 0 | 2016-10-04
ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001047/IF/22012034300830 — Cons. OF Compost Pit- Kamalkishore/ Ramratan | Deleted | 12000 | 0 | 2017-02-13
ATER | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702001047/IF/22012034352525 — वृक्षारोपण कार्य शान्तिधाम के पास कदोरा | Completed | 335000 | 5160 | 2017-06-20 | 2020-10-20
ATER | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702001047/IF/22012034368594 — vriksharopan punchayat bhawan ke pass talab par kadora | Closed | 335000 | 0 | 2017-07-22
ATER | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702001047/IF/22012034373731 — वृक्षारोपण कार्य कदोरा | Deleted | 335000 | 0 | 2017-06-05
ATER | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702001047/IF/22012034373776 — वृक्षारोपण कार्य कदोरा | Deleted | 335000 | 0 | 2017-06-05
ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Upland Bench Terrace for Individual / Construction of Upland Bench Terrace for Individual | Terracing | 1702001047/IF/22012034571878 — Med Bandhan Karya- Krishnabihari/ramdulare | Completed | 17286.37 | 14820 | 2020-07-23 | 2020-09-22
ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Upland Bench Terrace for Individual / Construction of Upland Bench Terrace for Individual | Terracing | 1702001047/IF/22012034571880 — Med Bandhan Karya- Bheemsen/Rajaram | Completed | 15557.73 | 13680 | 2020-07-23 | 2020-09-22
ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Upland Bench Terrace for Individual / Construction of Upland Bench Terrace for Individual | Terracing | 1702001047/IF/22012034571881 — Med Bandhan Karya- Tundepal/ Harpal | Completed | 13444.96 | 12540 | 2020-07-02 | 2020-09-22
ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Upland Bench Terrace for Individual / Construction of Upland Bench Terrace for Individual | Terracing | 1702001047/IF/22012034571882 — Med Bandhan Karya- Sewaram/Jimipal | Completed | 14751.03 | 12630 | 2020-07-02 | 2021-08-20
ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Upland Bench Terrace for Individual / Construction of Upland Bench Terrace for Individual | Terracing | 1702001047/IF/22012034571883 — Med Bandhan Karya- Ratiram/Jimipal | Completed | 15557.73 | 12540 | 2020-07-02 | 2020-09-22
ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Upland Bench Terrace for Individual / Construction of Upland Bench Terrace for Individual | Terracing | 1702001047/IF/22012034723224 — Med Bandhan karya-Radha krishna/Asharam, KAdora | Completed | 28732.19 | 23160 | 2021-04-29 | 2021-06-18
ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Upland Bench Terrace for Individual / Construction of Upland Bench Terrace for Individual | Terracing | 1702001047/IF/22012034723226 — Med Bandhan Karya- Beerbhadra/Gopichandra, Kadora | Completed | 29239.12 | 23160 | 2021-04-29 | 2021-06-18
ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Upland Bench Terrace for Individual / Construction of Upland Bench Terrace for Individual | Terracing | 1702001047/IF/22012034723229 — Med Bandhan Karya-Ramkresh/Ram dulare, Kadora | Completed | 29577.21 | 23160 | 2021-04-29 | 2021-06-18
ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Upland Bench Terrace for Individual / Construction of Upland Bench Terrace for Individual | Terracing | 1702001047/IF/22012034723231 — Med Bandhan karya- Hariom Sharma/ Dayaram, Kadora | Completed | 27887.02 | 23160 | 2021-04-29 | 2021-06-18
ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Upland Bench Terrace for Individual / Construction of Upland Bench Terrace for Individual | Terracing | 1702001047/IF/22012034723234 — Med Bandhan Karya- Ajay Kumar/ Rambaran, Kadora | Completed | 28225.12 | 23160 | 2021-04-29 | 2021-06-18
ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Upland Bench Terrace for Individual / Construction of Upland Bench Terrace for Individual | Terracing | 1702001047/IF/22012034724844 — Med Bandhan Karya- Brij bilas/ Matadeen, Kadora | Completed | 25351.94 | 20844 | 2021-05-06 | 2021-06-18
ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Upland Bench Terrace for Individual / Construction of Upland Bench Terrace for Individual | Terracing | 1702001047/IF/22012034724847 — Med Bandhan Karya- Visvanath/Jagatnarayan, Kadora | Completed | 25689.9 | 23160 | 2021-04-29 | 2021-06-18
ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Upland Bench Terrace for Individual / Construction of Upland Bench Terrace for Individual | Terracing | 1702001047/IF/22012034724851 — Med Bandhan Karya-Roop Singh/ Kishnu Singh, Kadora | Completed | 25858.87 | 23160 | 2021-04-29 | 2021-06-18
ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Upland Bench Terrace for Individual / Construction of Upland Bench Terrace for Individual | Terracing | 1702001047/IF/22012034724855 — Med Bandhan Karya- Vijay Singh/Dal Chand, Kadora | Completed | 25013.85 | 23160 | 2021-04-29 | 2021-06-18
ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Upland Bench Terrace for Individual / Construction of Upland Bench Terrace for Individual | Terracing | 1702001047/IF/22012034724860 — Med Bandhan karya- Dansahay/Dhaniram, Kadora | Completed | 24506.78 | 19686 | 2021-04-29 | 2021-06-18
ATER | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001047/IF/22012034820847 — Khet Talab Nirman Vedpal Ke Khet Par, Kadora | Completed | 338902.57 | 265182 | 2021-07-15 | 2022-02-02
ATER | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001047/IF/22012034820850 — Khet Talab Nirman Ashutosh Ke Khet par, Kadora | Completed | 338902.57 | 267498 | 2021-07-15 | 2022-01-02
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001047/IF/22012034848803 — Nandep Nirman Karya- Dinesh Sharma/Rambaran Ke Ghar ke Pass, Kadora | Closed | 0 | 0 | 2021-08-15
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001047/IF/22012034848804 — Nandep Nirman karya- Santosh Sharma Ke Ghar Ke pass, Kadora | Closed | 0 | 0 | 2021-08-15
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001047/IF/22012034848806 — Nandep Nirman Karya-Jay Shri Ram Ke Ghar Ke Pass, Kadora | Closed | 0 | 0 | 2021-08-15
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001047/IF/22012034848809 — Nandep Nirman karya- Jabar Singh/Kalyan Singh Ke Ghar Ke Pass, Kadora | Closed | 0 | 0 | 2021-08-15
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001047/IF/22012034848812 — Nandep Nirman Karya- Visvanath Ke Ghar Ke Pass, Kadora | Closed | 0 | 0 | 2021-08-15
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001047/IF/22012034848818 — Nandep Nirman karya- Siddhar Singh Ke Ghar Ke pass, Kadora | Closed | 0 | 0 | 2021-08-15
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001047/IF/22012034848822 — Nandep Nirman Karya- ramkaran Ke Ghar Ke pass, Kadora | Closed | 0 | 0 | 2021-08-15
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001047/IF/22012034848826 — Nandep Nirman Karya-Shyam Singh Ke Ghar Ke Pass, Kadora | Closed | 0 | 0 | 2021-08-15
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001047/IF/22012034848829 — Nandep Nirman Karya- Bhan Singh Ke Ghar Ke Pass, Kadora | Closed | 0 | 0 | 2021-08-15
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001047/IF/22012034848830 — Nandep Nirman Karya- Ramhet Ke Ghar Ke Pass, Kadora | Closed | 0 | 0 | 2021-08-15
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001047/IF/22012034848832 — Nandep Nirman Karya- Roop Singh ke Ghar ke pass, Kadora | Closed | 0 | 0 | 2021-08-15
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001047/IF/22012034848835 — Nandep Nirman Karya-Rajveer Singh Ke Ghar ke Pass, Kadora | Closed | 0 | 0 | 2021-08-15
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001047/IF/22012034848836 — Nandep nirman Karya-Vivek Sharma Ke Ghar Ke pass, kadora | Closed | 0 | 0 | 2021-08-15
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001047/IF/22012034848840 — Nandep Nirman Karya- Krishna Bihari Ke Ghar Ke Pass, Kadora | Closed | 0 | 0 | 2021-08-15
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001047/IF/22012034848841 — Nandep Nirman Karya- Vinod Singh ke Ghar Ke Pass, Kadora | Closed | 0 | 0 | 2021-08-15
ATER | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Mini Percolation Tank for Individuals / Construction of Mini Percolation Tank for Individuals | Construction of Percolation Tank | 1702001047/IF/22012035416995 — khet talab nirman karya siyaram ke khet par badapura | Closed | 147621.16 | 0 | 2025-05-12
ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001047/IF/22012035522305 — khet talab nirman karya siyaram ke khet par badapura | New | 0 | 0 | 2025-04-14
ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001047/IF/22012035522458 — khet talab nirman karya siyaram ke khet par badapura | Completed | 147621.16 | 103507.62 | 2025-05-18 | 2026-04-15
ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001047/IF/22012035522504 — khet talab nirman karya devendra ke khet par badapura | Completed | 147621.16 | 105149.94 | 2025-05-19 | 2026-04-13
ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001047/IF/22012035522548 — khet talab nirman karya jaynarayan ke khet par badapura | Completed | 147621.16 | 109524.16 | 2025-05-19 | 2026-04-13
ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001047/IF/22012035522568 — khet talab nirman karya asharam ke khet par badapura | Physically Completed | 147621.16 | 109539.72 | 2025-05-19 | 2026-04-15
ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001047/IF/22012035522588 — khet talab nirman karya kashiram ke khet par khinipura | Suspended | 147621.16 | 106730.52 | 2025-05-19
ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001047/IF/22012035522604 — khet talab nirman karya siyaram ke khet par badapura | New | 0 | 0 | 2025-04-14
ATER | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001047/IF/IAY/134099 — Construction of IAY House -IAY REG. NO. MP-02-001-047-001/17 | Completed | 14310 | 15364 | 2016-07-26 | 2017-09-01
ATER | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001047/IF/IAY/3894090 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149116528 | Completed | 18360 | 21342 | 2023-04-20 | 2025-05-06
ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001047/IF/IAY/4530720 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149116552 | Physically Completed | 23490 | 6264 | 2025-05-03 | 2026-07-19
ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001047/IF/IAY/4530721 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149116567 | Ongoing | 27000 | 3132 | 2025-05-03
ATER | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001047/IF/IAY/4868438 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149116471 | Approved | 27000 | 0 | 2024-10-28
ATER | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001047/IF/IAY/4868439 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149116495 | Approved | 27000 | 0 | 2024-10-28
ATER | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001047/IF/IAY/80091 — Construction of IAY House -IAY REG. NO. MP-02-001-047-001/4 | Completed | 14310 | 14362 | 2016-07-26 | 2017-09-01
ATER | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001047/LD/21 — मेढ बन्‍धान | Completed | 34200 | 24570 | 2009-06-28 | 2009-01-14
ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1702001047/LD/22012034293693 — Shantidham Vikas - Kadora | Completed | 641000 | 640098.4 | 2016-11-22 | 2017-10-15
ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1702001047/LD/22012034312228 — Shantidham- Kadora (Badapura) | Completed | 245000 | 230896 | 2017-05-30 | 2020-01-26
ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1702001047/LD/22012034313051 — Shantidham- Baghelan ka Pura, Kadora | Completed | 245000 | 10320 | 2017-05-16 | 2020-02-22
ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1702001047/LD/22012034313052 — Shanti Dham- Khinni ka pura, Kadora | Completed | 245000 | 227800 | 2017-05-16 | 2020-01-26
ATER | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001047/LD/394 — earth bunding rambeer / ganga singh | Deleted | 0 | 0 | 2010-01-26
ATER | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001047/LD/395 — earth bunding ramlal/harivilas | Completed | 0 | 19200 | 2010-10-22 | 2010-10-22
ATER | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001047/LD/410 — Earth bundig Ramveer/ganga singh | Completed | 0 | 21000 | 2010-09-08 | 2010-09-13
ATER | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001047/LD/411 — Earth bunding rameswar/Denanath | Completed | 0 | 19200 | 2010-10-29 | 2011-10-16
ATER | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001047/LD/412 — Earth bunding ramlal/Raghunath | Completed | 0 | 19800 | 2010-09-01 | 2010-09-06
ATER | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001047/LD/501 — Land develoment Munnidevi | Completed | 0 | 14640 | 2011-09-06 | 2011-09-11
ATER | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001047/LD/502 — Land develoment Suresh | Completed | 0 | 21716 | 2011-10-04 | 2011-10-09
ATER | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001047/LD/503 — Land develoment Samokhan | Completed | 0 | 15494 | 2011-09-13 | 2011-09-18
ATER | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001047/LD/504 — Land develoment Gokul prased | Completed | 0 | 21106 | 2011-10-18 | 2011-10-23
ATER | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001047/LD/505 — land develoment Rughveer | Completed | 0 | 17324 | 2011-09-20 | 2011-09-25
ATER | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001047/LD/506 — Land develoment | Completed | 0 | 15860 | 2011-10-11 | 2011-10-26
ATER | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001047/LD/507 — Land develoment Naryan | Completed | 0 | 20130 | 2011-09-27 | 2011-10-02
ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1702001047/PG/9425895796 — Play Ground- Kadora | Completed | 186000 | 92076 | 2017-03-22 | 2020-01-26
ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001047/RC/22012034194418 — C.C.Road Ramsebak ke ghar se malkhan ke darbaje ki | Completed | 207000 | 201935.9 | 2013-12-17 | 2014-04-30
ATER | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001047/RC/22012034230949 — C.C. Road from MAinroad to Rameshver dayal house a | Completed | 74000 | 73838 | 2014-10-28 | 2014-12-10
ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001047/RC/22012034287622 — cc road from Atibal house to Bhagbati charn sharma house | Completed | 179200 | 164062 | 2015-10-27 | 2015-12-20
ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702001047/RC/22012034292630 — Graval road from Panchayat bulding to Hnuman mandir | Deleted | 1500000 | 0 | 2015-12-15
ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702001047/RC/22012034292848 — Graval road from Rameshvarm house to Pthasviys Mata | Deleted | 704000 | 0 | 2015-12-15
ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702001047/RC/22012034292852 — Graval road from Muktidham to Jaynarayan house | Completed | 1407000 | 986252 | 2015-12-15 | 2016-10-25
ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001047/RC/22012034309792 — CC road Maniram house to Ramnath house | Completed | 188000 | 185554 | 2016-09-26 | 2020-01-24
ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001047/RC/22012034315550 — C.C.Road Rambaran Singh Baghel Ke Darwaje Se Punchayat Bhawan Ki Or | Completed | 142000 | 142788 | 2017-02-22 | 2020-01-26
ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001047/RC/22012034327424 — C.C. Road Malkhan Singh Ke Darwaje Se Jagnath Ke Darwaje Tak | Completed | 278748 | 280764 | 2017-05-16 | 2020-01-25
ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702001047/RC/22012034340389 — Sudur Samprak Kadora Se Khinni pura tak | Completed | 1100000 | 598080 | 2017-06-06 | 2020-02-22
ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702001047/RC/22012034340398 — Sudur Samprak Gram Kadora Se Hanuman Mandir Tak | Completed | 1430000 | 837576 | 2017-06-06 | 2020-06-07
ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001047/RC/22012034348051 — C C ROAD SEWARM KE DARWAJE SE RAM DULARE JATAV TAK | Completed | 442500 | 82560 | 2017-09-12 | 2020-01-26
ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001047/RC/22012034348053 — C C ROAD SIYARAM KE DARWAJE SE SANJU KE GHAR TAK | Completed | 61950 | 74648 | 2017-09-26 | 2020-01-26
ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001047/RC/22012034366464 — C.C.Raod Main Road Se Arvind Mama Ke Ghar Tak, Kadora | Completed | 135000 | 133632 | 2018-10-05 | 2020-01-26
ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001047/RC/22012034373257 — cc road | Deleted | 0 | 0 | 2018-01-26
ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001047/RC/22012034381936 — cc road | Closed | 0 | 0 | 2017-10-02
ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001047/RC/22012034382459 — cc road | Closed | 0 | 0 | 2017-10-02
ATER | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001047/RC/22012034388904 — C.C.Raod Mai Nali Shaiyad Baba Ke Than Se Rameshwar Ke ghar Hote Hue Rapta Talab Ki Or, Kadora | Completed | 74400 | 69696 | 2019-11-06 | 2020-02-22
ATER | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001047/RC/22012034388905 — C.C.Raod Mai Nali School Se Munna Lal Ke Ghar Ki or, Kadora | Completed | 74400 | 72864 | 2019-08-21 | 2020-02-22
ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001047/RC/22012034442382 — cc road | Closed | 0 | 0 | 2019-01-26
ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001047/RC/22012034469292 — सी.सी.रोड मय नाली सुरेश के दरवाजे से ख़ुशी राम के दरवाजे की ओर, कदोरा | Completed | 69750 | 47880 | 2020-07-23 | 2021-03-02
ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001047/RC/22012034509401 — सी.सी.रोड निर्माण मुरली प्रजापति के दरवाजे से कैलाशनारायण बरुआ के दरवाजे की ओर, कदोरा | Completed | 69750 | 64560 | 2020-07-27 | 2021-08-20
ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001047/RC/22012034510271 — सी.सी.रोड निर्माण मेवाराम के दरवाजे से पुष्पेन्द्र बरुआ के दरवाजे की ओर , कदोरा | Completed | 60000 | 60040 | 2020-07-27 | 2021-01-11
ATER | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001047/RC/22012034514734 — cc road | Closed | 0 | 0 | 2019-10-02
ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702001047/RC/22012034532263 — Sudur Samprak Sadak Ater Porsa Marg Se Aaganwadi Badapura Ki Or, Kadora | Completed | 1200936.07 | 1193121.26 | 2020-08-13 | 2021-03-02
ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702001047/RC/22012034532452 — सुदूर संपर्क सड़क अटेर पोरसा मार्ग से आँगनवाड़ी की ऒर कदोरा | Closed | 0 | 0 | 2020-07-03
ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001047/RC/22012034538239 — C.C.Raod Mai Nali Mata Ke Mandir Se Munnalal Jatav Ke Darwaje Ki Or, Kadora | Completed | 93000 | 92720 | 2020-11-26 | 2021-01-10
ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001047/RC/22012034562208 — C.C.Raod Nirman Rajkumar Ke Darwaje Se Hukum Singh Driver Ke Darwaje Ki Or, Kadora | Deleted | 17213 | 0 | 2021-01-26
ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001047/RC/22012034562211 — C.C.Raod Ram Kresh Rathore Ke Darwaje Se Ram Bharose Rathore Ke Darwaje Ki Or,Kadora | Deleted | 93000 | 0 | 2021-01-26
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001047/RC/22012034586897 — C.C.Raod Sanjay Singh Rathore Ke Makan Se Vasudev Ke Makan Ki Or, Khinnipura, Kadora | Completed | 57375 | 57900 | 2021-10-25 | 2022-01-02
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001047/RC/22012034586900 — C.C.Road Ram Kresh Ke Darwaje Se Bacchulal Ke Darwaje Ki Or, Kadora | Completed | 46500 | 42846 | 2021-10-25 | 2022-01-02
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702001047/RC/22012034604074 — Sudur Samprak Sadak Jaykishore Ke Ghar Ke Neeche Se Kali Mata Mandir Ki Or, Kadora | Closed | 0 | 0 | 2022-01-19
ATER | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702001047/RC/22012034613527 — Sudur Samprak Sadak Jaykishore Nai ke Ghar Ke Neeche Se Kali Mata Mandir Ki or, Kadora | Closed | 0 | 0 | 2022-04-14
ATER | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702001047/RC/22012034613528 — Sudur Samprak Sadak Jaykishore Nai ke Ghar Ke Neeche Se Kali Mata Mandir Ki or, Kadora | Closed | 0 | 0 | 2022-04-14
ATER | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702001047/RC/242 — rual connectivity bada pura se porsa road ki ror | Completed | 500000 | 451649.7 | 2012-02-20 | 2014-12-20
ATER | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702001047/RC/27 — पहुॅच मार्ग | Completed | 472000 | 405600 | 2009-11-22 | 2008-02-14
ATER | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001047/RC/325 — C.C. nirman main road pachyat bhavan tak | Completed | 0 | 24764 | 2012-03-18 | 2013-03-30
ATER | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001047/RC/326 — C.C. road Hunman mader de school tak | Completed | 0 | 107296 | 2012-07-31 | 2013-03-30
ATER | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001047/RC/501 — haman mander se gutti baghel ke makan tak | Completed | 165500 | 165312 | 2013-03-14 | 2013-11-30
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702001047/RS/22012034560391 — Soak Pit Nirman- Sonu Sharma Ke Ghar Ke Pass, Kadora | Closed | 4600 | 0 | 2021-09-07
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702001047/RS/22012034560392 — Soak Pit Nirman- Ajay Singh Ke Ghar Ke Pass, Kadora | Closed | 4600 | 0 | 2021-09-07
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702001047/RS/22012034560395 — Soak Pit Nirman- Bheekam Singh Ke Ghar Ke Pass, Kadora | Closed | 4600 | 0 | 2021-09-07
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702001047/RS/22012034560398 — Soak Pit Nirman- Ramkresh Ke Ghar ke pass, Kadora | Closed | 4600 | 0 | 2021-09-07
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702001047/RS/22012034560399 — Soak Pit Nirman- Ashok Singh Ke Ghar ke pass, Kadora | Closed | 4600 | 0 | 2021-09-07
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702001047/RS/22012034560400 — Soak Pit Nirman- Ram Dulare Ke Ghar ke pass, Kadora | Closed | 4600 | 0 | 2021-09-07
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702001047/RS/22012034560402 — Soak Pit Nirman- Yogesh Ke Ghar Ke pass, Kadora | Closed | 4600 | 0 | 2021-09-07
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702001047/RS/22012034560412 — Soak Pit Nirman- Barua Ke Ghar Ke Pass, Kadora | Closed | 4600 | 0 | 2021-09-07
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702001047/RS/22012034560414 — Soak Pit Nirman- Harnarayan Ke Ghar Ke Pass, Kadora | Closed | 4600 | 0 | 2021-09-07
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702001047/RS/22012034560416 — Soak Pit Nirman- Vijay Singh Baghel Ke Ghar Ke pass, Kadora | Closed | 4600 | 0 | 2021-09-07
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702001047/RS/22012034560421 — Soak Pit Nirman- Govt. Primary School Parisar Mai, Kadora | Closed | 4600 | 0 | 2021-09-07
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702001047/RS/22012034560423 — Soak Pit Nirman- Ramlal Ke Ghar Ke pass, Kadora | Closed | 4600 | 0 | 2021-09-07
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702001047/RS/22012034560424 — Soak Pit Nirman- Hariom Sharma Ke Ghar Ke pass, Kadora | Closed | 4600 | 0 | 2021-09-07
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702001047/RS/22012034560432 — Soak Pit Nirman- Vinod Kumar Ke Ghar Ke Pass, Kadora | Closed | 4600 | 0 | 2021-09-07
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702001047/RS/22012034560437 — Soak Pit Nirman- Nariya Mai mandir Ke Pass, Kadora | Closed | 4600 | 0 | 2021-09-07
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Berkeley Compost Pit for Groups / Construction of Berkeley Compost Pit for Groups | Construction of NADEP/Vermi Compost Pit | 1702001047/RS/22012034562969 — सेग्रीगेशन शैड निर्माण कार्य- कदोरा | Completed | 30076 | 28950 | 2021-09-25 | 2021-10-20
ATER | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1702001047/RS/22012034662326 — Kachcha Nala nirman karya jhad ki piliya se balarpura ki or badapura | Completed | 501870.43 | 423708 | 2022-09-10 | 2022-11-29
ATER | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1702001047/RS/22012035133950 — Samudayik Swachhta Parisar - Kadora | Approved | 43000 | 0 | 2024-04-14
ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Bharat Nirman Sewa Kendra | New Construction / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1702001047/SK/9993649066 — Bharat Nirman Rajeev Gandhi Sewa Kendra,KADHURA | Deleted | 500000 | 0 | 2017-01-27
ATER | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1702001047/WC/22012034323597 — Talab Nirman- Punchayat bhawan ke Pass | Completed | 467445 | 329016 | 2017-05-09 | 2020-01-26
ATER | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1702001047/WC/22012034326260 — Talab Nirman- Pathbariya Mata Ke Pass, Kadora | Completed | 481738 | 336776 | 2017-05-23 | 2020-01-26
ATER | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001047/WC/22012034355221 — बोरी बंधान गाँव के नीचे कदोरा | Completed | 16700 | 15745.49 | 2017-09-26 | 2017-10-20
ATER | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1702001047/WC/22012034355222 — बोरी बंधान पुरोहित के खेत के पास कदोरा | Completed | 30000 | 25227 | 2017-09-26 | 2019-08-30
ATER | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1702001047/WC/22012034355223 — बोरी बंधान नाला कदोरा | Completed | 20000 | 19252 | 2017-09-26 | 2019-08-28
ATER | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1702001047/WC/22012034355224 — बोरी बंधान पथबरिया माता के पास कदोरा | Completed | 33000 | 26791 | 2017-09-26 | 2019-08-28
ATER | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702001047/WC/22012034424836 — Earthan Bund Shantidham Ke Pass- Kadora | Completed | 169000 | 164736 | 2019-06-10 | 2020-01-26
ATER | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702001047/WC/22012034424839 — Earthan Bund Pathoriya Mata Ke Pass, Kadora | Completed | 159200 | 130944 | 2019-04-05 | 2020-01-26
ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001047/WC/22012034447272 — नवीन तालाब निर्माण-फुकलीमाता के नीचे, कदोरा | Completed | 240000 | 240864 | 2021-04-09 | 2021-08-06
ATER | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001047/WC/22012034447279 — नवीन तालाब निर्माण- मरघट के पास , कदोरा | Closed | 240000 | 0 | 2019-01-26
ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001047/WC/22012034447285 — नवीन तालाब निर्माण-पथवरिया तालाब के पास , कदोरा | Completed | 240000 | 238548 | 2021-04-09 | 2021-08-06
ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702001047/WC/22012034544872 — नवीन तालाब निर्माण -पुराने खाद के पास , कदोरा | Completed | 1037538.64 | 717540 | 2020-05-14 | 2021-01-05
ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1702001047/WC/22012034544970 — Naveen Talab Nirman-purane Khad Ke Pass, Kadora | Closed | 0 | 0 | 2020-04-01
ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1702001047/WC/22012034544971 — Naveen Talab Nirman- Shantidham, Kadora | Completed | 1017650.73 | 588240 | 2020-06-04 | 2020-09-22
ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702001047/WC/22012034574075 — Mitti Bund Nirman Chitriyai ke pass, Kadora | Completed | 201674.34 | 171000 | 2020-08-27 | 2021-01-20
ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702001047/WC/22012034574076 — Mitti Bund Nirman Behad Mai Mata Mandir ke Pass, Kadora | Completed | 201674.34 | 171000 | 2020-08-27 | 2021-01-16
ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702001047/WC/22012034574077 — Mitti Bund Nirman Atibal Singh Ke Khet Ke Pass, Kadora | Completed | 196785.43 | 177460 | 2020-10-08 | 2021-01-16
ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702001047/WC/22012034574078 — Mitti Bund Nirman Charkha Kole Ke Pass, Kadora | Completed | 209731.84 | 184868 | 2021-01-14 | 2021-06-18
ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702001047/WC/22012034574079 — Mitti Bund Nirman Kurvali Ke Pass, Kadora | Completed | 187269.03 | 165822 | 2021-01-21 | 2021-06-18
ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001047/WC/22012034609240 — Mitti Bandh Nirman Jhekur Ke Pass, Kadora | Completed | 235499.94 | 206870 | 2021-01-14 | 2021-06-18
ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001047/WC/22012034609248 — Mitti Bandh Nirman Charkha Kola ,Kadora | Closed | 0 | 0 | 2020-10-02
ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1702001047/WC/22012034622906 — Naveen Talab Nirman- Rajkumar Prajapati Ke Bandha Ke Pass, Kadora | Completed | 505740.9 | 442266 | 2021-03-22 | 2021-08-06
ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1702001047/WC/22012034622907 — Naveen Talab Nirman-Neem Bali mata Ke Pass, Kadora | Completed | 532301.07 | 467568 | 2021-03-25 | 2021-08-06
ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1702001047/WC/22012034622908 — Mitti Bandh Nirman-Sajana Kole Ke Pass, Kadora | Closed | 0 | 0 | 2021-01-26
ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1702001047/WC/22012034622910 — Mitti Bandha Nirman Ramkaran ke Khet Ke Pass, Kadora | Closed | 0 | 0 | 2021-01-26
ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1702001047/WC/22012034622912 — Mitti Bandha Nirman-Badan singh Ke Gonda Ke Neeche, Kadora | Closed | 0 | 0 | 2021-01-26
ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702001047/WC/22012034674050 — Mitti Bandh Nirman Sajna Kole Ke Pass, Kadora | Completed | 224016.12 | 194544 | 2021-04-29 | 2021-08-06
ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702001047/WC/22012034674053 — Mitti Bandh Nirman Road Ke Bagal Se Kadora | Completed | 202854.47 | 196860 | 2021-04-29 | 2021-08-06
ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702001047/WC/22012034674055 — Mitti Bandh Nirman Pathbariya Mata Ke Peeche Nala Ke pass, Kadora | Completed | 186680.1 | 163278 | 2021-04-29 | 2021-08-06
ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001047/WC/22012034785147 — Naveen Mitti Bund Nirman Behad Mai Emli Ke Neeche | Deleted | 0 | 0 | 2021-04-14
ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001047/WC/22012034785148 — Naveen Mitti Bund Nirman Ramesh Ke Khet Ke pass, Kadora | Deleted | 0 | 0 | 2021-04-14
ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001047/WC/22012034785149 — Naveen Mitti Bund Nirman Suresh dhakad Ke Khet Ke pass, Kadora | Completed | 557056.76 | 324240 | 2021-07-15 | 2022-01-02
ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001047/WC/22012034790467 — Naveen Mitti Bund Nirman Behad Mai Emli Ke Neeche, Kadora | Completed | 568499.89 | 346242 | 2021-07-22 | 2022-01-02
ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001047/WC/22012034790470 — Naveen Mitti Bund Nirman Ramesh Ke Khet Ke Pass, Kadora | Closed | 539594.83 | 0 | 2021-04-14
ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702001047/WC/22012034863391 — Mitti Bund Nirman Vinod Ke Khet Ke Pass, Kadora | Completed | 225299.89 | 195702 | 2021-11-10 | 2022-01-02
ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702001047/WC/22012034863393 — Mitti Bund Nirman Shantidham Ke Neeche Kamlesh Ke Khet Ke Pass, Kadora | Completed | 231505.44 | 203808 | 2021-11-10 | 2022-01-02
ATER | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702001047/WC/22012034950473 — Mitti Bund Nirman Bheemsen Ke Khet Ke pass, Kadora | Completed | 155206.54 | 138312 | 2022-04-30 | 2022-06-15
ATER | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702001047/WC/22012034950479 — Mitti Bund Nirman Bhumiya Ke pass, Kadora | Completed | 198306.9 | 172584 | 2022-04-30 | 2022-06-20
ATER | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702001047/WC/22012034950483 — Mitti Bund Nirman Kasakole Ke Pass, Kadora | Deleted | 0 | 0 | 2022-04-01
ATER | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702001047/WC/22012034950488 — Mitti Bund Nirman Kamlesh Singh ke Khet ke Pass, Kadora | Completed | 203634.62 | 175032 | 2022-04-30 | 2022-06-20
ATER | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702001047/WC/22012034950492 — Mitti Bund Nirman Kasakole ke Pass, Kadora | Completed | 197884.05 | 173808 | 2022-04-30 | 2022-06-20
ATER | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702001047/WC/22012034950493 — Mitti Bund Nirman Purane Kuya Ke Pass, Kadora | Completed | 174543.9 | 151776 | 2022-04-30 | 2022-06-20
ATER | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702001047/WC/22012034950496 — Mitti Bund Nirman Radhe lal Baretha Ke Khet Ke pass, Kadora | Completed | 238334.75 | 208080 | 2022-04-30 | 2022-06-26
ATER | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702001047/WC/22012034971915 — Mitti Bandh Nirman Behad Mai Kareela Teela Ke Pass, Kadora | Closed | 0 | 0 | 2022-04-14
ATER | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702001047/WC/22012034971916 — Mitti Bandh Nirman Khadera Ke Pass, Kadora | Completed | 248233.9 | 209304 | 2022-05-21 | 2022-06-30
ATER | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1702001047/WC/22012034978094 — Naveen Talab Nirman Behad Mai Ramu ke Khet ke pass, Kadora | Completed | 498602.19 | 441048 | 2022-08-20 | 2022-11-27
ATER | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1702001047/WC/22012034978099 — Naveen Talab Nirman Purane Pipara Ke Pass, Kadora | Completed | 490335.13 | 433908 | 2022-08-20 | 2022-11-27
ATER | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702001047/WC/22012034992334 — Navin talab nirman karya khinni pura | Completed | 1228024.72 | 747048 | 2022-09-04 | 2025-05-07
ATER | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001047/WC/22012034992352 — Naveen mitti band nirman kashiram ke khet ke neeche khinipura | Completed | 426573.04 | 366180 | 2022-11-27 | 2023-04-01
ATER | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702001047/WC/22012034992404 — naveen talab nirman ghar ki nariya ke pass khinipura | Physically Completed | 989288.7 | 715836 | 2023-01-08 | 2026-04-17
ATER | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Stone graded Bund for Community / Construction of Stone graded Bund for Community | Construction of Bund | 1702001047/WC/22012035014542 — naveen mitti band nirman karya purane talab ke pass kinnipura | Completed | 443405.11 | 383112 | 2022-12-18 | 2023-04-01
ATER | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702001047/WC/22012035027850 — naveen talab nirman karya teekaram ke ghar ke peeche khineepura | Closed | 0 | 0 | 2022-10-02
ATER | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702001047/WC/22012035027853 — naveen talab nirman karya geetaram ke khet ke pass khinnipura | Closed | 0 | 0 | 2022-10-02
ATER | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001047/WC/22012035033445 — Naveen mitti band nirman karya Santosh Sharma ke khet ke pass Khinnipura | Closed | 0 | 0 | 2022-11-15
ATER | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001047/WC/22012035052802 — naveen mitti band nirman santosh sharma ke khet ke pass | Closed | 0 | 0 | 2022-11-15
ATER | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702001047/WC/22012035052803 — naveen talab nirman karya geetaram ke khet ke pass khinnipura | Closed | 0 | 0 | 2023-01-25
ATER | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702001047/WC/22012035056346 — naveen talab nirman karya geetaram ke khet ke pass khinnipura | Closed | 0 | 0 | 2023-04-02
ATER | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702001047/WC/22012035058401 — naveen talab nirman karya geetaram ke khet ke pass khinnipura | Completed | 835851.21 | 726648 | 2023-05-14 | 2023-09-24
ATER | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001047/WC/22012035058403 — naveen mitti band nirman santosh sharma ke khet ke pass khinnipura | Completed | 533163.72 | 467857 | 2023-04-30 | 2023-08-04
ATER | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702001047/WC/22012035085432 — naveen talab nirman nirman karya rajaram ke khet ke pass | Closed | 0 | 0 | 2023-06-05
ATER | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001047/WC/22012035085436 — naveen mitti band nirman karya umesh khare ke khet ke pass badapura | Completed | 940673.31 | 821236 | 2023-07-04 | 2023-09-24
ATER | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001047/WC/22012035085441 — naveen mitti band nirman karya samokhan ke khet ke pass badapura | Closed | 530638.93 | 0 | 2023-06-05
ATER | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702001047/WC/22012035085443 — naveen talab nirman karya khar ke pass badapura | Closed | 0 | 0 | 2023-06-05
ATER | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001047/WC/22012035085445 — naveen mitti band nirman karya nale ke pass badapura | Closed | 0 | 0 | 2023-06-05
ATER | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001047/WC/22012035086049 — naveen mitti band nirman karya rajaram ke khet ke pass badapura | Closed | 0 | 0 | 2023-06-05
ATER | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001047/WC/22012035086050 — naveen mitti band nirman karya khar ke pass badapura | Completed | 456333.87 | 393822 | 2023-06-27 | 2023-09-24
ATER | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001047/WC/22012035095634 — naveen mitti band nirman karya vidhyaram ke khet ke pass badapura | Physically Completed | 566964.36 | 278460 | 2023-09-05 | 2026-04-17
ATER | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001047/WC/22012035095641 — naveen mitti band nirman karya jaynarayan ke khet ke pass badapura | Deleted | 0 | 0 | 2023-06-05
ATER | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001047/WC/22012035095642 — naveen mitti band nirman karya rambihari ke khet ke pass badapura | Suspended | 540089.16 | 118183 | 2023-09-19
ATER | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702001047/WC/22012035095783 — NAVEEN KHET TALAB NIRMAN KARYA JAYNARAYAN KE KHET PAR BADAPURA | Completed | 115762.06 | 78234 | 2023-09-05 | 2026-04-23
ATER | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Raising of Nursery for Community / Raising of Nursery for Community | Nursery Development | 1702001047/WC/22012035097144 — vriksharopan amrit vatika karya shanti dham par badapura | Suspended | 55847.4 | 5967 | 2023-09-05
ATER | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001047/WC/22012035118388 — naveen mitti band nirman karya ashok sharma ke khet ke pass kadora | Closed | 0 | 0 | 2023-08-16
ATER | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001047/WC/22012035118392 — naveen mitti band nirman karya ashok sharma ke khet ke pass kadora | Completed | 972744.16 | 362643 | 2023-10-06 | 2026-04-25
ATER | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001047/WC/22012035118401 — naveen mitti band nirman radhamohan sharma ke khet ke pass kadora | Suspended | 910282.15 | 79971 | 2023-12-08
ATER | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Coastal Line Plantation-Horticulture-Community / Along the coast Line Plantation of Horticulture Trees for Community | Plantation | 1702001047/WC/22012035118413 — kachcha nala nirman karya samudayak parishar se shanti dham ki or badapura | Suspended | 1224673.16 | 84864 | 2023-10-06
ATER | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702001047/WC/22012035258959 — khet talab nirman karya shiv kumar ke khet par badapura | Approved | 0 | 0 | 2025-04-06
ATER | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702001047/WC/22012035285267 — khet talab nirman karya siyaram ke khet par badapura | Approved | 0 | 0 | 2025-04-14
ATER | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702001047/WC/22012035285268 — khet talab nirman karya devendra sharma ke khet par badapura | Approved | 147621.16 | 0 | 2025-04-14
ATER | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702001047/WC/22012035285269 — khet talab nirman karya kashiram ke khet par khinnipura | Closed | 147621.16 | 0 | 2026-04-09
ATER | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702001047/WC/22012035285270 — khet talab nirman karya asharam ke khet par badapura | Approved | 147621.16 | 0 | 2025-04-14
ATER | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702001047/WC/22012035285271 — khet talab nirman karya jay narayan ke khet par badapura | Approved | 147621.16 | 0 | 2025-04-14
ATER | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter-Borewell recharge for Comm / Construction of Sand filter for borewell recharge for Community | Well Recharge | 1702001047/WC/22012035300897 — dag well reeharj pit baghiya ke kua ke pass kadora | Approved | 0 | 0 | 2025-04-14
ATER | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1702001047/WC/22012035301023 — dag well reeharj pit baghiya ke kua ke pass kadora | Physically Completed | 25899.46 | 7788.79 | 2025-05-14 | 2026-04-14
ATER | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1702001047/WC/VB/22012035330016 — Sokta gadda nirman karya subedar ke ghar ke pass kadora ka pura | Approved | 28505.05 | 0 | 2026-07-30
ATER | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1702001047/WH/19956754 — Talab Gahrikaran- Kadora | Deleted | 100000 | 0 | 2016-05-24
ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702001047/WH/22012034450227 — Renovation Of Talab Hariom Sharma Ke Khet Ke Pass Nahar Paar, Badapura, Kadora | Completed | 951283.41 | 520693 | 2022-01-08 | 2022-04-25
ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702001047/WH/22012034455074 — Talab Jidodhhar/Sudrikaran Gaon Ke Neeche, Khinnipura, Kadora | Completed | 804753.06 | 481788 | 2022-02-26 | 2022-05-25
ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702001047/WH/22012034455076 — Talab Jidodhhar/Sudrikaran Sayeed Baba Mandir Ke Neeche Kadora | Completed | 996586.24 | 518232 | 2022-02-26 | 2022-06-24